## PSO
Code | FR Sheet Name (WS F&G) | PID | UID | Projected / Actual In-Service (mmm-yyyy) | Project & TP# | - - - P R E V I O U S L Y P U B L I S H E D - - - | [17 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- WS-F and WS-G SUMMARY Input Data --- |  |  |  |  | COMMENTS
[6 empty] | 09 Update | 2010 "Corrected" Update |  |  | 2011 "Corrected" Update |  |  | 2012 Update |  |  | 2013 Update |  |  |  | 2014 Update |  |  |  | 2015 Update |  |  |  | 2016 Update |  |  |  | 2017 Update | [5 empty] | 2018 Update | [5 empty] | 2019 Update |  |  |  |  | 2020 Update | [5 empty] | 2021 Update
[6 empty] | YE2009 Projected (8/31/09) << WS-F >> | YE2009 Actual (3/29/11)* << WS-G >> | YE2010 Projected (3/29/11) << WS-F >> | YE09 to YE10 (Projected) Variance | YE2010 Actual (12/21/11)* << WS-G >> | YE2011 Projected (12/21/11) << WS-F >> | YE10 to YE11 (Projected) Variance | YE2011 Actual (May'12) << WS-G >> | YE2012 Projected (May '12) << WS-F >> | YE11 to YE12 (Projected) Variance | YE2012 Actual (May'13) << WS-G >> | YE2013 Projected (May '13) << WS-F >> | YE2012 Variance (Projected to Actual) | YE12 (actual) to YE13 (Projected) Variance | YE2013 Actual (May'14) << WS-G >> | YE2014 Projected (May '14) << WS-F >> | YE2013 Variance (Projected to Actual) | YE13 (actual) to YE14 (Projected) Variance | YE2014 Actual (May'15) << WS-G >> | YE2015 Projected (May '15) << WS-F >> | YE2014 Variance (Projected to Actual) | YE14 (actual) to YE15 (Projected) Variance | YE2015 Actual (May'16) << WS-G >> | YE2016 Projected (May '16) << WS-F >> | YE2015 Variance (Projected to Actual) | YE15 (actual) to YE16 (Projected) Variance | YE2016 Actual (May'17) << WS-G >> | YE2017 Projected (May '17) << WS-F >> | YE2017 Projected Adjusted (Oct '17) << WS-F >> | YE2018 Projected (Oct '17) << WS-F >> | YE2016 Variance (Projected to Actual) | YE16 (Actual) to YE17 (Projected) Variance | YE2017 Actual (May '18) << WS-G >> | YE2018 Projected (May '18) << WS-F >> | YE2018 Projected Adjusted (Oct '18) << WS-F >> | YE2019 Projected (Oct '18) << WS-F >> | YE2017 Variance (Projected to Actual) | YE17 (Actual) to YE18 (Projected) Variance | YE2018 Actual (May '19) << WS-G >> | YE2019 Projected (Oct '19) << WS-F >> | YE2020 Projected (Oct '19) << WS-F >> | YE2018 Variance (Projected to Actual) | YE18 (Actual) to YE19 (Projected) Variance | YE2019 Actual (May '20) << WS-G >> | YE2020 Projected (May '20) << WS-F >> | YE2020 Projected (Oct '20) << WS-F >> | YE2021 Projected (Oct '20) << WS-F >> | YE2019 Variance (Projected to Actual) | YE19 (Actual) to YE20 (Projected) Variance | YE2020 Actual (May '21) << WS-G >> | YE2021 Projected (Oct '21) << WS-F >> | YE2022 Projected (Oct '21) << WS-F >> | YE2020 Variance (Projected to Actual) | YE20 (Actual) to YE21 (Projected) Variance
t | P.001 | Total | Total | 2009-06-01 | Riverside-Glenpool (TP2006087) | 579098 | 893857.87 | 893857.87 | 54.35% | 893857.87 | 893857.87 | 0% | 893857.87 | 893857.87 | 0% | 893857.87 | 893857.87 | 0% | 0% | 893857.87 | 893857.87 | 0% | 0% | 893858 | 893858 | 1.454e-05% | 0% | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 |  |  | 0% | -100%
c | P.001 | 220 | 10279 |  | Reconductor 1.82 miles with ACCC. Replace wave trap jumpers at Riverside. | [18 empty] | 893858 | 893858 |  |  | 893858 | 893858 |  |  | 893858 | 893858 | 893858 | 893858 |  |  | 893858 | 893858 | 893858 | 893858 |  |  | 893858 | 893858 | 893858 |  |  | 893858 | 893858 | 893858 | 893858 |  |  | 893858
t | P.002 | Total | Total | 2009-05-01 | Craig Jct-Broken Bow (TP2007059) | 6704177 | 4725391.05 | 4725391.05 | -29.52% | 4688896 | 4688896 | 0.7783% | 4688896 | 4688896 | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 |  |  | 0% | -100%
c | P.002 | 230 | 10295 |  | Reconductor Broken Bow to Craig Junction 138 kV; Rebuild 7.66 miles of 3/0 CW CU with 795 ACSR | [18 empty] | 4688896 | 4688896 |  |  | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 | 4688896 |  |  | 4688896
t | P.003 | Total | Total | 2009-10-01 | WFEC new ties (TP2006054) | 9403820 | 8830340 | 12266531 | 30.44% | 12232148 | 12232148 | 0.2811% | 12232148 | 12232148 | 0% | 12232148 | 12232148 | 0% | 0% | 12232148 | 12232148 | 0% | 0% | 11456065 | 11456065 | -6.345% | 0% | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 |  |  | 0% | -100%
c | P.003 | 112 | 10139 |  | Build new 138 kV line AEP Sayre to WFEC Erick. | [18 empty] | 6998664 | 6998664 |  |  | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 | 6998664 |  |  | 6998664
c | P.003 | 177 | 10728 |  | Install 138 kV three breaker ring bus forming two new 138 kV terminals at the Atoka substation. | [18 empty] | 3041696 | 3041696 |  |  | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 | 3041696 |  |  | 3041696
c | P.003 | 177 | 10729 |  | Upgrade line relays, install SCADA and install Ethernet communication at Tupelo Substation. | [18 empty] | 1415705 | 1415705 |  |  | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 | 1415705 |  |  | 1415705
t | P.004 | Total | Total | 2008-07-01 | Cache-Snyder (TP2004147) | 14544152 | 14683511.33 | 14686911.33 | 0.02248% | 14615636 | 14615636 | 0.4877% | 14615636 | 14615636 | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 |  |  | 0% | -100% | Includes new line and new terminals at both ends.
c | P.004 | 106 | 10130 |  | Build new Snyder to Altus Jct 138 kV line | [18 empty] | 14615636 | 14615636 |  |  | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 | 14615636 |  |  | 14615636
c | P.004 | 119 | 10149 |  | Included in 10130 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | P.005 | Total | Total | 2006-05-01 | Catoosa 138 kV Device | 387742 | 387742 | 387742 | 0.02248% | 387742 | 387742 | 0% | 387742 | 387742 | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 |  |  | 0% | -100%
c | P.005 | 30001 | 50001 |  | Install switched capacitor bank. | [18 empty] | 387742 | 387742 |  |  | 387742 | 387742 |  |  | 387742 | 387742 | 387742 | 387742 |  |  | 387742 | 387742 | 387742 | 387742 |  |  | 387742 | 387742 | 387742 |  |  | 387742 | 387742 | 387742 | 387742 |  |  | 387742
t | P.006 | Total | Total | 2008-04-01 | Pryor Jct 138/60 Upgrade autoxfmr (TP2006090) | 1520473 | 1520502 | 1520502 | 0.02248% | 1520502 | 1520502 | 0% | 1520502 | 1520502 | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 |  |  | 0% | -100%
c | P.006 | 110 | 10137 |  | Upgrade Pryor Junction 138/69 kV transformer; Ratings A=133 and B=146 | [18 empty] | 1520502 | 1520502 |  |  | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 | 1520502 |  |  | 1520502
c | P.006 | 657 | 10862 |  | Included in 10137 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
< | P.007 | Total | Total | 2007-12-01 | Elk City-Elk City 69 CT upgrades (TP2007015) | 84424 | 84424 | 84424 | 0.02248% | 84424 | 84424 | 0% | 84424 | 84424 | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 |  |  | 0% | -100% | Not over $100K threshold for regional allocation.
c | P.007 | 118 | 10148 |  | Replace CTS & jumpers. Limits on AEP end will be 600A switches and Breaker | [18 empty] | 84424 | 84424 |  |  | 84424 | 84424 |  |  | 84424 | 84424 | 84424 | 84424 |  |  | 84424 | 84424 | 84424 | 84424 |  |  | 84424 | 84424 | 84424 |  |  | 84424 | 84424 | 84424 | 84424 |  |  | 84424
< | P.008 | Total | Total | 2006-03-01 | Weleetka & Okmulgee wavetrap r&r 81-805 (TP2005046) | 56133 | 56133 | 56133 | 0.02248% | 56133 | 56133 | 0% | 56133 | 56133 | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 |  |  | 0% | -100% | Not over $100K threshold for regional allocation.
c | P.008 | 3 | 10003 |  | Replace Weleetka wave trap | [18 empty] | 56133 | 56133 |  |  | 56133 | 56133 |  |  | 56133 | 56133 | 56133 | 56133 |  |  | 56133 | 56133 | 56133 | 56133 |  |  | 56133 | 56133 | 56133 |  |  | 56133 | 56133 | 56133 | 56133 |  |  | 56133
c | P.008 | 4 | 10004 |  | Replace Okmulgee wave trap | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Distribution; ignore
< | P.009 | Total | Total | 2007-04-01 | Tulsa SE r&r switches (TP2004033) | 72551 | 72551 | 72551 | 0.02248% | 72551 | 72551 | 0% | 72551 | 72551 | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 |  |  | 0% | -100% | Not over $100K threshold for regional allocation.
c | P.009 | 46 | 10050 |  | Replace 3 switches | [18 empty] | 72551 | 72551 |  |  | 72551 | 72551 |  |  | 72551 | 72551 | 72551 | 72551 |  |  | 72551 | 72551 | 72551 | 72551 |  |  | 72551 | 72551 | 72551 |  |  | 72551 | 72551 | 72551 | 72551 |  |  | 72551
< | P.010 | Total | Total | 2010-06-01 | Clinton City-Foss 69 wavetrap r&r (TP2009011) | n/a | n/a | 135400 | n/a | 96566 | 96566 | 40.21% | 96566 | 96566 | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 |  |  | 0% | -100% | Not over $100K threshold for regional allocation.
c | P.010 | 289 | 10375 |  | Replace wave trap at Clinton City Substation. | [18 empty] | 96566 | 96566 |  |  | 96566 | 96566 |  |  | 96566 | 96566 | 96566 | 96566 |  |  | 96566 | 96566 | 96566 | 96566 |  |  | 96566 | 96566 | 96566 |  |  | 96566 | 96566 | 96566 | 96566 |  |  | 96566
t | P.011 | Total | Total | 2011-06-01 | Bartlesville SE to Coffeyville T Rebuild (TP2008079-PSO) | --- | --- | --- | --- | --- | 1624000 | --- | 1436737 | 1436737 | 13.03% | 1493723 | 1493723 | 3.966% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 |  |  | 0% | -100% | Also see related OKTransco project (OKT.004).
c | P.011 | 446 | 10578 |  | Rebuild approximately 13 miles of line with 1590 ACSR to achieve a minimum 2000 Amp emergency rating | [18 empty] | 1493723 | 1493723 |  |  | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 | 1493723 |  |  | 1493723
c | P.011 | 454 | 10588 |  | Included in 10578 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | P.011 | 902 | 11199 |  | Included in 10578 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | P.011 | 911 | 11208 |  | Included in 10578 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | P.012 | Total | Total | 2013-08-01 | Canadian River - McAlester City 138 kV Line Conversion (TP2009095) | --- | --- | --- | --- | --- | --- | --- | --- | 1132400 | --- | 504034 | 2750034 | -55.49% | 445.6% | 3242134 | 3242134 | 17.89% | 0% | 3305767.14 | 3305767.14 | 1.963% | 0% | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 |  |  | 0% | -100% | Also see related OKTransco project (OKT.006). Multi-element multi-year base plan project. Final in-service yr in 12' and 13'.
c | P.012 | 767 | 11011 |  | Convert 17 mile Canadian River - McAlester City line from 69 kV to 138 kV. | [18 empty] | 3305767.14 | 3305767.14 |  |  | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 | 3305767 |  |  | 3305767
c | P.012 | 767 | 11012 |  | Included in 11011 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | P.012 | 767 | 11183 |  | Included in 11011 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | P.012 | 767 | 11184 |  | Included in 11011 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | P.013 | Total | Total | 2010-06-01 | CoffeyvilleT to Dearing 138 kv Rebuild - 1.1 mi (TP2008013) | --- | --- | --- | --- | --- | --- | --- | 22097 | 22097 | --- | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 |  |  | 0% | -100% | Also see related OKTransco project (OKT.002). Total project expenditure is over $100k.
c | P.013 | 295 | 10381 |  | AEPW to reconductor 1.09 miles of 795 ACSR with 1590 ACSR. (Also, Westar to rebuild 3.93 miles of 795 ACSR with 1590 ACSR.) These ratings are just for the AEP facilities. | [18 empty] | 22097 | 22097 |  |  | 22097 | 22097 |  |  | 22097 | 22097 | 22097 | 22097 |  |  | 22097 | 22097 | 22097 | 22097 |  |  | 22097 | 22097 | 22097 |  |  | 22097 | 22097 | 22097 | 22097 |  |  | 22097
t | P.014 | Total | Total | 2013-02-01 | Ashdown West - Craig Junction 138KV Rebuild (TP2009092) | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | n/a | 5562500 | --- | --- | 1035333 | 1035333 | -81.39% | 0% | 1035552 | 1035552 | 0.02115% | 0% | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 |  |  | 0% | -100% | Asset transfer to SWEPCO completed. Only a portion of the project was transferred.
c | P.014 | 770 | 11015 |  | Rebuild 2.45 miles of 795 ACSR with 1590 ACSR and reset relays. | [18 empty] | 1035552 | 1035552 |  |  | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 | 1035552 |  |  | 1035552
t | P.015 | Total | Total | 2014-02-01 | Locust Grove to Lone Star 115 kV Rebuild 2.1 miles (TP2009093) | [14 empty] | n/a | 2295000 |  |  | 2246628.57 | 2246628.57 | -2.108% | 0% | 2246629 | 2246629 | 1.914e-05% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 |  |  | 0% | -100%
c | P.015 | 649 | 10853 |  | Reconductor 2.15 mile section of 115 kV line with 795 ACSR. | [18 empty] | 2246628.57 | 2246628.57 |  |  | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 | 2246629 |  |  | 2246629
t | P.016 | Total | Total | 2014-12-01 | Cornville Station Conversion (TP2011093) | [14 empty] | n/a | 5300000 |  |  | 4980780.16 | 5300000 | -6.023% | 6.409% | 5059196 | 5059196 | -4.543% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0.001622% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 |  |  | 0% | -100% | Also see related OKTransco project (OKT.007).
c | P.016 | 30346 | 50438 |  | Upgrade the Cornville 138 kV bus to breaker-and-a-half configuration in preparation for the 138 kV line conversion to Lindsay Water substation. | [18 empty] | 4980780.16 | 5300000 |  |  | 5059196 | 5059196 |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04
n/a | P.017 | Total | Total | 2014-12-01 | OKMULGEE - RIVERSIDE STATION 138KV CKT 1 | [14 empty] | n/a | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; no Capital investment
c | P.017 | 387 | 10505 |  | Replace wave trap at Okmulgee. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | P.018 | Total | Total | 2017-03-01 | Valliant-NW Texarkana 345 kV | [14 empty] | n/a | 0 |  |  | 0 | 1500000 |  |  | 1338801 | 1338801 | -10.75% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0.01321% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 |  |  | 0% | -100% | 345 kV line relocation to be completed November 2015; Also see related SWEPCo project (S.058) and OKTCo project (OKT.009).Need to Update the ISD to 2017
c | P.018 | 936 | 11236 |  | 345 kV from Valliant substation to NW Texarkana substation | [18 empty] | 0 | 1500000 |  |  | 1338801 | 1338801 |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91
n/a | P.019 | Total | Total | 2016-06-01 | Broken Arrow North-South Tap-Oneta 138 kV Ckt 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0% | #DIV/0! | 0 |  |  |  |  | 100% Direct Assign project, not to be included in the Rate Base
n/a | P.019 | 947 | 11261 |  | Reconductor 4.33 miles of 795 ACSR with 1026 ACCC | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | This project was not REBUILT it is an actual recondutor of the existing structures.
t | P.020 | Total | Total | 2015-12-01 | Grady Customer Connection | [18 empty] | 0 | 1500000 |  |  | 1625288 | 1777912 | 8.353% | 9.391% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | -4.831% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 |  |  | 0% | -100% | Also see related OKTransco project (OKT.013).
c | P.020 | 30748 | 51015 |  | Transmission line cut-ins | [18 empty] | 0 | 1500000 |  |  | 1625288 | 1777912 |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 |  |  |  |  | Trailing charges due to being in-service in Dec 2015
t | P.021 | Total | Total | 2014-04-01 | Darlington-Red Rock 138 kV line | [18 empty] | 1725646.85 | 1725646.85 |  |  | 1725647 | 1725647 | 8.692e-06% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 |  |  | 0% | -100% | Also see related OKTransco project (OKT.014).
c | P.021 | 30746 | 51013 |  | Construct new 8-mile 138 kV line from Red Rock to Darlington. | [18 empty] | 1725646.85 | 1725646.85 |  |  | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 | 1725647 |  |  | 1725647 |  |  |  |  | Cost includes all terminal work also.
t | P.022 | Total | Total | 2018-12-19 | Sayre 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 483000 | 0 | 1140000 |  |  | 0 | 1140000 | 1140000 | 1140000 | 0% | 0% | 1919728.93 | 1919728.93 | 1919728.93 | 68.4% | -40.62% | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 2.161% | 0% | 1961220.71 |  |  | 0% | -100% | ISD moved out to 2018.
c | P.022 | 30997 | 51433 |  | Sayre 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 483000 | 0 | 483000 |  |  | 0 | 483000 | 1140000 | 1140000 |  |  | 1919728.93 | 1919728.93 | 1919728.93 |  |  | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 |  |  | 1961220.71
t | P.023 | Total | Total | 2017-06-29 | Darlington-Roman Nose 138 kV | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 262000 | 262000 | 262000 |  |  | 330824.19 | 262000 | 262000 | 262000 | 26.27% | -20.8% | 330872.36 | 330872.36 | 330872.36 | 26.29% | -20.82% | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 0% | 0% | 330872.36 |  |  | 0% | -100% | Also see related OKTransco project (OKT.016).
c | P.023 | 30619 | 50802 |  | Darlington-Install metering and relaying | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 262000 | 262000 | 262000 |  |  | 330824.19 | 262000 | 262000 | 262000 |  |  | 330872.36 | 330872.36 | 330872.36 |  |  | 330872.36 | 330872.36 | 330872.36 | 330872.36 |  |  | 330872.36
t | P.024 | Total | Total | 2018-06-01 | Northeastern Station 138 kV Terminal Upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 | 244000 | 0% | 0% | 244000 | 244000 | 244000 | 0% | 0% | 244000 | 244000 | 244000 | 244000 | 0% | 0% | 244000 |  |  | 0% | -100% | This project was slated for 06/2017, however, the metering CT failed, and was replaced by TFS in 05/2016.
c | P.024 | 31003 | 51446 |  | Northeastern Station 138 kV Terminal Upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 | 244000 |  |  | 244000
t | P.025 | Total | Total | 2018-05-25 | Elk City 138 kV Move Load | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1778000 |  |  | 0 | 1778000 | 2037000 | 2037000 | 0% | 0% | 1200324.32 | 1200324.32 | 1200324.32 | -41.07% | 69.7% | 1176180.46 | 1176180.46 | 1176180.46 | 1176180.46 | -2.011% | 0% | 1165593.01 |  |  | -0.9002% | -100% | Only included FERC T work, not Distribution; used cost estimate from the Capital Program Approval Improvement Requisition.
c | P.025 | 31005 | 51448 |  | Elk City 138 kV Move Load | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1778000 |  |  | 0 | 1778000 | 2037000 | 2037000 |  |  | 1200324.32 | 1200324.32 | 1200324.32 |  |  | 1176180.46 | 1176180.46 | 1176180.46 | 1176180.46 |  |  | 1165593.01
t | P.026 | Total | Total | 2018-12-21 | Fort Towson-Valliant Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1044000 |  |  | 27999.49 | 1044000 | 557000 | 557000 | 0% | 3629% | 302079.67 | 302079.67 | 302079.67 | -45.77% | 84.39% | 288859.6 | 288859.6 | 288859.6 | 288859.6 | -4.376% | 0% | 288859.6 |  |  | 0% | -100% | ROW only; refer to related OKTCo project, OKT.019, P15204002/005.
c | P.026 | 31058 | 51562 |  | Fort Towson-Valliant Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1044000 |  |  | 27999.49 | 1044000 | 557000 | 557000 |  |  | 302079.67 | 302079.67 | 302079.67 |  |  | 288859.6 | 288859.6 | 288859.6 | 288859.6 |  |  | 288859.6
c | P.026 | 31058 | 51561 |  | included above | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | P.027 | Total | Total | 2018-05-04 | Duncan-Comanche Tap 69 kV Rebuild and Duncan station upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1216000 |  |  | 0 | 1216000 | 1216000 | 1216000 | 0% | 0% | 1344938.51 | 1344938.51 | 1344938.51 | 10.6% | -9.587% | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 0.03302% | 0% | 1345382.62 |  |  | 0% | -100% | Refer to related OKTCo project, OKT.020. Only upgrades at Duncan Station are included here.
c | P.027 | 31009 | 51454 |  | Duncan-Tosco Rebuild and Duncan station upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1216000 |  |  | 0 | 1216000 | 1216000 | 1216000 |  |  | 1344938.51 | 1344938.51 | 1344938.51 |  |  | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 |  |  | 1345382.62 |  |  |  |  | Duncan station upgrades, line rebuild is in the TransCo line rehab program, b/c the NTC came after the program was approved.
c | P.027 | 31039 | 51524 |  | Comanche Tap-Tosco 69 kV Rebuild (included above) | [22 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Line rebuild is in the TransCo line rehab program, b/c the NTC came after the program was approved. Included in UID 51454.
t | P.028 | Total | Total | 2019-12-01 | Tulsa Southeast-E.61st 138 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 1039000 | 5024000 |  |  | --- | 7022000 | 7156000 | 0% | 0% | 6388895.58 | 7661895.58 | 9409645 | 9409645 | -9.016% | 19.93% | 8144613.64 |  |  | -13.44% | -100% | Includes line, ROW, and station work.
c | P.028 | 41202 | 61858 |  | Tulsa Southeast-E.61st 138 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 1039000 | 5024000 |  |  | --- | 7022000 | 7156000 |  |  | 6388895.58 | 7661895.58 | 9409645 | 9409645 |  |  | 8144613.64
t | P.029 | Total | Total | 2019-03-19 | Broken Arrow North-Lynn Lane East 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 2318000 | 4120000 |  |  | --- | 4236000 | 4236000 | 0% | 0% | 5058521.96 | 5058521.96 | 5058521.96 | 5058521.96 | 19.42% | 0% | 5058588.62 |  |  | 0.001318% | -100% | Includes reconductor and ROW.
c | P.029 | 41233 | 71945 |  | Broken Arrow North-Lynn Lane East 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 2318000 | 4120000 |  |  | --- | 4236000 | 4236000 |  |  | 5058521.96 | 5058521.96 | 5058521.96 | 5058521.96 |  |  | 5058588.62
t | P.030 | Total | Total | 2020-06-01 | Keystone Dam - Wekiwa 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 971000 | 1677000 | 0% | 0% | --- | 2842000 | 2345950 | 2345950 | 0% | #VALUE! | 2529407.75 |  |  | 7.82% | -100% | Includes Wekiwa station work, see Transco for line work, ROW and TFC. Note, duing this update, ROW was forecast on PSO, instead of OKT. (Manually moved the ROW to OKT.)
c | P.030 | 30809 | 51096 |  | Keystone Dam - Wekiwa 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 971000 | 1677000 |  |  | --- | 2842000 | 2345950 | 2345950 |  |  | 2529407.75
NOTES:
< | Not above SPP $100,000 BP threshold.
New | New to BP list
c | AEP project component (components sum up to project total)
t | AEP project total
n/a | informational only; not included in calculations
Matched Last Year
Does Not Match Last Year, Needs Updating
Changed from Last Year, Updated

## SWEPCO
Code | FR Sheet Name (WS F&G) | PID | UID | Projected / Actual In-Service (mmm-yyyy) | Project & TP# | --- PREVIOUSLY PUBLISHED --- | [17 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- WS-F and WS-G SUMMARY Input Data --- |  |  |  |  | COMMENTS
[6 empty] | 09 Update | 2010 "Corrected" Update |  |  | 2011 "Corrected" Update |  |  | 2012 Update |  |  | 2013 Update |  |  |  | 2014 Update |  |  |  | 2015 Update |  |  |  | 2016 Update |  |  |  | 2017 Update | [5 empty] | 2018 Update | [5 empty] | 2019 Update |  |  |  |  | 2020 Update | [5 empty] | 2021 Update
[6 empty] | YE2009 Projected (8/31/09) << WS-F >> | YE2009 Actual (3/29/11)* << WS-G >> | YE2010 Projected (3/29/11) << WS-F >> | YE09 to YE10 Variance | YE2010 Actual (12/21/11)* << WS-G >> | YE2011 Projected (12/21/11) << WS-F >> | YE10 to YE11 (Projected) Variance | YE2011 Actual (May'12) << WS-G >> | YE2012 Projected (May '12) << WS-F >> | YE11 to YE12 (Projected) Variance | YE2012 Actual (May'13) << WS-G >> | YE2013 Projected (May '13) << WS-F >> | YE2012 Variance (Projected to Actual) | YE12 (actual) to YE13 (Projected) Variance | YE2013 Actual (May'14) << WS-G >> | YE2014 Projected (May '14) << WS-F >> | YE2013 Variance (Projected to Actual) | YE13 (actual) to YE14 (Projected) Variance | YE2014 Actual (May'15) << WS-G >> | YE2015 Projected (May '15) << WS-F >> | YE2014 Variance (Projected to Actual) | YE14 (actual) to YE15 (Projected) Variance | YE2015 Actual (May'16) << WS-G >> | YE2016 Projected (May '16) << WS-F >> | YE2015 Variance (Projected to Actual) | YE15 (actual) to YE16 (Projected) Variance | YE2016 Actual (May'17) << WS-G >> | YE2017 Projected (May '17) << WS-F >> | YE2017 Projected Adjusted (Oct '17) << WS-F >> | YE2018 Projected (Oct '17) << WS-F >> | YE2016 Variance (Projected to Actual) | YE16 (actual) to YE17 (Projected) Variance | YE2017 Actual (May '18) << WS-G >> | YE2018 Projected (May '18) << WS-F >> | YE2018 Projected Adjusted (Oct '18) << WS-F >> | YE2019 Projected (Oct '18) << WS-F >> | YE2017 Variance (Projected to Actual) | YE17 (Actual) to YE18 (Projected) Variance | YE2018 Actual (May '19) << WS-G >> | YE2019 Projected (Oct '19) << WS-F >> | YE2020 Projected (Oct '19) << WS-F >> | YE2018 Variance (Projected to Actual) | YE18 (Actual) to YE19 (Projected) Variance | YE2019 Actual (May '20) << WS-G >> | YE2020 Projected (May '20) << WS-F >> | YE2020 Projected (Oct '20) << WS-F >> | YE2021 Projected (Oct '20) << WS-F >> | YE2019 Variance (Projected to Actual) | YE19 (Actual) to YE20 (Projected) Variance | YE2020 Actual (May '21) << WS-G >> | YE2021 Projected (Oct '21) << WS-F >> | YE2022 Projected (Oct '21) << WS-F >> | YE2020 Variance (Projected to Actual) | YE20 (Actual) to YE21 (Projected) Variance
t | S.001 | Total | Total | 2009-12-01 | AH auto & line (TP2007057) | 9057179 | 12134740.73 | 17740954.73 | 95.88% | 17671482 | 17671482 | 0.3931% | 17671482 | 17671482 | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 |  |  | 0% | -100%
c | S.001 | 108 | 10441 |  | Reconductor North Market - Arsenal Hill 69 kV 2.29 Miles With 1272 ACSR | [18 empty] | 2619131 | 2619131 |  |  | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 | 2619131 |  |  | 2619131
c | S.001 | 507 | 10652 |  | Rebuild 3.24 miles of 1272 AAC with 2156 ACSR. Replace 3 138KV switches, breaker jumpers, and reset CTs at Arsenal Hill. Replace 2 138KV switches and jumpers at Fort Humbug. | [18 empty] | 5576975 | 5576975 |  |  | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 | 5576975 |  |  | 5576975
c | S.001 | 30144 | 50152 |  | Included in 50154 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.001 | 30145 | 50153 |  | Rebuild 2.55 miles of 666 ACSR with 1272 ACSR | [18 empty] | 3024110 | 3024110 |  |  | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 | 3024110 |  |  | 3024110
c | S.001 | 30146 | 50154 |  | Replace auto and 69 KV breaker and switches. | [18 empty] | 6451266 | 6451266 |  |  | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 | 6451266 |  |  | 6451266
c | S.001 | 30147 | 50155 |  | Included in 50154 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | S.002 | Total | Total | 2009-01-01 | SW Shreveport (TP2007060) | 11979500 | 8402687.48 | 8402687.48 | -29.86% | 8402687.48 | 8402687.48 | 0% | 8402687.48 | 8402687.48 | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687 | 8402687 | -5.712e-06% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | -5.712e-06% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 |  |  | 0% | -100%
c | S.002 | 224 | 10283 |  | Replace two 138 kV breakers and five 138 kV switches. Reset relays and CTs | [18 empty] | 6631400 | 6631400 |  |  | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 | 6631400 |  |  | 6631400
c | S.002 | 224 | 10284 |  | Included in 10283 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.002 | 581 | 10744 |  | Rebuild 2.29 miles of 2-397.5 ACSR with 1590 ACSR. | [18 empty] | 1771287 | 1771287 |  |  | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 | 1771287 |  |  | 1771287
t | S.003 | Total | Total | 2009-06-01 | NW Ark 2009 (TP2007103) | 13558697 | 12384562 | 14833730 | 9.404% | 13742803 | 13742803 | 7.938% | 13742803 | 13742803 | 0% | 13742803 | 13742803 | 0% | 0% | 13742803 | 13742803 | 0% | 0% | 13742803 | 13742803 | 0% | 0% | 13742804 | 13742804 | 7.277e-06% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 7.277e-06% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 |  |  | 0% | -100%
c | S.003 | 107 | 10132 |  | Install 3% impedance reactor set at East Rogers on 161 kV line to Avoca REC. | [18 empty] | 1265280 | 1265280 |  |  | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 | 1265280 |  |  | 1265280
c | S.003 | 229 | 10292 |  | Reconductor 1 mile Flint Creek - Gentry 161 kV with 1590 ACSR. | [18 empty] | 10652438 | 10652438 |  |  | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 | 10652438 |  |  | 10652438
c | S.003 | 229 | 10293 |  | Included in 10292 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.003 | 229 | 10294 |  | Reconductor 5.14 mile Bentonville 279th St. - East Centerton 161 kV with 1590 conductor. | [18 empty] | 1825086 | 1825086 |  |  | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 | 1825086 |  |  | 1825086
t | S.004 | Total | Total | 2009-06-01 | N-Mag-Danville (TP2007114) | 5012222 | 11580312.94 | 11580312.94 | 131% | 11580312.94 | 11580312.94 | 0% | 11580312.94 | 11580312.94 | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580311 | 11580311 | -1.675e-05% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | -1.675e-05% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 |  |  | 0% | -100%
c | S.004 | 225 | 10286 |  | Magazine REC Danville 161 kV rebuild 17.96 miles of 250 Copperweld with 1272 ACSR. | [18 empty] | 11580311 | 11580311 |  |  | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 | 11580311 |  |  | 11580311
c | S.004 | 225 | 10289 |  | All work combined under 10286. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.004 | 30154 | 50162 |  | No specific work order for this. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | S.005 | Total | Total | 2009-12-01 | Greenwod, AR area (TP2007120) | 2111061 | 2981232 | 2981232 | 41.22% | 2981232 | 2981232 | 0% | 2981232 | 2981232 | 0% | 2981232 | 2981232 | 0% | 0% | 2981232 | 2981232 | 0% | 0% | 2981232 | 2981232 | 0% | 0% | 2981768 | 2981768 | 0.01798% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 0.01798% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 |  |  | 0% | -100% | slight discrepancy in sum of costs versus prior total
c | S.005 | 217 | 10276 |  | Reconnect the Huntington 69 kV station from the North Huntington-Midland 69 kV line to the North Huntington-Waldron 69 kV line. | [18 empty] | 462173 | 462173 |  |  | 462173 | 462173 |  |  | 462173 | 462173 | 462173 | 462173 |  |  | 462173 | 462173 | 462173 | 462173 |  |  | 462173 | 462173 | 462173 |  |  | 462173 | 462173 | 462173 | 462173 |  |  | 462173
c | S.005 | 218 | 10277 |  | Upgrade CT at North Huntington on N Huntington to Huntington Waldron 69 kV | [18 empty] | 689134 | 689134 |  |  | 689134 | 689134 |  |  | 689134 | 689134 | 689134 | 689134 |  |  | 689134 | 689134 | 689134 | 689134 |  |  | 689134 | 689134 | 689134 |  |  | 689134 | 689134 | 689134 | 689134 |  |  | 689134
c | S.005 | 219 | 10278 |  | Replace the Excelsior 69 kV station on the Midland-Excelsior 69 kV line with Reeves Road 161 kV station on the nearby the Hackett REC-North Huntington 161 kV line section. Open the Midland-Excelsior 69 kV line. | [18 empty] | 636354 | 636354 |  |  | 636354 | 636354 |  |  | 636354 | 636354 | 636354 | 636354 |  |  | 636354 | 636354 | 636354 | 636354 |  |  | 636354 | 636354 | 636354 |  |  | 636354 | 636354 | 636354 | 636354 |  |  | 636354
c | S.005 | 222 | 10281 |  | Reconductor 0.1 mile Bonanza - Bonanza Tap 161 kV line section to 1590 ACSR. | [18 empty] | 1194107 | 1194107 |  |  | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 | 1194107 |  |  | 1194107
t | S.006 | Total | Total | 2009-06-01 | Port Robson - Caplis - Red Point (SE 138 loop) (TP2007165) | 17101764 | 5339018.68 | 6524013.68 | -61.85% | 5997609 | 27373809 | -76.17% | 20890772 | 32463272 | -15.68% | 29567877 | 34986877 | 8.015% | 18.33% | 36928458 | 36928458 | 5.549% | 0% | 37028625 | 37028625 | 0.2712% | 0% | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 |  |  | 0% | -100% | Multi-element multi-year base plan project. Final in-service yr from '09 to '13.
c | S.006 | 113 | 10140 |  | Convert Red Point-Haughton to 138 kV, 1590 ACSR (includes Red Point terminal & Haughton station conversion). | [18 empty] | 11304565 | 11304565 |  |  | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 | 11304565 |  |  | 11304565
c | S.006 | 113 | 10141 |  | Convert Haughton-McDade to 138 kV, 1590 ACSR (includes McDade station conversion). | [18 empty] | 13469723 | 13469723 |  |  | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 | 13469723 |  |  | 13469723
c | S.006 | 113 | 10745 |  | Build new Port Robson-Bean 138 kV, 1590 ACSR line | [18 empty] | 4810545 | 4810545 |  |  | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 | 4810545 |  |  | 4810545
c | S.006 | 113 | 10746 |  | Included in 10745 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.006 | 113 | 10786 |  | Build new Caplis-McDade 138 kV, 1590 ACSR line | [18 empty] | 7443792 | 7443792 |  |  | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 | 7443792 |  |  | 7443792
< | S.007 | Total | Total | 2009-05-01 | Linwood 1238 switch r&r (TP2008080) | 64397 | 64769 | 82956 | 28.82% | 77750 | 77750 | 6.696% | 77750 | 77750 | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 |  |  | 0% | -100% | Not over $100K threshold for regional allocation.
c | S.007 | 30151 | 50159 |  | Replace Linwood Switches 10872 and 10873 and replace 138KV breaker jumpers | [18 empty] | 77750 | 77750 |  |  | 77750 | 77750 |  |  | 77750 | 77750 | 77750 | 77750 |  |  | 77750 | 77750 | 77750 | 77750 |  |  | 77750 | 77750 | 77750 |  |  | 77750 | 77750 | 77750 | 77750 |  |  | 77750
t | S.008 | Total | Total | 2008-07-01 | Dyess-S.Fayetteville 69 convert to 161 (TP2002085) | 6374367 | 6406782 | 6406782 | 0.5085% | 9655697 | 9655697 | -33.65% | 9655697 | 9655697 | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 |  |  | 0% | -100%
c | S.008 | 109 | 10133 |  | Convert 69 KV line to 161 kV | [18 empty] | 9655697 | 9655697 |  |  | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 | 9655697 |  |  | 9655697
c | S.008 | 109 | 10134 |  | Included in 10133 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.008 | 109 | 10135 |  | Included in 10133 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.008 | 109 | 10136 |  | Included in 10133 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | S.009 | Total | Total | 2008-04-01 | NW Texkna-Bann-Alumax 138 reconductor (TP2006130) | 1864928 | 1863106 | 1863106 | -0.0977% | 2820378 | 2820378 | -33.94% | 2820378 | 2820378 | 0% | 2820378 | 2820378 | 0% | 0% | 2820378 | 2820378 | 0% | 0% | 2820378 | 2820378 | 0% | 0% | 2820328 | 2820328 | -0.001773% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | -0.001773% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 |  |  | 0% | -100% | slight discrepancy in sum of costs versus prior total
c | S.009 | 115 | 10145 |  | Rebuild 2.0 miles of 1024 ACAR with 1590 ACSR, Replace wave trap & jumpers with 2156 ACSR. Replace Switch 2285 @ Alumax Tap. | [18 empty] | 1662449 | 1662449 |  |  | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 | 1662449 |  |  | 1662449
c | S.009 | 116 | 10146 |  | Replace six (6) 138 kV switches, five at Bann & one at Alumax Tap. Rebuild 0.67 miles of 1024 ACAR with 1590 ACSR. Replace wave trap & jumpers @ Bann. Replace breaker 3300 @ Bann. | [18 empty] | 1157879 | 1157879 |  |  | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 | 1157879 |  |  | 1157879
n/a | S.010 | 6 | 10006 | 2008-11-01 | Tontitown-Elm Springs REC 161 | [22 empty] | 0% |  |  |  | 0% | [27 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes. Confirmed 1/19/15.
n/a | S.010 | 42 | 10046 | 2008-11-01 | TONTITOWN 345/161KV TRANSFORMER CKT 1 | [22 empty] | 0% |  |  |  | 0% | [27 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes. Confirmed 1/19/15.
n/a | S.011 | 43 | 10047 | 2007-05-01 | Siloam Sprgs - Chamber Sprgs 161 line | [22 empty] | 0% |  |  |  | 0% | [27 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes. Confirmed 1/19/15.
t | S.012 | Total | Total | 2007-07-01 | Knox Lee - Oak Hill#2 1328 line, S.Shreveport (TP2004036) | 124047 | 124047 | 124047 | 0% | 185247 | 185247 | -33.04% | 185247 | 185247 | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 |  |  | 0% | -100%
c | S.012 | 41 | 10045 |  | Replace wave trap at South Shreveport | [18 empty] | 108157 | 108157 |  |  | 108157 | 108157 |  |  | 108157 | 108157 | 108157 | 108157 |  |  | 108157 | 108157 | 108157 | 108157 |  |  | 108157 | 108157 | 108157 |  |  | 108157 | 108157 | 108157 | 108157 |  |  | 108157
c | S.012 | 44 | 10048 |  | Replace relay, wave trap at Knoxlee | [18 empty] | 77090 | 77090 |  |  | 77090 | 77090 |  |  | 77090 | 77090 | 77090 | 77090 |  |  | 77090 | 77090 | 77090 | 77090 |  |  | 77090 | 77090 | 77090 |  |  | 77090 | 77090 | 77090 | 77090 |  |  | 77090
t | S.013 | Total | Total | 2006-04-01 | Carthage REC - Carthage T 138 (TP2004139) | 3884542 | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 0% | 3884542 | 3884542 | 0% | 0% | 5731607 | 5731607 | 47.55% | 0% | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 |  |  | 0% | -100% | Corrected total; Shadow work order was missing from prior reports. New total correlates with orginal estimate.
c | S.013 | 5 | 10005 |  | Included in 10007 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.013 | 7 | 10007 |  | Reconductor line with 1272 ACSR | [18 empty] | 5731607 | 5731607 |  |  | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 | 5731607 |  |  | 5731607
< | S.014 | Total | Total | 2007-06-01 | NW Henderson - Oak Hill 138 line (TP2006089) | 54301 | 54301 | 54301 | 0% | 81701 | 81701 | -33.54% | 81701 | 81701 | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 |  |  | 0% | -100% | Not over $100K threshold for regional allocation.
c | S.014 | 48 | 10065 |  | Replace wave trap and reset CTs @ NW Henderson. | [18 empty] | 81701 | 81701 |  |  | 81701 | 81701 |  |  | 81701 | 81701 | 81701 | 81701 |  |  | 81701 | 81701 | 81701 | 81701 |  |  | 81701 | 81701 | 81701 |  |  | 81701 | 81701 | 81701 | 81701 |  |  | 81701
t | S.015 | Total | Total | 2007-07-01 | Arsenal Hill 138 kV cap (TP2004148) | 247950 | 247950 | 247950 | 0% | 372149 | 372149 | -33.37% | 372149 | 372149 | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 |  |  | 0% | -100%
c | S.015 | 30000 | 50000 |  | Install switched capacitor bank. | [18 empty] | 372149 | 372149 |  |  | 372149 | 372149 |  |  | 372149 | 372149 | 372149 | 372149 |  |  | 372149 | 372149 | 372149 | 372149 |  |  | 372149 | 372149 | 372149 |  |  | 372149 | 372149 | 372149 | 372149 |  |  | 372149
t | S.016 | Total | Total | 2008-12-01 | Daingerfield repl CB 1M90 (TP2008017) | ** | 0 | 310667 | n/a | 389326 | 389326 | -20.2% | 389326 | 389326 | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 |  |  | 0% | -100%
c | S.016 | 227 | 10291 |  | Replace Daingerfield 69 kV Breaker # 1M90 & reset relays. | [18 empty] | 389326 | 389326 |  |  | 389326 | 389326 |  |  | 389326 | 389326 | 389326 | 389326 |  |  | 389326 | 389326 | 389326 | 389326 |  |  | 389326 | 389326 | 389326 |  |  | 389326 | 389326 | 389326 | 389326 |  |  | 389326
t | S.017 | Total | Total | 2008-06-01 | Linwood-McWillie (TP2007019) | 1300389 | 1949836.51 | 1949836.51 | 49.94% | 1949836.51 | 1949836.51 | 0% | 1949836.51 | 1949836.51 | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 |  |  | 0% | -100%
c | S.017 | 120 | 10150 |  | 'Rebuild 2.09 miles of 666 ACSR with 1272 ACSR | [18 empty] | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51
n/a | S.018 |  |  | 2008-10-01 | Port Robson - Caplis (SE 1238 kV loop - 2008) (TP2007165) | *** | n/a | n/a | n/a | --- | --- | --- | --- | --- |  | --- | --- | n/a | n/a | [8 empty] | 0% |  |  |  | 0% | [27 empty] | Delete duplicate project. Will track this multi-element multi-year project via 1 set of worksheet F and G tables.
t | S.019 | Total | Total | 2008-05-01 | Wallace Lake - Port Robson (TP2005142) | 2811966 | 4480167.62 | 4480167.62 | 59.33% | 4480167.62 | 4480167.62 | 0% | 4480167.62 | 4480167.62 | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480168 | 4480168 | 8.482e-06% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 8.482e-06% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 |  |  | 0% | -100%
c | S.019 | 113 | 10143 |  | New 138 kV line from Wallace Lake to Finney Tap (includes Wallace Lake terminal) | [18 empty] | 4480168 | 4480168 |  |  | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 | 4480168 |  |  | 4480168
n/a | S.020 |  |  | 2008-11-01 | [NW Ark Area Improve - 2008] Elm Springs, East Rogers,Shipe Rd stations | 1165466 | 1165466 | 1165466 | 0% | --- | --- | --- | --- | --- |  | --- | --- | n/a | n/a | [8 empty] | 0 |  |  |  | 0 | [27 empty] | Transfer: Will track this multi-element multi-year project via S.003 from 2011 Update forward. Investment now included in S.003 above.
t | S.021 | Total | Total | 2010-06-01 | McNabb-Turk 4mi reconductor | n/a | 837610 | 2389000 | n/a | 1609803 | 1609803 | 48.4% | 1638972 | 1638972 | -1.78% | 1638972 | 1638972 | 0% | 0% | 1638972 | 1638972 | 0% | 0% | 1642817 | 1642817 | 0.2346% | 0% | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 |  |  | 0% | -100% | Corrected total.
c | S.021 | 349 | 10449 |  | included in 10450 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
c | S.021 | 349 | 10450 |  | Reconductor 3.55 miles of 666 ACSR with 1590 ACSR | [18 empty] | 1642817 | 1642817 |  |  | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 | 1642817 |  |  | 1642817
t | S.022 | Total | Total | 2010-06-01 | Longwood: r&r switches & bus upgrade | n/a | 0 | 187900 | n/a | 215000 | 215000 | -12.6% | 205882 | 205882 | 4.429% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 |  |  | 0% | -100%
c | S.022 | 30153 | 50161 |  | Replace four (4) switches and upgrading bus work. | [18 empty] | 205882 | 205882 |  |  | 205882 | 205882 |  |  | 205882 | 205882 | 205882 | 205882 |  |  | 205882 | 205882 | 205882 | 205882 |  |  | 205882 | 205882 | 205882 |  |  | 205882 | 205882 | 205882 | 205882 |  |  | 205882
t | S.023 | Total | Total | 2010-06-01 | Reconductor: Greggton-Lake Lamond & Quitman-Westwood 69 kV lines (TP2008015) | n/a | 0 | 4839000 | n/a | 4795139 | 4795139 | 0.9147% | 4795139 | 4795139 | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 |  |  | 0% | -100%
c | S.023 | 292 | 10378 |  | Reconductor 2.66 mile Greggton - Lake Lamond 69 kV with 1272 ACSR. | [18 empty] | 2853625 | 2853625 |  |  | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 | 2853625 |  |  | 2853625
c | S.023 | 297 | 10383 |  | Reconductor Quitman - Westwood 69 kV 3.91 miles of 2/0 with 795 ACSR | [18 empty] | 1941514 | 1941514 |  |  | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 | 1941514 |  |  | 1941514
t | S.024 | Total | Total | 2010-06-01 | Rebuild/recondutor Dyess-ElmSprings REC [Dyess Station-Flint Creek] (TP2008026) | n/a | 0 | 5473000 | n/a | 5250739 | 5250739 | 4.233% | 5250739 | 5250739 | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 |  |  | 0% | -100%
c | S.024 | 296 | 10382 |  | Rebuild/reconductor 5.17 mile Dyess - Elm Springs 161 kV with 2156 ACSR. | [18 empty] | 4984285 | 4984285 |  |  | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 | 4984285 |  |  | 4984285
c | S.024 | 348 | 10445 |  | Replace 161 kV breaker, switches and CTs at Dyess. | [18 empty] | 266454 | 266454 |  |  | 266454 | 266454 |  |  | 266454 | 266454 | 266454 | 266454 |  |  | 266454 | 266454 | 266454 | 266454 |  |  | 266454 | 266454 | 266454 |  |  | 266454 | 266454 | 266454 | 266454 |  |  | 266454
c | S.024 | 30149 | 50157 |  | included in 10445 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
< | S.025 | Total | Total | 2010-12-01 | Replace sw @ Diana | n/a | 0 | 91500 | n/a | 88842 | 88842 | 2.992% | 88842 | 88842 | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 |  |  | 0% | -100% | Not over $100K threshold for regional allocation.
c | S.025 | 613 | 10784 |  | Replace switch at Diana for higher winter rating of 287/316 MVA. Summer rating unchanged. | [18 empty] | 88842 | 88842 |  |  | 88842 | 88842 |  |  | 88842 | 88842 | 88842 | 88842 |  |  | 88842 | 88842 | 88842 | 88842 |  |  | 88842 | 88842 | 88842 |  |  | 88842 | 88842 | 88842 | 88842 |  |  | 88842
t | S.026 | Total | Total | 2011-06-01 | Whitney repl CB and Switches | --- | --- | --- | --- | --- | 279600 | n/a | 249141 | 249141 | 12.23% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 |  |  | 0% | -100%
c | S.026 | 452 | 10586 |  | Replace one breaker and four switches. | [18 empty] | 249141 | 249141 |  |  | 249141 | 249141 |  |  | 249141 | 249141 | 249141 | 249141 |  |  | 249141 | 249141 | 249141 | 249141 |  |  | 249141 | 249141 | 249141 |  |  | 249141 | 249141 | 249141 | 249141 |  |  | 249141
t | S.027 | Total | Total | 2012-06-01 | Linwood - Powell Street 138 kV | --- | --- | --- | --- | --- | --- | n/a | --- | 450200 | n/a | 430017 | 430017 | -4.483% | 0% | 430017 | 430017 | 0% | 0% | 421517 | 421517 | -1.977% | 0% | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 |  |  | 0% | -100% | Corrected total (took out removal cost)
c | S.027 | 30152 | 50160 |  | Replace 138 kV breaker, switches, and jumpers at Linwood. Replace circuit switcher at Powell Street. | [18 empty] | 421517 | 421517 |  |  | 421517 | 421517 |  |  | 421517 | 421517 | 421517 | 421517 |  |  | 421517 | 421517 | 421517 | 421517 |  |  | 421517 | 421517 | 421517 |  |  | 421517 | 421517 | 421517 | 421517 |  |  | 421517
t | S.028 | Total | Total | 2012-06-01 | Bloomburg-Texarkana Plant (TP2008027) | --- | --- | --- | --- | --- | --- | n/a | --- | 5819300 | n/a | 5267709 | 5267709 | -9.479% | 0% | 5268487 | 5268487 | 0.01477% | 0% | 5268487 | 5268487 | 0% | 0% | 5268479 | 5268479 | -0.0001518% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | -0.0001518% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 |  |  | 0% | -100% | slight discrepancy in sum of costs versus prior total
c | S.028 | 30156 | 50164 |  | Change out the 500 Cu jumpers at Texarkana Plant. | [18 empty] | 37531 | 37531 |  |  | 37531 | 37531 |  |  | 37531 | 37531 | 37531 | 37531 |  |  | 37531 | 37531 | 37531 | 37531 |  |  | 37531 | 37531 | 37531 |  |  | 37531 | 37531 | 37531 | 37531 |  |  | 37531
c | S.028 | 30157 | 50165 |  | Rebuild 5.92 miles of 266 ACSR with 795 ACSR. Replace 69KV switches, jumpers, and reset CTs and relays at Texarkana Plant | [18 empty] | 5230948 | 5230948 |  |  | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 | 5230948 |  |  | 5230948
t | S.029 | Total | Total | 2012-12-01 | Knox Lee - Pirkey 138 kV / Pirkey - Whitney 138 kV - Replace Breaker, Wavetraps, and reset relays and CT's (TP2010062) | --- | --- | --- | --- | --- | --- | n/a | --- | 1521900 | n/a | 1886753 | 1886753 | 23.97% | 0% | 1881887 | 1881887 | -0.2579% | 0% | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 |  |  | 0% | -100%
c | S.029 | 30317 | 50363 |  | Replace 3 2000 A switches at Knox Lee | [18 empty] | 256687 | 256687 |  |  | 256687 | 256687 |  |  | 256687 | 256687 | 256687 | 256687 |  |  | 256687 | 256687 | 256687 | 256687 |  |  | 256687 | 256687 | 256687 |  |  | 256687 | 256687 | 256687 | 256687 |  |  | 256687
c | S.029 | 30318 | 50364 |  | Replace Switch at Easton, and Breaker and Switch at Pirkey | [18 empty] | 1158231 | 1158231 |  |  | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 | 1158231 |  |  | 1158231
c | S.029 | 30319 | 50365 |  | Reset CT, Replace Breaker and Switch | [18 empty] | 466969 | 466969 |  |  | 466969 | 466969 |  |  | 466969 | 466969 | 466969 | 466969 |  |  | 466969 | 466969 | 466969 | 466969 |  |  | 466969 | 466969 | 466969 |  |  | 466969 | 466969 | 466969 | 466969 |  |  | 466969
t | S.030 | Total | Total | 2012-08-31 | NW Texarkana - Turk 345 | --- | --- | --- | --- | --- | --- | n/a | --- | 47434000 | n/a | 47172572 | 47172572 | -0.5511% | 0% | 47415121 | 47415121 | 0.5142% | 0% | 47659752 | 47659900 | 0.5159% | 0.0003105% | 47660028.54 | 47659900 | 0.0002697% | -0.0002697% | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0.0002697% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 |  |  | 0% | -100%
c | S.030 | 349 | 10456 |  | Add Turk 345/138 kV transformer | [18 empty] | 7533965 | 7533965 |  |  | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 | 7533965 |  |  | 7533965
c | S.030 | 30142 | 50148 |  | Build approximately 33 miles of 2-954 ACSR from Turk to NW Texarkana. | [18 empty] | 38394007 | 38394007 |  |  | 38394283.54 | 38394007 |  |  | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54
c | S.030 | 30142 | 50149 |  | Add 345 kV terminal at NW Texarkana | [18 empty] | 1731780 | 1731780 |  |  | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 | 1731780 |  |  | 1731780
c | S.030 | 30142 | 50150 |  | included in 10456 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | S.031 | Total | Total | 2012-06-01 | Lone Star South - Pittsburg 138 kV - Replace Wavetraps, reset CT's and Relays (TP2009100) | --- | --- | --- | --- | --- | --- | n/a | --- | 284100 | n/a | 230750 | 230750 | -18.78% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 |  |  | 0% | -100%
c | S.031 | 391 | 10509 |  | Replace 138 kV wavetraps at both ends. Reset CTs at Lone Star South. Reset relays at Pittsburg. | [18 empty] | 230750 | 230750 |  |  | 230750 | 230750 |  |  | 230750 | 230750 | 230750 | 230750 |  |  | 230750 | 230750 | 230750 | 230750 |  |  | 230750 | 230750 | 230750 |  |  | 230750 | 230750 | 230750 | 230750 |  |  | 230750
t | S.032 | Total | Total | 2012-06-01 | Howell-Kilgore 69 kV rebuild | --- | --- | --- | --- | --- | --- | n/a | --- | 3985900 | n/a | 4204655 | 4204655 | 5.488% | 0% | 4157737 | 4157737 | -1.116% | 0% | 4175110 | 4175110 | 0.4178% | 0% | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 |  |  | 0% | -100%
c | S.032 | 392 | 10510 |  | Rebuild 3.49 miles of Howell - Kilgore 69 kV 4/0 ACSR with 795 ACSR. | [18 empty] | 4175110 | 4175110 |  |  | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 | 4175110 |  |  | 4175110
t | S.033 | Total | Total | 2014-04-01 | Flint Creek-Shipe Road 345 kV Line (TP2008126) | --- | --- | --- | --- | --- | --- | n/a | --- | 1609000 | n/a | 4101857 | 12471857 | 154.9% | 204.1% | 8981434 | 55496134 | -27.99% | 517.9% | 58065903 | 57951403 | 4.631% | -0.1972% | 58124321.73 | 59295600.19 | 0.2984% | 2.015% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0.01718% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 |  |  | 0% | -100% | Multi-element multi-year base plan project. Work orginally projected for 2013 was moved to 2014. Final in-service yr in 12', 13' and 14'.
c | S.033 | 450 | 10582 |  | Install 9 miles of 161 kV from new Shipe Road Substation to East Centerton Substation. | [18 empty] | 10957716 | 10957716 |  |  | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 | 10957716 |  |  | 10957716 |  |  |  |  | Includes all 161 kV line work.
c | S.033 | 450 | 10584 |  | Install 345/161 kV transformer at Shipe Road. | [18 empty] | 15546751 | 15546751 |  |  | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 | 15546751 |  |  | 15546751 |  |  |  |  | Includes all station work.
c | S.033 | 450 | 10585 |  | Install 18 miles of new 345 kV, 2-954 ACSR line. | [18 empty] | 31561436 | 31446936 |  |  | 31619854.73 | 32791133.19 |  |  | 31619854.73 | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 |  |  |  |  | Includes all 345 kV line work. Added this to include the revision for the condemnation
t | S.034 | Total | Total | 2013-11-01 | Bann - LS Ordnance - Hooks 69 kV - Rebuild 7.1 mi (TP2011024) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 8177700 | n/a | n/a | 8593855 | 8593855 | 5.089% | 0% | 8598828 | 8598828 | 0.05787% | 0% | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 |  |  | 0% | -100%
c | S.034 | 1081 | 11421 |  | Rebuild 1.68-mile Hooks - Lone Star Ordinance Tap 69 kV line. Replace switch 6006 at Lone Star Ordinance. | [18 empty] | 8598828 | 8598828 |  |  | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 | 8598828 |  |  | 8598828 |  |  |  |  | Includes 7.1 mile line rebuild, and terminal work at Lone Star Ordnance Tap and Bann.
c | S.034 | 30148 | 50156 |  | included in 11421 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | S.035 | Total | Total | 2013-06-01 | Diana - Replace North Autotransformer #3 (TP2010065) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 3795000 | n/a | n/a | 4344847 | 4344847 | 14.49% | 0% | 4344850 | 4344850 | 6.905e-05% | 0% | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 |  |  | 0% | -100%
c | S.035 | 30316 | 50375 |  | Replace auto with new 450 MVA. | [18 empty] | 4344850 | 4344850 |  |  | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 | 4344850 |  |  | 4344850
t | S.036 | Total | Total | 2013-09-01 | Osburn 161 kV Line Work | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 1750000 | n/a | n/a | 3038117 | 3038117 | 73.61% | 0% | 6389739 | 6389739 | 110.3% | 0% | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 |  |  | 0% | -100% | Includes T station and T line per Pennybaker/Rainbolt
c | S.036 | 443 | 10575 |  | Tap the South Springdale-East Fayetteville 161 kV line and build 1.5 miles of 161 kV to new Osbourne station. | [18 empty] | 6389739 | 6389739 |  |  | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 | 6389739 |  |  | 6389739
t | S.037 | Total | Total | 2013-06-01 | SW Shreveport to Spring Ridge REC 138 kV Line Rebuild (TP2010066) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 4585200 | n/a | n/a | 5048185 | 5048185 | 10.1% | 0% | 5048526 | 5048526 | 0.006755% | 0% | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 |  |  | 0% | -100%
c | S.037 | 1023 | 11347 |  | Rebuild 7.11 miles of 397.5 ACSR with 1272 ACSR | [18 empty] | 5048526 | 5048526 |  |  | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 | 5048526 |  |  | 5048526
t | S.038 | Total | Total | 2013-06-01 | Eastex Switching Station - Whitney 138 kV Station - Rebuild 2.5 miles of 138 kV (TP2010064) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 3095000 | n/a | n/a | 2636239 | 2636239 | -14.82% | 0% | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 |  |  | 0% | -100%
c | S.038 | 1024 | 11348 |  | Rebuild 2.49 miles with 1590 ACSR. Replace wavetrap and jumpers at Whitney. Replace metering CT at Eastex. | [18 empty] | 2636239 | 2636239 |  |  | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 | 2636239 |  |  | 2636239
t | S.039 | Total | Total | 2013-02-01 | Ashdown West - Craig Junction 138KV Rebuild (TP2009092) | [14 empty] | 4316127 | 4316127 |  |  | 4316668 | 4316668 | 0.01253% | 0% | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 |  |  | 0% | -100% | Asset has been transferred to SWEPCO from PSO, thus placing the line back with the original owner.
c | S.039 | 770 | 11015 |  | Rebuild 2.45 miles of 795 ACSR with 1590 ACSR and reset relays. | [18 empty] | 4316668 | 4316668 |  |  | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 | 4316668 |  |  | 4316668
t | S.040 | Total | Total | 2014-06-01 | Rock Hill to Carthage 69 kV Rebuild 11.4 Miles (TP2010102) | [14 empty] | 0 | 9550200 |  |  | 9637037 | 9637037 | 0.9093% | 0% | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 |  |  | 0% | -100%
c | S.040 | 882 | 11171 |  | Rebuild or reconductor 11.4-mile Rock Hill - Carthage line from 336 ACSR to 1272 ACSR and remove switches in middle of line. Upgrade breaker, switches, CT ratios, and relay settings at Carthage substation. Upgrade jumpers, switches, CT ratios, and relay settings at Rock Hill substation. | [18 empty] | 9637037 | 9637037 |  |  | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 | 9637037 |  |  | 9637037
t | S.041 | Total | Total | 2014-12-01 | Broadmoor to Fern Street 69 kV Rebuild 1 mile (TP2010103) | [14 empty] | 0 | 3846600 |  |  | 4675710 | 4795000 | 21.55% | 2.551% | 4825048 | 4795000 | 0.6267% | -0.6228% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 1.481% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 |  |  | 0% | -100% | Includes terminal work at both Fern Street and Broadmoor.
c | S.041 | 681 | 10898 |  | Rebuild 1-mile portion of the 69 kV line from Broadmoor to Fern Street with 1233.6 ACSR/TW. Replace switches at Fern Street. | [18 empty] | 4675710 | 4795000 |  |  | 4825048 | 4675710 |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31
t | S.042 | Total | Total | 2014-06-01 | Northwest Henderson to Poynter 69 kV Rebuild 3.2 miles (TP2004031) | [14 empty] | 0 | 4520000 |  |  | 5289194 | 5289194 | 17.02% | 0% | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 |  |  | 0% | -100% | Includes terminal work at both Northwest Henderson and Poynter
c | S.042 | 502 | 10647 |  | Reconductor 3.25-mile 69 kV line from Northwest Henderson to Poynter with 1272 ACSR. | [18 empty] | 5289194 | 5289194 |  |  | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 | 5289194 |  |  | 5289194
t | S.043 | Total | Total | 2014-11-01 | Diana to Perdue 138 kV Rebuild 21.8 miles; Station Upgrades at Diana and Perdue (TP2011023) | [14 empty] | 0 | 14332500 |  |  | 14950466 | 15026000 | 4.312% | 0.5052% | 14866883.03 | 15026000 | -1.059% | 1.07% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | -1.059% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 |  |  | 0% | -100%
c | S.043 | 1012 | 11331 |  | Rebuild 21.85-mile 138 kV line from Diana to Perdue. Replace switches, jumpers, and upgrade CT ratios at Diana and Perdue. Upgrade relay settings at Diana. | [18 empty] | 14950466 | 15026000 |  |  | 14866883.03 | 14986466 |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03
c | S.043 | 503 | 10648 |  | Included in 11331 | [18 empty] | 0 | 0 |  |  | 0 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12
c | S.043 | 30436 | 50531 |  | Included in 11331 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | S.044 | Total | Total | 2007-11-01 | Pittsburg-Winnsboro-North Mineola | [18 empty] | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 |  |  |  |  | not sure if stations are to be included
c | S.044 | 10 | 10010 | 2006-07-01 | PITTSBURG - WINNSBORO 138KV CKT 1 | [18 empty] | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79
c | S.044 | 40 | 10044 | 2007-10-01 | NORTH MINEOLA - WINNSBORO 138KV CKT 1 | [18 empty] | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6
c | S.044 |  |  | 2007-11-01 | Pittsburg and Mineola Stations | [18 empty] | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 |  |  |  |  | not sure if stations are to be included
t | S.045 | Total | Total | 2007-03-01 | CHAMBER SPRINGS - TONTITOWN 161KV CKT 1 | [18 empty] | 2658452 | 2658452 |  |  | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452
c | S.045 | 45 | 10049 |  | Reconductor 666 ACSR (11.6 miles) and 1272 ACSR (.1 mile) to Drake ACCC (2156 ACSR section 0.6 miles is not replaced) and remove the series reactors at Chamber Springs on the Chamber Springs to Tontitown 161 kV line | [18 empty] | 2658452 | 2658452 |  |  | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452
t | S.046 | Total | Total | 2008-05-01 | CHAMBER SPRINGS - TONTITOWN 345KV CKT 1 | [18 empty] | 16318844 | 16318844 |  |  | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 |  |  |  |  | Includes 345 kV line and Chamber Springs 345 kV terminal work.
c | S.046 | 117 | 10147 |  | Install new 345 kV line , ROW and terminal equipment at Chamber Springs | [18 empty] | 16318844 | 16318844 |  |  | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844
t | S.047 | Total | Total | 2012-02-01 | FULTON - HOPE 115KV CKT 1 | [18 empty] | 787880 | 787880 |  |  | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880
c | S.047 | 221 | 10280 |  | Replace conductor in Hope Substation | [18 empty] | 787880 | 787880 |  |  | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880
t | S.048 | Total | Total | 2010-03-01 | MINEOLA - NORTH MINEOLA 69KV CKT 1 | [18 empty] | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 |  |  |  |  | 69 kV Upgrade.
c | S.048 | 294 | 10380 |  | Replace Mineola 2 Switches & Breaker | [18 empty] | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1
n/a | S.049 | Total | Total |  | BANN - KINGS HIGHWAY 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; Distribution investment
c | S.049 | 1 | 10001 |  | Replace Switch in King Hwy substation | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
n/a | S.050 | Total | Total |  | LONE STAR SOUTH - PITTSBURG 138KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; no Capital investment
c | S.050 | 8 | 10008 |  | Replace CT | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
n/a | S.051 | Total | Total |  | BANN - LONESTAR ORDINANCE TAP 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; no Capital investment
c | S.051 | 291 | 10377 |  | Relay at Bann new limits will be 65/72 MVA summer (line conductor/Lonestar switch) and 72/72 MVA winter (Lonestar Switch) | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
n/a | S.052 | Total | Total |  | FOREST HILLS REC - QUITMAN 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; Distribution investment
c | S.052 | 346 | 10443 |  | Replace Quitman 69KV bus, switches and jumpers. Change CT and relay settings. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
n/a | S.053 | Total | Total |  | MAGNOLIA TAP - WINNSBORO 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; Distribution investment
c | S.053 | 343 | 10440 |  | Replace 69 kV switches at Winnsboro and reset CT ratios and relay settings. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
n/a | S.054 | Total | Total |  | CARTHAGE - ROCK HILL 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; no Capital investment
c | S.054 | 449 | 10581 |  | Reset CTs at Carthage on the Carthage - Rock Hill line. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
n/a | S.055 | Total | Total |  | FOREST HILLS REC - QUITMAN 69KV CKT 1 #2 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; no Capital investment
c | S.055 | 641 | 10842 |  | Replace two switches at Quitman substation. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
< | S.056 | Total | Total | 2010-11-01 | SUGAR HILL 138/69KV TRANSFORMER CKT 1 | [18 empty] | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 |  |  |  |  | Not over $100K threshold for regional allocation.
c | S.056 | 875 | 11155 |  | Replace 69 kV switch 11985 and 1033 AAC jumpers at Sugar Hill. | [18 empty] | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78
n/a | S.057 | Total | Total |  | OKAY - TOLLETTE 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | Ignore; no Capital investment
c | S.057 | 30155 | 50163 |  | Replace 69 kV switches. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | S.058 | Total | Total | 2016-12-16 | Valliant-NW Texarkana 345 kV | [18 empty] | 0 | 4700000 |  |  | 4525574.69 | 5020278.69 | -3.711% | 10.93% | 94208721.06 | 99956721.06 | 99956721.06 | 99956721.06 | 1777% | 6.101% | 97244454.87 | 99956721.06 | 99956721.06 | 99956721.06 | -2.713% | 2.789% | 97368971.1 | 97368971.1 | 97368971.1 | -2.589% | 2.658% | 97370354 | 97370354 | 97370354 | 97370354 | 0.00142% | 0% | 97370354 |  |  | 0% | -100% | Northwest Texarkana 345 kV terminal work and 345 kV ine relocations completed November 2015; Also see related PSO project (P.018) and OKTCo project (OKT.009).
c | S.058 | 936 | 11236 |  | 345 kV from Valliant substation to NW Texarkana substation | [18 empty] | 0 | 4700000 |  |  | 4525574.69 | 5020278.69 |  |  | 94208721.06 | 99956721.06 | 99956721.06 | 99956721.06 |  |  | 97244454.87 | 99956721.06 | 99956721.06 | 99956721.06 |  |  | 97368971.1 | 97368971.1 | 97368971.1 |  |  | 97370354 | 97370354 | 97370354 | 97370354 |  |  | 97370354
t | S.059 | Total | Total | 2017-07-01 | Brownlee-North Market 69 kV Rebuild | [18 empty] | 0 | 5900000 |  |  | 0 | 9636180.69 |  |  | 606412.23 | 16078412.23 | 16078412.23 | 16078412.23 | -93.71% | 2551% | 17140808.91 | 16078412.23 | 16078412.23 | 16078412.23 | 6.608% | -6.198% | 17132431.49 | 17132431.49 | 17132431.49 | 6.555% | -6.152% | 17132604 | 17132604 | 17132604 | 17132604 | 0.001007% | 0% | 17132604 |  |  | 0% | -100% | Brownlee Road Station upgrades in-serviced 5/16; remainder of project to be in-serviced 6/17.
c | S.059 | 504 | 10649 |  | Rebuild 4.7 mile 69 kV line from Brownlee to North Market | [18 empty] | 0 | 5900000 |  |  | 0 | 9636180.69 |  |  | 606412.23 | 16078412.23 | 16078412.23 | 16078412.23 |  |  | 17140808.91 | 16078412.23 | 16078412.23 | 16078412.23 |  |  | 17132431.49 | 17132431.49 | 17132431.49 |  |  | 17132604 | 17132604 | 17132604 | 17132604 |  |  | 17132604
t | S.060 | Total | Total | 2016-04-01 | Rock Hill-Springridge Pan-Harr REC 138 kV Ckt 1 | [18 empty] | 0 | 0 |  |  | 18845095.45 | 23229161.06 |  | 23.26% | 24727060.23 | 25217060.23 | 25217060.23 | 25217060.23 | 6.448% | 1.982% | 25330929.21 | 25217060.23 | 25217060.23 | 25217060.23 | 0.4516% | -0.4495% | 25330929.21 | 25217060.23 | 25217060.23 | 0.4516% | -0.4495% | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 0.4516% | 0% | 25330929.21 |  |  | 0% | -100% | Includes all components in project
c | S.060 | 30449 | 50545 |  | Rebuild 27.6 mile 138 kV ine with 1926.9 ACSR/TW. | [18 empty] | 0 | 0 |  |  | 18845095.45 | 23229161.06 |  |  | 24727060.23 | 25217060.23 | 25217060.23 | 25217060.23 |  |  | 25330929.21 | 25217060.23 | 25217060.23 | 25217060.23 |  |  | 25330929.21 | 25217060.23 | 25217060.23 |  |  | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 |  |  | 25330929.21
t | S.063 | Total | Total | 2016-04-21 | Winnsboro 138 kV (TP2013122) | [18 empty] | 0 | 0 |  |  | 0 | 1140471.94 |  |  | 1230858.46 | 1230858.46 | 1230858.46 | 1230858.46 | 7.925% | 0% | 1231360.51 | 1230858.46 | 1230858.46 | 1230858.46 | 0.04079% | -0.04077% | 1231360.51 | 1230858.46 | 1230858.46 | 0.04079% | -0.04077% | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 0.04079% | 0% | 1231360.51 |  |  | 0% | -100%
c | S.063 | 30296 | 50334 |  | Install a new 28.8 MVAr capacitor bank at Winnsboro 138 kV substation | [18 empty] | 0 | 0 |  |  | 0 | 1140471.94 |  |  | 1230858.46 | 1230858.46 | 1230858.46 | 1230858.46 |  |  | 1231360.51 | 1230858.46 | 1230858.46 | 1230858.46 |  |  | 1231360.51 | 1230858.46 | 1230858.46 |  |  | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 |  |  | 1231360.51
t | S.082 | Total | Total | 2016-06-01 | Messick 500/230 kV (TP2011033) | [18 empty] | 0 | 0 |  |  | 0 | 54032914.56 |  |  | 58503883.45 | 59534283.45 | 59534283.45 | 59534283.45 | 8.275% | 1.761% | 59387255.91 | 59534283.45 | 59534283.45 | 59534283.45 | -0.247% | 0.2476% | 58648888.77 | 58648888.77 | 58648888.77 | -1.487% | 1.51% | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 0.001691% | 0% | 58649880.67 |  |  | 0% | -100% | Includes all P11033 components: station, land, line connection work
c | S.082 | 30495 | 50607 |  | Messick 500/230 kV Transformer Ckt1 | [18 empty] | 0 | 0 |  |  | 0 | 54032914.56 |  |  | 58503883.45 | 59534283.45 | 59534283.45 | 59534283.45 |  |  | 59387255.91 | 59534283.45 | 59534283.45 | 59534283.45 |  |  | 58648888.77 | 58648888.77 | 58648888.77 |  |  | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 |  |  | 58649880.67
c | S.082 | 30495 | 50615 |  | included in 50607 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0
t | S.064 | Total | Total | 2016-09-10 | Logansport 138 kV (TP2011022) | [18 empty] | 0 | 0 |  |  | 0 | 1111301.77 |  |  | 1556621.42 | 1556621.42 | 1556621.42 | 1556621.42 | 40.07% | 0% | 1558180.61 | 1556621.42 | 1556621.42 | 1556621.42 | 0.1002% | -0.1001% | 1558180.61 | 1556621.42 | 1556621.42 | 0.1002% | -0.1001% | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 0.1002% | 0% | 1558180.61 |  |  | 0% | -100%
c | S.064 | 30298 | 50336 |  | Install a new 28.8 MVAr capacitor bank at Logansport 138 kV substation | [18 empty] | 0 | 0 |  |  | 0 | 1111301.77 |  |  | 1556621.42 | 1556621.42 | 1556621.42 | 1556621.42 |  |  | 1558180.61 | 1556621.42 | 1556621.42 | 1556621.42 |  |  | 1558180.61 | 1556621.42 | 1556621.42 |  |  | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 |  |  | 1558180.61
t | S.067 | Total | Total | 2015-06-05 | Dekalb-New Boston 69 kV | [18 empty] | 49364.11 | 15500000 |  |  | 15777910.71 | 15777910.71 | 1.793% | 0% | 15991916.9 | 15998916.9 | 15998916.9 | 15998916.9 | 1.356% | 0.04377% | 16142203.19 | 15998916.9 | 15998916.9 | 15998916.9 | 0.8956% | -0.8877% | 16209336.9 | 16209336.9 | 16209336.9 | 1.315% | -1.298% | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | -1.719% | 0% | 15930624.49 |  |  | 0% | -100% | 69 kV Upgrade. Dekalb Station upgrades in-serviced Oct-14.
c | S.067 | 30471 | 50567 |  | Rebuild 13.2 mile line; Upgrade CT ratios and relay settings at New Boston. | [18 empty] | 49364.11 | 15500000 |  |  | 15777910.71 | 15777910.71 |  |  | 15991916.9 | 15998916.9 | 15998916.9 | 15998916.9 |  |  | 16142203.19 | 15998916.9 | 15998916.9 | 15998916.9 |  |  | 16209336.9 | 16209336.9 | 16209336.9 |  |  | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 |  |  | 15930624.49
t | S.068 | Total | Total | 2016-04-13 | Ellerbe Rd - South Shreveport 69 kV Build (TP201154) | [18 empty] | 0 | 0 |  |  | 0 | 8831593.04 |  |  | 9375483.42 | 9375483.42 | 9375483.42 | 9375483.42 | 6.158% | 0% | 9381462.72 | 9375483.42 | 9375483.42 | 9375483.42 | 0.06378% | -0.06374% | 9381462.72 | 9375483.42 | 9375483.42 | 0.06378% | -0.06374% | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 | 0.06378% | 0% | 9381462.72 |  |  | 0% | -100%
c | S.068 | 478 | 10615 |  | Forbing Tap - South Shreveport 69 kV | [18 empty] | 0 | 0 |  |  | 0 | 619192.68 |  |  | 641980.68 | 641980.68 | 641980.68 | 641980.68 |  |  | 642202.51 | 641980.68 | 641980.68 | 641980.68 |  |  | 642202.51 | 641980.68 | 641980.68 |  |  | 642202.51 | 642202.51 | 642202.51 | 642202.51 |  |  | 642202.51 |  |  |  |  | Assumed S. Shreveport and Forbing terminal work only
c | S.068 | 512 | 10657 |  | Ellerbe Road - Forbing Tap 69 kV Ckt 1 | [18 empty] | 0 | 0 |  |  | 0 | 8212400.36 |  |  | 8733502.74 | 8733502.74 | 8733502.74 | 8733502.74 |  |  | 8739260.21 | 8733502.74 | 8733502.74 | 8733502.74 |  |  | 8739260.21 | 8733502.74 | 8733502.74 |  |  | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 |  |  | 8739260.21 |  |  |  |  | Assumed all line work plus Ellerbe Rd terminal work
t | S.069 | Total | Total | 2015-06-25 | Hardy Street-Waterworks 69 kV | [18 empty] | 0 | 5200000 |  |  | 5366606.14 | 5366606.14 | 3.204% | 0% | 5401890.07 | 5429685.07 | 5429685.07 | 5429685.07 | 0.6575% | 0.5145% | 5522411.15 | 5429685.07 | 5429685.07 | 5429685.07 | 1.708% | -1.679% | 5522411.15 | 5522411.15 | 5522411.15 | 1.708% | -1.679% | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 0% | 0% | 5522411.15 |  |  | 0% | -100% | 69 kV Upgrade.
c | S.069 | 30472 | 50568 |  | Rebuild 1.6 mile line from Hardy Street to Waterworks with 1233.6 ACSR/TW | [18 empty] | 0 | 5200000 |  |  | 5366606.14 | 5366606.14 |  |  | 5401890.07 | 5429685.07 | 5429685.07 | 5429685.07 |  |  | 5522411.15 | 5429685.07 | 5429685.07 | 5429685.07 |  |  | 5522411.15 | 5522411.15 | 5522411.15 |  |  | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 |  |  | 5522411.15
t | S.070 | Total | Total | 2015-05-15 | Red Oak (State Line)-North Huntington 69 kV | [18 empty] | 3741684.51 | 12300000 |  |  | 11990487.31 | 11990487.31 | -2.516% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0.2258% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 |  |  | 0% | -100% | 69 kV Upgrade. State Line to Midland line rebuild in-serviced Dec-14.
c | S.070 | 30473 | 50569 |  | Rebuild 4.0 mile line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington. | [18 empty] | 0 | 6300000 |  |  | 5181390.93 | 5181390.93 |  |  | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 |  |  |  |  | P12164003, P12164503
c | S.070 | 30474 | 50570 |  | Rebuild 1.3 mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | [18 empty] | 0 | 0 |  |  | 2368056.53 | 2368056.53 |  |  | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 |  |  |  |  | P12164005/006/007, P12164505/506/507
c | S.070 | 30475 | 50571 |  | Rebuild 7.0 mile 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of the line to be rebult is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | [18 empty] | 3741684.51 | 6000000 |  |  | 4441039.85 | 4441039.85 |  |  | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 |  |  |  |  | P12164001/002, P12164501/502
t | S.071 | Total | Total | 2015-05-01 | Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | [18 empty] | 0 | 5900000 |  |  | 5724549.21 | 5724549.21 | -2.974% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0.2352% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 |  |  | 0% | -100% | 69 kV Upgrade.
c | S.071 | 30731 | 50990 |  | Rebuild 2.75 mile 69 kV line from Mt. Pleasant to West Mt. Pleasant | [18 empty] | 0 | 5900000 |  |  | 5724549.21 | 5724549.21 |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91
t | S.072 | Total | Total | 2015-11-01 | Benteler - Port Robson 138 kV Ckt 1 and 2 | [18 empty] | 13776207.78 | 13860000 |  |  | 13851900 | 13875791.7 | -0.05844% | 0.1725% | 13851900 | 13851900 | 13851900 | 13851900 | -0.1722% | 0% | 13851900 | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 |  |  | 0% | -100%
c | S.072 | 30769 | 51045 |  | Build 138 kV line from Benteler to Port Robson (Ckt 1) | [18 empty] | 8781708.73 | 8800000 |  |  | 8784201 | 8796443.31 |  |  | 8784201 | 8784201 | 8784201 | 8784201 |  |  | 8784201 | 8784201 | 8784201 | 8784201 |  |  | 8784201 | 8784201 | 8784201 |  |  | 8784201 | 8784201 | 8784201 | 8784201 |  |  | 8784201
c | S.072 | 30769 | 51046 | 2014-12-01 | Build 138 kV line from Benteler to Port Robson (Ckt 2) | [18 empty] | 4994499.05 | 5060000 |  |  | 5067699 | 5079348.39 |  |  | 5067699 | 5067699 | 5067699 | 5067699 |  |  | 5067699 | 5067699 | 5067699 | 5067699 |  |  | 5067699 | 5067699 | 5067699 |  |  | 5067699 | 5067699 | 5067699 | 5067699 |  |  | 5067699
t | S.073 | Total | Total | 2017-06-26 | Letourneau 69 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1185000 | 1185000 | 1185000 |  |  | 1244156.8 | 1185000 | 1185000 | 1185000 | 4.992% | -4.755% | 1247291.61 | 1247291.61 | 1247291.61 | 5.257% | -4.994% | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 0% | 0% | 1247291.61 |  |  | 0% | -100%
c | S.073 | 30598 | 50759 |  | Letourneau 69 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1185000 | 1185000 | 1185000 |  |  | 1244156.8 | 1185000 | 1185000 | 1185000 |  |  | 1247291.61 | 1247291.61 | 1247291.61 |  |  | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 |  |  | 1247291.61
t | S.074 | Total | Total | 2017-12-20 | Brooks Street - Edwards Street 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 5508000 | 5508000 | 5508000 |  |  | 3816677.16 | 5508000 | 5508000 | 5508000 | -30.71% | 44.31% | 4649535.7 | 4649535.7 | 4649535.7 | -15.59% | 18.46% | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | -0.01644% | 0% | 4648771.29 |  |  | 0% | -100% | Includes line, ROW, and terminal upgrades. ISD moved out to 2018. Station components were moved to rehab, P14138004 and P14138005 (P14138006/007 are shadows - these two were not included last year) are under TA2015706.
c | S.074 | 30895 | 51215 |  | Brooks Street - Edwards Street 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 5508000 | 5508000 | 5508000 |  |  | 3816677.16 | 5508000 | 5508000 | 5508000 |  |  | 4649535.7 | 4649535.7 | 4649535.7 |  |  | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 |  |  | 4648771.29
t | S.075 | Total | Total | 2017-04-01 | Hallsville - Marshall New 69 kV Circuit | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 12938000 | 15870000 | 15870000 |  |  | 17094285.41 | 15870000 | 15870000 | 15870000 | 7.714% | -7.162% | 17159057.35 | 17159057.35 | 17159057.35 | 8.123% | -7.512% | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 0% | 0% | 17159057.35 |  |  | 0% | -100% | Includes line, ROW, and Marshall terminal upgrades. BPIDs P13167004, 005, 006, 009, 010, 014 and shadow BPIDs.
c | S.075 | 30576 | 50721 |  | Hallsville - Marshall New 69 kV Circuit | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 12938000 | 15870000 | 15870000 |  |  | 17094285.41 | 15870000 | 15870000 | 15870000 |  |  | 17159057.35 | 17159057.35 | 17159057.35 |  |  | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 |  |  | 17159057.35
t | S.076 | Total | Total | 2017-11-09 | Daingerfield - Jenkins Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1835000 | 1835000 | 1835000 |  |  | 2368917.22 | 1835000 | 1835000 | 1835000 | 29.1% | -22.54% | 2385215.9 | 2385215.9 | 2385215.9 | 29.98% | -23.07% | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 0% | 0% | 2385215.9 |  |  | 0% | -100% | Includes line and ROW.
c | S.076 | 30574 | 50719 |  | Daingerfield - Jenkins Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1835000 | 1835000 | 1835000 |  |  | 2368917.22 | 1835000 | 1835000 | 1835000 |  |  | 2385215.9 | 2385215.9 | 2385215.9 |  |  | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 |  |  | 2385215.9
t | S.077 | Total | Total | 2017-07-01 | Broadmoor - Fort Humbug 69 kV Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 6425000 | 6425000 | 6425000 |  |  | 6480399.04 | 6425000 | 6425000 | 6425000 | 0.8622% | -0.8549% | 6505905.04 | 6505905.04 | 6505905.04 | 1.259% | -1.244% | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 0.158% | 0% | 6516183.71 |  |  | 0% | -100% | Includes line and terminal upgrades. Project is in service in 2017.
c | S.077 | 30573 | 50718 |  | Broadmoor - Fort Humbug 69 kV Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 6425000 | 6425000 | 6425000 |  |  | 6480399.04 | 6425000 | 6425000 | 6425000 |  |  | 6505905.04 | 6505905.04 | 6505905.04 |  |  | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 |  |  | 6516183.71
t | S.078 | Total | Total | 2017-03-28 | Chamber Springs - Farmington 161 kV Line | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 554275 | 9206275 | 9206275 | 9206275 |  |  | 10563889.59 | 9206275 | 9206275 | 9206275 | 14.75% | -12.85% | 10670271.15 | 10670271.15 | 10670271.15 | 15.9% | -13.72% | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | -0.01378% | 0% | 10668801.15 |  |  | 0% | -100%
c | S.078 | 451 | 10583 |  | Chamber Springs - Farmington 161 kV Line | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 554275 | 9206275 | 9206275 | 9206275 |  |  | 10563889.59 | 9206275 | 9206275 | 9206275 |  |  | 10670271.15 | 10670271.15 | 10670271.15 |  |  | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 |  |  | 10668801.15
t | S.061 | Total | Total | 2018-05-11 | Evenside - Northwest Henderson 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9731000 |  |  | 0 | 9731000 | 9731000 | 9731000 | 0% | 0% | 11168314.8 | 11168314.8 | 11168314.8 | 14.77% | -12.87% | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 0.02813% | 0% | 11171456.22 |  |  | 0% | -100%
c | S.061 | 501 | 10646 |  | Evenside - Northwest Henderson 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9731000 |  |  | 0 | 9731000 | 9731000 | 9731000 |  |  | 11168314.8 | 11168314.8 | 11168314.8 |  |  | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 |  |  | 11171456.22
t | S.079 | Total | Total | 2017-04-01 | Hallsville - Longview Heights 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9152000 |  |  | 0 | 9152000 | 9152000 | 9152000 | 0% | 0% | 9930039.32 | 9930039.32 | 9930039.32 | 8.501% | -7.835% | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 0% | 0% | 9930039.32 |  |  | 0% | -100% | includes line, ROW, and Longview Hgts terminal upgrades. BPIDs P13167001, 002, 003 and shadow BPIDs.
c | S.079 | 30575 | 50720 |  | Hallsville - Longview Heights 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9152000 |  |  | 0 | 9152000 | 9152000 | 9152000 |  |  | 9930039.32 | 9930039.32 | 9930039.32 |  |  | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 |  |  | 9930039.32
t | S.080 | Total | Total | 2018-05-10 | Linwood - South Shreveport 138 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 7885000 |  |  | 0 | 7885000 | 7885000 | 7885000 | 0% | 0% | 7195411.25 | 7195411.25 | 7195411.25 | -8.746% | 9.584% | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 0.01325% | 0% | 7196364.36 |  |  | 0% | -100% | Includes line and ROW, and terminal work at Linwood and South Shreveport. Station work was done under TA2015706 (P14139003/004/503/504)
c | S.080 | 30889 | 51207 |  | Linwood - South Shreveport 138 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 7885000 |  |  | 0 | 7885000 | 7885000 | 7885000 |  |  | 7195411.25 | 7195411.25 | 7195411.25 |  |  | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 |  |  | 7196364.36
t | S.081 | Total | Total | 2018-12-13 | IPC 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1254000 |  |  | 0 | 1254000 | 1641000 | 1690000 | 0% | 0% | 1689644.66 | 1689644.66 | 1689644.66 | 2.964% | 0.02103% | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 3.153% | 0% | 1742923.97 |  |  | 0% | -100%
c | S.081 | 31186 | 51831 |  | IPC 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1254000 |  |  | 0 | 1254000 | 1641000 | 1690000 |  |  | 1689644.66 | 1689644.66 | 1689644.66 |  |  | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 |  |  | 1742923.97
t | S.082 | Total | Total | 2019-03-01 | Ellerbe Road - Lucas 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 6282000 | 7957000 |  |  | --- | 7957000 | 7957000 | 0% | 0% | 9626252.49 | 9626252.49 | 9628141 | 9628141 | 20.98% | 0% | 9628189.94 |  |  | 0.0005083% | -100%
c | S.082 | 30762 | 51034 |  | Ellerbe Road - Lucas 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 5590000 | 7046000 |  |  | --- | 7046000 | 7046000 |  |  | 9005866.55 | 9005866.55 | 9007755 | 9007755 |  |  | 9007804 |  |  |  |  | Includes line, ROW, and fiber transitions.
c | S.082 | 30762 | 51035 |  | Ellerbe Road - Lucas 69 kV Terminal Upgrades | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 692000 | 911000 |  |  | --- | 911000 | 911000 |  |  | 620385.94 | 620385.94 | 620385.94 | 620385.94 |  |  | 620385.94 |  |  |  |  | Includes terminal work at Ellerbe Rd and Lucas.
t | S.083 | Total | Total | 2019-06-01 | Siloam Springs - Siloam Springs City 161 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 661000 | 3858000 |  |  | --- | 3858000 | 3858000 | 0% | 0% | 3813966.16 | 3813966.16 | 3821662 | 3821662 | -1.141% | 0% | 3813966.16 |  |  | -0.2014% | -100% | Includes line, ROW, and terminal work at Siloam Springs.
c | S.083 | 31131 | 51738 |  | Siloam Springs - Siloam Springs City 161 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 661000 | 3858000 |  |  | --- | 3858000 | 3858000 |  |  | 3813966.16 | 3813966.16 | 3821662 | 3821662 |  |  | 3820524
t | S.084 | Total | Total | 2019-04-11 | Figure Five - VBI North 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 1951000 | 1951000 | 0% | 0% | 2910918 | 2910918 | 2910918 | 2910918 | 49.2% | 0% | 2910918 |  |  | 0% | -100% | A16806004 (A16806504 Shadow) is the line (43% of this BPID, as it includes more than the NTC), and A16806008 (A16806508) is the ROW (10% of this BPID, as it includes more than the NTC), located in the SWEPCo Line Rehab program. Project was not included last year b/c NTC was received after the update, so PIS data was used to get the cost for this project, as it went in-service in 2019.
c | S.084 | 51300 | 72066 |  | Figure Five - VBI North 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 1951000 | 1951000 |  |  | 2910918 | 2910918 | 2910918 | 2910918 |  |  | 2910918
NOTES:
< | Not above SPP $100,000 BP threshold.
New | New to BP list
c | AEP project component (components sum up to project total)
t | AEP project total
n/a | informational only; not included in calculations
Matched Last Year
Does Not Match Last Year, Needs Updating
Changed from Last Year, Updated

## Q4 2019 Initial PTP (hidden)
UID Lookup | UID | Cost Allocation | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Superproject | NTC ID | PID | Project Owner | Project Name | Upgrade Name | Project Type | Project Owner Indicated In-Service Date | Q4 2018 Project Owner Indicated ISD | RTO Determined Need Date | Latest NTC Issue Date | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Final Cost Source | Project Status | Project Description/Comments
#REF! | 51558 |  | #REF! | #REF! | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (BPID's A11012198&A11012075) | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 13512897 | 2016 | 14551912 | 13512897 |  |  | DELAY - MITIGATION | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester.
#REF! | 51559 |  | #REF! | #REF! | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (BPID A11012444) | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 15146464 | 2016 | 16311085 | 13767520 |  |  | DELAY - MITIGATION | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg.
#REF! | 51560 |  | #REF! | #REF! | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (BPID's A11012445&46) | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 21668582 | 2016 | 23334693 | 23047526 |  |  | DELAY - MITIGATION | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg.
#REF! | 72066 | BasePlan | #REF! | #REF! | #REF! | No | Need to Add | TA2016806 | 210491 | 51300 | AEP | Multi - Fig Five - VBI 69kV | Fig Five - VBI North 69kV Ckt 1 | Regional Reliability | 2019-04-11 | Not Found | 2019-06-01 | 2018-08-17 | 3357600 | 2018 | 3441540 | 3357600 |  |  | ON SCHEDULE < 4 | Rebuild 4.2 miles of 69 kV line from Fig Five to VBI.
#REF! | 51446 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2015169 | 200386 | 31003 | AEP | Sub - Northeastern Station 138 kV Terminal Upgrades | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | 2016-10-05 | 2016-10-05 | 2017-06-01 | 2016-05-17 | 518011 | 2016 | 557841 | 518011 |  |  | COMPLETE | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah.
#REF! | 51017 | TBD | #REF! | #REF! | #REF! | Yes |  | TP2012141 | 200272 | 30750 | AEP | Line - Stonewall - Wapanucka 138 kV Ckt 1 | Stonewall - Wapanucka 138 kV Ckt 1 | High Priority | 2013-12-31 | 2013-12-31 | 2015-06-01 | 2014-05-19 | 8934149 | 2014 | 10108169 | 8934149 | 7200874 | Formula Rate Update | COMPLETE | Construct new 6.4-mile 138 kV line from Stonewall to Wapanucka.
#REF! | 11236 |  | #REF! | #REF! | #REF! | Yes |  | TP2009089 | 20096 | 936 | AEP | Line - Valliant - NW Texarkana 345 kV | NORTHWEST TEXARKANA - VALLIANT 345KV CKT 1 | High Priority | 2016-12-16 | 2016-12-16 | 2014-10-01 | 2010-06-30 | 185751250 | 2016 | 200033780 | 185751250 |  |  | COMPLETE | Build a new 76 mile 345 kV line from Valliant to NW Texarkana with at least 3000 A capacity. Upgrade the Valliant and NW Texarkana substations with the necessary breakers and terminal equipment.
#REF! | 10649 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2009104 | 200216 | 504 | AEP | Line - Brownlee - North Market 69 kV | Brownlee - North Market 69 kV Ckt 1 | Regional Reliability | 2017-03-22 | 2017-03-22 | 2013-06-01 | 2013-02-20 | 12424849 | 2013 | 14409016 | 17162457 |  |  | COMPLETE | Rebuild 4.7-mile 69 kV line from Brownlee to North Market with 1233.6 ACSR/TW.
#REF! | 50607 |  | #REF! | #REF! | #REF! | Yes |  | TP2011033 | 200231 | 30495 | AEP | Sub - Messick 500/230 kV | Layfield 500/230 kV Transformer Ckt 1 | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 30369537 | 2013 | 35219352 | 22851755 |  |  | COMPLETE | Build Messick 500/230 kV substation. Connect to Carrol, Clarence, and Western Kraft 230 kV lines. Install 500/230 kV 675 MVA transformer. This upgrade is contingent upon approval from Cleco Power LLC.
#REF! | 50615 |  | #REF! | #REF! | #REF! | Yes |  | TP2011033 | 200231 | 30495 | AEP | Sub - Messick 500/230 kV | Layfield 500 kV Terminal Upgrades | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 21508234 | 2013 | 24942957 | 32212715 |  |  | COMPLETE | Install terminal equipment on 500 kV side of new Messick substation. Connect to Mt. Olive - Hartburg 500 kV line. This upgrade is contingent upon approval from Cleco Power LLC for Upgrade ID 50607.
#REF! | 50545 |  | #REF! | #REF! | #REF! | Yes |  | TP2010067 | 200231 | 30449 | AEP | Line - Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Regional Reliability | 2016-09-19 | 2016-09-19 | 2014-06-01 | 2013-09-23 | 25060655 | 2013 | 29062677 | 25060655 |  |  | COMPLETE | Rebuild 27.6-mile 138 kV line from Rock Hill to Springridge Pan-Harr REC with 1926.9 ACSR/TW conductor.
#REF! | 11261 |  | #REF! | #REF! | #REF! | No | Direct Assigned | TP2010092 | 20104 | 947 | AEP | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | 2016-05-25 | 2016-05-25 | 2015-06-01 | 2010-08-25 | 6072000 | 2014 | 6869911 | 6072000 |  |  | COMPLETE | Rebuild 4.33 of 795 ACSR with 1590 ACSR.
#REF! | 11158 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2010094 | 200216 | 879 | AEP | Line - Bluebell - Prattville 138 kV | Bluebell - Prattville 138 kV Ckt 1 | Regional Reliability | 2015-06-02 | 2015-06-02 | 2014-06-01 | 2013-02-20 | 10241314 | 2013 | 11876785 | 10241314 |  |  | COMPLETE | Rebuild 9.0-mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW.
#REF! | 10646 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2010100 | 200216 | 501 | AEP | Line - Evenside - Northwest Henderson 69 kV | Evenside - Northwest Henderson 69 kV Ckt 1 | Regional Reliability | 2018-05-11 | 2018-05-11 | 2018-06-01 | 2013-02-20 | 11980465 | 2013 | 13893666 | 11980465 |  |  | COMPLETE | Rebuild 6.4-mile 69 kV line from Evenside to Northwest Henderson with 1233.6 ACSR/TW. Replace breaker at Evenside.
#REF! | 50336 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2011022 | 20122 | 30298 | AEP | Device - Logansport 138 kV | LOGANSPORT 138KV | Regional Reliability | 2016-09-10 | 2016-09-10 | 2016-06-01 | 2011-02-14 | 1166400 | 2014 | 1319675 | 1731419 |  |  | COMPLETE | Install 28.8 MVAR capacitor bank at Logansport 138 kV substation.
#REF! | 10648 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2011023 | 200167 | 503 | AEP | Line - Diana - Perdue 138 kV | Diana - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2013-06-01 | 2012-04-09 | 1004187 | 2012 | 1193662 | 1004187 |  |  | COMPLETE | Replace two breakers, jumpers, and wave traps at Perdue substation. Replace wave traps at Diana substation.
#REF! | 50531 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2011023 | 200216 | 30436 | AEP | Line - New Gladewater - Perdue 138 kV | New Gladewater - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2016-06-01 | 2013-02-20 | 1000000 | 2013 | 1159693 | 1000000 |  |  | COMPLETE | Replace 138 kV breaker at Perdue.
#REF! | 51448 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2011110 | 200386 | 31005 | AEP | Sub - Elk City 138 kV Move Load (BPID P11110001) | Elk City 138 kV Move Load | Regional Reliability | 2018-05-25 | 2018-05-25 | 2017-06-01 | 2016-05-17 | 2904911 | 2016 | 3128271 | 2904911 |  |  | COMPLETE | Move load from 69 kV bus to 138 kV bus at Elk City.
#REF! | 10583 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2011147 | 200216 | 451 | AEP | Multi - Chamber Springs - Farmington 161 kV | Chamber Springs - Farmington REC 161 kV Ckt 1 | Regional Reliability | 2017-03-28 | 2017-03-28 | 2013-06-01 | 2013-02-20 | 12705537 | 2013 | 14734528 | 12705537 |  |  | COMPLETE | Rebuild and reconductor 11.1-mile 161 kV line from Chamber Springs to Farmington REC with 2-959.6 ACSR/TW. Upgrade wavetraps, CT ratios, and relay settings at Chamber Springs.
#REF! | 50413 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm - Gracemont 345kV Ckt 1 (AEP) | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 65082311 | 2017 | 68377103 | 65082311 |  |  | COMPLETE | Build new single circuit 345 kV line from new Chisholm substation to point of interconnection with Oklahoma Gas & Electric Co. (OGE) towards Gracemont. The approximate line length for the Chisholm - Gracemont 345 kV line is 100 miles, of which AEP will construct approximately 70 miles from Chisholm to the OGE interconnection point.
#REF! | 50414 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 345/230 kV Substation | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 17471695 | 2017 | 18356200 | 17471695 |  |  | COMPLETE | Construct new 345/230 kV Chisholm substation between existing 230 kV substations, Sweetwater and Elk City. Cut-in existing Sweetwater - Elk City 230 kV Ckt 1 line into new Chisholm substation and install any necessary 230 kV terminal equipment. Install new 345/230 675 MVA transformer at new Chisholm substation.
#REF! | 50768 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 230 kV | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 1270623 | 2017 | 1334948 | 1270623 |  |  | COMPLETE | Install approximately 2 miles of 230 kV transmission line for a cut-in to existing 230 kV line from Sweetwater to Elk City, creating termination points at new Chisholm substation.
#REF! | 51047 | TBD | #REF! | #REF! | #REF! | Yes |  | TP2012055 | 200272 | 30770 | AEP | Sub - Ellis 138 kV | Ellis 138 kV Substation | High Priority | 2013-06-01 | 2013-06-01 | 2015-06-01 | 2014-05-19 | 4100000 | 2014 | 4638774 | 4100000 | 4086696 | Formula Rate Update | COMPLETE | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation.
#REF! | 10615 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2012145 | 200216 | 478 | AEP | Line - Forbing Tap - South Shreveport 69 kV | Forbing Tap - South Shreveport 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2013-06-01 | 2013-02-20 | 1221505 | 2013 | 1416572 | 1221505 |  |  | COMPLETE | Rebuild 2.3-mile 69 kV line from Forbing to South Shreveport with 1233.6 ACSR/TW.
#REF! | 10657 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2012145 | 200246 | 512 | AEP | Line - Ellerbe Road - Forbing Tap 69 kV Ckt 1 | Ellerbe Road - Forbing T 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2014-06-01 | 2014-02-19 | 8174689 | 2014 | 9248911 | 8174689 |  |  | COMPLETE | Rebuild 2.0-mile 69 kV line from Ellerbe Road to Forbing T with 1233.6 ACSR/TW conductor.
#REF! | 50569 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2012164 | 200216 | 30473 | AEP | Line - Midland REC - North Huntington 69 kV | Midland REC - North Huntington 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 1829026 | 2013 | 2121109 | 1829026 | 11990487 | Formula Rate Update | COMPLETE | Rebuild 4.0-mile 69 kV line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington.
#REF! | 50570 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2012164 | 200216 | 30474 | AEP | Line - Midland - Midland REC 69 kV | Midland - Midland REC 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 5653353 | 2013 | 6556157 | 5653353 | Included in UID 50569 | Formula Rate Update | COMPLETE | Rebuild 1.3-mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland.
#REF! | 50571 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2012164 | 200216 | 30475 | AEP | Line - Howe Interchange - Midland 69 kV | Howe Interchange - Midland 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 9145130 | 2013 | 10605547 | 9145130 | Included in UID 50569 | Formula Rate Update | COMPLETE | Rebuild 7.0-mile portion of the 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of line to be rebuilt is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland.
#REF! | 51014 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2013002 | 200272 | 30747 | AEP | Line - Grady - Round Creek 138 kV Ckt 1 | Grady - Round Creek 138 kV Ckt 1 | High Priority | 2015-11-05 | 2015-11-05 | 2015-06-01 | 2014-05-19 | 12132497 | 2014 | 13726807 | 12132497 |  |  | COMPLETE | Construct new Round Creek box bay tap structure adjacent to the Rush Springs 138 kV substation. Construct new 6-mile 138 kV line from Grady to Round Creek. Install 3-breaker ring bus where hard tap to Round Creek intersects the Cornville to Duncan 138 kV transmission line.
#REF! | 51015 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2013002 | 200272 | 30748 | AEP | Line - Grady - Phillips Gas 138 kV Ckt 1 and 2 | Grady - Phillips 138 kV Ckt 1 and 2 | High Priority | 2014-12-31 | 2014-12-31 | 2015-06-01 | 2014-05-19 | 8318584 | 2014 | 9411714 | 8318584 |  |  | COMPLETE | Construct new 4-mile double circuit 138 kV line from the new 4-breaker ring bus station at Grady. Circuit 1 will terminate at Phillips Gas and Circuit 2 will terminate at Lindsey Water Flood.
#REF! | 50990 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2013081 | 200306 | 30731 | AEP | Line - Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | Mt Pleasant - West Mt Pleasant 69 kV Ckt 1 Rebuild | Regional Reliability | 2015-04-20 | 2015-04-20 | 2015-06-01 | 2014-11-24 | 4715419 | 2015 | 5204940 | 7381799 |  |  | COMPLETE | Rebuild 2.75-mile 69 kV line from Mt. Pleasant to West Mt. Pleasant to achieve a new emergency rating of 84 MVA.
#REF! | 50334 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2013122 | 20122 | 30296 | AEP | Device - Winnsboro 138 kV | WINNSBORO 138KV | Regional Reliability | 2016-04-21 | 2016-04-21 | 2016-06-01 | 2011-02-14 | 1166400 | 2014 | 1319675 | 1166400 |  |  | COMPLETE | Install a new 28.8 MVAR capacitor bank at Winnsboro 138 kV substation.
#REF! | 50718 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2013165 | 200246 | 30573 | AEP | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-21 | 2017-06-21 | 2019-06-01 | 2014-02-19 | 6695986 | 2014 | 7575893 | 6695986 |  |  | COMPLETE | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor.
#REF! | 50719 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2013166 | 200246 | 30574 | AEP | Line - Daingerfield - Jenkins Rec 69 kV Ckt 1 Rebuild | Daingerfield - Jenkins REC T 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-11-09 | 2017-11-09 | 2019-06-01 | 2014-02-19 | 2819806 | 2014 | 3190352 | 2819806 |  |  | COMPLETE | Rebuild 1.3-mile 69 kV line from Daingerfield to Jenkins REC T with 959.6 ACSR/TW conductor.
#REF! | 50720 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2013167 | 200246 | 30575 | AEP | Line - Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-03-02 | 2018-03-02 | 2014-06-01 | 2014-02-19 | 8851677 | 2014 | 10014860 | 11571330 |  |  | COMPLETE | Rebuild 6.6-mile 69 kV line from Longview Heights to Hallsville with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Longview Heights.
#REF! | 50721 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2013167 | 200246 | 30576 | AEP | Line - Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-02 | 2017-06-02 | 2014-06-01 | 2014-02-19 | 15248925 | 2014 | 17252760 | 19751448 |  |  | COMPLETE | Rebuild 11.2-mile 69 kV line from Hallsville to Marshall with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Marshall.
#REF! | 51215 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2014138 | 200314 | 30895 | AEP | Line - Brooks Street - Edwards Street 69kV Ckt 1 Rebuild | Brooks Street - Edwards Street 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-12-20 | 2017-12-20 | 2016-06-01 | 2015-02-18 | 4294228 | 2015 | 4740025 | 4294228 |  |  | COMPLETE | Rebuild 0.8-mile 69 kV line from Brooks Street to Edwards Street. Upgrade jumpers at both substations.
#REF! | 51033 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2014139 | 200298 | 30761 | AEP | Line - Cedar Grove - South Shreveport 138 kV | Cedar Grove - South Shreveport 138 kV | Transmission Service | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2014-09-30 | 6566218 | 2014 | 7429073 | 6566218 |  |  | ON SCHEDULE < 4 | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove.
#REF! | 51207 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2014139 | 200406 | 30889 | AEP | Line - Linwood - South Shreveport 138kV Ckt 1 Rebuild | Linwood - South Shreveport 138 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-10 | 2018-05-10 | 2017-06-01 | 2016-08-17 | 5285437 | 2016 | 5691838 | 5919107 |  |  | COMPLETE | Rebuild the 2.4-mile 138kV line from Linwood to Cedar Grove to South Shreveport. Upgrade the jumpers at Linwood.
#REF! | 51034 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2014154 | 200339 | 30762 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | 6629465 | 2015 | 7317689 | 9905114 |  |  | COMPLETE | Rebuild existing 3.2-mile 69 kV line from Ellerbe Road to Lucas.
#REF! | 51035 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2014154 | 200339 | 30762 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Terminal Upgrades | Regional Reliability | 2019-02-27 | 2019-03-01 | 2019-03-01 | 2015-03-17 | 652658 | 2015 | 720412 | 1144751 |  |  | COMPLETE | Replace jumpers at 69 kV substations Ellerbe Road and Lucas. Replace relay panel at Ellerbe Road. Change relay setting at Lucas.
#REF! | 51187 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2014207 | 200314 | 30873 | AEP | Line - Southwestern Station - Carnegie 138kV Ckt 1 Rebuild | Southwestern Station - Carnegie 138 kV Ckt 1 Rebuild | Regional Reliability | 2017-07-06 | 2017-07-06 | 2016-06-01 | 2015-02-18 | 15821763 | 2015 | 17464266 | 9397311 |  |  | COMPLETE | Rebuild 16.5-mile 138 kV from Southwestern Station to Carnegie.
#REF! | 50802 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2015027 | 200310 | 30619 | AEP | Line - Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | High Priority | 2017-06-29 | 2017-06-29 | 2015-06-01 | 2014-12-02 | 11652107 | 2014 | 13183289 | 11652107 |  |  | COMPLETE | Construct AEP's portion of new 25-mile 138 kV line from Darlington to Roman Nose (OGE).
#REF! | 50759 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2015106 | 200361 | 30598 | AEP | Device - Letourneau 69 kV Cap Bank | Letourneau 69 kV Cap Bank | Regional Reliability | 2017-06-26 | 2017-06-26 | 2017-06-01 | 2015-12-11 | 1409347 | 2016 | 1517713 | 1409347 |  |  | COMPLETE | Install 16.2-MVAR 69 kV capacitor bank at Letourneau.
#REF! | 51096 |  | #REF! | #REF! | #REF! | No | Need to Add | TP2015118 | 200382 | 30809 | AEP | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2016-04-12 | 4319501 | 2016 | 4651630 | 6445009 |  |  | ON SCHEDULE < 4 | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation.
#REF! | 51454 |  | #REF! | #REF! | #REF! | Yes |  | TP2015191 | 200406 | 31009 | AEP | Line - Duncan - Tosco 69 kV Ckt 1 Rebuild (Paula Keefe BPID P15190001) | Duncan - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-04 | 2018-05-04 | 2018-06-01 | 2016-08-17 | 5974766 | 2016 | 6434170 | 5974766 |  |  | COMPLETE | Rebuild 69 kV line from Duncan to Tosco. Replace wave trap at Duncan.
#REF! | 51524 |  | #REF! | #REF! | #REF! | Yes |  | TP2015191 | 200406 | 31039 | AEP | Line - Comanche Tap - Tosco 69 kV Ckt 1 Rebuild (Brent Garrett BPID's A11012077&A11012447) | Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2016-12-19 | 2016-12-19 | 2020-06-01 | 2016-08-17 | 4365864 | 2016 | 4701558 | 4365864 |  |  | COMPLETE | Rebuild 69 kV line from Comanche Tap to Tosco.
#REF! | 51433 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2015202 | 200386 | 30997 | AEP | Device - Sayre 138 kV Cap Bank | Sayre 138 kV Cap Bank | Regional Reliability | 2018-12-19 | 2018-12-31 | 2017-06-01 | 2016-05-17 | 758441 | 2016 | 816758 | 1997360 |  |  | COMPLETE | Install new 14.4-MVAR capacitor bank at Sayre 138 kV.
#REF! | 51561 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2015204 | 200386 | 31058 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Fort Towson - Kiamichi Pump Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-12-21 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 11778983 | 2016 | 12684677 | 11778983 |  |  | DELAY - MITIGATION | Rebuild 9.0-mile 69 kV line from Fort Towson to Kiamichi Pump Tap.
#REF! | 51562 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2015204 | 200386 | 31058 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-12-21 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 7699929 | 2016 | 8291982 | 7699929 |  |  | DELAY - MITIGATION | Rebuild 4.8-mile portion of 69 kV line from Kiamichi Pump Tap to Valliant.
#REF! | 51738 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2017010 | 200431 | 31131 | AEP | Line - Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild | Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild (AEP) | Economic | 2019-05-31 | 2020-01-01 | 2017-01-01 | 2017-02-21 | 4780000 | 2017 | 5021988 | 4780000 |  |  | DELAY - MITIGATION | Rebuild 2.1-mile 161 kV line from Siloam Springs (AEP) - Siloam Springs City (GRDA) and upgrade terminal equipment at Siloam Springs.
#REF! | 61858 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2017011 | 200446 | 41202 | AEP | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | 2019-12-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 6014381 | 2017 | 6318859 | 6510937 |  |  | DELAY - MITIGATION | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line.
#REF! | 51831 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2017012 | 200446 | 31186 | AEP | Device - IPC 138 kV Cap Bank | IPC 138 kV Cap Bank | Regional Reliability | 2018-12-13 | 2018-12-01 | 2018-12-01 | 2017-05-12 | 1298048 | 2017 | 1363762 | 1917591 |  |  | COMPLETE | Install 28.8-MVAR capacitor bank at IPC 138 kV
#REF! | 71945 | BasePlan | #REF! | #REF! | #REF! | Yes |  | TP2017016 | 200446 | 41233 | AEP | Line - Broken Arrow North - Lynn Lane East 138 kV Ckt 1 | Broken Arrow North - Lynn Lane East 138 kV Ckt 1 Reconductor | Regional Reliability | 2019-03-19 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 5714095 | 2017 | 6003371 | 5714095 |  |  | COMPLETE | Reconductor Broken Arrow - Lynn Lane East 7.2-mile 138 kV line
#REF! | 82137 |  | #REF! | #REF! | #REF! | No | Not Base Plan | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | 2019-08-09 | 2019-02-15 | [5 empty] | 700000 |  |  | ON SCHEDULE < 4 | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation.
#REF! | 82138 |  | #REF! | #REF! | #REF! | No | Not Base Plan | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | 2019-08-09 | 2019-03-31 | [5 empty] | 8700000 |  |  | ON SCHEDULE < 4 | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer.
Formulas:
Q4 2018 Project Owner Indicated ISD = IFNA(VLOOKUP([UID],'Q4 2018 Initial PTP'!$B2:Q61,16,0),"Not Found")

## Q2 2019 Initial PTP (hidden)
Cost Allocation | Superproject | NTC ID | RFP ID | PID | UID | Project Owner | Project Name | Upgrade Name | Project Type | Q4 2018 Project Owner Indicated ISD | Project Owner Indicated In-Service Date | RTO Determined Need Date | Latest NTC Issue Date | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Final Cost Source | Project Status | Project Description/Comments
Zonal | TA2011012 | 200386 |  | 31057 | 51558 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 13512897 | 2016 | 14551912 | 13512897 |  |  | DELAY - MITIGATION | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester.
Zonal | TA2011012 | 200386 |  | 31057 | 51559 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 15146464 | 2016 | 16311085 | 13767520 |  |  | DELAY - MITIGATION | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg.
Zonal | TA2011012 | 200386 |  | 31057 | 51560 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 21668582 | 2016 | 23334693 | 23047526 |  |  | DELAY - MITIGATION | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg.
BasePlan | TA2016806 | 210491 |  | 51300 | 72066 | AEP | Multi - Fig Five - VBI 69kV | Fig Five - VBI North 69kV Ckt 1 | Regional Reliability | Not In Previous Update | 2019-06-01 | 2019-06-01 | 2018-08-17 | 3357600 | 2018 | 3441540 | 3357600 |  |  | ON SCHEDULE < 4 | Rebuild 4.2 miles of 69 kV line from Fig Five to VBI.
BasePlan | TFS/Failure | 200386 |  | 31003 | 51446 | AEP | Sub - Northeastern Station 138 kV Terminal Upgrades | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | 2016-10-05 | 2016-10-05 | 2017-06-01 | 2016-05-17 | 518011 | 2016 | 518011 | 518011 |  |  | COMPLETE | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah.
TBD | TP2006067 | 200272 |  | 30750 | 51017 | AEP | Line - Stonewall - Wapanucka 138 kV Ckt 1 | Stonewall - Wapanucka 138 kV Ckt 1 | High Priority | 2013-12-31 | 2013-12-31 | 2015-06-01 | 2014-05-19 | 8934149 | 2014 | 8716242.9268 | 8934149 | 7200874 | Formula Rate Update | COMPLETE | Construct new 6.4-mile 138 kV line from Stonewall to Wapanucka.
| TP2009089 | 20096 |  | 936 | 11236 | AEP | Line - Valliant - NW Texarkana 345 kV | NORTHWEST TEXARKANA - VALLIANT 345KV CKT 1 | High Priority | 2016-12-16 | 2016-12-16 | 2014-10-01 | 2010-06-30 | 185751250 | 2016 | 185751250 | 185751250 |  |  | COMPLETE | Build a new 76 mile 345 kV line from Valliant to NW Texarkana with at least 3000 A capacity. Upgrade the Valliant and NW Texarkana substations with the necessary breakers and terminal equipment.
BasePlan | TP2009104 | 200216 |  | 504 | 10649 | AEP | Line - Brownlee - North Market 69 kV | Brownlee - North Market 69 kV Ckt 1 | Regional Reliability | 2017-03-22 | 2017-03-22 | 2013-06-01 | 2013-02-20 | 12424849 | 2013 | 13714708.4903 | 17162457 |  |  | COMPLETE | Rebuild 4.7-mile 69 kV line from Brownlee to North Market with 1233.6 ACSR/TW.
| TP2010067 | 200231 |  | 30449 | 50545 | AEP | Line - Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Regional Reliability | 2016-09-19 | 2016-09-19 | 2014-06-01 | 2013-09-23 | 25060655 | 2013 | 26987584.4259 | 25060655 |  |  | COMPLETE | Rebuild 27.6-mile 138 kV line from Rock Hill to Springridge Pan-Harr REC with 1926.9 ACSR/TW conductor.
| TP2010092 | 20104 |  | 947 | 11261 | AEP | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | 2016-05-25 | 2016-05-25 | 2015-06-01 | 2010-08-25 | 6072000 | 2014 | 6379395 | 6072000 |  |  | COMPLETE | Rebuild 4.33 of 795 ACSR with 1590 ACSR.
BasePlan | TP2010094 | 200216 |  | 879 | 11158 | AEP | Line - Bluebell - Prattville 138 kV | Bluebell - Prattville 138 kV Ckt 1 | Regional Reliability | 2015-06-02 | 2015-06-02 | 2014-06-01 | 2013-02-20 | 10241314 | 2013 | 10759780.5212 | 10241314 |  |  | COMPLETE | Rebuild 9.0-mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW.
BasePlan | TP2010100 | 200216 |  | 501 | 10646 | AEP | Line - Evenside - Northwest Henderson 69 kV | Evenside - Northwest Henderson 69 kV Ckt 1 | Regional Reliability | 2018-05-11 | 2018-05-11 | 2018-06-01 | 2013-02-20 | 11980465 | 2013 | 13554796.4952 | 11980465 |  |  | COMPLETE | Rebuild 6.4-mile 69 kV line from Evenside to Northwest Henderson with 1233.6 ACSR/TW. Replace breaker at Evenside.
BasePlan | TP2011022 | 20122 |  | 30298 | 50336 | AEP | Device - Logansport 138 kV | LOGANSPORT 138KV | Regional Reliability | 2016-09-10 | 2016-09-10 | 2016-06-01 | 2011-02-14 | 1166400 | 2014 | 1225449 | 1731419 |  |  | COMPLETE | Install 28.8 MVAR capacitor bank at Logansport 138 kV substation.
BasePlan | TP2011023 | 200167 |  | 503 | 10648 | AEP | Line - Diana - Perdue 138 kV | Diana - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2013-06-01 | 2012-04-09 | 1004187 | 2012 | 1055023.9669 | 1004187 |  |  | COMPLETE | Replace two breakers, jumpers, and wave traps at Perdue substation. Replace wave traps at Diana substation.
BasePlan | TP2011023 | 200216 |  | 30436 | 50531 | AEP | Line - New Gladewater - Perdue 138 kV | New Gladewater - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2016-06-01 | 2013-02-20 | 1000000 | 2013 | 1025000 | 1000000 |  |  | COMPLETE | Replace 138 kV breaker at Perdue.
| TP2011033 | 200231 |  | 30495 | 50607 | AEP | Sub - Messick 500/230 kV | Layfield 500/230 kV Transformer Ckt 1 | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 30369537 | 2013 | 32704669.6809 | 22851755 |  |  | COMPLETE | Build Messick 500/230 kV substation. Connect to Carrol, Clarence, and Western Kraft 230 kV lines. Install 500/230 kV 675 MVA transformer. This upgrade is contingent upon approval from Cleco Power LLC.
| TP2011033 | 200231 |  | 30495 | 50615 | AEP | Sub - Messick 500/230 kV | Layfield 500 kV Terminal Upgrades | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 21508234 | 2013 | 23162015.5549 | 32212715 |  |  | COMPLETE | Install terminal equipment on 500 kV side of new Messick substation. Connect to Mt. Olive - Hartburg 500 kV line. This upgrade is contingent upon approval from Cleco Power LLC for Upgrade ID 50607.
BasePlan | TP2011110 | 200386 |  | 31005 | 51448 | AEP | Sub - Elk City 138 kV Move Load | Elk City 138 kV Move Load | Regional Reliability | 2018-05-25 | 2018-05-25 | 2017-06-01 | 2016-05-17 | 2904911 | 2016 | 3051972.1194 | 2904911 |  |  | COMPLETE | Move load from 69 kV bus to 138 kV bus at Elk City.
BasePlan | TP2011147 | 200216 |  | 451 | 10583 | AEP | Multi - Chamber Springs - Farmington 161 kV | Chamber Springs - Farmington REC 161 kV Ckt 1 | Regional Reliability | 2017-03-28 | 2017-03-28 | 2013-06-01 | 2013-02-20 | 12705537 | 2013 | 14024535.5229 | 12705537 |  |  | COMPLETE | Rebuild and reconductor 11.1-mile 161 kV line from Chamber Springs to Farmington REC with 2-959.6 ACSR/TW. Upgrade wavetraps, CT ratios, and relay settings at Chamber Springs.
BasePlan | TP2011150 | 200255 |  | 30361 | 50413 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm - Gracemont 345kV Ckt 1 (AEP) | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 65082311 | 2017 | 65082311 | 65082311 |  |  | COMPLETE | Build new single circuit 345 kV line from new Chisholm substation to point of interconnection with Oklahoma Gas & Electric Co. (OGE) towards Gracemont. The approximate line length for the Chisholm - Gracemont 345 kV line is 100 miles, of which AEP will construct approximately 70 miles from Chisholm to the OGE interconnection point.
BasePlan | TP2011150 | 200255 |  | 30361 | 50414 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 345/230 kV Substation | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 17471695 | 2017 | 17471695 | 17471695 |  |  | COMPLETE | Construct new 345/230 kV Chisholm substation between existing 230 kV substations, Sweetwater and Elk City. Cut-in existing Sweetwater - Elk City 230 kV Ckt 1 line into new Chisholm substation and install any necessary 230 kV terminal equipment. Install new 345/230 675 MVA transformer at new Chisholm substation.
BasePlan | TP2011150 | 200255 |  | 30361 | 50768 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 230 kV | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 1270623 | 2017 | 1270623 | 1270623 |  |  | COMPLETE | Install approximately 2 miles of 230 kV transmission line for a cut-in to existing 230 kV line from Sweetwater to Elk City, creating termination points at new Chisholm substation.
TBD | TP2012055 | 200272 |  | 30770 | 51047 | AEP | Sub - Ellis 138 kV | Ellis 138 kV Substation | High Priority | 2013-06-01 | 2013-06-01 | 2015-06-01 | 2014-05-19 | 4100000 | 2014 | 4000000 | 4100000 | 4086696 | Formula Rate Update | COMPLETE | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation.
BasePlan | TP2012144 | 200216 |  | 30471 | 50567 | AEP | Line - Dekalb - New Boston 69 kV | Dekalb - New Boston 69 kV Ckt 1 | Regional Reliability | 2015-06-05 | 2015-06-05 | 2013-06-01 | 2013-02-20 | 16548317 | 2013 | 17386075.5481 | 16548317 | 15777911 | Formula Rate Update | COMPLETE | Rebuild 13.2-mile 69 kV line from Dekalb to New Boston with 1233.6 ACSR/TW. Upgrade CT ratios and relay settings at New Boston.
BasePlan | TP2012145 | 200216 |  | 478 | 10615 | AEP | Line - Forbing Tap - South Shreveport 69 kV | Forbing Tap - South Shreveport 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2013-06-01 | 2013-02-20 | 1221505 | 2013 | 1315427.2829 | 1221505 |  |  | COMPLETE | Rebuild 2.3-mile 69 kV line from Forbing to South Shreveport with 1233.6 ACSR/TW.
BasePlan | TP2012145 | 200246 |  | 512 | 10657 | AEP | Line - Ellerbe Road - Forbing Tap 69 kV Ckt 1 | Ellerbe Road - Forbing T 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2014-06-01 | 2014-02-19 | 8174689 | 2014 | 8588532.6306 | 8174689 |  |  | COMPLETE | Rebuild 2.0-mile 69 kV line from Ellerbe Road to Forbing T with 1233.6 ACSR/TW conductor.
BasePlan | TP2012146 | 200216 |  | 30472 | 50568 | AEP | Line - Hardy Street - Waterworks 69 kV | Hardy Street - Waterworks 69 kV Ckt 1 | Regional Reliability | 2015-06-25 | 2015-06-25 | 2013-06-01 | 2013-02-20 | 7519658 | 2013 | 7900340.6862 | 7519658 | 5366606 | Formula Rate Update | COMPLETE | Rebuild 1.6-mile 69 kV line from Hardy Street to Waterworks with 1233.6 ACSR/TW.
BasePlan | TP2012164 | 200216 |  | 30473 | 50569 | AEP | Line - Midland REC - North Huntington 69 kV | Midland REC - North Huntington 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 1829026 | 2013 | 1921620.4412 | 1829026 | 11990487 | Formula Rate Update | COMPLETE | Rebuild 4.0-mile 69 kV line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington.
BasePlan | TP2012164 | 200216 |  | 30474 | 50570 | AEP | Line - Midland - Midland REC 69 kV | Midland - Midland REC 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 5653353 | 2013 | 5939553.9956 | 5653353 | Included in UID 50569 | Formula Rate Update | COMPLETE | Rebuild 1.3-mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland.
BasePlan | TP2012164 | 200216 |  | 30475 | 50571 | AEP | Line - Howe Interchange - Midland 69 kV | Howe Interchange - Midland 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 9145130 | 2013 | 9608102.2062 | 9145130 | Included in UID 50569 | Formula Rate Update | COMPLETE | Rebuild 7.0-mile portion of the 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of line to be rebuilt is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland.
BasePlan | TP2013002 | 200272 |  | 30747 | 51014 | AEP | Line - Grady - Round Creek 138 kV Ckt 1 | Grady - Round Creek 138 kV Ckt 1 | High Priority | 2015-11-05 | 2015-11-05 | 2015-06-01 | 2014-05-19 | 12132497 | 2014 | 12435809.425 | 12132497 |  |  | COMPLETE | Construct new Round Creek box bay tap structure adjacent to the Rush Springs 138 kV substation. Construct new 6-mile 138 kV line from Grady to Round Creek. Install 3-breaker ring bus where hard tap to Round Creek intersects the Cornville to Duncan 138 kV transmission line.
BasePlan | TP2013002 | 200272 |  | 30748 | 51015 | AEP | Line - Grady - Phillips Gas 138 kV Ckt 1 and 2 | Grady - Phillips 138 kV Ckt 1 and 2 | High Priority | 2014-12-31 | 2014-12-31 | 2015-06-01 | 2014-05-19 | 8318584 | 2014 | 8318584 | 8318584 |  |  | COMPLETE | Construct new 4-mile double circuit 138 kV line from the new 4-breaker ring bus station at Grady. Circuit 1 will terminate at Phillips Gas and Circuit 2 will terminate at Lindsey Water Flood.
BasePlan | TP2013081 | 200306 |  | 30731 | 50990 | AEP | Line - Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | Mt Pleasant - West Mt Pleasant 69 kV Ckt 1 Rebuild | Regional Reliability | 2015-04-20 | 2015-04-20 | 2015-06-01 | 2014-11-24 | 4715419 | 2015 | 4715419 | 7381799 |  |  | COMPLETE | Rebuild 2.75-mile 69 kV line from Mt. Pleasant to West Mt. Pleasant to achieve a new emergency rating of 84 MVA.
BasePlan | TP2013122 | 20122 |  | 30296 | 50334 | AEP | Device - Winnsboro 138 kV | WINNSBORO 138KV | Regional Reliability | 2016-04-21 | 2016-04-21 | 2016-06-01 | 2011-02-14 | 1166400 | 2014 | 1225449 | 1166400 |  |  | COMPLETE | Install a new 28.8 MVAR capacitor bank at Winnsboro 138 kV substation.
BasePlan | TP2013165 | 200246 |  | 30573 | 50718 | AEP | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-21 | 2017-06-21 | 2019-06-01 | 2014-02-19 | 6695986 | 2014 | 7210844.5485 | 6695986 |  |  | COMPLETE | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor.
BasePlan | TP2013166 | 200246 |  | 30574 | 50719 | AEP | Line - Daingerfield - Jenkins Rec 69 kV Ckt 1 Rebuild | Daingerfield - Jenkins REC T 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-11-09 | 2017-11-09 | 2019-06-01 | 2014-02-19 | 2819806 | 2014 | 3036622.6457 | 2819806 |  |  | COMPLETE | Rebuild 1.3-mile 69 kV line from Daingerfield to Jenkins REC T with 959.6 ACSR/TW conductor.
BasePlan | TP2013167 | 200246 |  | 30575 | 50720 | AEP | Line - Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-03-02 | 2018-03-02 | 2014-06-01 | 2014-02-19 | 8851677 | 2014 | 9770595.1762 | 11571330 |  |  | COMPLETE | Rebuild 6.6-mile 69 kV line from Longview Heights to Hallsville with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Longview Heights.
BasePlan | TP2013167 | 200246 |  | 30576 | 50721 | AEP | Line - Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-02 | 2017-06-02 | 2014-06-01 | 2014-02-19 | 15248925 | 2014 | 16421424.3738 | 19751448 |  |  | COMPLETE | Rebuild 11.2-mile 69 kV line from Hallsville to Marshall with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Marshall.
BasePlan | TP2014138 | 200314 |  | 30895 | 51215 | AEP | Line - Brooks Street - Edwards Street 69kV Ckt 1 Rebuild | Brooks Street - Edwards Street 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-12-20 | 2017-12-20 | 2016-06-01 | 2015-02-18 | 4294228 | 2015 | 4511623.2925 | 4294228 |  |  | COMPLETE | Rebuild 0.8-mile 69 kV line from Brooks Street to Edwards Street. Upgrade jumpers at both substations.
BasePlan | TP2014139 | 200298 |  | 30761 | 51033 | AEP | Line - Cedar Grove - South Shreveport 138 kV | Cedar Grove - South Shreveport 138 kV | Transmission Service | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2014-09-30 | 6566218 | 2014 | 7429073 | 6566218 |  |  | ON SCHEDULE < 4 | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove.
BasePlan | TP2014139 | 200406 |  | 30889 | 51207 | AEP | Line - Linwood - South Shreveport 138kV Ckt 1 Rebuild | Linwood - South Shreveport 138 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-10 | 2018-05-10 | 2017-06-01 | 2016-08-17 | 5285437 | 2016 | 5553012.2481 | 5919107 |  |  | COMPLETE | Rebuild the 2.4-mile 138kV line from Linwood to Cedar Grove to South Shreveport. Upgrade the jumpers at Linwood.
BasePlan | TP2014154 | 200339 |  | 30762 | 51034 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | 6629465 | 2015 | 7317689 | 9905114 |  |  | ON SCHEDULE < 4 | Rebuild existing 3.2-mile 69 kV line from Ellerbe Road to Lucas.
BasePlan | TP2014154 | 200339 |  | 30762 | 51035 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Terminal Upgrades | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | 652658 | 2015 | 720412 | 1144751 |  |  | ON SCHEDULE < 4 | Replace jumpers at 69 kV substations Ellerbe Road and Lucas. Replace relay panel at Ellerbe Road. Change relay setting at Lucas.
BasePlan | TP2014207 | 200314 |  | 30873 | 51187 | AEP | Line - Southwestern Station - Carnegie 138kV Ckt 1 Rebuild | Southwestern Station - Carnegie 138 kV Ckt 1 Rebuild | Regional Reliability | 2017-07-06 | 2017-07-06 | 2016-06-01 | 2015-02-18 | 15821763 | 2015 | 16622739.7519 | 9397311 |  |  | COMPLETE | Rebuild 16.5-mile 138 kV from Southwestern Station to Carnegie.
BasePlan | TP2015027 | 200310 |  | 30619 | 50802 | AEP | Line - Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | High Priority | 2017-06-29 | 2017-06-29 | 2015-06-01 | 2014-12-02 | 11652107 | 2014 | 12548044.7898 | 11652107 |  |  | COMPLETE | Construct AEP's portion of new 25-mile 138 kV line from Darlington to Roman Nose (OGE).
BasePlan | TP2015106 | 200361 |  | 30598 | 50759 | AEP | Device - Letourneau 69 kV Cap Bank | Letourneau 69 kV Cap Bank | Regional Reliability | 2017-06-26 | 2017-06-26 | 2017-06-01 | 2015-12-11 | 1409347 | 2016 | 1444580.675 | 1409347 |  |  | COMPLETE | Install 16.2-MVAR 69 kV capacitor bank at Letourneau.
| TP2015118 | 200382 |  | 30809 | 51096 | AEP | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2016-04-12 | 4319501 | 2016 | 4651630 | 4319501 |  |  | ON SCHEDULE < 4 | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation.
| TP2015191 | 200406 |  | 31009 | 51454 | AEP | Line - Duncan - Tosco 69 kV Ckt 1 Rebuild | Duncan - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-04 | 2018-05-04 | 2018-06-01 | 2016-08-17 | 5974766 | 2016 | 6277238.5287 | 5974766 |  |  | COMPLETE | Rebuild 69 kV line from Duncan to Tosco. Replace wave trap at Duncan.
| TP2015191 | 200406 |  | 31039 | 51524 | AEP | Line - Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2016-12-19 | 2016-12-19 | 2020-06-01 | 2016-08-17 | 4365864 | 2016 | 4365864 | 4365864 |  |  | COMPLETE | Rebuild 69 kV line from Comanche Tap to Tosco.
BasePlan | TP2015202 | 200386 |  | 30997 | 51433 | AEP | Device - Sayre 138 kV Cap Bank | Sayre 138 kV Cap Bank | Regional Reliability | 2018-12-31 | 2018-12-19 | 2017-06-01 | 2016-05-17 | 758441 | 2016 | 816758 | 1997360 |  |  | DELAY - MITIGATION | Install new 14.4-MVAR capacitor bank at Sayre 138 kV.
BasePlan | TP2015204 | 200386 |  | 31058 | 51561 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Fort Towson - Kiamichi Pump Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 11778983 | 2016 | 12684677 | 11778983 |  |  | DELAY - MITIGATION | Rebuild 9.0-mile 69 kV line from Fort Towson to Kiamichi Pump Tap.
BasePlan | TP2015204 | 200386 |  | 31058 | 51562 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 7699929 | 2016 | 8291982 | 7699929 |  |  | DELAY - MITIGATION | Rebuild 4.8-mile portion of 69 kV line from Kiamichi Pump Tap to Valliant.
BasePlan | TP2017010 | 200431 |  | 31131 | 51738 | AEP | Line - Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild | Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild (AEP) | Economic | 2020-01-01 | 2020-01-01 | 2017-01-01 | 2017-02-21 | 4780000 | 2017 | 5021988 | 4780000 |  |  | DELAY - MITIGATION | Rebuild 2.1-mile 161 kV line from Siloam Springs (AEP) - Siloam Springs City (GRDA) and upgrade terminal equipment at Siloam Springs.
BasePlan | TP2017011 | 200446 |  | 41202 | 61858 | AEP | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 6014381 | 2017 | 6318859 | 6014381 |  |  | DELAY - MITIGATION | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line.
BasePlan | TP2017012 | 200446 |  | 31186 | 51831 | AEP | Device - IPC 138 kV Cap Bank | IPC 138 kV Cap Bank | Regional Reliability | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2017-05-12 | 1298048 | 2017 | 1363762 | 1917591 |  |  | ON SCHEDULE < 4 | Install 28.8-MVAR capacitor bank at IPC 138 kV
BasePlan | TP2017016 | 200446 |  | 41233 | 71945 | AEP | Line - Broken Arrow North - Lynn Lane East 138 kV Ckt 1 | Broken Arrow North - Lynn Lane East 138 kV Ckt 1 Reconductor | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 5714095 | 2017 | 6003371 | 5714095 |  |  | DELAY - MITIGATION | Reconductor Broken Arrow - Lynn Lane East 7.2-mile 138 kV line
| TP2017247 |  |  | 51337 | 82137 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | 2019-02-15 | 2019-02-15 | [5 empty] | 700000 |  |  | ON SCHEDULE < 4 | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation.
| TP2017247 |  |  | 51337 | 82138 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | 2019-03-31 | 2019-03-31 | [5 empty] | 8700000 |  |  | ON SCHEDULE < 4 | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer.
Formulas:
Q4 2018 Project Owner Indicated ISD = IFNA(VLOOKUP([UID],'Q4 2018 Initial PTP'!$B1:AJ61,16,0),"Not In Previous Update")

## Q4 2018 Initial PTP (hidden)
UID Lookup | UID | Cost Allocation | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Superproject | NTC ID | PID | Project Owner | Project Name | Upgrade Name | Project Type | Q2 2019 Project Owner Indicated ISD | Project Owner Indicated In-Service Date | RTO Determined Need Date | Latest NTC Issue Date | NTC Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Final Cost Source | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion
#REF! | 51558 | Zonal | #REF! | #REF! | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (A11012198&A11012075) | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 13512897 | 2016 | 14196987 | 13512897 |  |  | DELAY - MITIGATION | 510912 | ARMY AMMUNITION DEPOT | 510899 | McALESTER 69KV | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester. | 69
#REF! | 51559 | Zonal | #REF! | #REF! | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (A11012444) | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15146464 | 2016 | 15913253 | 13767520 |  |  | DELAY - MITIGATION | 510912 | ARMY AMMUNITION DEPOT | 510885 | PITTSBURG 69KV | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg. | 69
#REF! | 51560 | Zonal | #REF! | #REF! | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (A11012445&46) | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668582 | 2016 | 22765554 | 23047526 |  |  | DELAY - MITIGATION | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69
#REF! | 51446 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2015169 | 200386 | 31003 | AEP | Sub - Northeastern Station 138 kV Terminal Upgrades (WO T0176861) | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | 2016-10-05 | 2016-10-05 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 518011 | 2016 | 544235 | 518011 |  |  | COMPLETE | 510396 | NORTHEAST STATION 138KV |  |  | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah. | 138
#REF! | 51017 | TBD | #REF! | #REF! | #REF! | Yes |  | TP2012141 | 200272 | 30750 | AEP | Line - Stonewall - Wapanucka 138 kV Ckt 1 | Stonewall - Wapanucka 138 kV Ckt 1 | High Priority | 2013-12-31 | 2013-12-31 | 2015-06-01 | 2014-05-19 | HPILS | 8934149 | 2014 | 9861629 | 8934149 | 7200874 | Formula Rate Update | COMPLETE | 521075 |  | 510949 |  | Construct new 6.4-mile 138 kV line from Stonewall to Wapanucka. | 138 | 6.4
#REF! | 11236 |  | #REF! | #REF! | #REF! | Yes |  | TP2009089 | 20096 | 936 | AEP | Line - Valliant - NW Texarkana 345 kV | NORTHWEST TEXARKANA - VALLIANT 345KV CKT 1 | High Priority | 2016-12-16 | 2016-12-16 | 2014-10-01 | 2010-06-30 | Priority Projects | 185751250 | 2016 | 195154907 | 185751250 |  |  | COMPLETE | 510911 | VALLIANT 345KV | 508072 | NORTHWEST TEXARKANA 345KV | Build a new 76 mile 345 kV line from Valliant to NW Texarkana with at least 3000 A capacity. Upgrade the Valliant and NW Texarkana substations with the necessary breakers and terminal equipment. | 345 | 76.25
#REF! | 10649 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2009104 | 200216 | 504 | AEP | Line - Brownlee - North Market 69 kV | Brownlee - North Market 69 kV Ckt 1 | Regional Reliability | 2017-03-22 | 2017-03-22 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 12424849 | 2013 | 14057576 | 17162457 |  |  | COMPLETE | 507718 | BROWNLEE | 507745 | NORTH MARKET | Rebuild 4.7-mile 69 kV line from Brownlee to North Market with 1233.6 ACSR/TW. | 69 | 4.7
#REF! | 50545 |  | #REF! | #REF! | #REF! | Yes |  | TP2010067 | 200231 | 30449 | AEP | Line - Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Regional Reliability | 2016-09-19 | 2016-09-19 | 2014-06-01 | 2013-09-23 | 2013 ITPNT | 25060655 | 2013 | 28353831 | 25060655 |  |  | COMPLETE | 509083 | ROCK HILL 138 | 507757 | SPRINGRIDGE PAN-HARR REC | Rebuild 27.6-mile 138 kV line from Rock Hill to Springridge Pan-Harr REC with 1926.9 ACSR/TW conductor. | 138 | 27.6
#REF! | 11261 |  | #REF! | #REF! | #REF! | No | Direct Assigned | TP2010092 | 20104 | 947 | AEP | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | 2016-05-25 | 2016-05-25 | 2015-06-01 | 2010-08-25 | SPP-2008-AGP1-AFS-9 | 6072000 | 2014 | 6702352 | 6072000 |  |  | COMPLETE | 509806 | ONETA 138KV | 509786 | BROKEN ARROW NORTH - SOUTH TAP | Rebuild 4.33 of 795 ACSR with 1590 ACSR. | 138 |  | 4.33
#REF! | 11158 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2010094 | 200216 | 879 | AEP | Line - Bluebell - Prattville 138 kV | Bluebell - Prattville 138 kV Ckt 1 | Regional Reliability | 2015-06-02 | 2015-06-02 | 2014-06-01 | 2013-02-20 | 2013 ITPNT | 10241314 | 2013 | 11587107 | 10241314 |  |  | COMPLETE | 515242 | BLUEBELL 138 | 509758 | PRATTVILLE | Rebuild 9.0-mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW. | 138 |  | 9
#REF! | 10646 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2010100 | 200216 | 501 | AEP | Line - Evenside - Northwest Henderson 69 kV | Evenside - Northwest Henderson 69 kV Ckt 1 | Regional Reliability | 2018-05-11 | 2018-05-11 | 2018-06-01 | 2013-02-20 | 2013 ITPNT | 11980465 | 2013 | 13554796 | 11980465 |  |  | ON SCHEDULE < 4 | 509061 | EVENSIDE | 509075 | NORTHWEST HENDERSON 69KV | Rebuild 6.4-mile 69 kV line from Evenside to Northwest Henderson with 1233.6 ACSR/TW. Replace breaker at Evenside. | 69 |  | 6.4
#REF! | 50336 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2011022 | 20122 | 30298 | AEP | Device - Logansport 138 kV | LOGANSPORT 138KV | Regional Reliability | 2016-09-10 | 2016-09-10 | 2016-06-01 | 2011-02-14 | 2010 STEP | 1166400 | 2014 | 1287487 | 1731419 |  |  | COMPLETE | 509071 | LOGANSPORT 138KV |  |  | Install 28.8 MVAR capacitor bank at Logansport 138 kV substation. | 138
#REF! | 10648 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2011023 | 200167 | 503 | AEP | Line - Diana - Perdue 138 kV | Diana - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2013-06-01 | 2012-04-09 | 2012 ITPNT | 1004187 | 2012 | 1164549 | 1004187 |  |  | COMPLETE | 508351 | PERDUE 138KV | 508831 | DIANA 138KV | Replace two breakers, jumpers, and wave traps at Perdue substation. Replace wave traps at Diana substation. | 138
#REF! | 50531 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2011023 | 200216 | 30436 | AEP | Line - New Gladewater - Perdue 138 kV | New Gladewater - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2016-06-01 | 2013-02-20 | 2013 ITPNT | 1000000 | 2013 | 1131408 | 1000000 |  |  | COMPLETE | 508560 | NEW GLADEWATER | 508351 | PERDUE 138KV | Replace 138 kV breaker at Perdue. | 138
#REF! | 50607 |  | #REF! | #REF! | #REF! | Yes |  | TP2011033 | 200231 | 30495 | AEP | Sub - Messick 500/230 kV | Layfield 500/230 kV Transformer Ckt 1 | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 2013 ITPNT | 30369537 | 2013 | 34360344 | 22851755 |  |  | COMPLETE | 999113 | Messick 500 kV | 999114 |  | Build Messick 500/230 kV substation. Connect to Carrol, Clarence, and Western Kraft 230 kV lines. Install 500/230 kV 675 MVA transformer. This upgrade is contingent upon approval from Cleco Power LLC. | 500/230
#REF! | 50615 |  | #REF! | #REF! | #REF! | Yes |  | TP2011033 | 200231 | 30495 | AEP | Sub - Messick 500/230 kV | Layfield 500 kV Terminal Upgrades | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 2013 ITPNT | 21508234 | 2013 | 24334593 | 32212715 |  |  | COMPLETE | 999113 | Messick 500 kV |  |  | Install terminal equipment on 500 kV side of new Messick substation. Connect to Mt. Olive - Hartburg 500 kV line. This upgrade is contingent upon approval from Cleco Power LLC for Upgrade ID 50607. | 500
#REF! | 51448 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2011110 | 200386 | 31005 | AEP | Sub - Elk City 138 kV Move Load (BPID P11110001) | Elk City 138 kV Move Load | Regional Reliability | 2018-05-25 | 2018-05-25 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2904911 | 2016 | 3051972 | 2904911 |  |  | DELAY - MITIGATION | 511458 | ELK CITY 138 | 511459 | ELK CITY 69 | Move load from 69 kV bus to 138 kV bus at Elk City. | 138
#REF! | 10583 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2011147 | 200216 | 451 | AEP | Multi - Chamber Springs - Farmington 161 kV | Chamber Springs - Farmington REC 161 kV Ckt 1 | Regional Reliability | 2017-03-28 | 2017-03-28 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 12705537 | 2013 | 14375149 | 12705537 |  |  | COMPLETE | 506944 | CHAMBER SPRINGS 161KV | 504020 | FARMINGTON AECC | Rebuild and reconductor 11.1-mile 161 kV line from Chamber Springs to Farmington REC with 2-959.6 ACSR/TW. Upgrade wavetraps, CT ratios, and relay settings at Chamber Springs. | 161 |  | 11.1
#REF! | 50413 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm - Gracemont 345kV Ckt 1 (AEP) | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 65082311 | 2017 | 66709369 | 65082311 |  |  | COMPLETE | 700345 | Chisholm 345 kV | 515800 | Gracemont 345kv | Build new single circuit 345 kV line from new Chisholm substation to point of interconnection with Oklahoma Gas & Electric Co. (OGE) towards Gracemont. The approximate line length for the Chisholm - Gracemont 345 kV line is 100 miles, of which AEP will construct approximately 70 miles from Chisholm to the OGE interconnection point. | 345 | 72
#REF! | 50414 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 345/230 kV Substation | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 17471695 | 2017 | 17908487 | 17471695 |  |  | COMPLETE | 700345 | Chisholm 345 kV | 700231 | Chisholm 230 kV | Construct new 345/230 kV Chisholm substation between existing 230 kV substations, Sweetwater and Elk City. Cut-in existing Sweetwater - Elk City 230 kV Ckt 1 line into new Chisholm substation and install any necessary 230 kV terminal equipment. Install new 345/230 675 MVA transformer at new Chisholm substation. | 345/230
#REF! | 50768 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 230 kV | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 1270623 | 2017 | 1302389 | 1270623 |  |  | COMPLETE | 700345 | Chisholm 345 kV |  |  | Install approximately 2 miles of 230 kV transmission line for a cut-in to existing 230 kV line from Sweetwater to Elk City, creating termination points at new Chisholm substation. | 230 | 2
#REF! | 51047 | TBD | #REF! | #REF! | #REF! | Yes |  | TP2012055 | 200272 | 30770 | AEP | Sub - Ellis 138 kV | Ellis 138 kV Substation | High Priority | 2013-06-01 | 2013-06-01 | 2015-06-01 | 2014-05-19 | HPILS | 4100000 | 2014 | 4525633 | 4100000 | 4086696 | Formula Rate Update | COMPLETE | 511561 |  | 521001 | MOREWOOD SW | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation. | 138
#REF! | 50567 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2012144 | 200216 | 30471 | AEP | Line - Dekalb - New Boston 69 kV | Dekalb - New Boston 69 kV Ckt 1 | Regional Reliability | 2015-06-05 | 2015-06-05 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 16548317 | 2013 | 18722901 | 16548317 | 15777911 | Formula Rate Update | COMPLETE | 508067 | NEW BOSTON | 508289 | DEKALB | Rebuild 13.2-mile 69 kV line from Dekalb to New Boston with 1233.6 ACSR/TW. Upgrade CT ratios and relay settings at New Boston. | 69 | 13.2
#REF! | 10615 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2012145 | 200216 | 478 | AEP | Line - Forbing Tap - South Shreveport 69 kV | Forbing Tap - South Shreveport 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 1221505 | 2013 | 1382021 | 1221505 |  |  | COMPLETE | 507728 | FORBING TAP | 507754 | SOUTH SHREVEPORT 69KV | Rebuild 2.3-mile 69 kV line from Forbing to South Shreveport with 1233.6 ACSR/TW. | 69 |  | 2.3
#REF! | 10657 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2012145 | 200246 | 512 | AEP | Line - Ellerbe Road - Forbing Tap 69 kV Ckt 1 | Ellerbe Road - Forbing T 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 8174689 | 2014 | 9023327 | 8174689 |  |  | COMPLETE | 507723 | ELLERBE ROAD 69 kV | 507728 | FORBING TAP | Rebuild 2.0-mile 69 kV line from Ellerbe Road to Forbing T with 1233.6 ACSR/TW conductor. | 69 | 2
#REF! | 50568 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2012146 | 200216 | 30472 | AEP | Line - Hardy Street - Waterworks 69 kV | Hardy Street - Waterworks 69 kV Ckt 1 | Regional Reliability | 2015-06-25 | 2015-06-25 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 7519658 | 2013 | 8507803 | 7519658 | 5366606 | Formula Rate Update | COMPLETE | 507734 | HARDY STREET | 507766 | WATERWORKS | Rebuild 1.6-mile 69 kV line from Hardy Street to Waterworks with 1233.6 ACSR/TW. | 69 | 1.65
#REF! | 50569 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2012164 | 200216 | 30473 | AEP | Line - Midland REC - North Huntington 69 kV | Midland REC - North Huntington 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 1829026 | 2013 | 2069375 | 1829026 | 11990487 | Formula Rate Update | COMPLETE | 507196 | MIDLAND REC | 507188 | NORTH HUNTINGTON 69KV | Rebuild 4.0-mile 69 kV line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington. | 69 | 1.3
#REF! | 50570 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2012164 | 200216 | 30474 | AEP | Line - Midland - Midland REC 69 kV | Midland - Midland REC 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 5653353 | 2013 | 6396250 | 5653353 | Included in UID 50569 | Formula Rate Update | COMPLETE | 507187 | MIDLAND | 507196 | MIDLAND REC | Rebuild 1.3-mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | 69 | 4.3
#REF! | 50571 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2012164 | 200216 | 30475 | AEP | Line - Howe Interchange - Midland 69 kV | Howe Interchange - Midland 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 9145130 | 2013 | 10346875 | 9145130 | Included in UID 50569 | Formula Rate Update | COMPLETE | 515259 | HOWE INT 69 | 507187 | MIDLAND | Rebuild 7.0-mile portion of the 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of line to be rebuilt is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | 69 | 7
#REF! | 51014 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2013002 | 200272 | 30747 | AEP | Line - Grady - Round Creek 138 kV Ckt 1 | Grady - Round Creek 138 kV Ckt 1 | High Priority | 2015-11-05 | 2015-11-05 | 2015-06-01 | 2014-05-19 | HPILS | 12132497 | 2014 | 13392006 | 12132497 |  |  | COMPLETE | 511560 |  | 511427 | RUSH SPRINGS NATURAL GAS | Construct new Round Creek box bay tap structure adjacent to the Rush Springs 138 kV substation. Construct new 6-mile 138 kV line from Grady to Round Creek. Install 3-breaker ring bus where hard tap to Round Creek intersects the Cornville to Duncan 138 kV transmission line. | 138
#REF! | 51015 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2013002 | 200272 | 30748 | AEP | Line - Grady - Phillips Gas 138 kV Ckt 1 and 2 | Grady - Phillips 138 kV Ckt 1 and 2 | High Priority | 2014-12-31 | 2014-12-31 | 2015-06-01 | 2014-05-19 | HPILS | 8318584 | 2014 | 9182160 | 8318584 |  |  | COMPLETE | 511514 | PHILLIPS | 511560 |  | Construct new 4-mile double circuit 138 kV line from the new 4-breaker ring bus station at Grady. Circuit 1 will terminate at Phillips Gas and Circuit 2 will terminate at Lindsey Water Flood. | 138 | 4
#REF! | 50990 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2013081 | 200306 | 30731 | AEP | Line - Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | Mt Pleasant - West Mt Pleasant 69 kV Ckt 1 Rebuild | Regional Reliability | 2015-04-20 | 2015-04-20 | 2015-06-01 | 2014-11-24 | DPA-2013-SEP-351 | 4715419 | 2015 | 5077991 | 7381799 |  |  | COMPLETE |  |  |  |  | Rebuild 2.75-mile 69 kV line from Mt. Pleasant to West Mt. Pleasant to achieve a new emergency rating of 84 MVA. | 69 |  | 2.72
#REF! | 50334 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2013122 | 20122 | 30296 | AEP | Device - Winnsboro 138 kV | WINNSBORO 138KV | Regional Reliability | 2016-04-21 | 2016-04-21 | 2016-06-01 | 2011-02-14 | 2010 STEP | 1166400 | 2014 | 1287487 | 1166400 |  |  | COMPLETE | 508317 | Winnsboro 138 kV |  |  | Install a new 28.8 MVAR capacitor bank at Winnsboro 138 kV substation. | 138
#REF! | 50718 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2013165 | 200246 | 30573 | AEP | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-21 | 2017-06-21 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 6695986 | 2014 | 7391116 | 6695986 |  |  | COMPLETE | 507716 | BROADMOOR | 507730 | FORT HUMBUG 69KV | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor. | 69 |  | 1.7
#REF! | 50719 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2013166 | 200246 | 30574 | AEP | Line - Daingerfield - Jenkins Rec 69 kV Ckt 1 Rebuild | Daingerfield - Jenkins REC T 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-11-09 | 2017-11-09 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 2819806 | 2014 | 3112538 | 2819806 |  |  | COMPLETE | 508288 | DAINGERFIELD | 508293 | JENKINS REC T | Rebuild 1.3-mile 69 kV line from Daingerfield to Jenkins REC T with 959.6 ACSR/TW conductor. | 69 |  | 1.3
#REF! | 50720 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2013167 | 200246 | 30575 | AEP | Line - Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-03-02 | 2018-03-02 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 8851677 | 2014 | 9770595 | 11571330 |  |  | COMPLETE | 508543 | HALLSVILLE | 508553 | LONGVIEW HEIGHTS 69KV | Rebuild 6.6-mile 69 kV line from Longview Heights to Hallsville with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Longview Heights. | 69 |  | 6.6
#REF! | 50721 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2013167 | 200246 | 30576 | AEP | Line - Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-02 | 2017-06-02 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 15248925 | 2014 | 16831960 | 19751448 |  |  | COMPLETE | 508556 | MARSHALL 69KV | 508543 | HALLSVILLE | Rebuild 11.2-mile 69 kV line from Hallsville to Marshall with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Marshall. | 69 |  | 11.2
#REF! | 11423 | Base Plan | #REF! | #REF! | #REF! | No | Suspended | TP2013169 | 200305 | 1083 | AEP | Line - Welsh Reserve - Wilkes 138 kV Ckt 1 | Welsh Reserve - Wilkes 138 kV Ckt 1 Rebuild | Regional Reliability | Not Found in Future | 2019-06-01 | 2019-06-01 | 2014-09-30 | 2014 ITPNT | 24880495 | 2014 | 27463411 | 24880495 |  |  | RE-EVALUATION | 508355 | Welsh Reserve 138 kV | 508840 | WILKES 138KV | Rebuild 23.7-mile 138 kV line from Welsh Reserve to Wilkes with 1926.9 ACSR/TW conductor. Upgrade switches at Welsh Reserve and Wilkes and wave traps, jumpers, CT ratios, and relay settings at Wilkes. | 138 |  | 23.74
#REF! | 50697 | Base Plan | #REF! | #REF! | #REF! | No | Suspended | TP2013169 | 200246 | 30559 | AEP | Line - Chapel Hill REC - Welsh Reserve 138 kV Ckt 1 | Chapel Hill REC - Welsh Reserve 138 kV Ckt 1 Rebuild | Regional Reliability | Not Found in Future | 2019-06-01 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 6651694 | 2014 | 7342226 | 6651694 |  |  | RE-EVALUATION | 508337 | CHAPEL HILL REC | 508355 | Welsh Reserve 138 kV | Rebuild 4.4-mile 138 kV line from Chapel Hill REC to Welsh Reserve. | 138 |  | 4.39
#REF! | 51215 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2014138 | 200314 | 30895 | AEP | Line - Brooks Street - Edwards Street 69kV Ckt 1 Rebuild | Brooks Street - Edwards Street 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-12-20 | 2017-12-20 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 4294228 | 2015 | 4624414 | 4294228 |  |  | COMPLETE | 507717 | BROOKS STREET | 507722 | EDWARDS STREET | Rebuild 0.8-mile 69 kV line from Brooks Street to Edwards Street. Upgrade jumpers at both substations. | 69 |  | 0.85
#REF! | 51033 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2014139 | 200298 | 30761 | AEP | Line - Cedar Grove - South Shreveport 138 kV | Cedar Grove - South Shreveport 138 kV | Transmission Service | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2014-09-30 | SPP-2010-AGP1-AFS-8 | 6566218 | 2014 | 7247876 | 6566218 |  |  | ON SCHEDULE < 4 | 507771 | CEDARGROVE | 507755 | SOUTH SHREVEPORT 138KV | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove. | 138
#REF! | 51207 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2014139 | 200406 | 30889 | AEP | Line - Linwood - South Shreveport 138kV Ckt 1 Rebuild | Linwood - South Shreveport 138 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-10 | 2018-05-10 | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 5285437 | 2016 | 5553013 | 5919107 |  |  | DELAY - MITIGATION | 507738 | LINWOOD | 507771 | CEDARGROVE | Rebuild the 2.4-mile 138kV line from Linwood to Cedar Grove to South Shreveport. Upgrade the jumpers at Linwood. | 138 |  | 2.42
#REF! | 51034 | Base Plan | #REF! | #REF! | #REF! | No | Need to Add | TP2014154 | 200339 | 30762 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | DPA-2013-MAR-296 | 6629465 | 2015 | 7139209 | 6629465 |  |  | ON SCHEDULE < 4 | 507723 | ELLERBE ROAD 69 kV | 507739 | LUCAS | Rebuild existing 3.2-mile 69 kV line from Ellerbe Road to Lucas. | 69 | 3.2
#REF! | 51035 | Base Plan | #REF! | #REF! | #REF! | No | Need to Add | TP2014154 | 200339 | 30762 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Terminal Upgrades | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | DPA-2013-MAR-296 | 652658 | 2015 | 702841 | 652658 |  |  | ON SCHEDULE < 4 | 507723 | ELLERBE ROAD 69 kV |  |  | Replace jumpers at 69 kV substations Ellerbe Road and Lucas. Replace relay panel at Ellerbe Road. Change relay setting at Lucas. | 69
#REF! | 51187 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2014207 | 200314 | 30873 | AEP | Line - Southwestern Station - Carnegie 138kV Ckt 1 Rebuild | Southwestern Station - Carnegie 138 kV Ckt 1 Rebuild | Regional Reliability | 2017-07-06 | 2017-07-06 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 15821763 | 2015 | 17038308 | 9397311 |  |  | COMPLETE | 511477 | SOUTHWESTERN STATION 138KV | 511445 | CARNEGIE | Rebuild 16.5-mile 138 kV from Southwestern Station to Carnegie. | 138 |  | 16.52 | 138
#REF! | 50802 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2015027 | 200310 | 30619 | AEP | Line - Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | High Priority | 2017-06-29 | 2017-06-29 | 2015-06-01 | 2014-12-02 | HPILS | 11652107 | 2014 | 12861746 | 11652107 |  |  | COMPLETE | 511559 |  | 514823 | ROMAN NOSE 138 | Construct AEP's portion of new 25-mile 138 kV line from Darlington to Roman Nose (OGE). | 138 | 14.25
#REF! | 50759 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2015106 | 200361 | 30598 | AEP | Device - Letourneau 69 kV Cap Bank | Letourneau 69 kV Cap Bank | Regional Reliability | 2017-06-26 | 2017-06-26 | 2017-06-01 | 2015-12-11 | 2016 ITPNT | 1409347 | 2016 | 1480696 | 1409347 |  |  | COMPLETE | 508536 | LETOURNEAU STEEL | 508594 | Letouteau W tap 69 kV | Install 16.2-MVAR 69 kV capacitor bank at Letourneau. | 69
#REF! | 51096 |  | #REF! | #REF! | #REF! | No | No 2018-2019 Forecast | TP2015118 | 200382 | 30809 | AEP | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2016-04-12 | SPP-2014-AG1-AFS-6 | 4319501 | 2016 | 4538176 | 4319501 |  |  | ON SCHEDULE < 4 | 505610 | Keystone Dam | 509757 | WEKIWA 138KV | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation. | 138 | 2 | 2 | 2
#REF! | 51454 |  | #REF! | #REF! | #REF! | Yes |  | TP2015191 | 200406 | 31009 | AEP | Line - Duncan - Tosco 69 kV Ckt 1 Rebuild (Paula Keefe BPID P151910001) | Duncan - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-04 | 2018-05-04 | 2018-06-01 | 2016-08-17 | 2016 ITPNT | 5974766 | 2016 | 6277239 | 5974766 |  |  | DELAY - MITIGATION | 511452 | DUNCAN 69KV | 511457 | TOSCO 69KV | Rebuild 69 kV line from Duncan to Tosco. Replace wave trap at Duncan. | 69 | 3.86 | 3.86 | 69
#REF! | 51524 |  | #REF! | #REF! | #REF! | Yes |  | TP2015191 | 200406 | 31039 | AEP | Line - Comanche Tap - Tosco 69 kV Ckt 1 Rebuild (Brent Garret BPID's A11012077&A11012447) | Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2016-12-19 | 2016-12-19 | 2020-06-01 | 2016-08-17 | 2016 ITPNT | 4365864 | 2016 | 4586886 | 4365864 |  |  | COMPLETE | 511498 | COMANCHE TAP 69KV | 511457 | TOSCO 69KV | Rebuild 69 kV line from Comanche Tap to Tosco. | 69 | 3.2 | 3.2 | 69
#REF! | 51433 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2015202 | 200386 | 30997 | AEP | Device - Sayre 138 kV Cap Bank | Sayre 138 kV Cap Bank | Regional Reliability | 2018-12-19 | 2018-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 758441 | 2016 | 796837 | 1483426 |  |  | DELAY - MITIGATION | 511504 | SAYRE |  |  | Install new 14.4-MVAR capacitor bank at Sayre 138 kV. | 138
#REF! | 51561 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2015204 | 200386 | 31058 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Fort Towson - Kiamichi Pump Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 2016 ITPNT | 11778983 | 2016 | 12375294 | 11778983 |  |  | DELAY - MITIGATION | 510876 | KIAMICHI PUMP TAP | 510917 | FORT TOWSON | Rebuild 9.0-mile 69 kV line from Fort Towson to Kiamichi Pump Tap. | 69
#REF! | 51562 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2015204 | 200386 | 31058 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 2016 ITPNT | 7699929 | 2016 | 8089738 | 7699929 |  |  | DELAY - MITIGATION | 510876 | KIAMICHI PUMP TAP | 510910 | VALLIANT 69KV | Rebuild 4.8-mile portion of 69 kV line from Kiamichi Pump Tap to Valliant. | 69
#REF! | 51738 | Base Plan | #REF! | #REF! | #REF! | No | Need to Add | TP2017010 | 200431 | 31131 | AEP | Line - Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild | Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild (AEP) | Economic | 2020-01-01 | 2020-01-01 | 2017-01-01 | 2017-02-21 | 2017 ITP10 | 4780000 | 2017 | 4899500 | 4780000 |  |  | DELAY - MITIGATION | 506948 | SILOAM SPRINGS | 512643 | SILOAM CITY 161 | Rebuild 2.1-mile 161 kV line from Siloam Springs (AEP) - Siloam Springs City (GRDA) and upgrade terminal equipment at Siloam Springs. | 161
#REF! | 61858 | Base Plan | #REF! | #REF! | #REF! | No | Need to Add | TP2017011 | 200446 | 41202 | AEP | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 6014381 | 2017 | 6164741 | 6014381 |  |  | DELAY - MITIGATION | 509811 | TULSA SOUTHEAST 138KV | 509831 | EAST 61st STREET | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line. | 138 | 1.8
#REF! | 51831 | Base Plan | #REF! | #REF! | #REF! | Yes |  | TP2017012 | 200446 | 31186 | AEP | Device - IPC 138 kV Cap Bank | IPC 138 kV Cap Bank | Regional Reliability | 2018-12-13 | 2018-12-01 | 2018-12-01 | 2017-05-12 | 2017 ITPNT | 1298048 | 2017 | 1330499 | 1917591 |  |  | ON SCHEDULE < 4 |  |  |  |  | Install 28.8-MVAR capacitor bank at IPC 138 kV | 138
#REF! | 71945 | Base Plan | #REF! | #REF! | #REF! | No | Need to Add | TP2017016 | 200446 | 41233 | AEP | Line - Broken Arrow North - Lynn Lane East 138 kV Ckt 1 | Broken Arrow North - Lynn Lane East 138 kV Ckt 1 Reconductor | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 5714095 | 2017 | 5856947 | 5714095 |  |  | DELAY - MITIGATION | 509786 | BROKEN ARROW NORTH - SOUTH TAP | 509804 | LYNN LANE TAP | Reconductor Broken Arrow - Lynn Lane East 7.2-mile 138 kV line | 138 |  | 7.13
#REF! | 82137 |  | #REF! | #REF! | #REF! | No | Not Base Plan | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | 2019-02-15 | 2019-02-15 | [6 empty] | 700000 |  |  | ON SCHEDULE < 4 |  |  |  |  | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation.
#REF! | 82138 |  | #REF! | #REF! | #REF! | No | Not Base Plan | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | 2019-03-31 | 2019-03-31 | [6 empty] | 8700000 |  |  | ON SCHEDULE < 4 |  |  |  |  | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer.
#REF! | 10001 |  | #REF! | #REF! | #REF! | No | OLD |  | 19999 | 1 | AEP | Line - Bann - Kings Highway 69 kV | BANN - KINGS HIGHWAY 69 kV CKT 1 | Regional Reliability | Not Found in Future | 2007-06-01 | 2008-06-01 | 2007-02-02 | 2006 STEP |  |  |  | 5174095 | 0 | Formula Rate Update | COMPLETE | 508053 | BANN 69KV | 508061 | KINGS HIGHWAY | Replace Switch in King Hwy substation | 69
Formulas:
Q2 2019 Project Owner Indicated ISD = IFNA(VLOOKUP([UID],'Q2 2019 Initial PTP'!$F1:L59,7,0),"Not Found in Future")