## OKTCo
Code | FR Sheet Name (WS F&G) | Projected / Actual In-Service (mmm-yyyy) | Project & TP# | --- P R E V I O S L Y P U B L I S H E D --- | [15 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- WS-F and WS-G SUMMARY Input Data --- | [5 empty] | COMMENTS
|  |  |  | 09 Update | 2010 Update |  |  | 2011 Update |  |  |  | 2012 Update |  |  |  | 2013 Update |  |  |  | 2014 Update |  |  |  | 2015 Update |  |  |  | 2016 Update |  |  |  | 2017 Update | [5 empty] | 2018 Update | [5 empty] | 2019 Update |  |  |  |  | 2020 Update
|  |  |  | YE2009 Projected (8/31/09) << WS-F >> | YE2009 Actual << WS-G >> | YE2010 Projected << WS-F >> | YE09 to YE10 Variance | YE2010 Actual (May'11) << WS-G >> | YE2011 Projected (May '11) << WS-F >> | YE2010 Variance (Projected to Actual) | YE10 (actual) to YE11 (Projected) Variance | YE2011 Actual (May'12) << WS-G >> | YE2012 Projected (May '12) << WS-F >> | YE2011 Variance (Projected to Actual) | YE11 (actual) to YE12 (Projected) Variance | YE2012 Actual (May'13) << WS-G >> | YE2013 Projected (May '13) << WS-F >> | YE2012 Variance (Projected to Actual) | YE12 (actual) to YE13 (Projected) Variance | YE2013 Actual (May'14) << WS-G >> | YE2014 Projected (May '14) << WS-F >> | YE2013 Variance (Projected to Actual) | YE13 (actual) to YE14 (Projected) Variance | YE2014 Actual (May'15) << WS-G >> | YE2015 Projected (May '15) << WS-F >> | YE2014 Variance (Projected to Actual) | YE14 (actual) to YE15 (Projected) Variance | YE2015 Actual (May'16) << WS-G >> | YE2016 Projected (May '16) << WS-F >> | YE2015 Variance (Projected to Actual) | YE15 (actual) to YE16 (Projected) Variance | YE2016 Actual (May'17) << WS-G >> | YE2017 Projected (May '17) << WS-F >> | YE2017 Projected Adjusted (Oct '17) << WS-F >> | YE2018 Projected (Oct '17) << WS-F >> | YE2016 Variance (Projected to Actual) | YE16 (actual) to YE17 (Projected) Variance | YE2017 Actual (May '18) << WS-G >> | YE2018 Projected (May '18) << WS-F >> | YE2018 Projected Adjusted (Oct '18) << WS-F >> | YE2019 Projected (Oct '18) << WS-F >> | YE2017 Variance (Projected to Actual) | YE17 (Actual) to YE18 (Projected) Variance | YE2018 Actual (May '19) << WS-G >> | YE2019 Projected (Oct '19) << WS-F >> | YE2020 Projected (Oct '19) << WS-F >> | YE2018 Variance (Projected to Actual) | YE18 (Actual) to YE19 (Projected) Variance | YE2019 Actual (May '20) << WS-G >> | YE2020 Projected (May '2020) << WS-F >> | YE2020 Projected (Oct '20) << WS-F >> | YE2021 Projected (Oct '20) << WS-F >> | YE2019 Variance (Projected to Actual) | YE19 (Actual) to YE20 (Projected) Variance
t | OKT.001 | 2010-12-01 | Snyder 138 kv Terminal Addition (TP2009013) | --- | --- | 767749 | --- | 634790 | 634790 | -17.32% | 0% | 706495.57 | 706495.57 | 11.3% | 0% | 723818 | 723818 | 2.452% | 0% | 723818 | 723818 | 0% | 0% | 723818 | 723818 | 0% | 0% | 723818 | 723818 |  |  | 723818 | 723818 | 723818 | 723818 |  |  | 723818 | 723818 | 723818 | 723818 |  |  | 723818 | 723818 | 723818 |  |  | 723818 | 723818
t | OKT.002 | 2010-06-01 | CoffeyvilleT to Dearing 138 kv Rebuild - 1.1 mi (TP2008013) | --- | --- | 1000000 | --- | 981860 | 981860 | -1.814% | 0% | 985777.34 | 985777.34 | 0.399% | 0% | 985777 | 985777 | -3.449e-05% | 0% | 985777 | 985777 | 0% | 0% | 985777.34 | 985777.34 | 3.449e-05% | 0% | 985777 | 985777 |  |  | 985777 | 985777 | 985777 | 985777 |  |  | 985777 | 985777 | 985777 | 985777 |  |  | 985777 | 985777 | 985777 |  |  | 985777 | 985777 |  |  |  |  | Also see related PSO project (P.013).
t | OKT.003 | 2011-10-01 | Tulsa Power Station Reactor (TP2009090) | --- | --- | --- | --- | --- | 956000 | --- | --- | 614691 | 614691 | -35.7% | 0% | 614753 | 614753 | 0.01009% | 0% | 614753 | 614753 | 0% | 0% | 614752.9 | 614752.9 | -1.627e-05% | 0% | 614753 | 614753 |  |  | 614753 | 614753 | 614753 | 614753 |  |  | 614753 | 614753 | 614753 | 614753 |  |  | 614753 | 614753 | 614753 |  |  | 614753 | 614753
t | OKT.004 | 2011-06-01 | Bartlesville SE to Coffeyville T Rebuild (TP2008079-Transco) | --- | --- | --- | --- | --- | 12876000 | --- | --- | 11790024 | 11790024 | -8.434% | 0% | 11742800 | 11742800 | -0.4005% | 0% | 11742800 | 11742800 | 0% | 0% | 11742800 | 11742800 | 0% | 0% | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800 |  |  |  |  | Also see related PSO project (P.011).
n/a | OKT.005 | 2012-04-01 | Install 345kV terminal at Valliant (TP2007167) | --- | --- | --- | --- | --- | --- | --- | --- | --- | 3951600 | --- | --- | 4377316 | 4377316 | 10.77% | 0% | [8 empty] | 0% |  |  |  | 0% | [22 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes.
t | OKT.006 | 2013-08-01 | Canadian River - McAlester City 138 kV Line Conversion (TP2009095) | --- | --- | --- | --- | --- | --- | --- | --- | --- | 6627800 | --- | --- | 9966686 | 28567786 | 50.38% | 186.6% | 28682400 | 28682400 | 0.4012% | 0% | 28914235.74 | 28914235.74 | 0.8083% | 0% | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236 |  |  |  |  | Also see related PSO project (P.012). Multi-element multi-year base plan project. Final in-service yr in 12' and 13'.
t | OKT.007 | 2014-10-01 | Cornville Station Conversion (TP2011093) | [17 empty] | 10780000 |  |  | 10166784.78 | 10250000 | -5.688% | 0.8185% | 10218098.37 | 10218098.37 | -0.3112% | 0% | 10218098.37 | 10218098.37 | 10218098.37 | 10218098.37 | 0% | 0% | 10218098.37 | 10218098.37 | 10218098.37 | 10218098.37 | 0% | 0% | 10218098.37 | 10218098.37 | 10218098.37 | 0% | 0% | 10218098.37 | 10218098.37 |  |  | 0% | 0% | Also see related PSO project (P.016).
t | OKT.008 | 2014-06-01 | Coweta 69 kV Capacitor | --- | --- | --- | --- | [13 empty] | 669000 |  |  | 1864625.01 | 1864625.01 | 178.7% | 0% | 1864625 | 1864625 |  |  | 1864625 | 1864625 | 1864625 | 1864625 |  |  | 1864625 | 1864625 | 1864625 | 1864625 | 0% | 0% | 1864625 | 1864625 | 1864625 | 0% | 0% | 1864625 | 1864625 |  |  | 0% | 0%
t | OKT.009 | 2016-12-16 | Valliant-NW Texarkana 345 kV | --- | --- | --- | --- | [16 empty] | 0 | 2960000 |  |  | 2844116 | 3408237 | -3.915% | 19.83% | 67708596.12 | 69121596.12 | 69121596.12 | 69121596.12 | 1887% | 2.087% | 68230087.8 | 69121596.12 | 69121596.12 | 69121596.12 | -1.29% | 1.307% | 68247468.75 | 68247468.75 | 68247468.75 | -1.265% | 1.281% | 68247468.75 | 68247468.75 |  |  | 0% | 0% | 345 kV terminal work to be completed October 2015; Also see related PSO project (P.018) and SWEPCo project (S.058).
t | OKT.011 | 2015-06-02 | Prattville-Bluebell 138 kV | --- | --- | --- | --- | [16 empty] | 0 | 7400000 |  |  | 8430000 | 8456490 | 13.92% | 0.3142% | 8535104 | 8535104 | 8535104 | 8535104 | 0.9296% | 0% | 8535104 | 8535104 | 8535104 | 8535104 | 0% | 0% | 8535104 | 8535104 | 8535104 | 0% | 0% | 8535104 | 8535104 |  |  | 0% | 0%
t | OKT.012 | 2013-12-01 | Wapanucka Customer Connection | --- | --- | --- | --- | [16 empty] | 7200873.82 | 7200873.82 |  | 0% | 7210308.95 | 7210308.95 |  |  | 7210308.95 | 7210308.95 | 7210308.95 | 7210308.95 |  |  | 7210308.95 | 7210308.95 | 7210308.95 | 7210308.95 | 0% | 0% | 7210308.95 | 7210308.95 | 7210308.95 | 0% | 0% | 7210308.95 | 7210308.95 |  |  | 0% | 0% | This was originally a customer-service project, then later became a BP project. Associated BPIDs P1214101, P12141005, and P12141009.
t | OKT.013 | 2015-11-05 | Grady Customer Connection | --- | --- | --- | --- | [16 empty] | #REF! | 19043679.66 |  | #REF! | #REF! | #REF! | #REF! | #REF! | 20242007 | 20248060 | 20248060 | 20248060 | #REF! | 0.0299% | #REF! | 20248060 | 20248060 | 20248060 | #REF! | #REF! | 20242585.05 | 20248060 | 20248060 | -0.02704% | 0.02705% | 20242585.05 | 20242585.05 |  |  | -0.02704% | 0% | This was originally a customer-service project, then later became a BP project. Also see related PSO project (P.020).
t | OKT.014 | 2014-04-01 | Darlington-Red Rock 138 kV line | --- | --- | --- | --- | [16 empty] | 13254470.19 | 13254470.19 |  | 0% | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 | 13254470 | 0% | 0% | 13254470 | 13254470 | 13254470 | 0% | 0% | 13254470 | 13254470 |  |  | 0% | 0% | Also see related PSO project (P.021).
c | OKT.014 |  | Construct new 8-mile 138 kV line from Red Rock to Darlington. | [20 empty] | 13254470.19 | 13254470.19 |  |  | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 |  |  | 13254470 | 13254470 |  |  |  |  | Cost includes all terminal work also.
t | OKT.015 | 2013-10-01 | Ellis 138 kV | --- | --- | --- | --- | [16 empty] | 4086696.07 | 4086696.07 |  | 0% | 4086696 | 4086696 |  |  | 4800037.86 | 0 | 0 | 0 |  |  | 4817114 | 0 | 0 | 0 | 0% | -100% | 4817114 | 0 | 0 | #DIV/0! | -100% | 4817114 | 4817114 |  |  | #DIV/0! | 0%
t | OKT.016 | 2017-06-29 | Darlington-Roman Nose 138 kV | --- | --- | --- | --- | [16 empty] | 0 | 0 |  | 0% | 0 | 0 |  |  | 0 | 10615000 | 10615000 | 10615000 |  |  | 11033622.83 | 10615000 | 10615000 | 10615000 | 3.944% | -3.794% | 11056565.36 | 11056565.36 | 11056565.36 | 4.16% | -3.994% | 11056565.36 | 11056565.36 |  |  | 0% | 0%
t | OKT.017 | 2017-07-06 | Carnegie South-Southwestern 138 kV Line Rebuild | --- | --- | --- | --- | [16 empty] | 0 | 0 |  | 0% | 0 | 0 |  |  | 0 | 8899000 | 8899000 | 8899000 |  |  | 9557910 | 8899000 | 8899000 | 8899000 | 7.404% | -6.894% | 9589270.28 | 9657270.28 | 9657270.28 | 7.757% | -7.198% | 9589270.28 | 9589270.28 |  |  | -0.7041% | 0%
t | OKT.018 | 2017-12-07 | Chisholm - Gracemont 345 kV | --- | --- | --- | --- | [16 empty] | 0 | 0 |  | 0% | 0 | 0 |  |  | 0 | 82823000 | 82823000 | 82823000 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 88257196.21 | 88257196.21 | 88257196.21 | 6.561% | -6.157% | 87569395.13 | 87569395.13 |  |  | -0.7793% | 0%
t | OKT.019 | 2018-12-21 | Fort Towson-Valliant 69 kV Line Rebuild | --- | --- | --- | --- | [16 empty] | 0 | 0 |  | 0% | 0 | 0 |  |  | 0 | 0 | 0 | 14897000 |  |  | 0 | 14897000 | 22387000 | 22387000 | 0% | 0% | 15689737.6 | 15833737.6 | 15833737.6 | -29.92% | 42.69% | 17124157 | 17124157 |  |  | 8.15% | 0% | Refer to related PSO project P.026. Estimates from improvement requisition; do not include Hugo line work (do not include P15204008)
t | OKT.020 | 2018-05-04 | Duncan-Comanche Tap 69 kV Rebuild and Duncan station upgrades | [28 empty] | 8338595.45 | 0 | 8591402.45 | 8591402.45 |  |  | 8789790.23 | 8591402.45 | 8591402.45 | 8591402.45 | 2.309% | -2.257% | 8934664.39 | 8934664.39 | 8934664.39 | 3.995% | -3.842% | 8934664.39 | 8934664.39 |  |  | 0% | 0% | Refer to related PSO project P.027. Line rebuild is in the TransCo line rehab program, b/c the NTC came after the program was approved. A11012089, A11012200, A11012077, A11012447, A13004055 are possible BPIDs for the line. Duncan station work was done under TP-2015-191.
new | OKT.021 | 2020-06-01 | Keystone Dam - Wekiwa 138 kV | [34 empty] | --- | --- | --- | --- | 0% | 0% | --- | 1282000 | 3543000 | 0% | 0% | --- | --- |  |  | 0% | #VALUE! | Includes line work, ROW and TFC, see PSO for Wekiwa station work. Note, for this update, ROW was forecast on PSO instead of OKT. (Manually moved the ROW to OKT.)
NOTES:
< | Not above SPP $100,000 BP threshold.
New | New to BP list
c | AEP project component (components sum up to project total)
t | AEP project total
n/a | informational only; not included in calculations
Matched Last Year
Does Not Match Last Year, Needs Updating
Changed from Last Year, Updated