## PSO
|  | Code | FR Sheet Name (WS F&G) | PID | UID | Projected / Actual In-Service (mmm-yyyy) | Project & TP# | - - - P R E V I O U S L Y P U B L I S H E D - - - | [17 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [10 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [10 empty] | --- WS-F and WS-G SUMMARY Input Data --- | [10 empty] | COMMENTS
[8 empty] | 09 Update | 2010 "Corrected" Update |  |  | 2011 "Corrected" Update |  |  | 2012 Update |  |  | 2013 Update |  |  |  | 2014 Update |  |  |  | 2015 Update |  |  |  | 2016 Update |  |  |  | 2017 Update | [5 empty] | 2018 Update | [5 empty] | 2019 Update |  |  |  |  | 2020 Update | [5 empty] | 2021 Update |  |  |  |  | 2022 Update | [10 empty] | 2023 Update | [10 empty] | 2024 Update
CPP Trunked | CPP | [6 empty] | YE2009 Projected (8/31/09) << WS-F >> | YE2009 Actual (3/29/11)* << WS-G >> | YE2010 Projected (3/29/11) << WS-F >> | YE09 to YE10 (Projected) Variance | YE2010 Actual (12/21/11)* << WS-G >> | YE2011 Projected (12/21/11) << WS-F >> | YE10 to YE11 (Projected) Variance | YE2011 Actual (May'12) << WS-G >> | YE2012 Projected (May '12) << WS-F >> | YE11 to YE12 (Projected) Variance | YE2012 Actual (May'13) << WS-G >> | YE2013 Projected (May '13) << WS-F >> | YE2012 Variance (Projected to Actual) | YE12 (actual) to YE13 (Projected) Variance | YE2013 Actual (May'14) << WS-G >> | YE2014 Projected (May '14) << WS-F >> | YE2013 Variance (Projected to Actual) | YE13 (actual) to YE14 (Projected) Variance | YE2014 Actual (May'15) << WS-G >> | YE2015 Projected (May '15) << WS-F >> | YE2014 Variance (Projected to Actual) | YE14 (actual) to YE15 (Projected) Variance | YE2015 Actual (May'16) << WS-G >> | YE2016 Projected (May '16) << WS-F >> | YE2015 Variance (Projected to Actual) | YE15 (actual) to YE16 (Projected) Variance | YE2016 Actual (May'17) << WS-G >> | YE2017 Projected (May '17) << WS-F >> | YE2017 Projected Adjusted (Oct '17) << WS-F >> | YE2018 Projected (Oct '17) << WS-F >> | YE2016 Variance (Projected to Actual) | YE16 (Actual) to YE17 (Projected) Variance | YE2017 Actual (May '18) << WS-G >> | YE2018 Projected (May '18) << WS-F >> | YE2018 Projected Adjusted (Oct '18) << WS-F >> | YE2019 Projected (Oct '18) << WS-F >> | YE2017 Variance (Projected to Actual) | YE17 (Actual) to YE18 (Projected) Variance | YE2018 Actual (May '19) << WS-G >> | YE2019 Projected (Oct '19) << WS-F >> | YE2020 Projected (Oct '19) << WS-F >> | YE2018 Variance (Projected to Actual) | YE18 (Actual) to YE19 (Projected) Variance | YE2019 Actual (May '20) << WS-G >> | YE2020 Projected (May '20) << WS-F >> | YE2020 Projected (Oct '20) << WS-F >> | YE2021 Projected (Oct '20) << WS-F >> | YE2019 Variance (Projected to Actual) | YE19 (Actual) to YE20 (Projected) Variance | YE2020 Actual (May '21) << WS-G >> | YE2021 Projected (Oct '21) << WS-F >> | YE2022 Projected (Oct '21) << WS-F >> | YE2020 Variance (Projected to Actual) | YE20 (Actual) to YE21 (Projected) Variance | YE2021 Actual (Mar '22) << WS-G >> | YE2022 Projected (Apr '22) 4+8 | YE2023 Projected (Apr '22) 4+8 | YE2022 Projected (Aug '22) 7+5 | YE2023 Projected (Aug '22) 7+5 | YE2022 Projected (Oct '22) << WS-F >> | YE2023 Projected (Oct '22) << WS-F >> | YE2022 Projected (Dec '22) EOY | YE2023 Projected (Dec '22) EOY | YE2021 Variance (Projected to Actual) | YE21 (Actual) to YE22 (Projected) Variance | YE2022 Actual (Mar '23) << WS-G >> | YE2023 Projected (Apr '23) 4+8 | YE2024 Projected (Apr '23) 4+8 | YE2023 Projected (Aug '23) 7+5 | YE2024 Projected (Aug '23) 7+5 | YE2023 Projected (Oct '23) << WS-F >> | YE2024 Projected (Oct '23) << WS-F >> | YE2023 Projected (Dec '23) EOY | YE2024 Projected (Dec '23) EOY | YE2022 Variance (Projected to Actual) | YE22 (Actual) to YE23 (Projected) Variance | YE2023 Actual (Mar '24) << WS-G >> | YE2024 Projected (Apr '24) 4+8 | YE2025 Projected (Apr '24) 4+8 | YE2024 Projected (Aug '24) 7+5 | YE2025 Projected (Aug '24) 7+5 | YE2024 Projected (Oct '24) << WS-F >> | YE2025 Projected (Oct '24) << WS-F >> | YE2024 Projected (Dec '24) EOY | YE2025 Projected (Dec '24) EOY | YE2023 Variance (Projected to Actual) | YE23 (Actual) to YE24 (Projected) Variance
TP2006087 | TP2006087 | t | P.001 | Total | Total | 2009-06-01 | Riverside-Glenpool (TP2006087) | 579098 | 893857.87 | 893857.87 | 54.35% | 893857.87 | 893857.87 | 0% | 893857.87 | 893857.87 | 0% | 893857.87 | 893857.87 | 0% | 0% | 893857.87 | 893857.87 | 0% | 0% | 893858 | 893858 | 1.454e-05% | 0% | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 0% | 0% | 893858 |  |  | 893858 | 893858 | 893858 | 893858 |  |  | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 893858 | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 | [8 empty] | 0% | -100%
|  | c | P.001 | 220 | 10279 |  | Reconductor 1.82 miles with ACCC. Replace wave trap jumpers at Riverside. | [18 empty] | 893858 | 893858 |  |  | 893858 | 893858 |  |  | 893858 | 893858 | 893858 | 893858 |  |  | 893858 | 893858 | 893858 | 893858 |  |  | 893858 | 893858 | 893858 |  |  | 893858 | 893858 | 893858 | 893858 |  |  | 893858 | 893858 | 893858 |  |  | 893858 |  |  | 893858 | 893858 | 893858 | 893858 |  |  |  |  | 893858 | 893858 | 893858 | 893858 | 893858 | 893858 | 893858 | 893858 | 893858 |  |  | 893858
TP2007059 | TP2007059 | t | P.002 | Total | Total | 2009-05-01 | Craig Jct-Broken Bow (TP2007059) | 6704177 | 4725391.05 | 4725391.05 | -29.52% | 4688896 | 4688896 | 0.7783% | 4688896 | 4688896 | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 |  |  | 4688896 | 4688896 | 4688896 | 4688896 |  |  | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | [8 empty] | 0% | -100%
|  | c | P.002 | 230 | 10295 |  | Reconductor Broken Bow to Craig Junction 138 kV; Rebuild 7.66 miles of 3/0 CW CU with 795 ACSR | [18 empty] | 4688896 | 4688896 |  |  | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 | 4688896 |  |  | 4688896 | 4688896 | 4688896 |  |  | 4688896 |  |  | 4688896 | 4688896 | 4688896 | 4688896 |  |  |  |  | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 | 4688896 |  |  | 4688896
TP2006054 | TP2006054 | t | P.003 | Total | Total | 2009-10-01 | WFEC new ties (TP2006054) | 9403820 | 8830340 | 12266531 | 30.44% | 12232148 | 12232148 | 0.2811% | 12232148 | 12232148 | 0% | 12232148 | 12232148 | 0% | 0% | 12232148 | 12232148 | 0% | 0% | 11456065 | 11456065 | -6.345% | 0% | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 |  |  | 11456065 | 11456065 | 11456065 | 11456065 |  |  | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 11456065 | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | [8 empty] | 0% | -100%
|  | c | P.003 | 112 | 10139 |  | Build new 138 kV line AEP Sayre to WFEC Erick. | [18 empty] | 6998664 | 6998664 |  |  | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 | 6998664 |  |  | 6998664 | 6998664 | 6998664 |  |  | 6998664 |  |  | 6998664 | 6998664 | 6998664 | 6998664 |  |  |  |  | 6998664 | 6998664 | 6998664 | 6998664 | 6998664 | 6998664 | 6998664 | 6998664 | 6998664 |  |  | 6998664
|  | c | P.003 | 177 | 10728 |  | Install 138 kV three breaker ring bus forming two new 138 kV terminals at the Atoka substation. | [18 empty] | 3041696 | 3041696 |  |  | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 | 3041696 |  |  | 3041696 | 3041696 | 3041696 |  |  | 3041696 |  |  | 3041696 | 3041696 | 3041696 | 3041696 |  |  |  |  | 3041696 | 3041696 | 3041696 | 3041696 | 3041696 | 3041696 | 3041696 | 3041696 | 3041696 |  |  | 3041696
|  | c | P.003 | 177 | 10729 |  | Upgrade line relays, install SCADA and install Ethernet communication at Tupelo Substation. | [18 empty] | 1415705 | 1415705 |  |  | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 | 1415705 |  |  | 1415705 | 1415705 | 1415705 |  |  | 1415705 |  |  | 1415705 | 1415705 | 1415705 | 1415705 |  |  |  |  | 1415705 | 1415705 | 1415705 | 1415705 | 1415705 | 1415705 | 1415705 | 1415705 | 1415705 |  |  | 1415705
TP2004147 | TP2004147 | t | P.004 | Total | Total | 2008-07-01 | Cache-Snyder (TP2004147) | 14544152 | 14683511.33 | 14686911.33 | 0.02248% | 14615636 | 14615636 | 0.4877% | 14615636 | 14615636 | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 |  |  | 14615636 | 14615636 | 14615636 | 14615636 |  |  | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | [8 empty] | 0% | -100% | Includes new line and new terminals at both ends.
|  | c | P.004 | 106 | 10130 |  | Build new Snyder to Altus Jct 138 kV line | [18 empty] | 14615636 | 14615636 |  |  | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 | 14615636 |  |  | 14615636 | 14615636 | 14615636 |  |  | 14615636 |  |  | 14615636 | 14615636 | 14615636 | 14615636 |  |  |  |  | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 | 14615636 |  |  | 14615636
|  | c | P.004 | 119 | 10149 |  | Included in 10130 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2005006 | TP2005006 | t | P.005 | Total | Total | 2006-05-01 | Catoosa 138 kV Device | 387742 | 387742 | 387742 | 0.02248% | 387742 | 387742 | 0% | 387742 | 387742 | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 0% | 0% | 387742 |  |  | 387742 | 387742 | 387742 | 387742 |  |  | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 387742 | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 | [8 empty] | 0% | -100%
|  | c | P.005 | 30001 | 50001 |  | Install switched capacitor bank. | [18 empty] | 387742 | 387742 |  |  | 387742 | 387742 |  |  | 387742 | 387742 | 387742 | 387742 |  |  | 387742 | 387742 | 387742 | 387742 |  |  | 387742 | 387742 | 387742 |  |  | 387742 | 387742 | 387742 | 387742 |  |  | 387742 | 387742 | 387742 |  |  | 387742 |  |  | 387742 | 387742 | 387742 | 387742 |  |  |  |  | 387742 | 387742 | 387742 | 387742 | 387742 | 387742 | 387742 | 387742 | 387742 |  |  | 387742
TP2006090 | TP2006090 | t | P.006 | Total | Total | 2008-04-01 | Pryor Jct 138/60 Upgrade autoxfmr (TP2006090) | 1520473 | 1520502 | 1520502 | 0.02248% | 1520502 | 1520502 | 0% | 1520502 | 1520502 | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 |  |  | 1520502 | 1520502 | 1520502 | 1520502 |  |  | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | [8 empty] | 0% | -100%
|  | c | P.006 | 110 | 10137 |  | Upgrade Pryor Junction 138/69 kV transformer; Ratings A=133 and B=146 | [18 empty] | 1520502 | 1520502 |  |  | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 | 1520502 |  |  | 1520502 | 1520502 | 1520502 |  |  | 1520502 |  |  | 1520502 | 1520502 | 1520502 | 1520502 |  |  |  |  | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 | 1520502 |  |  | 1520502
|  | c | P.006 | 657 | 10862 |  | Included in 10137 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2007015 | TP2007015 | < | P.007 | Total | Total | 2007-12-01 | Elk City-Elk City 69 CT upgrades (TP2007015) | 84424 | 84424 | 84424 | 0.02248% | 84424 | 84424 | 0% | 84424 | 84424 | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 0% | 0% | 84424 |  |  | 84424 | 84424 | 84424 | 84424 |  |  | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 84424 | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 | [8 empty] | 0% | -100% | Not over $100K threshold for regional allocation.
|  | c | P.007 | 118 | 10148 |  | Replace CTS & jumpers. Limits on AEP end will be 600A switches and Breaker | [18 empty] | 84424 | 84424 |  |  | 84424 | 84424 |  |  | 84424 | 84424 | 84424 | 84424 |  |  | 84424 | 84424 | 84424 | 84424 |  |  | 84424 | 84424 | 84424 |  |  | 84424 | 84424 | 84424 | 84424 |  |  | 84424 | 84424 | 84424 |  |  | 84424 |  |  | 84424 | 84424 | 84424 | 84424 |  |  |  |  | 84424 | 84424 | 84424 | 84424 | 84424 | 84424 | 84424 | 84424 | 84424 |  |  | 84424
TP2005046 | TP2005046 | < | P.008 | Total | Total | 2006-03-01 | Weleetka & Okmulgee wavetrap r&r 81-805 (TP2005046) | 56133 | 56133 | 56133 | 0.02248% | 56133 | 56133 | 0% | 56133 | 56133 | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 0% | 0% | 56133 |  |  | 56133 | 56133 | 56133 | 56133 |  |  | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 56133 | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 | [8 empty] | 0% | -100% | Not over $100K threshold for regional allocation.
|  | c | P.008 | 3 | 10003 |  | Replace Weleetka wave trap | [18 empty] | 56133 | 56133 |  |  | 56133 | 56133 |  |  | 56133 | 56133 | 56133 | 56133 |  |  | 56133 | 56133 | 56133 | 56133 |  |  | 56133 | 56133 | 56133 |  |  | 56133 | 56133 | 56133 | 56133 |  |  | 56133 | 56133 | 56133 |  |  | 56133 |  |  | 56133 | 56133 | 56133 | 56133 |  |  |  |  | 56133 | 56133 | 56133 | 56133 | 56133 | 56133 | 56133 | 56133 | 56133 |  |  | 56133
|  | c | P.008 | 4 | 10004 |  | Replace Okmulgee wave trap | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Distribution; ignore
TP2004033 | TP2004033 | < | P.009 | Total | Total | 2007-04-01 | Tulsa SE r&r switches (TP2004033) | 72551 | 72551 | 72551 | 0.02248% | 72551 | 72551 | 0% | 72551 | 72551 | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 0% | 0% | 72551 |  |  | 72551 | 72551 | 72551 | 72551 |  |  | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 72551 | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 | [8 empty] | 0% | -100% | Not over $100K threshold for regional allocation.
|  | c | P.009 | 46 | 10050 |  | Replace 3 switches | [18 empty] | 72551 | 72551 |  |  | 72551 | 72551 |  |  | 72551 | 72551 | 72551 | 72551 |  |  | 72551 | 72551 | 72551 | 72551 |  |  | 72551 | 72551 | 72551 |  |  | 72551 | 72551 | 72551 | 72551 |  |  | 72551 | 72551 | 72551 |  |  | 72551 |  |  | 72551 | 72551 | 72551 | 72551 |  |  |  |  | 72551 | 72551 | 72551 | 72551 | 72551 | 72551 | 72551 | 72551 | 72551 |  |  | 72551
TP2009011 | TP2009011 | < | P.010 | Total | Total | 2010-06-01 | Clinton City-Foss 69 wavetrap r&r (TP2009011) | n/a | n/a | 135400 | n/a | 96566 | 96566 | 40.21% | 96566 | 96566 | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 0% | 0% | 96566 |  |  | 96566 | 96566 | 96566 | 96566 |  |  | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 96566 | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 | [8 empty] | 0% | -100% | Not over $100K threshold for regional allocation.
|  | c | P.010 | 289 | 10375 |  | Replace wave trap at Clinton City Substation. | [18 empty] | 96566 | 96566 |  |  | 96566 | 96566 |  |  | 96566 | 96566 | 96566 | 96566 |  |  | 96566 | 96566 | 96566 | 96566 |  |  | 96566 | 96566 | 96566 |  |  | 96566 | 96566 | 96566 | 96566 |  |  | 96566 | 96566 | 96566 |  |  | 96566 |  |  | 96566 | 96566 | 96566 | 96566 |  |  |  |  | 96566 | 96566 | 96566 | 96566 | 96566 | 96566 | 96566 | 96566 | 96566 |  |  | 96566
TP2008079 | TP2008079 | t | P.011 | Total | Total | 2011-06-01 | Bartlesville SE to Coffeyville T Rebuild (TP2008079-PSO) | --- | --- | --- | --- | --- | 1624000 | --- | 1436737 | 1436737 | 13.03% | 1493723 | 1493723 | 3.966% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 |  |  | 1493723 | 1493723 | 1493723 | 1493723 |  |  | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | [8 empty] | 0% | -100% | Also see related OKTransco project (OKT.004).
|  | c | P.011 | 446 | 10578 |  | Rebuild approximately 13 miles of line with 1590 ACSR to achieve a minimum 2000 Amp emergency rating | [18 empty] | 1493723 | 1493723 |  |  | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 | 1493723 |  |  | 1493723 | 1493723 | 1493723 |  |  | 1493723 |  |  | 1493723 | 1493723 | 1493723 | 1493723 |  |  |  |  | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 | 1493723 |  |  | 1493723
|  | c | P.011 | 454 | 10588 |  | Included in 10578 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | P.011 | 902 | 11199 |  | Included in 10578 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | P.011 | 911 | 11208 |  | Included in 10578 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2009095 | TP2009095 | t | P.012 | Total | Total | 2013-08-01 | Canadian River - McAlester City 138 kV Line Conversion (TP2009095) | --- | --- | --- | --- | --- | --- | --- | --- | 1132400 | --- | 504034 | 2750034 | -55.49% | 445.6% | 3242134 | 3242134 | 17.89% | 0% | 3305767.14 | 3305767.14 | 1.963% | 0% | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 |  |  | 3305767 | 3305767 | 3305767 | 3305767 |  |  | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | [8 empty] | 0% | -100% | Also see related OKTransco project (OKT.006). Multi-element multi-year base plan project. Final in-service yr in 12' and 13'.
|  | c | P.012 | 767 | 11011 |  | Convert 17 mile Canadian River - McAlester City line from 69 kV to 138 kV. | [18 empty] | 3305767.14 | 3305767.14 |  |  | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 | 3305767 |  |  | 3305767 | 3305767 | 3305767 |  |  | 3305767 |  |  | 3305767 | 3305767 | 3305767 | 3305767 |  |  |  |  | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 | 3305767 |  |  | 3305767
|  | c | P.012 | 767 | 11012 |  | Included in 11011 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | P.012 | 767 | 11183 |  | Included in 11011 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | P.012 | 767 | 11184 |  | Included in 11011 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2008013 | TP2008013 | < | P.013 | Total | Total | 2010-06-01 | CoffeyvilleT to Dearing 138 kv Rebuild - 1.1 mi (TP2008013) | --- | --- | --- | --- | --- | --- | --- | 22097 | 22097 | --- | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 0% | 0% | 22097 |  |  | 22097 | 22097 | 22097 | 22097 |  |  | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 22097 | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 | [8 empty] | 0% | -100% | Also see related OKTransco project (OKT.002). Total project expenditure is over $100k.
|  | c | P.013 | 295 | 10381 |  | AEPW to reconductor 1.09 miles of 795 ACSR with 1590 ACSR. (Also, Westar to rebuild 3.93 miles of 795 ACSR with 1590 ACSR.) These ratings are just for the AEP facilities. | [18 empty] | 22097 | 22097 |  |  | 22097 | 22097 |  |  | 22097 | 22097 | 22097 | 22097 |  |  | 22097 | 22097 | 22097 | 22097 |  |  | 22097 | 22097 | 22097 |  |  | 22097 | 22097 | 22097 | 22097 |  |  | 22097 | 22097 | 22097 |  |  | 22097 |  |  | 22097 | 22097 | 22097 | 22097 |  |  |  |  | 22097 | 22097 | 22097 | 22097 | 22097 | 22097 | 22097 | 22097 | 22097 |  |  | 22097
TP2009092 | TP2009092 | t | P.014 | Total | Total | 2013-02-01 | Ashdown West - Craig Junction 138KV Rebuild (TP2009092) | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | n/a | 5562500 | --- | --- | 1035333 | 1035333 | -81.39% | 0% | 1035552 | 1035552 | 0.02115% | 0% | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 |  |  | 1035552 | 1035552 | 1035552 | 1035552 |  |  | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | [8 empty] | 0% | -100% | Asset transfer to SWEPCO completed. Only a portion of the project was transferred.
|  | c | P.014 | 770 | 11015 |  | Rebuild 2.45 miles of 795 ACSR with 1590 ACSR and reset relays. | [18 empty] | 1035552 | 1035552 |  |  | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 | 1035552 |  |  | 1035552 | 1035552 | 1035552 |  |  | 1035552 |  |  | 1035552 | 1035552 | 1035552 | 1035552 |  |  |  |  | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 | 1035552 |  |  | 1035552
TP2009093 | TP2009093 | t | P.015 | Total | Total | 2014-02-01 | Locust Grove to Lone Star 115 kV Rebuild 2.1 miles (TP2009093) | [14 empty] | n/a | 2295000 |  |  | 2246628.57 | 2246628.57 | -2.108% | 0% | 2246629 | 2246629 | 1.914e-05% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 |  |  | 2246629 | 2246629 | 2246629 | 2246629 |  |  | 0% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | [8 empty] | 0% | -100%
|  | c | P.015 | 649 | 10853 |  | Reconductor 2.15 mile section of 115 kV line with 795 ACSR. | [18 empty] | 2246628.57 | 2246628.57 |  |  | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 | 2246629 |  |  | 2246629 | 2246629 | 2246629 |  |  | 2246629 |  |  | 2246629 | 2246629 | 2246629 | 2246629 |  |  |  |  | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 | 2246629 |  |  | 2246629
|  | t | P.016 | Total | Total | 2014-12-01 | Cornville Station Conversion (TP2011093) | [14 empty] | n/a | 5300000 |  |  | 4980780.16 | 5300000 | -6.023% | 6.409% | 5059196 | 5059196 | -4.543% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0.001622% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 0% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 | [8 empty] | 0% | -100% | Also see related OKTransco project (OKT.007).
TP2011093 | TP2011093 | c | P.016 | 30346 | 50438 |  | Upgrade the Cornville 138 kV bus to breaker-and-a-half configuration in preparation for the 138 kV line conversion to Lindsay Water substation. | [18 empty] | 4980780.16 | 5300000 |  |  | 5059196 | 5059196 |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04 |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  |  |  | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 |  |  | 5059278.04
|  | n/a | - | Total | Total | 2014-12-01 | OKMULGEE - RIVERSIDE STATION 138KV CKT 1 | [14 empty] | n/a | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; no Capital investment
|  | n/a | - | 387 | 10505 |  | Replace wave trap at Okmulgee. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | n/a | - | Total | Total | 2016-06-01 | Broken Arrow North-South Tap-Oneta 138 kV Ckt 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | 100% Direct Assign project, not to be included in the Rate Base
|  | n/a | - | 947 | 11261 |  | Reconductor 4.33 miles of 795 ACSR with 1026 ACCC | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | This project was not REBUILT it is an actual recondutor of the existing structures.
|  | t | P.017 | Total | Total | 2015-12-01 | Grady Customer Connection | [18 empty] | 0 | 1500000 |  |  | 1625288 | 1777912 | 8.353% | 9.391% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | -4.831% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 0% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 | [8 empty] | 0% | -100% | Also see related OKTransco project (OKT.013).
TP2013002 | TP2013002Y | c | P.017 | 30748 | 51015 |  | Transmission line cut-ins | [18 empty] | 0 | 1500000 |  |  | 1625288 | 1777912 |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  |  |  | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 |  |  | 1692023.17 | [10 empty] | Trailing charges due to being in-service in Dec 2015
|  | t | P.018 | Total | Total | 2014-04-01 | Darlington-Red Rock 138 kV line | [18 empty] | 1725646.85 | 1725646.85 |  |  | 1725647 | 1725647 | 8.692e-06% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 |  |  | 1725647 | 1725647 | 1725647 | 1725647 |  |  | 0% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | [8 empty] | 0% | -100% | Also see related OKTransco project (OKT.014).
TP2012112 | TP2012112 | c | P.018 | 30746 | 51013 |  | Construct new 8-mile 138 kV line from Red Rock to Darlington. | [18 empty] | 1725646.85 | 1725646.85 |  |  | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 | 1725647 |  |  | 1725647 | 1725647 | 1725647 |  |  | 1725647 |  |  | 1725647 | 1725647 | 1725647 | 1725647 |  |  |  |  | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 | 1725647 |  |  | 1725647 | [10 empty] | Cost includes all terminal work also.
|  | t | P.019 | Total | Total | 2017-03-01 | Valliant-NW Texarkana 345 kV | [14 empty] | n/a | 0 |  |  | 0 | 1500000 |  |  | 1338801 | 1338801 | -10.75% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0.01321% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 0% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 | [8 empty] | 0% | -100% | 345 kV line relocation to be completed November 2015; Also see related SWEPCo project (S.058) and OKTCo project (OKT.009).Need to Update the ISD to 2017
TP2009089 | TP2009089 | c | P.019 | 936 | 11236 |  | 345 kV from Valliant substation to NW Texarkana substation | [18 empty] | 0 | 1500000 |  |  | 1338801 | 1338801 |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91 |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  |  |  | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 |  |  | 1338977.91
|  | t | P.020 | Total | Total | 2018-12-19 | Sayre 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 483000 | 0 | 1140000 |  |  | 0 | 1140000 | 1140000 | 1140000 | 0% | 0% | 1919728.93 | 1919728.93 | 1919728.93 | 68.4% | -40.62% | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 2.161% | 0% | 1961220.71 | 1961220.71 | 1961220.71 | 0% | 0% | 1961220.71 |  |  | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 |  |  | 0% | 0% | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 0% | 0% | 1961220.71 | [8 empty] | 0% | -100% | ISD moved out to 2018.
TP2015202 | TP2015202 | c | P.020 | 30997 | 51433 |  | Sayre 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 483000 | 0 | 483000 |  |  | 0 | 483000 | 1140000 | 1140000 |  |  | 1919728.93 | 1919728.93 | 1919728.93 |  |  | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 |  |  | 1961220.71 | 1961220.71 | 1961220.71 |  |  | 1961220.71 |  |  | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 |  |  |  |  | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 | 1961220.71 |  |  | 1961220.71
|  | t | P.021 | Total | Total | 2017-06-29 | Darlington-Roman Nose 138 kV | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 262000 | 262000 | 262000 |  |  | 330824.19 | 262000 | 262000 | 262000 | 26.27% | -20.8% | 330872.36 | 330872.36 | 330872.36 | 26.29% | -20.82% | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 0% | 0% | 330872.36 | 330872.36 | 330872.36 | 0% | 0% | 330872.36 |  |  | 330872.36 | 330872.36 | 330872.36 | 330872.36 |  |  | 0% | 0% | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 0% | 0% | 330872.36 | [8 empty] | 0% | -100% | Also see related OKTransco project (OKT.016).
TP2015027 | TP2015027 | c | P.021 | 30619 | 50802 |  | Darlington-Install metering and relaying | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 262000 | 262000 | 262000 |  |  | 330824.19 | 262000 | 262000 | 262000 |  |  | 330872.36 | 330872.36 | 330872.36 |  |  | 330872.36 | 330872.36 | 330872.36 | 330872.36 |  |  | 330872.36 | 330872.36 | 330872.36 |  |  | 330872.36 |  |  | 330872.36 | 330872.36 | 330872.36 | 330872.36 |  |  |  |  | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 | 330872.36 |  |  | 330872.36
|  | t | P.022 | Total | Total | 2018-06-01 | Northeastern Station 138 kV Terminal Upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 | 244000 | 0% | 0% | 244000 | 244000 | 244000 | 0% | 0% | 244000 | 244000 | 244000 | 244000 | 0% | 0% | 244000 | 244000 | 244000 | 0% | 0% | 244000 |  |  | 244000 | 244000 | 244000 | 244000 |  |  | 0% | 0% | 244000 | 244000 | 244000 | 244000 | 244000 | 244000 | 244000 | 244000 | 244000 | 0% | 0% | 244000 | [8 empty] | 0% | -100% | This project was slated for 06/2017, however, the metering CT failed, and was replaced by TFS in 05/2016. BPID P15169001
TP2015169 | TP2015169 | c | P.022 | 31003 | 51446 |  | Northeastern Station 138 kV Terminal Upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 |  |  | 244000 |  |  | 244000 | 244000 | 244000 | 244000 |  |  |  |  | 244000 | 244000 | 244000 | 244000 | 244000 | 244000 | 244000 | 244000 | 244000 |  |  | 244000
|  | t | P.023 | Total | Total | 2018-05-25 | Elk City 138 kV Move Load | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1778000 |  |  | 0 | 1778000 | 2037000 | 2037000 | 0% | 0% | 1200324.32 | 1200324.32 | 1200324.32 | -41.07% | 69.7% | 1176180.46 | 1176180.46 | 1176180.46 | 1176180.46 | -2.011% | 0% | 1165593.01 | 1165593.01 | 1165593.01 | -0.9002% | 0% | 1165593.01 |  |  | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 |  |  | 0% | 0% | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 0% | 0% | 1165593.01 | [8 empty] | 0% | -100% | Only included FERC T work, not Distribution; used cost estimate from the Capital Program Approval Improvement Requisition.
TP2011110 | TP2011110 | c | P.023 | 31005 | 51448 |  | Elk City 138 kV Move Load | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1778000 |  |  | 0 | 1778000 | 2037000 | 2037000 |  |  | 1200324.32 | 1200324.32 | 1200324.32 |  |  | 1176180.46 | 1176180.46 | 1176180.46 | 1176180.46 |  |  | 1165593.01 | 1165593.01 | 1165593.01 |  |  | 1165593.01 |  |  | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 |  |  |  |  | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 | 1165593.01 |  |  | 1165593.01
|  | t | P.024 | Total | Total | 2018-05-04 | Duncan-Comanche Tap 69 kV Rebuild and Duncan station upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1216000 |  |  | 0 | 1216000 | 1216000 | 1216000 | 0% | 0% | 1344938.51 | 1344938.51 | 1344938.51 | 10.6% | -9.587% | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 0.03302% | 0% | 1345382.62 | 1345382.62 | 1345382.62 | 0% | 0% | 1345382.62 |  |  | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 |  |  | 0% | 0% | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 0% | 0% | 1345382.62 | [8 empty] | 0% | -100% | Refer to related OKTCo project, OKT.018. Only upgrades at Duncan Station are included here.
TP2015191 | TP2015191 | c | P.024 | 31009 | 51454 |  | Duncan-Tosco Rebuild and Duncan station upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1216000 |  |  | 0 | 1216000 | 1216000 | 1216000 |  |  | 1344938.51 | 1344938.51 | 1344938.51 |  |  | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 |  |  | 1345382.62 | 1345382.62 | 1345382.62 |  |  | 1345382.62 |  |  | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 |  |  |  |  | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 | 1345382.62 |  |  | 1345382.62 | [10 empty] | Duncan station upgrades, line rebuild is in the TransCo line rehab program, b/c the NTC came after the program was approved.
TP2015191 | TP2015191 | c | P.024 | 31039 | 51524 |  | Comanche Tap-Tosco 69 kV Rebuild (included above) | [22 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Line rebuild is in the TransCo line rehab program, b/c the NTC came after the program was approved. Included in UID 51454.
|  | t | P.025 | Total | Total | 2018-12-21 | Fort Towson-Valliant Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1044000 |  |  | 27999.49 | 1044000 | 557000 | 557000 | 0% | 3629% | 302079.67 | 302079.67 | 302079.67 | -45.77% | 84.39% | 288859.6 | 288859.6 | 288859.6 | 288859.6 | -4.376% | 0% | 288859.6 | 288859.6 | 288859.6 | 0% | 0% | 288859.6 |  |  | 288859.6 | 288859.6 | 288859.6 | 288859.6 |  |  | 0% | 0% | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 0% | 0% | 288859.6 | [8 empty] | 0% | -100% | ROW only; refer to related OKTCo project, OKT.019, P15204002/005.
TP2015204 | TP2015204 | c | P.025 | 31058 | 51562 |  | Fort Towson-Valliant Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1044000 |  |  | 27999.49 | 1044000 | 557000 | 557000 |  |  | 302079.67 | 302079.67 | 302079.67 |  |  | 288859.6 | 288859.6 | 288859.6 | 288859.6 |  |  | 288859.6 | 288859.6 | 288859.6 |  |  | 288859.6 |  |  | 288859.6 | 288859.6 | 288859.6 | 288859.6 |  |  |  |  | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 | 288859.6 |  |  | 288859.6
TP2015204 | TP2015204 | c | P.025 | 31058 | 51561 |  | included above | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | t | P.026 | Total | Total | 2019-12-01 | Tulsa Southeast-E.61st 138 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 1039000 | 5024000 |  |  | --- | 7022000 | 7156000 | 0% | 0% | 6388895.58 | 7661895.58 | 9409645 | 9409645 | -9.016% | 19.93% | 8144613.64 | 8147700.64 | 8147700.64 | -13.44% | 0.0379% | 8147276.87 |  |  | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 |  |  | -0.005201% | 0% | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 0% | 0% | 8147276.87 | [8 empty] | 0% | -100% | Includes line, ROW, and station work.
TP2017011 | TP2017011 | c | P.026 | 41202 | 61858 |  | Tulsa Southeast-E.61st 138 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 1039000 | 5024000 |  |  | --- | 7022000 | 7156000 |  |  | 6388895.58 | 7661895.58 | 9409645 | 9409645 |  |  | 8144613.64 | 8147700.64 | 8147700.64 |  |  | 8147276.87 |  |  | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 |  |  |  |  | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 | 8147276.87 |  |  | 8147276.87
|  | t | P.027 | Total | Total | 2019-03-19 | Broken Arrow North-Lynn Lane East 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 2318000 | 4120000 |  |  | --- | 4236000 | 4236000 | 0% | 0% | 5058521.96 | 5058521.96 | 5058521.96 | 5058521.96 | 19.42% | 0% | 5058588.62 | 5058588.62 | 5058588.62 | 0.001318% | 0% | 5058588.62 |  |  | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 |  |  | 0% | 0% | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 0% | 0% | 5058588.62 | [8 empty] | 0% | -100% | Includes reconductor and ROW.
TP2017016 | TP2017016 | c | P.027 | 41233 | 71945 |  | Broken Arrow North-Lynn Lane East 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 2318000 | 4120000 |  |  | --- | 4236000 | 4236000 |  |  | 5058521.96 | 5058521.96 | 5058521.96 | 5058521.96 |  |  | 5058588.62 | 5058588.62 | 5058588.62 |  |  | 5058588.62 |  |  | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 |  |  |  |  | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 | 5058588.62 |  |  | 5058588.62
|  | t | P.028 | Total | Total | 2020-06-01 | Keystone Dam - Wekiwa 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 971000 | 1677000 | 0% | 0% | --- | 2842000 | 2345950 | 2345950 | 0% | #VALUE! | 2529407.75 | 2537088.75 | 2537088.75 | 7.82% | 0.3037% | 2536388.52 |  |  | 2536388.52 | 2536388.52 | 2536388.52 | 2536388.52 |  |  | -0.0276% | 0% | 2394794 | 2394794 | 2394794 | 2394794 | 2394794 | 2394794 | 2394794 | 2394352.82 | 2394352.82 | -5.583% | -0.01842% | 2394352.82 | [8 empty] | 0% | -100% | Includes Wekiwa station work, see Transco for line work, ROW (P15118002) and TFC. Note, duing this update, ROW was forecast on PSO, instead of OKT. (Manually moved the ROW to OKT.)
TP2015118 | TP2015118 | c | P.028 | 30809 | 51096 |  | Keystone Dam - Wekiwa 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 971000 | 1677000 |  |  | --- | 2842000 | 2345950 | 2345950 |  |  | 2529407.75 | 2537088.75 | 2537088.75 |  |  | 2536388.52 |  |  | 2536388.52 | 2536388.52 | 2536388.52 | 2536388.52 |  |  |  |  | 2394794 | 2394794 | 2394794 | 2394794 | 2394794 | 2394794 | 2394794 | 2394352.82 | 2394352.82 |  |  | 2394352.82
|  | < | P.029 | Total | Total | 2022-06-02 | Tulsa SE - S Hudson 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | --- | --- | 0% | 0% | --- | --- | --- | --- | 0% | #VALUE! |  | 0 | 0 | 0% | N/A | 0 |  |  | 0 | 0 | 0 | 0 |  |  | N/A | N/A | 31450.1 | 31450.1 | 31450.1 | 31450.1 | 31450.1 | 37862.59 | 37862.59 | 31450.1 | 31450.1 | N/A | 0% | 37862.59 | [8 empty] | 20.39% | -100% | Includes P20033003. See Transco for other work.
TP2020033 | TP2020033 | c | P.029 | 81520 | 112389 |  | Tulsa SE - S Hudson 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | --- | --- |  |  | --- | --- | --- | --- |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 31450.1 | 31450.1 | 31450.1 | 31450.1 | 31450.1 | 37862.59 | 37862.59 | 31450.1 | 31450.1 |  |  | 37862.59
|  | t | P.030 | Total | Total | 2021-11-17 | Tulsa SE - E 21st St Tap 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | --- | --- | 0% | 0% | --- | --- | --- | --- | 0% | #VALUE! |  | 0 | 1616718 | 0% | N/A | 1203703.96 |  |  | 1865489.96 | 1865489.96 | 1865411 | 1865411 |  |  | N/A | 54.97% | 1504560.18 | 1504560.18 | 1504560.18 | 1504560.18 | 1504560.18 | 1822549 | 1822797 | 1822797.39 | 1822797.39 | -19.34% | 21.15% | 1822797 | [8 empty] | -2.14e-05% | -100% | Includes P20033004, P20033005 and P20033007 (actuals didn’t come through till 2023).
TP2020033 | TP2020033X | c | P.030 | 81523 | 112393 |  | Tulsa SE - E 21st St Tap 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | --- | --- |  |  | --- | --- | --- | --- |  |  |  | 0 | 1616718 |  |  | 1203703.96 |  |  | 1865489.96 | 1865489.96 | 1865411 | 1865411 |  |  |  |  | 1504560.18 | 1504560.18 | 1504560.18 | 1504560.18 | 1504560.18 | 1822549 | 1822797 | 1822797.39 | 1822797.39 |  |  | 1822797
|  | < | P.031 | Total | Total | 2022-06-01 | Pryor Junction 138/115 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | --- | --- | 0% | 0% | --- | --- | --- | --- | 0% | #VALUE! |  | 0 | 56102.1142 | 0% | N/A | 0 |  |  | 70968.2442 | 70968.2442 | 70968.2442 | 70968.2442 |  |  | N/A | N/A | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | -0.0007668% | 0% | 70967.7 | [8 empty] | 0% | -100% | Includes P19132001 and P19132006. See Transco for other work.
TP2019132 | TP2019132 | c | P.031 | 81571 | 112488 |  | Pryor Junction 138/115 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | --- | --- |  |  | --- | --- | --- | --- |  |  |  | 0 | 56102.1142 |  |  | 0 |  |  | 70968.2442 | 70968.2442 | 70968.2442 | 70968.2442 |  |  |  |  | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 | 70967.7 |  |  | 70967.7
NOTES:
|  | < | Not above SPP $100,000 BP threshold.
|  | New | New to BP list
|  | c | AEP project component (components sum up to project total)
|  | t | AEP project total
|  | n/a | informational only; not included in calculations
Matched Last Year
Does Not Match Last Year, Needs Updating
Changed from Last Year, Updated
Changes from Previous Update

## SWEPCO
|  | Code | FR Sheet Name (WS F&G) | PID | UID | Projected / Actual In-Service (mmm-yyyy) | Project & TP# | --- PREVIOUSLY PUBLISHED --- | [17 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [10 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [10 empty] | --- WS-F and WS-G SUMMARY Input Data --- | [10 empty] | COMMENTS
[8 empty] | 09 Update | 2010 "Corrected" Update |  |  | 2011 "Corrected" Update |  |  | 2012 Update |  |  | 2013 Update |  |  |  | 2014 Update |  |  |  | 2015 Update |  |  |  | 2016 Update |  |  |  | 2017 Update | [5 empty] | 2018 Update | [5 empty] | 2019 Update |  |  |  |  | 2020 Update | [5 empty] | 2021 Update |  |  |  |  | 2022 Update | [10 empty] | 2023 Update | [10 empty] | 2024 Update
CPP Trunked | CPP | [6 empty] | YE2009 Projected (8/31/09) << WS-F >> | YE2009 Actual (3/29/11)* << WS-G >> | YE2010 Projected (3/29/11) << WS-F >> | YE09 to YE10 Variance | YE2010 Actual (12/21/11)* << WS-G >> | YE2011 Projected (12/21/11) << WS-F >> | YE10 to YE11 (Projected) Variance | YE2011 Actual (May'12) << WS-G >> | YE2012 Projected (May '12) << WS-F >> | YE11 to YE12 (Projected) Variance | YE2012 Actual (May'13) << WS-G >> | YE2013 Projected (May '13) << WS-F >> | YE2012 Variance (Projected to Actual) | YE12 (actual) to YE13 (Projected) Variance | YE2013 Actual (May'14) << WS-G >> | YE2014 Projected (May '14) << WS-F >> | YE2013 Variance (Projected to Actual) | YE13 (actual) to YE14 (Projected) Variance | YE2014 Actual (May'15) << WS-G >> | YE2015 Projected (May '15) << WS-F >> | YE2014 Variance (Projected to Actual) | YE14 (actual) to YE15 (Projected) Variance | YE2015 Actual (May'16) << WS-G >> | YE2016 Projected (May '16) << WS-F >> | YE2015 Variance (Projected to Actual) | YE15 (actual) to YE16 (Projected) Variance | YE2016 Actual (May'17) << WS-G >> | YE2017 Projected (May '17) << WS-F >> | YE2017 Projected Adjusted (Oct '17) << WS-F >> | YE2018 Projected (Oct '17) << WS-F >> | YE2016 Variance (Projected to Actual) | YE16 (actual) to YE17 (Projected) Variance | YE2017 Actual (May '18) << WS-G >> | YE2018 Projected (May '18) << WS-F >> | YE2018 Projected Adjusted (Oct '18) << WS-F >> | YE2019 Projected (Oct '18) << WS-F >> | YE2017 Variance (Projected to Actual) | YE17 (Actual) to YE18 (Projected) Variance | YE2018 Actual (May '19) << WS-G >> | YE2019 Projected (Oct '19) << WS-F >> | YE2020 Projected (Oct '19) << WS-F >> | YE2018 Variance (Projected to Actual) | YE18 (Actual) to YE19 (Projected) Variance | YE2019 Actual (May '20) << WS-G >> | YE2020 Projected (May '20) << WS-F >> | YE2020 Projected (Oct '20) << WS-F >> | YE2021 Projected (Oct '20) << WS-F >> | YE2019 Variance (Projected to Actual) | YE19 (Actual) to YE20 (Projected) Variance | YE2020 Actual (May '21) << WS-G >> | YE2021 Projected (Oct '21) << WS-F >> | YE2022 Projected (Oct '21) << WS-F >> | YE2020 Variance (Projected to Actual) | YE20 (Actual) to YE21 (Projected) Variance | YE2021 Actual (Mar '22) << WS-G >> | YE2022 Projected (Apr '22) 4+8 | YE2023 Projected (Apr '22) 4+8 | YE2022 Projected (Aug '22) 7+5 | YE2023 Projected (Aug '22) 7+5 | YE2022 Projected (Oct '22) << WS-F >> | YE2023 Projected (Oct '22) << WS-F >> | YE2022 Projected (Dec '22) EOY | YE2023 Projected (Dec '22) EOY | YE2021 Variance (Projected to Actual) | YE21 (Actual) to YE22 (Projected) Variance | YE2022 Actual (Mar '23) << WS-G >> | YE2023 Projected (Apr '23) 4+8 | YE2024 Projected (Apr '23) 4+8 | YE2023 Projected (Aug '23) 7+5 | YE2024 Projected (Aug '23) 7+5 | YE2023 Projected (Oct '23) << WS-F >> | YE2024 Projected (Oct '23) << WS-F >> | YE2023 Projected (Dec '23) EOY | YE2024 Projected (Dec '23) EOY | YE2022 Variance (Projected to Actual) | YE22 (Actual) to YE23 (Projected) Variance | YE2023 Actual (Mar '24) << WS-G >> | YE2024 Projected (Apr '24) 4+8 | YE2025 Projected (Apr '24) 4+8 | YE2024 Projected (Aug '24) 7+5 | YE2025 Projected (Aug '24) 7+5 | YE2024 Projected (Oct '24) << WS-F >> | YE2025 Projected (Oct '24) << WS-F >> | YE2024 Projected (Dec '24) EOY | YE2025 Projected (Dec '24) EOY | YE2023 Variance (Projected to Actual) | YE23 (Actual) to YE24 (Projected) Variance
TP2007057 | TP2007057 | t | S.001 | Total | Total | 2009-12-01 | AH auto & line (TP2007057) | 9057179 | 12134740.73 | 17740954.73 | 95.88% | 17671482 | 17671482 | 0.3931% | 17671482 | 17671482 | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 |  |  | 17671482 | 17671482 | 17671482 | 17671482 |  |  | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 17671482 | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | [8 empty] | 0% | -100%
|  | c | S.001 | 108 | 10441 |  | Reconductor North Market - Arsenal Hill 69 kV 2.29 Miles With 1272 ACSR | [18 empty] | 2619131 | 2619131 |  |  | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 | 2619131 |  |  | 2619131 | 2619131 | 2619131 |  |  | 2619131 |  |  | 2619131 | 2619131 | 2619131 | 2619131 |  |  |  |  | 2619131 | 2619131 | 2619131 | 2619131 | 2619131 | 2619131 | 2619131 | 2619131 | 2619131 |  |  | 2619131
|  | c | S.001 | 507 | 10652 |  | Rebuild 3.24 miles of 1272 AAC with 2156 ACSR. Replace 3 138KV switches, breaker jumpers, and reset CTs at Arsenal Hill. Replace 2 138KV switches and jumpers at Fort Humbug. | [18 empty] | 5576975 | 5576975 |  |  | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 | 5576975 |  |  | 5576975 | 5576975 | 5576975 |  |  | 5576975 |  |  | 5576975 | 5576975 | 5576975 | 5576975 |  |  |  |  | 5576975 | 5576975 | 5576975 | 5576975 | 5576975 | 5576975 | 5576975 | 5576975 | 5576975 |  |  | 5576975
|  | c | S.001 | 30144 | 50152 |  | Included in 50154 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.001 | 30145 | 50153 |  | Rebuild 2.55 miles of 666 ACSR with 1272 ACSR | [18 empty] | 3024110 | 3024110 |  |  | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 | 3024110 |  |  | 3024110 | 3024110 | 3024110 |  |  | 3024110 |  |  | 3024110 | 3024110 | 3024110 | 3024110 |  |  |  |  | 3024110 | 3024110 | 3024110 | 3024110 | 3024110 | 3024110 | 3024110 | 3024110 | 3024110 |  |  | 3024110
|  | c | S.001 | 30146 | 50154 |  | Replace auto and 69 KV breaker and switches. | [18 empty] | 6451266 | 6451266 |  |  | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 | 6451266 |  |  | 6451266 | 6451266 | 6451266 |  |  | 6451266 |  |  | 6451266 | 6451266 | 6451266 | 6451266 |  |  |  |  | 6451266 | 6451266 | 6451266 | 6451266 | 6451266 | 6451266 | 6451266 | 6451266 | 6451266 |  |  | 6451266
|  | c | S.001 | 30147 | 50155 |  | Included in 50154 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2007060 | TP2007060 | t | S.002 | Total | Total | 2009-01-01 | SW Shreveport (TP2007060) | 11979500 | 8402687.48 | 8402687.48 | -29.86% | 8402687.48 | 8402687.48 | 0% | 8402687.48 | 8402687.48 | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687 | 8402687 | -5.712e-06% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | -5.712e-06% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 |  |  | 8402687 | 8402687 | 8402687 | 8402687 |  |  | 0% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | 8402687 | 8402687 | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 | [8 empty] | 0% | -100%
|  | c | S.002 | 224 | 10283 |  | Replace two 138 kV breakers and five 138 kV switches. Reset relays and CTs | [18 empty] | 6631400 | 6631400 |  |  | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 | 6631400 |  |  | 6631400 | 6631400 | 6631400 |  |  | 6631400 |  |  | 6631400 | 6631400 | 6631400 | 6631400 |  |  |  |  | 6631400 | 6631400 | 6631400 | 6631400 | 6631400 | 6631400 | 6631400 | 6631400 | 6631400 |  |  | 6631400
|  | c | S.002 | 224 | 10284 |  | Included in 10283 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.002 | 581 | 10744 |  | Rebuild 2.29 miles of 2-397.5 ACSR with 1590 ACSR. | [18 empty] | 1771287 | 1771287 |  |  | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 | 1771287 |  |  | 1771287 | 1771287 | 1771287 |  |  | 1771287 |  |  | 1771287 | 1771287 | 1771287 | 1771287 |  |  |  |  | 1771287 | 1771287 | 1771287 | 1771287 | 1771287 | 1771287 | 1771287 | 1771287 | 1771287 |  |  | 1771287
TP2007103 | TP2007103 | t | S.003 | Total | Total | 2009-06-01 | NW Ark 2009 (TP2007103) | 13558697 | 12384562 | 14833730 | 9.404% | 13742803 | 13742803 | 7.938% | 13742803 | 13742803 | 0% | 13742803 | 13742803 | 0% | 0% | 13742803 | 13742803 | 0% | 0% | 13742803 | 13742803 | 0% | 0% | 13742804 | 13742804 | 7.277e-06% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 7.277e-06% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 |  |  | 13742804 | 13742804 | 13742804 | 13742804 |  |  | 0% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 13742804 | 13742804 | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 | [8 empty] | 0% | -100%
|  | c | S.003 | 107 | 10132 |  | Install 3% impedance reactor set at East Rogers on 161 kV line to Avoca REC. | [18 empty] | 1265280 | 1265280 |  |  | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 | 1265280 |  |  | 1265280 | 1265280 | 1265280 |  |  | 1265280 |  |  | 1265280 | 1265280 | 1265280 | 1265280 |  |  |  |  | 1265280 | 1265280 | 1265280 | 1265280 | 1265280 | 1265280 | 1265280 | 1265280 | 1265280 |  |  | 1265280
|  | c | S.003 | 229 | 10292 |  | Reconductor 1 mile Flint Creek - Gentry 161 kV with 1590 ACSR. | [18 empty] | 10652438 | 10652438 |  |  | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 | 10652438 |  |  | 10652438 | 10652438 | 10652438 |  |  | 10652438 |  |  | 10652438 | 10652438 | 10652438 | 10652438 |  |  |  |  | 10652438 | 10652438 | 10652438 | 10652438 | 10652438 | 10652438 | 10652438 | 10652438 | 10652438 |  |  | 10652438
|  | c | S.003 | 229 | 10293 |  | Included in 10292 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.003 | 229 | 10294 |  | Reconductor 5.14 mile Bentonville 279th St. - East Centerton 161 kV with 1590 conductor. | [18 empty] | 1825086 | 1825086 |  |  | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 | 1825086 |  |  | 1825086 | 1825086 | 1825086 |  |  | 1825086 |  |  | 1825086 | 1825086 | 1825086 | 1825086 |  |  |  |  | 1825086 | 1825086 | 1825086 | 1825086 | 1825086 | 1825086 | 1825086 | 1825086 | 1825086 |  |  | 1825086
TP2007114 | TP2007114 | t | S.004 | Total | Total | 2009-06-01 | N-Mag-Danville (TP2007114) | 5012222 | 11580312.94 | 11580312.94 | 131% | 11580312.94 | 11580312.94 | 0% | 11580312.94 | 11580312.94 | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580311 | 11580311 | -1.675e-05% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | -1.675e-05% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 |  |  | 11580311 | 11580311 | 11580311 | 11580311 |  |  | 0% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 | [8 empty] | 0% | -100%
|  | c | S.004 | 225 | 10286 |  | Magazine REC Danville 161 kV rebuild 17.96 miles of 250 Copperweld with 1272 ACSR. | [18 empty] | 11580311 | 11580311 |  |  | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 | 11580311 |  |  | 11580311 | 11580311 | 11580311 |  |  | 11580311 |  |  | 11580311 | 11580311 | 11580311 | 11580311 |  |  |  |  | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 | 11580311 |  |  | 11580311
|  | c | S.004 | 225 | 10289 |  | All work combined under 10286. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.004 | 30154 | 50162 |  | No specific work order for this. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2007120 | TP2007120 | t | S.005 | Total | Total | 2009-12-01 | Greenwod, AR area (TP2007120) | 2111061 | 2981232 | 2981232 | 41.22% | 2981232 | 2981232 | 0% | 2981232 | 2981232 | 0% | 2981232 | 2981232 | 0% | 0% | 2981232 | 2981232 | 0% | 0% | 2981232 | 2981232 | 0% | 0% | 2981768 | 2981768 | 0.01798% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 0.01798% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 |  |  | 2981768 | 2981768 | 2981768 | 2981768 |  |  | 0% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 2981768 | 2981768 | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 | [8 empty] | 0% | -100% | slight discrepancy in sum of costs versus prior total
|  | c | S.005 | 217 | 10276 |  | Reconnect the Huntington 69 kV station from the North Huntington-Midland 69 kV line to the North Huntington-Waldron 69 kV line. | [18 empty] | 462173 | 462173 |  |  | 462173 | 462173 |  |  | 462173 | 462173 | 462173 | 462173 |  |  | 462173 | 462173 | 462173 | 462173 |  |  | 462173 | 462173 | 462173 |  |  | 462173 | 462173 | 462173 | 462173 |  |  | 462173 | 462173 | 462173 |  |  | 462173 |  |  | 462173 | 462173 | 462173 | 462173 |  |  |  |  | 462173 | 462173 | 462173 | 462173 | 462173 | 462173 | 462173 | 462173 | 462173 |  |  | 462173
|  | c | S.005 | 218 | 10277 |  | Upgrade CT at North Huntington on N Huntington to Huntington Waldron 69 kV | [18 empty] | 689134 | 689134 |  |  | 689134 | 689134 |  |  | 689134 | 689134 | 689134 | 689134 |  |  | 689134 | 689134 | 689134 | 689134 |  |  | 689134 | 689134 | 689134 |  |  | 689134 | 689134 | 689134 | 689134 |  |  | 689134 | 689134 | 689134 |  |  | 689134 |  |  | 689134 | 689134 | 689134 | 689134 |  |  |  |  | 689134 | 689134 | 689134 | 689134 | 689134 | 689134 | 689134 | 689134 | 689134 |  |  | 689134
|  | c | S.005 | 219 | 10278 |  | Replace the Excelsior 69 kV station on the Midland-Excelsior 69 kV line with Reeves Road 161 kV station on the nearby the Hackett REC-North Huntington 161 kV line section. Open the Midland-Excelsior 69 kV line. | [18 empty] | 636354 | 636354 |  |  | 636354 | 636354 |  |  | 636354 | 636354 | 636354 | 636354 |  |  | 636354 | 636354 | 636354 | 636354 |  |  | 636354 | 636354 | 636354 |  |  | 636354 | 636354 | 636354 | 636354 |  |  | 636354 | 636354 | 636354 |  |  | 636354 |  |  | 636354 | 636354 | 636354 | 636354 |  |  |  |  | 636354 | 636354 | 636354 | 636354 | 636354 | 636354 | 636354 | 636354 | 636354 |  |  | 636354
|  | c | S.005 | 222 | 10281 |  | Reconductor 0.1 mile Bonanza - Bonanza Tap 161 kV line section to 1590 ACSR. | [18 empty] | 1194107 | 1194107 |  |  | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 | 1194107 |  |  | 1194107 | 1194107 | 1194107 |  |  | 1194107 |  |  | 1194107 | 1194107 | 1194107 | 1194107 |  |  |  |  | 1194107 | 1194107 | 1194107 | 1194107 | 1194107 | 1194107 | 1194107 | 1194107 | 1194107 |  |  | 1194107
TP2007165 | TP2007165 | t | S.006 | Total | Total | 2009-06-01 | Port Robson - Caplis - Red Point (SE 138 loop) (TP2007165) | 17101764 | 5339018.68 | 6524013.68 | -61.85% | 5997609 | 27373809 | -76.17% | 20890772 | 32463272 | -15.68% | 29567877 | 34986877 | 8.015% | 18.33% | 36928458 | 36928458 | 5.549% | 0% | 37028625 | 37028625 | 0.2712% | 0% | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 |  |  | 37028625 | 37028625 | 37028625 | 37028625 |  |  | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 37028625 | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | [8 empty] | 0% | -100% | Multi-element multi-year base plan project. Final in-service yr from '09 to '13.
|  | c | S.006 | 113 | 10140 |  | Convert Red Point-Haughton to 138 kV, 1590 ACSR (includes Red Point terminal & Haughton station conversion). | [18 empty] | 11304565 | 11304565 |  |  | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 | 11304565 |  |  | 11304565 | 11304565 | 11304565 |  |  | 11304565 |  |  | 11304565 | 11304565 | 11304565 | 11304565 |  |  |  |  | 11304565 | 11304565 | 11304565 | 11304565 | 11304565 | 11304565 | 11304565 | 11304565 | 11304565 |  |  | 11304565
|  | c | S.006 | 113 | 10141 |  | Convert Haughton-McDade to 138 kV, 1590 ACSR (includes McDade station conversion). | [18 empty] | 13469723 | 13469723 |  |  | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 | 13469723 |  |  | 13469723 | 13469723 | 13469723 |  |  | 13469723 |  |  | 13469723 | 13469723 | 13469723 | 13469723 |  |  |  |  | 13469723 | 13469723 | 13469723 | 13469723 | 13469723 | 13469723 | 13469723 | 13469723 | 13469723 |  |  | 13469723
|  | c | S.006 | 113 | 10745 |  | Build new Port Robson-Bean 138 kV, 1590 ACSR line | [18 empty] | 4810545 | 4810545 |  |  | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 | 4810545 |  |  | 4810545 | 4810545 | 4810545 |  |  | 4810545 |  |  | 4810545 | 4810545 | 4810545 | 4810545 |  |  |  |  | 4810545 | 4810545 | 4810545 | 4810545 | 4810545 | 4810545 | 4810545 | 4810545 | 4810545 |  |  | 4810545
|  | c | S.006 | 113 | 10746 |  | Included in 10745 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.006 | 113 | 10786 |  | Build new Caplis-McDade 138 kV, 1590 ACSR line | [18 empty] | 7443792 | 7443792 |  |  | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 | 7443792 |  |  | 7443792 | 7443792 | 7443792 |  |  | 7443792 |  |  | 7443792 | 7443792 | 7443792 | 7443792 |  |  |  |  | 7443792 | 7443792 | 7443792 | 7443792 | 7443792 | 7443792 | 7443792 | 7443792 | 7443792 |  |  | 7443792
TP2008080 | TP2008080 | < | S.007 | Total | Total | 2009-05-01 | Linwood 1238 switch r&r (TP2008080) | 64397 | 64769 | 82956 | 28.82% | 77750 | 77750 | 6.696% | 77750 | 77750 | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 0% | 0% | 77750 |  |  | 77750 | 77750 | 77750 | 77750 |  |  | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 77750 | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 | [8 empty] | 0% | -100% | Not over $100K threshold for regional allocation.
|  | c | S.007 | 30151 | 50159 |  | Replace Linwood Switches 10872 and 10873 and replace 138KV breaker jumpers | [18 empty] | 77750 | 77750 |  |  | 77750 | 77750 |  |  | 77750 | 77750 | 77750 | 77750 |  |  | 77750 | 77750 | 77750 | 77750 |  |  | 77750 | 77750 | 77750 |  |  | 77750 | 77750 | 77750 | 77750 |  |  | 77750 | 77750 | 77750 |  |  | 77750 |  |  | 77750 | 77750 | 77750 | 77750 |  |  |  |  | 77750 | 77750 | 77750 | 77750 | 77750 | 77750 | 77750 | 77750 | 77750 |  |  | 77750
|  | t | S.008 | Total | Total | 2008-07-01 | Dyess-S.Fayetteville 69 convert to 161 (TP2002085) | 6374367 | 6406782 | 6406782 | 0.5085% | 9655697 | 9655697 | -33.65% | 9655697 | 9655697 | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 |  |  | 9655697 | 9655697 | 9655697 | 9655697 |  |  | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | [8 empty] | 0% | -100%
TP2002085 | TP2002085 | c | S.008 | 109 | 10133 |  | Convert 69 KV line to 161 kV | [18 empty] | 9655697 | 9655697 |  |  | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 | 9655697 |  |  | 9655697 | 9655697 | 9655697 |  |  | 9655697 |  |  | 9655697 | 9655697 | 9655697 | 9655697 |  |  |  |  | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 | 9655697 |  |  | 9655697
|  | c | S.008 | 109 | 10134 |  | Included in 10133 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.008 | 109 | 10135 |  | Included in 10133 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.008 | 109 | 10136 |  | Included in 10133 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2006130 | TP2006130 | t | S.009 | Total | Total | 2008-04-01 | NW Texkna-Bann-Alumax 138 reconductor (TP2006130) | 1864928 | 1863106 | 1863106 | -0.0977% | 2820378 | 2820378 | -33.94% | 2820378 | 2820378 | 0% | 2820378 | 2820378 | 0% | 0% | 2820378 | 2820378 | 0% | 0% | 2820378 | 2820378 | 0% | 0% | 2820328 | 2820328 | -0.001773% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | -0.001773% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 |  |  | 2820328 | 2820328 | 2820328 | 2820328 |  |  | 0% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | 2820328 | 2820328 | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 | [8 empty] | 0% | -100% | slight discrepancy in sum of costs versus prior total
|  | c | S.009 | 115 | 10145 |  | Rebuild 2.0 miles of 1024 ACAR with 1590 ACSR, Replace wave trap & jumpers with 2156 ACSR. Replace Switch 2285 @ Alumax Tap. | [18 empty] | 1662449 | 1662449 |  |  | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 | 1662449 |  |  | 1662449 | 1662449 | 1662449 |  |  | 1662449 |  |  | 1662449 | 1662449 | 1662449 | 1662449 |  |  |  |  | 1662449 | 1662449 | 1662449 | 1662449 | 1662449 | 1662449 | 1662449 | 1662449 | 1662449 |  |  | 1662449
|  | c | S.009 | 116 | 10146 |  | Replace six (6) 138 kV switches, five at Bann & one at Alumax Tap. Rebuild 0.67 miles of 1024 ACAR with 1590 ACSR. Replace wave trap & jumpers @ Bann. Replace breaker 3300 @ Bann. | [18 empty] | 1157879 | 1157879 |  |  | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 | 1157879 |  |  | 1157879 | 1157879 | 1157879 |  |  | 1157879 |  |  | 1157879 | 1157879 | 1157879 | 1157879 |  |  |  |  | 1157879 | 1157879 | 1157879 | 1157879 | 1157879 | 1157879 | 1157879 | 1157879 | 1157879 |  |  | 1157879
|  | n/a | S.010 | 6 | 10006 | 2008-11-01 | Tontitown-Elm Springs REC 161 | [22 empty] | 0% |  |  |  | 0% | [22 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes. Confirmed 1/19/15.
|  | n/a | S.010 | 42 | 10046 | 2008-11-01 | TONTITOWN 345/161KV TRANSFORMER CKT 1 | [22 empty] | 0% |  |  |  | 0% | [22 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes. Confirmed 1/19/15.
|  | n/a | S.011 | 43 | 10047 | 2007-05-01 | Siloam Sprgs - Chamber Sprgs 161 line | [22 empty] | 0% |  |  |  | 0% | [22 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes. Confirmed 1/19/15.
TP2004036 | TP2004036 | t | S.012 | Total | Total | 2007-07-01 | Knox Lee - Oak Hill#2 1328 line, S.Shreveport (TP2004036) | 124047 | 124047 | 124047 | 0% | 185247 | 185247 | -33.04% | 185247 | 185247 | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 0% | 0% | 185247 |  |  | 185247 | 185247 | 185247 | 185247 |  |  | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 185247 | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 | [8 empty] | 0% | -100%
|  | c | S.012 | 41 | 10045 |  | Replace wave trap at South Shreveport | [18 empty] | 108157 | 108157 |  |  | 108157 | 108157 |  |  | 108157 | 108157 | 108157 | 108157 |  |  | 108157 | 108157 | 108157 | 108157 |  |  | 108157 | 108157 | 108157 |  |  | 108157 | 108157 | 108157 | 108157 |  |  | 108157 | 108157 | 108157 |  |  | 108157 |  |  | 108157 | 108157 | 108157 | 108157 |  |  |  |  | 108157 | 108157 | 108157 | 108157 | 108157 | 108157 | 108157 | 108157 | 108157 |  |  | 108157
|  | c | S.012 | 44 | 10048 |  | Replace relay, wave trap at Knoxlee | [18 empty] | 77090 | 77090 |  |  | 77090 | 77090 |  |  | 77090 | 77090 | 77090 | 77090 |  |  | 77090 | 77090 | 77090 | 77090 |  |  | 77090 | 77090 | 77090 |  |  | 77090 | 77090 | 77090 | 77090 |  |  | 77090 | 77090 | 77090 |  |  | 77090 |  |  | 77090 | 77090 | 77090 | 77090 |  |  |  |  | 77090 | 77090 | 77090 | 77090 | 77090 | 77090 | 77090 | 77090 | 77090 |  |  | 77090
TP2004139 | TP2004139 | t | S.013 | Total | Total | 2006-04-01 | Carthage REC - Carthage T 138 (TP2004139) | 3884542 | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 0% | 3884542 | 3884542 | 0% | 0% | 5731607 | 5731607 | 47.55% | 0% | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 |  |  | 5731607 | 5731607 | 5731607 | 5731607 |  |  | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | [8 empty] | 0% | -100% | Corrected total; Shadow work order was missing from prior reports. New total correlates with orginal estimate.
|  | c | S.013 | 5 | 10005 |  | Included in 10007 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.013 | 7 | 10007 |  | Reconductor line with 1272 ACSR | [18 empty] | 5731607 | 5731607 |  |  | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 | 5731607 |  |  | 5731607 | 5731607 | 5731607 |  |  | 5731607 |  |  | 5731607 | 5731607 | 5731607 | 5731607 |  |  |  |  | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 | 5731607 |  |  | 5731607
TP2006089 | TP2006089 | < | S.014 | Total | Total | 2007-06-01 | NW Henderson - Oak Hill 138 line (TP2006089) | 54301 | 54301 | 54301 | 0% | 81701 | 81701 | -33.54% | 81701 | 81701 | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 0% | 0% | 81701 |  |  | 81701 | 81701 | 81701 | 81701 |  |  | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 81701 | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 | [8 empty] | 0% | -100% | Not over $100K threshold for regional allocation.
|  | c | S.014 | 48 | 10065 |  | Replace wave trap and reset CTs @ NW Henderson. | [18 empty] | 81701 | 81701 |  |  | 81701 | 81701 |  |  | 81701 | 81701 | 81701 | 81701 |  |  | 81701 | 81701 | 81701 | 81701 |  |  | 81701 | 81701 | 81701 |  |  | 81701 | 81701 | 81701 | 81701 |  |  | 81701 | 81701 | 81701 |  |  | 81701 |  |  | 81701 | 81701 | 81701 | 81701 |  |  |  |  | 81701 | 81701 | 81701 | 81701 | 81701 | 81701 | 81701 | 81701 | 81701 |  |  | 81701
TP2004148 | TP2004148 | t | S.015 | Total | Total | 2007-07-01 | Arsenal Hill 138 kV cap (TP2004148) | 247950 | 247950 | 247950 | 0% | 372149 | 372149 | -33.37% | 372149 | 372149 | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 0% | 0% | 372149 |  |  | 372149 | 372149 | 372149 | 372149 |  |  | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 372149 | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 | [8 empty] | 0% | -100%
|  | c | S.015 | 30000 | 50000 |  | Install switched capacitor bank. | [18 empty] | 372149 | 372149 |  |  | 372149 | 372149 |  |  | 372149 | 372149 | 372149 | 372149 |  |  | 372149 | 372149 | 372149 | 372149 |  |  | 372149 | 372149 | 372149 |  |  | 372149 | 372149 | 372149 | 372149 |  |  | 372149 | 372149 | 372149 |  |  | 372149 |  |  | 372149 | 372149 | 372149 | 372149 |  |  |  |  | 372149 | 372149 | 372149 | 372149 | 372149 | 372149 | 372149 | 372149 | 372149 |  |  | 372149
TP2008017 | TP2008017 | t | S.016 | Total | Total | 2008-12-01 | Daingerfield repl CB 1M90 (TP2008017) | ** | 0 | 310667 | n/a | 389326 | 389326 | -20.2% | 389326 | 389326 | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 0% | 0% | 389326 |  |  | 389326 | 389326 | 389326 | 389326 |  |  | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 389326 | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 | [8 empty] | 0% | -100%
|  | c | S.016 | 227 | 10291 |  | Replace Daingerfield 69 kV Breaker # 1M90 & reset relays. | [18 empty] | 389326 | 389326 |  |  | 389326 | 389326 |  |  | 389326 | 389326 | 389326 | 389326 |  |  | 389326 | 389326 | 389326 | 389326 |  |  | 389326 | 389326 | 389326 |  |  | 389326 | 389326 | 389326 | 389326 |  |  | 389326 | 389326 | 389326 |  |  | 389326 |  |  | 389326 | 389326 | 389326 | 389326 |  |  |  |  | 389326 | 389326 | 389326 | 389326 | 389326 | 389326 | 389326 | 389326 | 389326 |  |  | 389326
TP2007019 | TP2007019 | t | S.017 | Total | Total | 2008-06-01 | Linwood-McWillie (TP2007019) | 1300389 | 1949836.51 | 1949836.51 | 49.94% | 1949836.51 | 1949836.51 | 0% | 1949836.51 | 1949836.51 | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | [8 empty] | 0% | -100%
|  | c | S.017 | 120 | 10150 |  | 'Rebuild 2.09 miles of 666 ACSR with 1272 ACSR | [18 empty] | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51 |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  |  |  | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 |  |  | 1949836.51
|  | n/a | S.018 |  |  | 2008-10-01 | Port Robson - Caplis (SE 1238 kV loop - 2008) (TP2007165) | *** | n/a | n/a | n/a | --- | --- | --- | --- | --- |  | --- | --- | n/a | n/a | [8 empty] | 0% |  |  |  | 0% | [22 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Delete duplicate project. Will track this multi-element multi-year project via 1 set of worksheet F and G tables.
TP2005142 | TP2005142 | t | S.019 | Total | Total | 2008-05-01 | Wallace Lake - Port Robson (TP2005142) | 2811966 | 4480167.62 | 4480167.62 | 59.33% | 4480167.62 | 4480167.62 | 0% | 4480167.62 | 4480167.62 | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480168 | 4480168 | 8.482e-06% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 8.482e-06% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 |  |  | 4480168 | 4480168 | 4480168 | 4480168 |  |  | 0% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 | [8 empty] | 0% | -100%
|  | c | S.019 | 113 | 10143 |  | New 138 kV line from Wallace Lake to Finney Tap (includes Wallace Lake terminal) | [18 empty] | 4480168 | 4480168 |  |  | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 | 4480168 |  |  | 4480168 | 4480168 | 4480168 |  |  | 4480168 |  |  | 4480168 | 4480168 | 4480168 | 4480168 |  |  |  |  | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 | 4480168 |  |  | 4480168
|  | n/a | S.020 |  |  | 2008-11-01 | [NW Ark Area Improve - 2008] Elm Springs, East Rogers,Shipe Rd stations | 1165466 | 1165466 | 1165466 | 0% | --- | --- | --- | --- | --- |  | --- | --- | n/a | n/a | [8 empty] | 0 |  |  |  | 0 | [22 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Transfer: Will track this multi-element multi-year project via S.003 from 2011 Update forward. Investment now included in S.003 above.
? | ? | t | S.021 | Total | Total | 2010-06-01 | McNabb-Turk 4mi reconductor | n/a | 837610 | 2389000 | n/a | 1609803 | 1609803 | 48.4% | 1638972 | 1638972 | -1.78% | 1638972 | 1638972 | 0% | 0% | 1638972 | 1638972 | 0% | 0% | 1642817 | 1642817 | 0.2346% | 0% | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 |  |  | 1642817 | 1642817 | 1642817 | 1642817 |  |  | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | [8 empty] | 0% | -100% | Corrected total.
|  | c | S.021 | 349 | 10449 |  | included in 10450 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | c | S.021 | 349 | 10450 |  | Reconductor 3.55 miles of 666 ACSR with 1590 ACSR | [18 empty] | 1642817 | 1642817 |  |  | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 | 1642817 |  |  | 1642817 | 1642817 | 1642817 |  |  | 1642817 |  |  | 1642817 | 1642817 | 1642817 | 1642817 |  |  |  |  | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 | 1642817 |  |  | 1642817
? | ? | t | S.022 | Total | Total | 2010-06-01 | Longwood: r&r switches & bus upgrade | n/a | 0 | 187900 | n/a | 215000 | 215000 | -12.6% | 205882 | 205882 | 4.429% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 0% | 0% | 205882 |  |  | 205882 | 205882 | 205882 | 205882 |  |  | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 205882 | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 | [8 empty] | 0% | -100%
|  | c | S.022 | 30153 | 50161 |  | Replace four (4) switches and upgrading bus work. | [18 empty] | 205882 | 205882 |  |  | 205882 | 205882 |  |  | 205882 | 205882 | 205882 | 205882 |  |  | 205882 | 205882 | 205882 | 205882 |  |  | 205882 | 205882 | 205882 |  |  | 205882 | 205882 | 205882 | 205882 |  |  | 205882 | 205882 | 205882 |  |  | 205882 |  |  | 205882 | 205882 | 205882 | 205882 |  |  |  |  | 205882 | 205882 | 205882 | 205882 | 205882 | 205882 | 205882 | 205882 | 205882 |  |  | 205882
TP2008015 | TP2008015 | t | S.023 | Total | Total | 2010-06-01 | Reconductor: Greggton-Lake Lamond & Quitman-Westwood 69 kV lines (TP2008015) | n/a | 0 | 4839000 | n/a | 4795139 | 4795139 | 0.9147% | 4795139 | 4795139 | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 |  |  | 4795139 | 4795139 | 4795139 | 4795139 |  |  | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 4795139 | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | [8 empty] | 0% | -100%
|  | c | S.023 | 292 | 10378 |  | Reconductor 2.66 mile Greggton - Lake Lamond 69 kV with 1272 ACSR. | [18 empty] | 2853625 | 2853625 |  |  | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 | 2853625 |  |  | 2853625 | 2853625 | 2853625 |  |  | 2853625 |  |  | 2853625 | 2853625 | 2853625 | 2853625 |  |  |  |  | 2853625 | 2853625 | 2853625 | 2853625 | 2853625 | 2853625 | 2853625 | 2853625 | 2853625 |  |  | 2853625
|  | c | S.023 | 297 | 10383 |  | Reconductor Quitman - Westwood 69 kV 3.91 miles of 2/0 with 795 ACSR | [18 empty] | 1941514 | 1941514 |  |  | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 | 1941514 |  |  | 1941514 | 1941514 | 1941514 |  |  | 1941514 |  |  | 1941514 | 1941514 | 1941514 | 1941514 |  |  |  |  | 1941514 | 1941514 | 1941514 | 1941514 | 1941514 | 1941514 | 1941514 | 1941514 | 1941514 |  |  | 1941514
TP2008026 | TP2008026 | t | S.024 | Total | Total | 2010-06-01 | Rebuild/recondutor Dyess-ElmSprings REC [Dyess Station-Flint Creek] (TP2008026) | n/a | 0 | 5473000 | n/a | 5250739 | 5250739 | 4.233% | 5250739 | 5250739 | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 |  |  | 5250739 | 5250739 | 5250739 | 5250739 |  |  | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 5250739 | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | [8 empty] | 0% | -100%
|  | c | S.024 | 296 | 10382 |  | Rebuild/reconductor 5.17 mile Dyess - Elm Springs 161 kV with 2156 ACSR. | [18 empty] | 4984285 | 4984285 |  |  | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 | 4984285 |  |  | 4984285 | 4984285 | 4984285 |  |  | 4984285 |  |  | 4984285 | 4984285 | 4984285 | 4984285 |  |  |  |  | 4984285 | 4984285 | 4984285 | 4984285 | 4984285 | 4984285 | 4984285 | 4984285 | 4984285 |  |  | 4984285
|  | c | S.024 | 348 | 10445 |  | Replace 161 kV breaker, switches and CTs at Dyess. | [18 empty] | 266454 | 266454 |  |  | 266454 | 266454 |  |  | 266454 | 266454 | 266454 | 266454 |  |  | 266454 | 266454 | 266454 | 266454 |  |  | 266454 | 266454 | 266454 |  |  | 266454 | 266454 | 266454 | 266454 |  |  | 266454 | 266454 | 266454 |  |  | 266454 |  |  | 266454 | 266454 | 266454 | 266454 |  |  |  |  | 266454 | 266454 | 266454 | 266454 | 266454 | 266454 | 266454 | 266454 | 266454 |  |  | 266454
|  | c | S.024 | 30149 | 50157 |  | included in 10445 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
? | ? | < | S.025 | Total | Total | 2010-12-01 | Replace sw @ Diana | n/a | 0 | 91500 | n/a | 88842 | 88842 | 2.992% | 88842 | 88842 | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 0% | 0% | 88842 |  |  | 88842 | 88842 | 88842 | 88842 |  |  | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 88842 | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 | [8 empty] | 0% | -100% | Not over $100K threshold for regional allocation.
|  | c | S.025 | 613 | 10784 |  | Replace switch at Diana for higher winter rating of 287/316 MVA. Summer rating unchanged. | [18 empty] | 88842 | 88842 |  |  | 88842 | 88842 |  |  | 88842 | 88842 | 88842 | 88842 |  |  | 88842 | 88842 | 88842 | 88842 |  |  | 88842 | 88842 | 88842 |  |  | 88842 | 88842 | 88842 | 88842 |  |  | 88842 | 88842 | 88842 |  |  | 88842 |  |  | 88842 | 88842 | 88842 | 88842 |  |  |  |  | 88842 | 88842 | 88842 | 88842 | 88842 | 88842 | 88842 | 88842 | 88842 |  |  | 88842
? | ? | t | S.026 | Total | Total | 2011-06-01 | Whitney repl CB and Switches | --- | --- | --- | --- | --- | 279600 | n/a | 249141 | 249141 | 12.23% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 0% | 0% | 249141 |  |  | 249141 | 249141 | 249141 | 249141 |  |  | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 249141 | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 | [8 empty] | 0% | -100%
|  | c | S.026 | 452 | 10586 |  | Replace one breaker and four switches. | [18 empty] | 249141 | 249141 |  |  | 249141 | 249141 |  |  | 249141 | 249141 | 249141 | 249141 |  |  | 249141 | 249141 | 249141 | 249141 |  |  | 249141 | 249141 | 249141 |  |  | 249141 | 249141 | 249141 | 249141 |  |  | 249141 | 249141 | 249141 |  |  | 249141 |  |  | 249141 | 249141 | 249141 | 249141 |  |  |  |  | 249141 | 249141 | 249141 | 249141 | 249141 | 249141 | 249141 | 249141 | 249141 |  |  | 249141
? | ? | t | S.027 | Total | Total | 2012-06-01 | Linwood - Powell Street 138 kV | --- | --- | --- | --- | --- | --- | n/a | --- | 450200 | n/a | 430017 | 430017 | -4.483% | 0% | 430017 | 430017 | 0% | 0% | 421517 | 421517 | -1.977% | 0% | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 0% | 0% | 421517 |  |  | 421517 | 421517 | 421517 | 421517 |  |  | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 421517 | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 | [8 empty] | 0% | -100% | Corrected total (took out removal cost)
|  | c | S.027 | 30152 | 50160 |  | Replace 138 kV breaker, switches, and jumpers at Linwood. Replace circuit switcher at Powell Street. | [18 empty] | 421517 | 421517 |  |  | 421517 | 421517 |  |  | 421517 | 421517 | 421517 | 421517 |  |  | 421517 | 421517 | 421517 | 421517 |  |  | 421517 | 421517 | 421517 |  |  | 421517 | 421517 | 421517 | 421517 |  |  | 421517 | 421517 | 421517 |  |  | 421517 |  |  | 421517 | 421517 | 421517 | 421517 |  |  |  |  | 421517 | 421517 | 421517 | 421517 | 421517 | 421517 | 421517 | 421517 | 421517 |  |  | 421517
TP2008027 | TP2008027 | t | S.028 | Total | Total | 2012-06-01 | Bloomburg-Texarkana Plant (TP2008027) | --- | --- | --- | --- | --- | --- | n/a | --- | 5819300 | n/a | 5267709 | 5267709 | -9.479% | 0% | 5268487 | 5268487 | 0.01477% | 0% | 5268487 | 5268487 | 0% | 0% | 5268479 | 5268479 | -0.0001518% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | -0.0001518% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 |  |  | 5268479 | 5268479 | 5268479 | 5268479 |  |  | 0% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | 5268479 | 5268479 | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 | [8 empty] | 0% | -100% | slight discrepancy in sum of costs versus prior total
|  | c | S.028 | 30156 | 50164 |  | Change out the 500 Cu jumpers at Texarkana Plant. | [18 empty] | 37531 | 37531 |  |  | 37531 | 37531 |  |  | 37531 | 37531 | 37531 | 37531 |  |  | 37531 | 37531 | 37531 | 37531 |  |  | 37531 | 37531 | 37531 |  |  | 37531 | 37531 | 37531 | 37531 |  |  | 37531 | 37531 | 37531 |  |  | 37531 |  |  | 37531 | 37531 | 37531 | 37531 |  |  |  |  | 37531 | 37531 | 37531 | 37531 | 37531 | 37531 | 37531 | 37531 | 37531 |  |  | 37531
|  | c | S.028 | 30157 | 50165 |  | Rebuild 5.92 miles of 266 ACSR with 795 ACSR. Replace 69KV switches, jumpers, and reset CTs and relays at Texarkana Plant | [18 empty] | 5230948 | 5230948 |  |  | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 | 5230948 |  |  | 5230948 | 5230948 | 5230948 |  |  | 5230948 |  |  | 5230948 | 5230948 | 5230948 | 5230948 |  |  |  |  | 5230948 | 5230948 | 5230948 | 5230948 | 5230948 | 5230948 | 5230948 | 5230948 | 5230948 |  |  | 5230948
TP2010062 | TP2010062 | t | S.029 | Total | Total | 2012-12-01 | Knox Lee - Pirkey 138 kV / Pirkey - Whitney 138 kV - Replace Breaker, Wavetraps, and reset relays and CT's (TP2010062) | --- | --- | --- | --- | --- | --- | n/a | --- | 1521900 | n/a | 1886753 | 1886753 | 23.97% | 0% | 1881887 | 1881887 | -0.2579% | 0% | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 |  |  | 1881887 | 1881887 | 1881887 | 1881887 |  |  | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 1881887 | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | [8 empty] | 0% | -100%
|  | c | S.029 | 30317 | 50363 |  | Replace 3 2000 A switches at Knox Lee | [18 empty] | 256687 | 256687 |  |  | 256687 | 256687 |  |  | 256687 | 256687 | 256687 | 256687 |  |  | 256687 | 256687 | 256687 | 256687 |  |  | 256687 | 256687 | 256687 |  |  | 256687 | 256687 | 256687 | 256687 |  |  | 256687 | 256687 | 256687 |  |  | 256687 |  |  | 256687 | 256687 | 256687 | 256687 |  |  |  |  | 256687 | 256687 | 256687 | 256687 | 256687 | 256687 | 256687 | 256687 | 256687 |  |  | 256687
|  | c | S.029 | 30318 | 50364 |  | Replace Switch at Easton, and Breaker and Switch at Pirkey | [18 empty] | 1158231 | 1158231 |  |  | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 | 1158231 |  |  | 1158231 | 1158231 | 1158231 |  |  | 1158231 |  |  | 1158231 | 1158231 | 1158231 | 1158231 |  |  |  |  | 1158231 | 1158231 | 1158231 | 1158231 | 1158231 | 1158231 | 1158231 | 1158231 | 1158231 |  |  | 1158231
|  | c | S.029 | 30319 | 50365 |  | Reset CT, Replace Breaker and Switch | [18 empty] | 466969 | 466969 |  |  | 466969 | 466969 |  |  | 466969 | 466969 | 466969 | 466969 |  |  | 466969 | 466969 | 466969 | 466969 |  |  | 466969 | 466969 | 466969 |  |  | 466969 | 466969 | 466969 | 466969 |  |  | 466969 | 466969 | 466969 |  |  | 466969 |  |  | 466969 | 466969 | 466969 | 466969 |  |  |  |  | 466969 | 466969 | 466969 | 466969 | 466969 | 466969 | 466969 | 466969 | 466969 |  |  | 466969
TP2006077 | TP2006077 | t | S.030 | Total | Total | 2012-08-31 | NW Texarkana - Turk 345 | --- | --- | --- | --- | --- | --- | n/a | --- | 47434000 | n/a | 47172572 | 47172572 | -0.5511% | 0% | 47415121 | 47415121 | 0.5142% | 0% | 47659752 | 47659900 | 0.5159% | 0.0003105% | 47660028.54 | 47659900 | 0.0002697% | -0.0002697% | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0.0002697% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 |  |  | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 |  |  | 0% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 | [8 empty] | 0% | -100%
|  | c | S.030 | 349 | 10456 |  | Add Turk 345/138 kV transformer | [18 empty] | 7533965 | 7533965 |  |  | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 | 7533965 |  |  | 7533965 | 7533965 | 7533965 |  |  | 7533965 |  |  | 7533965 | 7533965 | 7533965 | 7533965 |  |  |  |  | 7533965 | 7533965 | 7533965 | 7533965 | 7533965 | 7533965 | 7533965 | 7533965 | 7533965 |  |  | 7533965
|  | c | S.030 | 30142 | 50148 |  | Build approximately 33 miles of 2-954 ACSR from Turk to NW Texarkana. | [18 empty] | 38394007 | 38394007 |  |  | 38394283.54 | 38394007 |  |  | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54 |  |  | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 |  |  |  |  | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 | 38394283.54 |  |  | 38394283.54
|  | c | S.030 | 30142 | 50149 |  | Add 345 kV terminal at NW Texarkana | [18 empty] | 1731780 | 1731780 |  |  | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 | 1731780 |  |  | 1731780 | 1731780 | 1731780 |  |  | 1731780 |  |  | 1731780 | 1731780 | 1731780 | 1731780 |  |  |  |  | 1731780 | 1731780 | 1731780 | 1731780 | 1731780 | 1731780 | 1731780 | 1731780 | 1731780 |  |  | 1731780
|  | c | S.030 | 30142 | 50150 |  | included in 10456 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2009100 | TP2009100 | t | S.031 | Total | Total | 2012-06-01 | Lone Star South - Pittsburg 138 kV - Replace Wavetraps, reset CT's and Relays (TP2009100) | --- | --- | --- | --- | --- | --- | n/a | --- | 284100 | n/a | 230750 | 230750 | -18.78% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 0% | 0% | 230750 |  |  | 230750 | 230750 | 230750 | 230750 |  |  | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 230750 | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 | [8 empty] | 0% | -100%
|  | c | S.031 | 391 | 10509 |  | Replace 138 kV wavetraps at both ends. Reset CTs at Lone Star South. Reset relays at Pittsburg. | [18 empty] | 230750 | 230750 |  |  | 230750 | 230750 |  |  | 230750 | 230750 | 230750 | 230750 |  |  | 230750 | 230750 | 230750 | 230750 |  |  | 230750 | 230750 | 230750 |  |  | 230750 | 230750 | 230750 | 230750 |  |  | 230750 | 230750 | 230750 |  |  | 230750 |  |  | 230750 | 230750 | 230750 | 230750 |  |  |  |  | 230750 | 230750 | 230750 | 230750 | 230750 | 230750 | 230750 | 230750 | 230750 |  |  | 230750
? | ? | t | S.032 | Total | Total | 2012-06-01 | Howell-Kilgore 69 kV rebuild | --- | --- | --- | --- | --- | --- | n/a | --- | 3985900 | n/a | 4204655 | 4204655 | 5.488% | 0% | 4157737 | 4157737 | -1.116% | 0% | 4175110 | 4175110 | 0.4178% | 0% | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 |  |  | 4175110 | 4175110 | 4175110 | 4175110 |  |  | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | [8 empty] | 0% | -100%
|  | c | S.032 | 392 | 10510 |  | Rebuild 3.49 miles of Howell - Kilgore 69 kV 4/0 ACSR with 795 ACSR. | [18 empty] | 4175110 | 4175110 |  |  | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 | 4175110 |  |  | 4175110 | 4175110 | 4175110 |  |  | 4175110 |  |  | 4175110 | 4175110 | 4175110 | 4175110 |  |  |  |  | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 | 4175110 |  |  | 4175110
TP2008126 | TP2008126 | t | S.033 | Total | Total | 2014-04-01 | Flint Creek-Shipe Road 345 kV Line (TP2008126) | --- | --- | --- | --- | --- | --- | n/a | --- | 1609000 | n/a | 4101857 | 12471857 | 154.9% | 204.1% | 8981434 | 55496134 | -27.99% | 517.9% | 58065903 | 57951403 | 4.631% | -0.1972% | 58124321.73 | 59295600.19 | 0.2984% | 2.015% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0.01718% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 |  |  | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 |  |  | 0% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 | [8 empty] | 0% | -100% | Multi-element multi-year base plan project. Work orginally projected for 2013 was moved to 2014. Final in-service yr in 12', 13' and 14'.
|  | c | S.033 | 450 | 10582 |  | Install 9 miles of 161 kV from new Shipe Road Substation to East Centerton Substation. | [18 empty] | 10957716 | 10957716 |  |  | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 | 10957716 |  |  | 10957716 | 10957716 | 10957716 |  |  | 10957716 |  |  | 10957716 | 10957716 | 10957716 | 10957716 |  |  |  |  | 10957716 | 10957716 | 10957716 | 10957716 | 10957716 | 10957716 | 10957716 | 10957716 | 10957716 |  |  | 10957716 | [10 empty] | Includes all 161 kV line work.
|  | c | S.033 | 450 | 10584 |  | Install 345/161 kV transformer at Shipe Road. | [18 empty] | 15546751 | 15546751 |  |  | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 | 15546751 |  |  | 15546751 | 15546751 | 15546751 |  |  | 15546751 |  |  | 15546751 | 15546751 | 15546751 | 15546751 |  |  |  |  | 15546751 | 15546751 | 15546751 | 15546751 | 15546751 | 15546751 | 15546751 | 15546751 | 15546751 |  |  | 15546751 | [10 empty] | Includes all station work.
|  | c | S.033 | 450 | 10585 |  | Install 18 miles of new 345 kV, 2-954 ACSR line. | [18 empty] | 31561436 | 31446936 |  |  | 31619854.73 | 32791133.19 |  |  | 31619854.73 | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 |  |  | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 |  |  |  |  | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 | 32791133.19 |  |  | 32791133.19 | [10 empty] | Includes all 345 kV line work. Added this to include the revision for the condemnation
TP2011024 | TP2011024 | t | S.034 | Total | Total | 2013-11-01 | Bann - LS Ordnance - Hooks 69 kV - Rebuild 7.1 mi (TP2011024) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 8177700 | n/a | n/a | 8593855 | 8593855 | 5.089% | 0% | 8598828 | 8598828 | 0.05787% | 0% | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 |  |  | 8598828 | 8598828 | 8598828 | 8598828 |  |  | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | [8 empty] | 0% | -100%
|  | c | S.034 | 1081 | 11421 |  | Rebuild 1.68-mile Hooks - Lone Star Ordinance Tap 69 kV line. Replace switch 6006 at Lone Star Ordinance. | [18 empty] | 8598828 | 8598828 |  |  | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 | 8598828 |  |  | 8598828 | 8598828 | 8598828 |  |  | 8598828 |  |  | 8598828 | 8598828 | 8598828 | 8598828 |  |  |  |  | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 | 8598828 |  |  | 8598828 | [10 empty] | Includes 7.1 mile line rebuild, and terminal work at Lone Star Ordnance Tap and Bann.
|  | c | S.034 | 30148 | 50156 |  | included in 11421 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TP2010065 | TP2010065 | t | S.035 | Total | Total | 2013-06-01 | Diana - Replace North Autotransformer #3 (TP2010065) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 3795000 | n/a | n/a | 4344847 | 4344847 | 14.49% | 0% | 4344850 | 4344850 | 6.905e-05% | 0% | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 |  |  | 4344850 | 4344850 | 4344850 | 4344850 |  |  | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | [8 empty] | 0% | -100%
|  | c | S.035 | 30316 | 50375 |  | Replace auto with new 450 MVA. | [18 empty] | 4344850 | 4344850 |  |  | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 | 4344850 |  |  | 4344850 | 4344850 | 4344850 |  |  | 4344850 |  |  | 4344850 | 4344850 | 4344850 | 4344850 |  |  |  |  | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 | 4344850 |  |  | 4344850
? | ? | t | S.036 | Total | Total | 2013-09-01 | Osburn 161 kV Line Work | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 1750000 | n/a | n/a | 3038117 | 3038117 | 73.61% | 0% | 6389739 | 6389739 | 110.3% | 0% | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 |  |  | 6389739 | 6389739 | 6389739 | 6389739 |  |  | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | [8 empty] | 0% | -100% | Includes T station and T line per Pennybaker/Rainbolt
|  | c | S.036 | 443 | 10575 |  | Tap the South Springdale-East Fayetteville 161 kV line and build 1.5 miles of 161 kV to new Osbourne station. | [18 empty] | 6389739 | 6389739 |  |  | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 | 6389739 |  |  | 6389739 | 6389739 | 6389739 |  |  | 6389739 |  |  | 6389739 | 6389739 | 6389739 | 6389739 |  |  |  |  | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 | 6389739 |  |  | 6389739
TP2010066 | TP2010066 | t | S.037 | Total | Total | 2013-06-01 | SW Shreveport to Spring Ridge REC 138 kV Line Rebuild (TP2010066) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 4585200 | n/a | n/a | 5048185 | 5048185 | 10.1% | 0% | 5048526 | 5048526 | 0.006755% | 0% | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 |  |  | 5048526 | 5048526 | 5048526 | 5048526 |  |  | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | [8 empty] | 0% | -100%
|  | c | S.037 | 1023 | 11347 |  | Rebuild 7.11 miles of 397.5 ACSR with 1272 ACSR | [18 empty] | 5048526 | 5048526 |  |  | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 | 5048526 |  |  | 5048526 | 5048526 | 5048526 |  |  | 5048526 |  |  | 5048526 | 5048526 | 5048526 | 5048526 |  |  |  |  | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 | 5048526 |  |  | 5048526
TP2010064 | TP2010064 | t | S.038 | Total | Total | 2013-06-01 | Eastex Switching Station - Whitney 138 kV Station - Rebuild 2.5 miles of 138 kV (TP2010064) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 3095000 | n/a | n/a | 2636239 | 2636239 | -14.82% | 0% | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 |  |  | 2636239 | 2636239 | 2636239 | 2636239 |  |  | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | [8 empty] | 0% | -100%
|  | c | S.038 | 1024 | 11348 |  | Rebuild 2.49 miles with 1590 ACSR. Replace wavetrap and jumpers at Whitney. Replace metering CT at Eastex. | [18 empty] | 2636239 | 2636239 |  |  | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 | 2636239 |  |  | 2636239 | 2636239 | 2636239 |  |  | 2636239 |  |  | 2636239 | 2636239 | 2636239 | 2636239 |  |  |  |  | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 | 2636239 |  |  | 2636239
TP2009092 | TP2009092 | t | S.039 | Total | Total | 2013-02-01 | Ashdown West - Craig Junction 138KV Rebuild (TP2009092) | [14 empty] | 4316127 | 4316127 |  |  | 4316668 | 4316668 | 0.01253% | 0% | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 |  |  | 4316668 | 4316668 | 4316668 | 4316668 |  |  | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | [8 empty] | 0% | -100% | Asset has been transferred to SWEPCO from PSO, thus placing the line back with the original owner.
|  | c | S.039 | 770 | 11015 |  | Rebuild 2.45 miles of 795 ACSR with 1590 ACSR and reset relays. | [18 empty] | 4316668 | 4316668 |  |  | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 | 4316668 |  |  | 4316668 | 4316668 | 4316668 |  |  | 4316668 |  |  | 4316668 | 4316668 | 4316668 | 4316668 |  |  |  |  | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 | 4316668 |  |  | 4316668
TP2010102 | TP2010102 | t | S.040 | Total | Total | 2014-06-01 | Rock Hill to Carthage 69 kV Rebuild 11.4 Miles (TP2010102) | [14 empty] | 0 | 9550200 |  |  | 9637037 | 9637037 | 0.9093% | 0% | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 |  |  | 9637037 | 9637037 | 9637037 | 9637037 |  |  | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | [8 empty] | 0% | -100%
|  | c | S.040 | 882 | 11171 |  | Rebuild or reconductor 11.4-mile Rock Hill - Carthage line from 336 ACSR to 1272 ACSR and remove switches in middle of line. Upgrade breaker, switches, CT ratios, and relay settings at Carthage substation. Upgrade jumpers, switches, CT ratios, and relay settings at Rock Hill substation. | [18 empty] | 9637037 | 9637037 |  |  | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 | 9637037 |  |  | 9637037 | 9637037 | 9637037 |  |  | 9637037 |  |  | 9637037 | 9637037 | 9637037 | 9637037 |  |  |  |  | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 | 9637037 |  |  | 9637037
TP2010103 | TP2010103 | t | S.041 | Total | Total | 2014-12-01 | Broadmoor to Fern Street 69 kV Rebuild 1 mile (TP2010103) | [14 empty] | 0 | 3846600 |  |  | 4675710 | 4795000 | 21.55% | 2.551% | 4825048 | 4795000 | 0.6267% | -0.6228% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 1.481% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 0% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 | [8 empty] | 0% | -100% | Includes terminal work at both Fern Street and Broadmoor.
|  | c | S.041 | 681 | 10898 |  | Rebuild 1-mile portion of the 69 kV line from Broadmoor to Fern Street with 1233.6 ACSR/TW. Replace switches at Fern Street. | [18 empty] | 4675710 | 4795000 |  |  | 4825048 | 4675710 |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31 |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  |  |  | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 |  |  | 4866028.31
TP2004031 | TP2004031 | t | S.042 | Total | Total | 2014-06-01 | Northwest Henderson to Poynter 69 kV Rebuild 3.2 miles (TP2004031) | [14 empty] | 0 | 4520000 |  |  | 5289194 | 5289194 | 17.02% | 0% | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 |  |  | 5289194 | 5289194 | 5289194 | 5289194 |  |  | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | [8 empty] | 0% | -100% | Includes terminal work at both Northwest Henderson and Poynter
|  | c | S.042 | 502 | 10647 |  | Reconductor 3.25-mile 69 kV line from Northwest Henderson to Poynter with 1272 ACSR. | [18 empty] | 5289194 | 5289194 |  |  | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 | 5289194 |  |  | 5289194 | 5289194 | 5289194 |  |  | 5289194 |  |  | 5289194 | 5289194 | 5289194 | 5289194 |  |  |  |  | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 | 5289194 |  |  | 5289194
TP2011023 | TP2011023 | t | S.043 | Total | Total | 2014-11-01 | Diana to Perdue 138 kV Rebuild 21.8 miles; Station Upgrades at Diana and Perdue (TP2011023) | [14 empty] | 0 | 14332500 |  |  | 14950466 | 15026000 | 4.312% | 0.5052% | 14866883.03 | 15026000 | -1.059% | 1.07% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | -1.059% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 0% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 | [8 empty] | 0% | -100%
|  | c | S.043 | 1012 | 11331 |  | Rebuild 21.85-mile 138 kV line from Diana to Perdue. Replace switches, jumpers, and upgrade CT ratios at Diana and Perdue. Upgrade relay settings at Diana. | [18 empty] | 14950466 | 15026000 |  |  | 14866883.03 | 14986466 |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03 |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  |  |  | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 |  |  | 14866883.03
|  | c | S.043 | 503 | 10648 |  | Included in 11331 | [18 empty] | 0 | 0 |  |  | 0 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12 |  |  | -83583.12 | -83583.12 | -83583.12 | -83583.12 |  |  |  |  | -83583.12 | -83583.12 | -83583.12 | -83583.12 | -83583.12 | -83583.12 | -83583.12 | -83583.12 | -83583.12 |  |  | -83583.12
Cancelled | Cancelled | c | S.043 | 30436 | 50531 |  | Included in 11331 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | t | S.044 | Total | Total | 2007-11-01 | Pittsburg-Winnsboro-North Mineola | [18 empty] | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 0% | 0% | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 | 0% | 0% | 29107362.05 | [8 empty] | 0% | -100% | not sure if stations are to be included
|  | c | S.044 | 10 | 10010 | 2006-07-01 | PITTSBURG - WINNSBORO 138KV CKT 1 | [18 empty] | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79 |  |  | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 |  |  |  |  | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 | 13495617.79 |  |  | 13495617.79
|  | c | S.044 | 40 | 10044 | 2007-10-01 | NORTH MINEOLA - WINNSBORO 138KV CKT 1 | [18 empty] | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6 |  |  | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 |  |  |  |  | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 | 13496861.6 |  |  | 13496861.6
|  | c | S.044 |  |  | 2007-11-01 | Pittsburg and Mineola Stations | [18 empty] | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 |  |  | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 |  |  |  |  | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 | 2114882.66 |  |  | 2114882.66 | [10 empty] | not sure if stations are to be included
? | ? | t | S.045 | Total | Total | 2007-03-01 | CHAMBER SPRINGS - TONTITOWN 161KV CKT 1 | [18 empty] | 2658452 | 2658452 |  |  | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 |  |  | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 0% | 0% | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 0% | 0% | 2658452 | [8 empty] | 0% | -100%
|  | c | S.045 | 45 | 10049 |  | Reconductor 666 ACSR (11.6 miles) and 1272 ACSR (.1 mile) to Drake ACCC (2156 ACSR section 0.6 miles is not replaced) and remove the series reactors at Chamber Springs on the Chamber Springs to Tontitown 161 kV line | [18 empty] | 2658452 | 2658452 |  |  | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 |  |  | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  |  |  | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452
? | ? | t | S.046 | Total | Total | 2008-05-01 | CHAMBER SPRINGS - TONTITOWN 345KV CKT 1 | [18 empty] | 16318844 | 16318844 |  |  | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 |  |  | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 0% | 0% | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 0% | 0% | 16318844 | [8 empty] | 0% | -100% | Includes 345 kV line and Chamber Springs 345 kV terminal work.
|  | c | S.046 | 117 | 10147 |  | Install new 345 kV line , ROW and terminal equipment at Chamber Springs | [18 empty] | 16318844 | 16318844 |  |  | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 |  |  | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  |  |  | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844
? | ? | t | S.047 | Total | Total | 2012-02-01 | FULTON - HOPE 115KV CKT 1 | [18 empty] | 787880 | 787880 |  |  | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 |  |  | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 0% | 0% | 787880 | 787880 | 787880 | 787880 | 787880 | 787880 | 787880 | 787880 | 787880 | 0% | 0% | 787880 | [8 empty] | 0% | -100%
|  | c | S.047 | 221 | 10280 |  | Replace conductor in Hope Substation | [18 empty] | 787880 | 787880 |  |  | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 |  |  | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  |  |  | 787880 | 787880 | 787880 | 787880 | 787880 | 787880 | 787880 | 787880 | 787880 |  |  | 787880
? | ? | t | S.048 | Total | Total | 2010-03-01 | MINEOLA - NORTH MINEOLA 69KV CKT 1 | [18 empty] | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 0% | 0% | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 0% | 0% | 160296.1 | [8 empty] | 0% | -100% | 69 kV Upgrade.
|  | c | S.048 | 294 | 10380 |  | Replace Mineola 2 Switches & Breaker | [18 empty] | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1
|  | n/a | - | Total | Total |  | BANN - KINGS HIGHWAY 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; Distribution investment
|  | n/a | - | 1 | 10001 |  | Replace Switch in King Hwy substation | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | n/a | - | Total | Total |  | LONE STAR SOUTH - PITTSBURG 138KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; no Capital investment
|  | n/a | - | 8 | 10008 |  | Replace CT | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | n/a | - | Total | Total |  | BANN - LONESTAR ORDINANCE TAP 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; no Capital investment
|  | n/a | - | 291 | 10377 |  | Relay at Bann new limits will be 65/72 MVA summer (line conductor/Lonestar switch) and 72/72 MVA winter (Lonestar Switch) | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | n/a | - | Total | Total |  | FOREST HILLS REC - QUITMAN 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; Distribution investment
|  | n/a | - | 346 | 10443 |  | Replace Quitman 69KV bus, switches and jumpers. Change CT and relay settings. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | n/a | - | Total | Total |  | MAGNOLIA TAP - WINNSBORO 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; Distribution investment
|  | n/a | - | 343 | 10440 |  | Replace 69 kV switches at Winnsboro and reset CT ratios and relay settings. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | n/a | - | Total | Total |  | CARTHAGE - ROCK HILL 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; no Capital investment
|  | n/a | - | 449 | 10581 |  | Reset CTs at Carthage on the Carthage - Rock Hill line. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | n/a | - | Total | Total |  | FOREST HILLS REC - QUITMAN 69KV CKT 1 #2 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; no Capital investment
|  | n/a | - | 641 | 10842 |  | Replace two switches at Quitman substation. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | < | S.049 | Total | Total | 2010-11-01 | SUGAR HILL 138/69KV TRANSFORMER CKT 1 | [18 empty] | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 0% | 0% | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 0% | 0% | 23215.78 | [8 empty] | 0% | -100% | Not over $100K threshold for regional allocation.
? | ? | c | S.049 | 875 | 11155 |  | Replace 69 kV switch 11985 and 1033 AAC jumpers at Sugar Hill. | [18 empty] | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78
|  | n/a | - | Total | Total |  | OKAY - TOLLETTE 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [10 empty] | Ignore; no Capital investment
|  | n/a | - | 30155 | 50163 |  | Replace 69 kV switches. | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | t | S.050 | Total | Total | 2015-06-05 | Dekalb-New Boston 69 kV | [18 empty] | 49364.11 | 15500000 |  |  | 15777910.71 | 15777910.71 | 1.793% | 0% | 15991916.9 | 15998916.9 | 15998916.9 | 15998916.9 | 1.356% | 0.04377% | 16142203.19 | 15998916.9 | 15998916.9 | 15998916.9 | 0.8956% | -0.8877% | 16209336.9 | 16209336.9 | 16209336.9 | 1.315% | -1.298% | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | -1.719% | 0% | 15930624.49 | 15930624.49 | 15930624.49 | 0% | 0% | 15930624.49 |  |  | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 |  |  | 0% | 0% | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 0% | 0% | 15930624.49 | [8 empty] | 0% | -100% | 69 kV Upgrade. Dekalb Station upgrades in-serviced Oct-14.
TP2012144 | TP2012144 | c | S.050 | 30471 | 50567 |  | Rebuild 13.2 mile line; Upgrade CT ratios and relay settings at New Boston. | [18 empty] | 49364.11 | 15500000 |  |  | 15777910.71 | 15777910.71 |  |  | 15991916.9 | 15998916.9 | 15998916.9 | 15998916.9 |  |  | 16142203.19 | 15998916.9 | 15998916.9 | 15998916.9 |  |  | 16209336.9 | 16209336.9 | 16209336.9 |  |  | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 |  |  | 15930624.49 | 15930624.49 | 15930624.49 |  |  | 15930624.49 |  |  | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 |  |  |  |  | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 | 15930624.49 |  |  | 15930624.49
|  | t | S.051 | Total | Total | 2015-06-25 | Hardy Street-Waterworks 69 kV | [18 empty] | 0 | 5200000 |  |  | 5366606.14 | 5366606.14 | 3.204% | 0% | 5401890.07 | 5429685.07 | 5429685.07 | 5429685.07 | 0.6575% | 0.5145% | 5522411.15 | 5429685.07 | 5429685.07 | 5429685.07 | 1.708% | -1.679% | 5522411.15 | 5522411.15 | 5522411.15 | 1.708% | -1.679% | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 0% | 0% | 5522411.15 | 5522411.15 | 5522411.15 | 0% | 0% | 5522411.15 |  |  | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 |  |  | 0% | 0% | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 0% | 0% | 5522411.15 | [8 empty] | 0% | -100% | 69 kV Upgrade.
TP2012146 | TP2012146 | c | S.051 | 30472 | 50568 |  | Rebuild 1.6 mile line from Hardy Street to Waterworks with 1233.6 ACSR/TW | [18 empty] | 0 | 5200000 |  |  | 5366606.14 | 5366606.14 |  |  | 5401890.07 | 5429685.07 | 5429685.07 | 5429685.07 |  |  | 5522411.15 | 5429685.07 | 5429685.07 | 5429685.07 |  |  | 5522411.15 | 5522411.15 | 5522411.15 |  |  | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 |  |  | 5522411.15 | 5522411.15 | 5522411.15 |  |  | 5522411.15 |  |  | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 |  |  |  |  | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 | 5522411.15 |  |  | 5522411.15
|  | t | S.052 | Total | Total | 2015-05-15 | Red Oak (State Line)-North Huntington 69 kV | [18 empty] | 3741684.51 | 12300000 |  |  | 11990487.31 | 11990487.31 | -2.516% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0.2258% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 |  |  | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 |  |  | 0% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 | [8 empty] | 0% | -100% | 69 kV Upgrade. State Line to Midland line rebuild in-serviced Dec-14.
TP2012164 | TP2012164Y | c | S.052 | 30473 | 50569 |  | Rebuild 4.0 mile line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington. | [18 empty] | 0 | 6300000 |  |  | 5181390.93 | 5181390.93 |  |  | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 |  |  | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 |  |  |  |  | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 | 5200667.03 |  |  | 5200667.03 | [10 empty] | P12164003, P12164503
TP2012164 | TP2012164 | c | S.052 | 30474 | 50570 |  | Rebuild 1.3 mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | [18 empty] | 0 | 0 |  |  | 2368056.53 | 2368056.53 |  |  | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 |  |  | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 |  |  |  |  | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 | 2375720.96 |  |  | 2375720.96 | [10 empty] | P12164005/006/007, P12164505/506/507
TP2012164 | TP2012164X | c | S.052 | 30475 | 50571 |  | Rebuild 7.0 mile 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of the line to be rebult is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | [18 empty] | 3741684.51 | 6000000 |  |  | 4441039.85 | 4441039.85 |  |  | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 |  |  | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 |  |  |  |  | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 | 4441178.61 |  |  | 4441178.61 | [10 empty] | P12164001/002, P12164501/502
|  | t | S.053 | Total | Total | 2015-05-01 | Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | [18 empty] | 0 | 5900000 |  |  | 5724549.21 | 5724549.21 | -2.974% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0.2352% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 0% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 | [8 empty] | 0% | -100% | 69 kV Upgrade.
TP2013081 | TP2013081 | c | S.053 | 30731 | 50990 |  | Rebuild 2.75 mile 69 kV line from Mt. Pleasant to West Mt. Pleasant | [18 empty] | 0 | 5900000 |  |  | 5724549.21 | 5724549.21 |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91 |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  |  |  | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 |  |  | 5738012.91
|  | t | S.054 | Total | Total | 2015-11-01 | Benteler - Port Robson 138 kV Ckt 1 and 2 | [18 empty] | 13776207.78 | 13860000 |  |  | 13851900 | 13875791.7 | -0.05844% | 0.1725% | 13851900 | 13851900 | 13851900 | 13851900 | -0.1722% | 0% | 13851900 | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 |  |  | 13851900 | 13851900 | 13851900 | 13851900 |  |  | 0% | 0% | 13851900 | 13851900 | 13851900 | 13851900 | 13851900 | 13851900 | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 | [8 empty] | 0% | -100%
TP2012172 | TP2012172X | c | S.054 | 30769 | 51045 |  | Build 138 kV line from Benteler to Port Robson (Ckt 1) | [18 empty] | 8781708.73 | 8800000 |  |  | 8784201 | 8796443.31 |  |  | 8784201 | 8784201 | 8784201 | 8784201 |  |  | 8784201 | 8784201 | 8784201 | 8784201 |  |  | 8784201 | 8784201 | 8784201 |  |  | 8784201 | 8784201 | 8784201 | 8784201 |  |  | 8784201 | 8784201 | 8784201 |  |  | 8784201 |  |  | 8784201 | 8784201 | 8784201 | 8784201 |  |  |  |  | 8784201 | 8784201 | 8784201 | 8784201 | 8784201 | 8784201 | 8784201 | 8784201 | 8784201 |  |  | 8784201
TP2012172 | TP2012172 | c | S.054 | 30769 | 51046 | 2014-12-01 | Build 138 kV line from Benteler to Port Robson (Ckt 2) | [18 empty] | 4994499.05 | 5060000 |  |  | 5067699 | 5079348.39 |  |  | 5067699 | 5067699 | 5067699 | 5067699 |  |  | 5067699 | 5067699 | 5067699 | 5067699 |  |  | 5067699 | 5067699 | 5067699 |  |  | 5067699 | 5067699 | 5067699 | 5067699 |  |  | 5067699 | 5067699 | 5067699 |  |  | 5067699 |  |  | 5067699 | 5067699 | 5067699 | 5067699 |  |  |  |  | 5067699 | 5067699 | 5067699 | 5067699 | 5067699 | 5067699 | 5067699 | 5067699 | 5067699 |  |  | 5067699
|  | t | S.055 | Total | Total | 2016-04-13 | Ellerbe Rd - South Shreveport 69 kV Build (TP201154) | [18 empty] | 0 | 0 |  |  | 0 | 8831593.04 |  |  | 9375483.42 | 9375483.42 | 9375483.42 | 9375483.42 | 6.158% | 0% | 9381462.72 | 9375483.42 | 9375483.42 | 9375483.42 | 0.06378% | -0.06374% | 9381462.72 | 9375483.42 | 9375483.42 | 0.06378% | -0.06374% | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 | 0.06378% | 0% | 9381462.72 | 9381462.72 | 9381462.72 | 0% | 0% | 9381462.72 |  |  | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 |  |  | 0% | 0% | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 | 9381462.72 | 0% | 0% | 9381462.72 | [8 empty] | 0% | -100%
TP2012145 | TP2012145 | c | S.055 | 478 | 10615 |  | Forbing Tap - South Shreveport 69 kV | [18 empty] | 0 | 0 |  |  | 0 | 619192.68 |  |  | 641980.68 | 641980.68 | 641980.68 | 641980.68 |  |  | 642202.51 | 641980.68 | 641980.68 | 641980.68 |  |  | 642202.51 | 641980.68 | 641980.68 |  |  | 642202.51 | 642202.51 | 642202.51 | 642202.51 |  |  | 642202.51 | 642202.51 | 642202.51 |  |  | 642202.51 |  |  | 642202.51 | 642202.51 | 642202.51 | 642202.51 |  |  |  |  | 642202.51 | 642202.51 | 642202.51 | 642202.51 | 642202.51 | 642202.51 | 642202.51 | 642202.51 | 642202.51 |  |  | 642202.51 | [10 empty] | Assumed S. Shreveport and Forbing terminal work only
TP2012145 | TP2012145X | c | S.055 | 512 | 10657 |  | Ellerbe Road - Forbing Tap 69 kV Ckt 1 | [18 empty] | 0 | 0 |  |  | 0 | 8212400.36 |  |  | 8733502.74 | 8733502.74 | 8733502.74 | 8733502.74 |  |  | 8739260.21 | 8733502.74 | 8733502.74 | 8733502.74 |  |  | 8739260.21 | 8733502.74 | 8733502.74 |  |  | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 |  |  | 8739260.21 | 8739260.21 | 8739260.21 |  |  | 8739260.21 |  |  | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 |  |  |  |  | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 | 8739260.21 |  |  | 8739260.21 | [10 empty] | Assumed all line work plus Ellerbe Rd terminal work
|  | t | S.056 | Total | Total | 2016-09-10 | Logansport 138 kV (TP2011022) | [18 empty] | 0 | 0 |  |  | 0 | 1111301.77 |  |  | 1556621.42 | 1556621.42 | 1556621.42 | 1556621.42 | 40.07% | 0% | 1558180.61 | 1556621.42 | 1556621.42 | 1556621.42 | 0.1002% | -0.1001% | 1558180.61 | 1556621.42 | 1556621.42 | 0.1002% | -0.1001% | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 0.1002% | 0% | 1558180.61 | 1558180.61 | 1558180.61 | 0% | 0% | 1558180.61 |  |  | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 |  |  | 0% | 0% | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 0% | 0% | 1558180.61 | [8 empty] | 0% | -100%
TP2011022 | TP2011022 | c | S.056 | 30298 | 50336 |  | Install a new 28.8 MVAr capacitor bank at Logansport 138 kV substation | [18 empty] | 0 | 0 |  |  | 0 | 1111301.77 |  |  | 1556621.42 | 1556621.42 | 1556621.42 | 1556621.42 |  |  | 1558180.61 | 1556621.42 | 1556621.42 | 1556621.42 |  |  | 1558180.61 | 1556621.42 | 1556621.42 |  |  | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 |  |  | 1558180.61 | 1558180.61 | 1558180.61 |  |  | 1558180.61 |  |  | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 |  |  |  |  | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 | 1558180.61 |  |  | 1558180.61
|  | t | S.057 | Total | Total | 2016-04-21 | Winnsboro 138 kV (TP2013122) | [18 empty] | 0 | 0 |  |  | 0 | 1140471.94 |  |  | 1230858.46 | 1230858.46 | 1230858.46 | 1230858.46 | 7.925% | 0% | 1231360.51 | 1230858.46 | 1230858.46 | 1230858.46 | 0.04079% | -0.04077% | 1231360.51 | 1230858.46 | 1230858.46 | 0.04079% | -0.04077% | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 0.04079% | 0% | 1231360.51 | 1231360.51 | 1231360.51 | 0% | 0% | 1231360.51 |  |  | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 |  |  | 0% | 0% | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 0% | 0% | 1231360.51 | [8 empty] | 0% | -100%
TP2013122 | TP2013122 | c | S.057 | 30296 | 50334 |  | Install a new 28.8 MVAr capacitor bank at Winnsboro 138 kV substation | [18 empty] | 0 | 0 |  |  | 0 | 1140471.94 |  |  | 1230858.46 | 1230858.46 | 1230858.46 | 1230858.46 |  |  | 1231360.51 | 1230858.46 | 1230858.46 | 1230858.46 |  |  | 1231360.51 | 1230858.46 | 1230858.46 |  |  | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 |  |  | 1231360.51 | 1231360.51 | 1231360.51 |  |  | 1231360.51 |  |  | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 |  |  |  |  | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 | 1231360.51 |  |  | 1231360.51
|  | t | S.058 | Total | Total | 2016-04-01 | Rock Hill-Springridge Pan-Harr REC 138 kV Ckt 1 | [18 empty] | 0 | 0 |  |  | 18845095.45 | 23229161.06 |  | 23.26% | 24727060.23 | 25217060.23 | 25217060.23 | 25217060.23 | 6.448% | 1.982% | 25330929.21 | 25217060.23 | 25217060.23 | 25217060.23 | 0.4516% | -0.4495% | 25330929.21 | 25217060.23 | 25217060.23 | 0.4516% | -0.4495% | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 0.4516% | 0% | 25330929.21 | 25330929.21 | 25330929.21 | 0% | 0% | 25330929.21 |  |  | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 |  |  | 0% | 0% | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 0% | 0% | 25330929.21 | [8 empty] | 0% | -100% | Includes all components in project
TP2010067 | TP2010067 | c | S.058 | 30449 | 50545 |  | Rebuild 27.6 mile 138 kV ine with 1926.9 ACSR/TW. | [18 empty] | 0 | 0 |  |  | 18845095.45 | 23229161.06 |  |  | 24727060.23 | 25217060.23 | 25217060.23 | 25217060.23 |  |  | 25330929.21 | 25217060.23 | 25217060.23 | 25217060.23 |  |  | 25330929.21 | 25217060.23 | 25217060.23 |  |  | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 |  |  | 25330929.21 | 25330929.21 | 25330929.21 |  |  | 25330929.21 |  |  | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 |  |  |  |  | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 | 25330929.21 |  |  | 25330929.21
|  | t | S.059 | Total | Total | 2017-07-01 | Brownlee-North Market 69 kV Rebuild | [18 empty] | 0 | 5900000 |  |  | 0 | 9636180.69 |  |  | 606412.23 | 16078412.23 | 16078412.23 | 16078412.23 | -93.71% | 2551% | 17140808.91 | 16078412.23 | 16078412.23 | 16078412.23 | 6.608% | -6.198% | 17132431.49 | 17132431.49 | 17132431.49 | 6.555% | -6.152% | 17132604 | 17132604 | 17132604 | 17132604 | 0.001007% | 0% | 17132604 | 17132604 | 17132604 | 0% | 0% | 17132604 |  |  | 17132604 | 17132604 | 17132604 | 17132604 |  |  | 0% | 0% | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 0% | 0% | 17132604 | [8 empty] | 0% | -100% | Brownlee Road Station upgrades in-serviced 5/16; remainder of project to be in-serviced 6/17.
TP2009104 | TP2009104 | c | S.059 | 504 | 10649 |  | Rebuild 4.7 mile 69 kV line from Brownlee to North Market | [18 empty] | 0 | 5900000 |  |  | 0 | 9636180.69 |  |  | 606412.23 | 16078412.23 | 16078412.23 | 16078412.23 |  |  | 17140808.91 | 16078412.23 | 16078412.23 | 16078412.23 |  |  | 17132431.49 | 17132431.49 | 17132431.49 |  |  | 17132604 | 17132604 | 17132604 | 17132604 |  |  | 17132604 | 17132604 | 17132604 |  |  | 17132604 |  |  | 17132604 | 17132604 | 17132604 | 17132604 |  |  |  |  | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 | 17132604 |  |  | 17132604
|  | t | S.060 | Total | Total | 2016-12-16 | Valliant-NW Texarkana 345 kV | [18 empty] | 0 | 4700000 |  |  | 4525574.69 | 5020278.69 | -3.711% | 10.93% | 94208721.06 | 99956721.06 | 99956721.06 | 99956721.06 | 1777% | 6.101% | 97244454.87 | 99956721.06 | 99956721.06 | 99956721.06 | -2.713% | 2.789% | 97368971.1 | 97368971.1 | 97368971.1 | -2.589% | 2.658% | 97370354 | 97370354 | 97370354 | 97370354 | 0.00142% | 0% | 97370354 | 97370354 | 97370354 | 0% | 0% | 97370354 |  |  | 97370354 | 97370354 | 97370354 | 97370354 |  |  | 0% | 0% | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 0% | 0% | 97370354 | [8 empty] | 0% | -100% | Northwest Texarkana 345 kV terminal work and 345 kV ine relocations completed November 2015; Also see related PSO project (P.018) and OKTCo project (OKT.009).
TP2009089 | TP2009089 | c | S.060 | 936 | 11236 |  | 345 kV from Valliant substation to NW Texarkana substation | [18 empty] | 0 | 4700000 |  |  | 4525574.69 | 5020278.69 |  |  | 94208721.06 | 99956721.06 | 99956721.06 | 99956721.06 |  |  | 97244454.87 | 99956721.06 | 99956721.06 | 99956721.06 |  |  | 97368971.1 | 97368971.1 | 97368971.1 |  |  | 97370354 | 97370354 | 97370354 | 97370354 |  |  | 97370354 | 97370354 | 97370354 |  |  | 97370354 |  |  | 97370354 | 97370354 | 97370354 | 97370354 |  |  |  |  | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 | 97370354 |  |  | 97370354
|  | t | S.061 | Total | Total | 2016-06-01 | Messick 500/230 kV (TP2011033) | [18 empty] | 0 | 0 |  |  | 0 | 54032914.56 |  |  | 58503883.45 | 59534283.45 | 59534283.45 | 59534283.45 | 8.275% | 1.761% | 59387255.91 | 59534283.45 | 59534283.45 | 59534283.45 | -0.247% | 0.2476% | 58648888.77 | 58648888.77 | 58648888.77 | -1.487% | 1.51% | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 0.001691% | 0% | 58649880.67 | 58649880.67 | 58649880.67 | 0% | 0% | 58649880.67 |  |  | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 |  |  | 0% | 0% | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 0% | 0% | 58649880.67 | [8 empty] | 0% | -100% | Includes all P11033 components: station, land, line connection work
TP2011033 | TP2011033 | c | S.061 | 30495 | 50607 |  | Messick 500/230 kV Transformer Ckt1 | [18 empty] | 0 | 0 |  |  | 0 | 54032914.56 |  |  | 58503883.45 | 59534283.45 | 59534283.45 | 59534283.45 |  |  | 59387255.91 | 59534283.45 | 59534283.45 | 59534283.45 |  |  | 58648888.77 | 58648888.77 | 58648888.77 |  |  | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 |  |  | 58649880.67 | 58649880.67 | 58649880.67 |  |  | 58649880.67 |  |  | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 |  |  |  |  | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 | 58649880.67 |  |  | 58649880.67
|  | c | S.061 | 30495 | 50615 |  | included in 50607 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | t | S.062 | Total | Total | 2017-06-26 | Letourneau 69 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1185000 | 1185000 | 1185000 |  |  | 1244156.8 | 1185000 | 1185000 | 1185000 | 4.992% | -4.755% | 1247291.61 | 1247291.61 | 1247291.61 | 5.257% | -4.994% | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 0% | 0% | 1247291.61 | 1247291.61 | 1247291.61 | 0% | 0% | 1247291.61 |  |  | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 |  |  | 0% | 0% | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 0% | 0% | 1247291.61 | [8 empty] | 0% | -100%
TP2015106 | TP2015106 | c | S.062 | 30598 | 50759 |  | Letourneau 69 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1185000 | 1185000 | 1185000 |  |  | 1244156.8 | 1185000 | 1185000 | 1185000 |  |  | 1247291.61 | 1247291.61 | 1247291.61 |  |  | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 |  |  | 1247291.61 | 1247291.61 | 1247291.61 |  |  | 1247291.61 |  |  | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 |  |  |  |  | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 | 1247291.61 |  |  | 1247291.61
|  | t | S.063 | Total | Total | 2017-12-20 | Brooks Street - Edwards Street 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 5508000 | 5508000 | 5508000 |  |  | 3816677.16 | 5508000 | 5508000 | 5508000 | -30.71% | 44.31% | 4649535.7 | 4649535.7 | 4649535.7 | -15.59% | 18.46% | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | -0.01644% | 0% | 4648771.29 | 4648771.29 | 4648771.29 | 0% | 0% | 4648771.29 |  |  | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 |  |  | 0% | 0% | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 0% | 0% | 4648771.29 | [8 empty] | 0% | -100% | Includes line, ROW, and terminal upgrades. ISD moved out to 2018. Station components were moved to rehab, P14138004 and P14138005 (P14138006/007 are shadows - these two were not included last year) are under TA2015706.
TP2014138 | TP2014138 | c | S.063 | 30895 | 51215 |  | Brooks Street - Edwards Street 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 5508000 | 5508000 | 5508000 |  |  | 3816677.16 | 5508000 | 5508000 | 5508000 |  |  | 4649535.7 | 4649535.7 | 4649535.7 |  |  | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 |  |  | 4648771.29 | 4648771.29 | 4648771.29 |  |  | 4648771.29 |  |  | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 |  |  |  |  | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 | 4648771.29 |  |  | 4648771.29
|  | t | S.064 | Total | Total | 2017-04-01 | Hallsville - Marshall New 69 kV Circuit | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 12938000 | 15870000 | 15870000 |  |  | 17094285.41 | 15870000 | 15870000 | 15870000 | 7.714% | -7.162% | 17159057.35 | 17159057.35 | 17159057.35 | 8.123% | -7.512% | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 0% | 0% | 17159057.35 | 17159057.35 | 17159057.35 | 0% | 0% | 17159057.35 |  |  | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 |  |  | 0% | 0% | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 0% | 0% | 17159057.35 | [8 empty] | 0% | -100% | Includes line, ROW, and Marshall terminal upgrades. BPIDs P13167004, 005, 006, 009, 010, 014 and shadow BPIDs.
TP2013167 | TP2013167X | c | S.064 | 30576 | 50721 |  | Hallsville - Marshall New 69 kV Circuit | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 12938000 | 15870000 | 15870000 |  |  | 17094285.41 | 15870000 | 15870000 | 15870000 |  |  | 17159057.35 | 17159057.35 | 17159057.35 |  |  | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 |  |  | 17159057.35 | 17159057.35 | 17159057.35 |  |  | 17159057.35 |  |  | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 |  |  |  |  | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 | 17159057.35 |  |  | 17159057.35
|  | t | S.065 | Total | Total | 2017-11-09 | Daingerfield - Jenkins Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1835000 | 1835000 | 1835000 |  |  | 2368917.22 | 1835000 | 1835000 | 1835000 | 29.1% | -22.54% | 2385215.9 | 2385215.9 | 2385215.9 | 29.98% | -23.07% | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 0% | 0% | 2385215.9 | 2385215.9 | 2385215.9 | 0% | 0% | 2385215.9 |  |  | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 |  |  | 0% | 0% | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 0% | 0% | 2385215.9 | [8 empty] | 0% | -100% | Includes line and ROW.
TP2013166 | TP2013166 | c | S.065 | 30574 | 50719 |  | Daingerfield - Jenkins Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1835000 | 1835000 | 1835000 |  |  | 2368917.22 | 1835000 | 1835000 | 1835000 |  |  | 2385215.9 | 2385215.9 | 2385215.9 |  |  | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 |  |  | 2385215.9 | 2385215.9 | 2385215.9 |  |  | 2385215.9 |  |  | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 |  |  |  |  | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 | 2385215.9 |  |  | 2385215.9
|  | t | S.066 | Total | Total | 2017-07-01 | Broadmoor - Fort Humbug 69 kV Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 6425000 | 6425000 | 6425000 |  |  | 6480399.04 | 6425000 | 6425000 | 6425000 | 0.8622% | -0.8549% | 6505905.04 | 6505905.04 | 6505905.04 | 1.259% | -1.244% | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 0.158% | 0% | 6516183.71 | 6516183.71 | 6516183.71 | 0% | 0% | 6516183.71 |  |  | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 |  |  | 0% | 0% | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 0% | 0% | 6516183.71 | [8 empty] | 0% | -100% | Includes line and terminal upgrades. Project is in service in 2017.
TP2013165 | TP2013165 | c | S.066 | 30573 | 50718 |  | Broadmoor - Fort Humbug 69 kV Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 6425000 | 6425000 | 6425000 |  |  | 6480399.04 | 6425000 | 6425000 | 6425000 |  |  | 6505905.04 | 6505905.04 | 6505905.04 |  |  | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 |  |  | 6516183.71 | 6516183.71 | 6516183.71 |  |  | 6516183.71 |  |  | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 |  |  |  |  | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 | 6516183.71 |  |  | 6516183.71
|  | t | S.067 | Total | Total | 2017-03-28 | Chamber Springs - Farmington 161 kV Line | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 554275 | 9206275 | 9206275 | 9206275 |  |  | 10563889.59 | 9206275 | 9206275 | 9206275 | 14.75% | -12.85% | 10670271.15 | 10670271.15 | 10670271.15 | 15.9% | -13.72% | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | -0.01378% | 0% | 10668801.15 | 10668801.15 | 10668801.15 | 0% | 0% | 10668801.15 |  |  | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 |  |  | 0% | 0% | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 0% | 0% | 10668801.15 | [8 empty] | 0% | -100%
TP2011147 | TP2011147 | c | S.067 | 451 | 10583 |  | Chamber Springs - Farmington 161 kV Line | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 554275 | 9206275 | 9206275 | 9206275 |  |  | 10563889.59 | 9206275 | 9206275 | 9206275 |  |  | 10670271.15 | 10670271.15 | 10670271.15 |  |  | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 |  |  | 10668801.15 | 10668801.15 | 10668801.15 |  |  | 10668801.15 |  |  | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 |  |  |  |  | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 | 10668801.15 |  |  | 10668801.15
|  | t | S.068 | Total | Total | 2018-05-11 | Evenside - Northwest Henderson 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9731000 |  |  | 0 | 9731000 | 9731000 | 9731000 | 0% | 0% | 11168314.8 | 11168314.8 | 11168314.8 | 14.77% | -12.87% | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 0.02813% | 0% | 11171456.22 | 11171456.22 | 11171456.22 | 0% | 0% | 11171456.22 |  |  | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 |  |  | 0% | 0% | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 0% | 0% | 11171456.22 | [8 empty] | 0% | -100%
TP2010100 | TP2010100 | c | S.068 | 501 | 10646 |  | Evenside - Northwest Henderson 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9731000 |  |  | 0 | 9731000 | 9731000 | 9731000 |  |  | 11168314.8 | 11168314.8 | 11168314.8 |  |  | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 |  |  | 11171456.22 | 11171456.22 | 11171456.22 |  |  | 11171456.22 |  |  | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 |  |  |  |  | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 | 11171456.22 |  |  | 11171456.22
|  | t | S.069 | Total | Total | 2017-04-01 | Hallsville - Longview Heights 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9152000 |  |  | 0 | 9152000 | 9152000 | 9152000 | 0% | 0% | 9930039.32 | 9930039.32 | 9930039.32 | 8.501% | -7.835% | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 0% | 0% | 9930039.32 | 9930039.32 | 9930039.32 | 0% | 0% | 9930039.32 |  |  | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 |  |  | 0% | 0% | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 0% | 0% | 9930039.32 | [8 empty] | 0% | -100% | includes line, ROW, and Longview Hgts terminal upgrades. BPIDs P13167001, 002, 003 and shadow BPIDs.
TP2013167 | TP2013167Y | c | S.069 | 30575 | 50720 |  | Hallsville - Longview Heights 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9152000 |  |  | 0 | 9152000 | 9152000 | 9152000 |  |  | 9930039.32 | 9930039.32 | 9930039.32 |  |  | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 |  |  | 9930039.32 | 9930039.32 | 9930039.32 |  |  | 9930039.32 |  |  | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 |  |  |  |  | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 | 9930039.32 |  |  | 9930039.32
|  | t | S.070 | Total | Total | 2018-05-10 | Linwood - South Shreveport 138 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 7885000 |  |  | 0 | 7885000 | 7885000 | 7885000 | 0% | 0% | 7195411.25 | 7195411.25 | 7195411.25 | -8.746% | 9.584% | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 0.01325% | 0% | 7196364.36 | 7196364.36 | 7196364.36 | 0% | 0% | 7196364.36 |  |  | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 |  |  | 0% | 0% | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 0% | 0% | 7196364.36 | [8 empty] | 0% | -100% | Includes line and ROW, and terminal work at Linwood and South Shreveport. Station work was done under TA2015706 (P14139003/004/503/504)
TP2014139 | TP2014139 | c | S.070 | 30889 | 51207 |  | Linwood - South Shreveport 138 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 7885000 |  |  | 0 | 7885000 | 7885000 | 7885000 |  |  | 7195411.25 | 7195411.25 | 7195411.25 |  |  | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 |  |  | 7196364.36 | 7196364.36 | 7196364.36 |  |  | 7196364.36 |  |  | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 |  |  |  |  | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 | 7196364.36 |  |  | 7196364.36
|  | t | S.071 | Total | Total | 2018-12-13 | IPC 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1254000 |  |  | 0 | 1254000 | 1641000 | 1690000 | 0% | 0% | 1689644.66 | 1689644.66 | 1689644.66 | 2.964% | 0.02103% | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 3.153% | 0% | 1742923.97 | 1742923.97 | 1742923.97 | 0% | 0% | 1742923.97 |  |  | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 |  |  | 0% | 0% | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 0% | 0% | 1742923.97 | [8 empty] | 0% | -100%
TP2017012 | TP2017012 | c | S.071 | 31186 | 51831 |  | IPC 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1254000 |  |  | 0 | 1254000 | 1641000 | 1690000 |  |  | 1689644.66 | 1689644.66 | 1689644.66 |  |  | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 |  |  | 1742923.97 | 1742923.97 | 1742923.97 |  |  | 1742923.97 |  |  | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 |  |  |  |  | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 | 1742923.97 |  |  | 1742923.97
|  | t | S.072 | Total | Total | 2019-03-01 | Ellerbe Road - Lucas 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 6282000 | 7957000 |  |  | --- | 7957000 | 7957000 | 0% | 0% | 9626252.49 | 9626252.49 | 9628141 | 9628141 | 20.98% | 0% | 9628189.94 | 9628189.94 | 9628189.94 | 0.0005083% | 0% | 9628189.94 |  |  | 9628189.94 | 9628189.94 | 9628189.94 | 9628189.94 |  |  | 0% | 0% | 9628189.94 | 9628189.94 | 9628189.94 | 9628189.94 | 9628189.94 | 9628189.94 | 9628189.94 | 9628189.94 | 9628189.94 | 0% | 0% | 9628189.94 | [8 empty] | 0% | -100%
TP2014154 | TP2014154 | c | S.072 | 30762 | 51034 |  | Ellerbe Road - Lucas 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 5590000 | 7046000 |  |  | --- | 7046000 | 7046000 |  |  | 9005866.55 | 9005866.55 | 9007755 | 9007755 |  |  | 9007804 | 9007804 | 9007804 |  |  | 9007804 |  |  | 9007804 | 9007804 | 9007804 | 9007804 |  |  |  |  | 9007804 | 9007804 | 9007804 | 9007804 | 9007804 | 9007804 | 9007804 | 9007804 | 9007804 |  |  | 9007804 | [10 empty] | Includes line, ROW, and fiber transitions.
TP2014154 | TP2014154Y | c | S.072 | 30762 | 51035 |  | Ellerbe Road - Lucas 69 kV Terminal Upgrades | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 692000 | 911000 |  |  | --- | 911000 | 911000 |  |  | 620385.94 | 620385.94 | 620385.94 | 620385.94 |  |  | 620385.94 | 620385.94 | 620385.94 |  |  | 620385.94 |  |  | 620385.94 | 620385.94 | 620385.94 | 620385.94 |  |  |  |  | 620385.94 | 620385.94 | 620385.94 | 620385.94 | 620385.94 | 620385.94 | 620385.94 | 620385.94 | 620385.94 |  |  | 620385.94 | [10 empty] | Includes terminal work at Ellerbe Rd and Lucas.
|  | t | S.073 | Total | Total | 2019-06-01 | Siloam Springs - Siloam Springs City 161 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 661000 | 3858000 |  |  | --- | 3858000 | 3858000 | 0% | 0% | 3813966.16 | 3813966.16 | 3821662 | 3821662 | -1.141% | 0% | 3813966.16 | 3813966.16 | 3813966.16 | -0.2014% | 0% | 3813966.16 |  |  | 3813966.16 | 3813966.16 | 3813966.16 | 3813966.16 |  |  | 0% | 0% | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 0.1719% | 0% | 3820524 | [8 empty] | 0% | -100% | Includes line, ROW, and terminal work at Siloam Springs.
TP2017010 | TP2017010 | c | S.073 | 31131 | 51738 |  | Siloam Springs - Siloam Springs City 161 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 661000 | 3858000 |  |  | --- | 3858000 | 3858000 |  |  | 3813966.16 | 3813966.16 | 3821662 | 3821662 |  |  | 3820524 | 3820524 | 3820524 |  |  | 3820524 |  |  | 3820524 | 3820524 | 3820524 | 3820524 |  |  |  |  | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 | 3820524 |  |  | 3820524
|  | t | S.074 | Total | Total | 2019-04-11 | Figure Five - VBI North 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 1951000 | 1951000 | 0% | 0% | 2910918 | 2910918 | 2910918 | 2910918 | 49.2% | 0% | 2910918 | 2910918 | 2910918 | 0% | 0% | 2910918 |  |  | 2910918 | 2910918 | 2910918 | 2910918 |  |  | 0% | 0% | 2910918 | 2910918 | 2910918 | 2910918 | 2910918 | 3013320 | 3013320 | 2910918 | 2910918 | 0% | 0% | 3013320 | [8 empty] | 3.518% | -100% | A16806004 (A16806504 Shadow) is the line (43% of this BPID, as it includes more than the NTC), and A16806008 (A16806508) is the ROW (10% of this BPID, as it includes more than the NTC), located in the SWEPCo Line Rehab program. Project was not included last year b/c NTC was received after the update, so PIS data was used to get the cost for this project, as it went in-service in 2019.
TA2016806 | TA2016806 | c | S.074 | 51300 | 72066 |  | Figure Five - VBI North 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 1951000 | 1951000 |  |  | 2910918 | 2910918 | 2910918 | 2910918 |  |  | 2910918 | 2910918 | 2910918 |  |  | 2910918 |  |  | 2910918 | 2910918 | 2910918 | 2910918 |  |  |  |  | 2910918 | 2910918 | 2910918 | 2910918 | 2910918 | 3013320 | 3013320 | 2910918 | 2910918 |  |  | 3013320
NOTES:
|  | < | Not above SPP $100,000 BP threshold.
|  | New | New to BP list
|  | c | AEP project component (components sum up to project total)
|  | t | AEP project total
|  | n/a | informational only; not included in calculations
Matched Last Year
Does Not Match Last Year, Needs Updating
Changed from Last Year, Updated
Changes from Previous Update

## Data (hidden)
OpCo | Tmplt Yr | Study | Project ID | Upgrade ID | AEP Project | Description (Project) | Description (Element) | CPP | PS Project ID |  | Work Order | PVID | Complete Date | Loaded Costs | Actual Costs 2011 | Actual Cost 2012 | Actual Cost 2013 | Actual Cost 2014 (YearEnd 2013) | Actual Cost 2015 (YearEnd 2014) | Comments | Closed Projects | Closed Projects | Super Project' | Cost Recovery | lookup
SWEPCO |  | 2006 STEP | 1 | 10001 | S.049 | BANN - KINGS HIGHWAY 69KV CKT 1 | Replace Switch in King Hwy substation | TP2004032 | SI161TXPC |  | 40562168 |  |  |  |  | 27985.83 |  |  |  | under $100k, also Distr asset |  |  | TP2009089 | Socialized | TP2009089
SWEPCO |  | 2006 STEP | 6 | 10006 | S.010 | Tontitown - Elm Springs REC 161 kV | Rebuild line with 2-397 ACSR. Replace 1200 A switch 1045, and bus Elm Springs. | TP2012133 | n/a |  | n/a | [8 empty] | no longer BP per call with SPP 1/19/15 |  |  | TP2009093 | Base Plan | TP2009093
SWEPCO |  | 2006 STEP | 8 | 10008 | S.050 | LONE STAR SOUTH - PITTSBURG 138KV CKT 1 | Replace CT | n/a | n/a |  | n/a |  |  |  |  | 0 |  |  |  | uner $100k; likely O&M |  |  | TP2010091 | Base Plan | #N/A | no go
SWEPCO |  | 2006 STEP | 10 | 10010 | S.044 | PITTSBURG - WINNSBORO 138KV CKT 1 | New 138 kV Line | TP2002006 | 000001025/ETN102422 |  |  |  | 2006-07-01 | 18220000 |  |  |  |  | 13495617.79 |  | closed 2009 |  | TP2010092 | Directly Assigned | TP2010092 | 2016
SWEPCO |  | 2006 STEP | 40 | 10044 | S.044 | NORTH MINEOLA - WINNSBORO 138KV CKT 1 | New 138 kV Line | TP2002006 | 000001043/ETN103558 |  |  |  | 2007-10-01 | 20770000 |  |  |  |  | 13496861.6 |  | closed 2009 |  | TP2011036 | Base Plan | #N/A | no go
SWEPCO |  | 2006 STEP | ? | ? | S.044 | Pittsburg and Mineola station upgrades | stations elements | TP2002006 | 000001042/ETN103557/000001038/ETN103555 |  |  |  | 2007-11-01 | [5 empty] | 2114882.66 |  | closed 2009 |  | TP2011110 | Base Plan | #N/A | no go
SWEPCO |  | 2008-2017 | 343 | 10440 | S.053 | Replace 69 kV switch #9114 Winnsboro/Magnolia | Winnboro/Magnolia | TP2007166 | TP0716601 |  | 41396228 | 28884 | 2010-06-01 | 89000 | 45682 | 45682.07 |  |  |  | under $100k; DISTRIBUTION | closed | closed | TP2012142 | Base Plan | #N/A | no go
SWEPCO |  | 2006 STEP | 42 | 10046 | S.010 | TONTITOWN 345/161KV TRANSFORMER CKT 1 | Install new 345/161 kV Auto and install terminal equipment at Tontitown | TP2012133 | n/a |  | n/a | [8 empty] | no longer BP per call with SPP 1/19/15 |  |  | TP2004031 | Base Plan | TP2004031
SWEPCO |  | SPP-2006-AG3-AFS-11 | 346 | 10443 | S.052 | Forest Hill REC Station to Quitman Station 69 kV switches and bus replacement | Forest Hills - Quitman | TP2007166 | TP0716601 |  | 41396775 | 30007 | 2010-06-01 | 185000 | 66001 | 66001.08 |  |  |  | under $100k; DISTRIBUTION | closed | closed | TP2008126 | Base Plan | TP2008126
SWEPCO |  | 2006 STEP | 43 | 10047 | S.011 | CHAMBER SPRINGS - SILOAM SPRINGS 161KV CKT 1 | New 161 line, Terminal equipment at Chamber Springs and Siloam Springs | TP2012133 | n/a |  | n/a | [8 empty] | no longer BP per call with SPP 1/19/15 |  |  | TP2008127 | Base Plan | #N/A | ShipeR-KR no go
SWEPCO |  | 2006 STEP | 45 | 10049 | S.045 | CHAMBER SPRINGS - TONTITOWN 161KV CKT 1 | Reconductor 666 ACSR (11.6 miles) and 1272 ACSR (.1 mile) to Drake ACCC (2156 ACSR section 0.6 miles is not replaced) and remove the series reactors at Chamber Springs on the Chamber Springs to Tontitown 161 kV line | TP2005152 | 000012672/000012673 |  | 40732945;40932969 | 23274 | 2007-06-01 | 4000000 |  |  |  |  | 2658451.58 |  | closed 4/4/2008 |  | TP2009089 | Socialized | TP2009089
SWEPCO |  | 2008-2017 | 113 | 10786 | S.006 | New 138 kV line from Port Robson-McDade | Caplis-McDade | TP2007165 | 000013997 |  |  |  | 2011-07-01 | 11988300 | 0 | 4152035.47 | 4130431.24 | 4130431.24 | 4130431.24 |  | closed | X | TP2009104 | Base Plan | TP2009104 | 2016
SWEPCO |  | 2008-2017 | 113 | 10786 | S.006 | New 138 kV line from Port Robson-McDade | Caplis-McDade | TP2007165 | 000013998 |  |  |  | 2011-07-01 |  | 0 | 2137076.49 | 2125976.82 | 2125976.82 | 2125976.82 | Shadow to 000013997 | closed | X | TP2009105 | Base Plan | #N/A | no go; Big Sandy-Perdue 6/19
SWEPCO |  | 2008-2017 | 113 | 10786 | S.006 | New 138 kV line from Port Robson-McDade | Caplis-McDade | TP2007165 | 000013999 |  |  |  | 2010-03-20 | 1186000 | 782200.81 | 782412.2 | 782412.2 | 782412.2 | 782412.2 |  | closed | X | TP2010067 | Base Plan | TP2010067 | 2016
SWEPCO |  | 2008-2017 | 113 | 10786 | S.006 | New 138 kV line from Port Robson-McDade | Caplis-McDade | TP2007165 | 000014000 | [5 empty] | 404862.84 | 404971.45 | 404971.45 | 404971.45 | 404971.45 | Shadow to 000013999 | closed | X | TP2010098 | Base Plan | #N/A | no go; Georgia Pacific-Keatchie REC
SWEPCO |  | 2006 STEP | 117 | 10147 | S.046 | CHAMBER SPRINGS - TONTITOWN 345KV CKT 1 | Install new 345 kV line , ROW and terminal equipment at Chamber Springs | TP2002133 | 000007838/000007839/000006116/000006993/000006989/ETN101661 |  |  |  | 2008-05-15 | 14405000 |  |  |  |  | 16318844 |  |  |  | TP2010100 | Base Plan | TP2010100 | 2018
PSO |  | SPP-2005-AG2-AFS-3 | 119 | 10149 | n/a | CACHE - SNYDER 138KV CKT 1 | Replace Snyder wave trap | n/a | n/a |  | n/a | [8 empty] | included in scope of P.004 |  |  | TP2010102 | Base Plan | TP2010102
SWEPCO |  | 2007 STEP | 221 | 10280 | S.047 | FULTON - HOPE 115KV CKT 1 | Replace conductor in Hope Substation | TP2006077 | 000016410/000016438 |  | 41126810 | 27957 | 2009-03-31 | 100000 |  |  |  |  | 787879.55 |  | closed 1/30/2013 |  | TP2010103 | Base Plan | TP2010103
OK TransCo |  | 2009-2018 | 480 | 10617 | OKT.001 | Snyder 138 kV Terminal Addition | Snyder 138 kV Terminal Addition | TP2009013 | TP0901301 |  |  |  | 2010-12-01 | 769700 | 634790 | 706495.57 | 723818.11 |  |  |  | closed | X | TP2010104 | Base Plan | TP2010104 | 2018?;North Mineola-Mineola
OK TransCO |  | SPP Priority Project | 937 | 11237 | OKT.003 | Tulsa Power Station Reactor | Tulsa Power Station | TP2009090 | TP0909001 |  |  |  | 2011-10-01 | 956000 | 0 | 614691.11 | 614752.9 |  |  |  | closed | X | TP2011021 | Base Plan | #N/A | changed to TP2013122 Winnsboro cap; 2016
OK TransCO |  | SPP-2007-AG3-AFS-9 | 902 | 11199 | OKT.004, P.011 | Coffeyville Tap - South Coffeyville City 138 kV Ckt1 | Coffeyville T - South Coffeyville Tap | TP2008079 | TP0807902 |  | OKTco | 29154/29155/32276 | 2011-12-01 | 4966000 | 0 | 3017791.4 | 3017791.4 |  |  |  | closed | X | TP2011022 | Base Plan | TP2011022 | 2016
PSO |  | SPP-2007-AG3-AFS-9 | 902 | 11199 | OKT.004, P.011 | Coffeyville Tap - South Coffeyville City 138 kV Ckt1 | Coffeyville T - South Coffeyville Tap | TP2008079 | 000019010 |  | PSO | 32497 | 2011-12-01 | 363600 | 0 | 0 | 0 |  |  |  | closed | X | TP2011023 | Base Plan | TP2011023 | 2015
PSO |  | SPP-2007-AG3-AFS-9 | 911 | 11208 | OKT.004, P.011 | Coffeyville Farmland - South Coffeyville City | South Coffeyville Tap - City of Coffeyville | TP2008079 | 000019010 |  | PSO | 32275 | 2011-12-01 | 816900 | 0 | 413121.76 | 413121.76 |  |  |  | closed | X | TP2011033 | Socialized | TP2011033 | 2016
OK TransCO |  | SPP-2007-AGI-AFS-12 | 446/454 | 10578/10588 | OKT.004, P.011 | Coffeyville Tap - North Bartesville 138 kV Ckt 1& Bartesville SE -N Bartesville 138 kV | Bartesville SE - Coffeyville T | TP2008079 | TP0807901 |  | OKTco | 28901/32281 | 2011-06-01 | 16546600 | 0 | 8772232.94 | 8724216.24 |  |  |  | closed | X | TP2011147 | Base Plan | TP2011147 | 2017
PSO |  | SPP-2007-AGI-AFS-12 | 446/454 | 10578/10588 | OKT.004, P.011 | Coffeyville Tap - North Bartesville 138 kV Ckt 1& Bartesville SE -N Bartesville 138 kV | Bartesville SE - Dearing | TP2008079 | 000019010 |  | PSO | 32496 | 2011-06-01 |  | 0 | 0 | 0 |  |  |  | closed | X | TP2012144 | Base Plan | TP2012144 | 2016
PSO |  | SPP-2007-AGI-AFS-12 | 446/454 | 10578/10588 | OKT.004, P.011 | Coffeyville Tap - North Bartesville 138 kV Ckt 1& Bartesville SE -N Bartesville 138 kV | Bartesville SE - Dearing | TP2008079 | 000019011 |  | PSO | 29151/29152/31327 | 2011-06-01 | 1598700 | 0 | 1023614.83 | 1080600.85 |  |  |  | closed | X | TP2012145 | Base Plan | TP2012145 | 2016
PSO |  | SPP-2006-AG3-AFS-11 | 288 | 10374 | OKT.005 | Install 345kV terminal at Valliant | Valliant Sub | TP2007167 | 000015835 |  |  | 26130 | 2012-04-01 | 0 | [6 empty] | closed | X | TP2012146 | Base Plan | TP2012146 | 2015
OK Transco |  | SPP-2006-AG3-AFS-11 | 288 | 10374 | OKT.005 | Install 345kV terminal at Valliant | Valliant Sub | TP2007167 | TP0716701 | TP0716701 |  | 31815 | 2012-04-01 | 3951600 |  |  | 4377316 | 4387380.13 | 4387380.13 | closed 1/30/2015 |  |  | TP2012164 | Base Plan | TP2012164 | 2014/2015
SWEPCO |  | SPP-2006-AG3-AFS-11 | 291 | 10377 | S.051 | BANN - LONESTAR ORDINANCE TAP 69KV CKT 1 | Relay at Bann new limits will be 65/72 MVA summer (line conductor/Lonestar switch) and 72/72 MVA winter (Lonestar Switch) | n/a | n/a |  | n/a |  |  |  |  | 0 |  |  |  | uner $100k; likely O&M |  |  | TP2009089 | Socialized | TP2009089
PSO | 2009 | SPP-2005-AG2-AFS-3 | 220 | 10279 | P.001 | Reconductor 81-523 Riverside - Glenpool Explorer | Riverside Station | TP2006087 | 000013909 |  |  |  | 2009-06-01 | 49900 | 15623.36 | [5 empty] | closed | closed-09 | TP2010093 | Base Plan | #N/A | 2019; Clinton City-Thomas Tap
PSO | 2009 | SPP-2005-AG2-AFS-3 | 220 | 10279 | P.001 | Reconductor 81-523 Riverside - Glenpool Explorer | Riverside-Glenpool | TP2006087 | 000013910 |  |  |  | 2009-06-01 | 947000 | 878234.51 | [5 empty] | closed | closed-09 | TP2010094 | Base Plan | TP2010094 | 2015
PSO | 2009 | 2008-2017 | 230 | 10295 | P.002 | Craig Jct. to Broken Bow Dam 138 kV Rebuild - 7.7 miles | Broken Bow - Craig Junction Line | TP2007059 | 000016256 |  |  | 25731 | 2009-05-01 | 6602600 | 4688896.14 | [5 empty] | closed | closed-09 | TP2011036 | Base Plan | #N/A | 2018;Commanche-Walters Jct 138 kV
PSO | 2009 | 2008-2018 | 112 | 10139 | P.003 | 10 Mile 138 kV Line from Sayre to WFEC’s Rebuilt Erick Substation & | Sayre - Erick (WFEC) | TP2006054 | 000015052 |  |  |  | 2009-05-30 | 9005400 | 6820629.49 |  |  |  | 6820629.49 |  | closed | closed-09 | TP2011093 | Base Plan | TP2011093
PSO | 2009 | 2008-2018 | 112 | 10139 | P.003 | 10 Mile 138 kV Line from Sayre to WFEC’s Rebuilt Erick Substation & | Elk City - Sayre | TP2006054 | 000015053 |  |  |  | 2009-05-30 | 805800 | 178034.66 |  |  |  | 178034.66 |  | closed | closed-09 | TP2011150 | Socialized | TP2011150
PSO | 2009 | 2008-2017 | 177 | 10728 | P.003 | 10 Mile 138 kV Line from Sayre to WFEC’s Rebuilt Erick Substation & | Atoka 138 kV Sub | TP2006054 | 000015051 |  |  |  | 2009-10-01 | 2887800 | 3019333.65 | 3035251.15 | 3041696.08 |  | 3041696.08 |  | closed | X | TP2011156 | Base Plan | TP2011156
PSO | 2009 | 2008-2017 | 177 | 10729 | P.003 | 10 Mile 138 kV Line from Sayre to WFEC’s Rebuilt Erick Substation & | Tupelo Substation | TP2006054 | 000015305 |  |  |  | 2010-02-18 | 442800 | 1415705.01 | 1415705.01 | 1415705.01 |  | 1415705.01 |  | closed | X
PSO | 2008 | 2008-2017 | 106 | 10130 | P.004 | Snyder to Altus Jct. 138 kV line | Snyder Station | TP2004147 | 000010817 |  |  | 20059;20425 | 2008-07-21 | 2344528 | 2338981.87 | [5 empty] | closed | closed-09
PSO | 2008 | 2008-2017 | 106 | 10130 | P.004 | Snyder to Altus Jct. 138 kV line | Altus Junction Station | TP2004147 | 000010818 |  |  | 20060;20424;30077 | 2008-05-24 | 2644944 | 2708779.55 | [5 empty] | closed | closed-09
PSO | 2008 | 2008-2017 | 106 | 10130 | P.004 | Snyder to Altus Jct. 138 kV line | Altus Jct-Snyder 138 kV Line | TP2004147 | 000010820 |  |  | 16222;20296 | 2008-07-01 | 8966101 | 8976028.79 | [5 empty] | closed | closed-09
PSO | 2008 | 2008-2017 | 106 | 10130 | P.004 | Snyder to Altus Jct. 138 kV line | PSO Relay Upgrades | TP2004147 | 000011066 |  |  | 20426;20427 | 2008-04-04 | 591848 | 591846.16 | [5 empty] | closed | closed-09
PSO | 2007 | 2006-2016 | 30001 | 50001 | P.005 | PSO - Catoosa 138kV Capacitor Bank | Catoosa; Sta - Inst 138 kV 50 MVAR Cap | TP2005006 | SI114OKPC |  | 40612018 - closed-09 | 20428 | 2006-05-13 | 387742 | 387742 | [5 empty] | closed | 40612018 - closed-09
PSO | 2008 | 2008-2017 | 110 | 10137 | P.006 | Gatorade POD | Pryor Junction Auto | TP2006090 | 000014029 |  |  |  | 2008-04-25 | 1520473 | 1520501.57 |  |  |  |  | WO inservice 4/25/08 in Indus | closed | closed-09
PSO | 2007 | 2006-2016 | 118 | 10148 | P.007 | Elk City CT Upgrades | Elk City; Replace 69 kV CT & jumpers | TP2007015 | SI114OKPC |  | 40935380 - closed-09 | 26651 | 2007-12-07 | 84424 | 84424 | [5 empty] | closed | 40935380 - closed-09
PSO | 2007 | SPP-2005-AG2-AFS-3 | 3 | 10003 | P.008 | Weleetka & Okmulgee Wavetrap replacement 81-805 | Weleetka Power; Wave Trap Replacement | TP2005046 | SI114OKPC |  | 40626676 - closed-09 | 20615 | 2006-03-04 | 56133 | 56133 | [5 empty] | closed | 40626676 - closed-09
PSO | 2007 | SPP-2005-AG2-AFS-3 | 4 | 10004 | P.008 | Weleetka & Okmulgee Wavetrap replacement 81-805 | Okmulgee City; Wave Trap Replacement | TP2005046 | SI167OKPC |  | 40626610 - closed-09 | 20614 | 2006-02-17 | 48929 | 48928.18 |  |  |  |  | Distribution | closed | 40626610 - closed-09
PSO | 2007 | 2006-2016 | 46 | 10050 | P.009 | Replace 600 A switches 1302, 1303, and 1304 at Tulsa Southeast Station on the 81-553 | Tulsa Southeast Upgrade | TP2004033 | SI114OKPC |  | 40831357 - closed-09 | 18620 | 2007-04-14 | 72551 | 72550.73 | [5 empty] | closed | 40831357 - closed-09
PSO |  | SPP-2005-AG1-AFS-2 | 289 | 10375 | P.010 | Wavetrap Clinton City-Foss Tap 69kV Ckt 1 | Clinton City Sub | TP2009011 | SI114OKPC |  | 41396127 - closed | 28892 | 2010-06-01 | 135400 | 96566 | 96565.67 |  |  |  |  | closed | 41396127 - closed
SWEPCO |  | 2007 STEP | 387 | 10505 | P.017 | OKMULGEE - RIVERSIDE STATION 138KV CKT 1 | Replace wave trap at Okmulgee. | n/a | n/a |  | n/a | [8 empty] | cancelled
SWEPCO |  | 2008-2017 | 392 | 10510 | S.032 | Howell-Kilgore 69 kV rebuild | Kilgore-Howell | TP2009012 | 000018814 |  |  | 28886 | 2012-06-01 | 3985900 |  |  | 2776689.61 | 2745695.9 | 2757172.49 | closed 4/29/14 | closed
SWEPCO |  | 2008-2017 | 392 | 10510 | S.032 |  |  | TP2009012 | 000018815 |  |  | SHADOW |  |  |  |  | 1427965 | 1412040.98 | 1417937.41 | closed 4/29/14 | closed
SWEPCO |  | 2009-2018 | 443 | 10575 | S.036 | Tap South Springdale-East Fayetville and build 1.5 miles of 161 kV to New Osborne | Osborne - Osborne Tap | TP2009103 | TP0910301 |  | 41719855;41743173;41840551;41854467 | 30953/34773 | 2013-06-01 | 1750000 |  |  |  | 2021012.6 | 4232223.4 | included T station along with T line per emails from Pennybaker and Rainbolt
OK TransCo |  | SPP-2006-AG2-AFS-4 | 295 | 10381 | P.013,OKT.002 | Coffeyville Tap-Dearing Rebuild 1.09 miles | Coffeyvile Tap-Dearing 138 kV | TP2008013 | TP0801301 |  |  |  | 2010-06-01 | 1007600 | 981860 | 985777.34 | 985777.34 |  |  |  | closed | X
PSO |  | SPP-2006-AG2-AFS-4 | 295 | 10381 | P.013,OKT.002 | Coffeyville Tap-Dearing Rebuild 1.09 miles | Coffeyvile Tap-Dearing 138 kV | TP2008013 | 000017021 |  |  |  | 2010-06-01 | 36000 |  | 22096.84 | 22096.84 |  |  |  | closed | X
SWEPCO |  | 2009-2018 | 443 | 10575 | S.036 |  |  | TP2009103 | TP0910351 |  |  | SHADOW | [5 empty] | 1047109.12 | 2153515.35
SWEPCO |  | 2008 STEP | 449 | 10581 | S.054 | CARTHAGE - ROCK HILL 69KV CKT 1 | Reset CTs at Carthage on the Carthage - Rock Hill line. | n/a | n/a |  | n/a | [8 empty] | under $100k; likely O&M
SWEPCO |  | 2008-2017 | 450 | 10582 | S.033 | EAST CENTERTON - SHIPE ROAD 161KV CKT 1 | All 161 kV line components | TP2008126 | 000018739/000018742 |  | 41388207;41390066;41390174;41390179;41390212;41390213;41704516 |  |  | 1609000 |  |  | 2709658 | 5943226 | 7248433 | refer to TP2008126.xlsx for cost detail | still some w/o open
SWEPCO | 2009 | 2008-2017 | 108 | 10441 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill - N. Market | TP2007057 | 000015383 |  |  |  | 2009-01-30 | 3215700 | 1719257.68 |  |  |  | 1719257.68 |  | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 108 | 10441 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill - N. Market | TP2007057 | 000015384 | [5 empty] | 899873.2 |  |  |  | 899873.2 | Shadow to 000015383 | closed | closed-09
SWEPCO |  | SPP-2006-AG3-AFS-11 | 507 | 10652 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill - Fort Humbug/Ft Humbug | TP2007057 | 000015375 |  |  |  | 2010-06-01 | 5480400 | 3622244.85 | 3622244.85 |  |  | 3622244.85 |  | closed | closed
SWEPCO |  | SPP-2006-AG3-AFS-11 | 507 | 10652 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill - Fort Humbug/Ft Humbug | TP2007057 | 000015376 | [5 empty] | 1871396.27 | 1871396.27 |  |  | 1871396.27 | Shadow to 000015375 | closed | closed
SWEPCO |  | SPP-2006-AG3-AFS-11 | 507 | 10652 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill - Fort Humbug/Ft Humbug | TP2007057 | 000015377 | [5 empty] | 54962.37 | 54962.37 |  |  | 54962.37 |  | closed | closed
SWEPCO |  | SPP-2006-AG3-AFS-11 | 507 | 10652 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill - Fort Humbug/Ft Humbug | TP2007057 | 000015378 | [5 empty] | 28371.18 | 28371.18 |  |  | 28371.18 | Shadow to 000015377 | closed | closed
SWEPCO |  | 2008-2017 | 450 | 10582 | S.033 | EAST CENTERTON - SHIPE ROAD 161KV CKT 1 | All 161 kV line components | TP2008126 | 000018741/000018742 |  |  | SHADOW |  |  |  |  | 1392199 | 3038117 | 3709283 | refer to TP2008126.xlsx for cost detail | still some w/o open
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30144 | 50152 | S.001 | ARSENAL HILL - MCWILLIE STREET 138KV CKT 1 | Replace Arsenal Hill 138KV switches and jumpers | TP2007057 | n/a |  | n/a | [8 empty] | likely included in S.001; 30146/50154
SWEPCO | 2009 | SPP-2006-AG3-AFS-11 | 30145 | 50153 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill - Waterworks | TP2007057 | 000015380 |  |  |  | 2009-06-01 | 4440700 | 1997748.4 | [5 empty] | closed | closed-09
SWEPCO | 2009 | SPP-2006-AG3-AFS-11 | 30145 | 50153 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill - Waterworks | TP2007057 | 000015381 | [5 empty] | 1026361.55 |  |  |  |  | Shadow to 000015380 | closed | closed-09
SWEPCO | 2009 | SPP-2006-AG3-AFS-11 | 30146 | 50154 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill Auto | TP2007057 | 000015386 |  |  |  | 2009-12-01 | 6245400 | 4261802.7 | [5 empty] | closed | closed-09
SWEPCO |  | 2008-2017 | 450 | 10582 | S.033 | Centerton Station | Centerton Station - GLBU 159 | TP2008126 | 000018740 |  | 41390795 | 30372 | 2012-06-01 | 2909000 | [5 empty] | refer to TP2008126.xlsx for cost detail
SWEPCO | 2009 | SPP-2006-AG2-AFS-4 | 224 | 10283 | S.002 | SW Shreveport Station and Area SPP Aggregate Study Projects | SW Shreveport Sub | TP2007060 | 000015408 |  |  |  | 2009-01-01 | 6872800 | 4383325.17 | [5 empty] | closed | closed-09
SWEPCO | 2009 | SPP-2006-AG2-AFS-4 | 224 | 10283 | S.002 | SW Shreveport Station and Area SPP Aggregate Study Projects | SW Shreveport Sub | TP2007060 | 000015409 | [5 empty] | 2248075.11 |  |  |  |  | Shadow to 000015408 | closed | closed-09
SWEPCO | 2009 | SPP-2006-AG3-AFS-11 | 581 | 10744 | S.002 | SW Shreveport Station and Area SPP Aggregate Study Projects | SW Shreveport Tap | TP2007060 | 000015406 |  |  |  | 2009-01-01 | 2552700 | 1170796.66 | [5 empty] | closed | closed-09
SWEPCO | 2009 | SPP-2006-AG3-AFS-11 | 581 | 10744 | S.002 | SW Shreveport Station and Area SPP Aggregate Study Projects | SW Shreveport Tap | TP2007060 | 000015407 | [5 empty] | 600490.54 |  |  |  |  | Shadow to 000015406 | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 107 | 10132 | S.003 | NW Arkansas Area Improvements | Elm Springs 161 kV Subs | TP2007103 | 000016043 |  |  |  | 2008-05-21 | 25288 | 27455.73 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 107 | 10132 | S.003 | NW Arkansas Area Improvements | Elm Springs 161 kV Subs | TP2007103 | 000016044 | [5 empty] | 14106.09 |  |  |  |  | Shadow to 000016043 | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 107 | 10132 | S.003 | NW Arkansas Area Improvements | East Rogers 161 kV Subs | TP2007103 | 000016045 |  |  |  | 2008-05-16 | 807418 | 808427.25 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 107 | 10132 | S.003 | NW Arkansas Area Improvements | East Rogers 161 kV Subs | TP2007103 | 000016046 | [5 empty] | 415290.63 |  |  |  |  | Shadow to 000016045 | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 107 | 10132 | S.003Excl | NW Arkansas Area Improvements | Shipe Road Property Purchase | TP2007103 | 000017397 |  |  |  | 2008-11-01 | 332762 | 0 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 229 | 10292 | S.003 | NW Arkansas Area Improvements | East Centerton - Flint Creek | TP2007103 | 000016047 |  |  | 27714 | 2009-06-01 | 11119200 | 6864974 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 229 | 10292 | S.003 | NW Arkansas Area Improvements | East Centerton - Flint Creek | TP2007103 | 000016048 |  |  | 27714 |  |  | 3527397 |  |  |  |  | Shadow to 000016047 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 229 | 10292 | S.003 | NW Arkansas Area Improvements | East Rogers - N Rogers | TP2007103 | 000016049 |  |  |  | 2009-06-01 | 136700 | 171810.95 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 229 | 10292 | S.003 | NW Arkansas Area Improvements | East Rogers - N Rogers | TP2007103 | 000016050 | [5 empty] | 88255.7 |  |  |  |  | Shadow to 000016049 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 229 | 10293 | S.003D | NW Arkansas Area Improvements | Centerton | TP2007103 | 000017395 |  |  |  | 2009-12-31 | 564200 | 223821.68 |  |  |  |  | Distribution | closed | closed-09
SWEPCO |  | 2008-2017 | 229 | 10294 | S.003 | NW Arkansas Area Improvements | East Centerton - Flint Creek | TP2007103 | 000016047 |  |  | 29033 | 2010-06-01 | 1934200 | 1205436 | 1205435.83 |  |  |  |  | closed | closed
SWEPCO |  | 2008-2017 | 229 | 10294 | S.003 | NW Arkansas Area Improvements | East Centerton - Flint Creek | TP2007103 | 000016048 | [5 empty] | 619650 | 619649.96 |  |  |  | Shadow to 000016047 | closed | closed
SWEPCO |  | 2008-2017 | 450 | 10584 | S.033 | Shipe Road 345/161 kV transformer Ckt 1 | All station components | TP2008126 | 000018738/000018739/000018741 |  | 41390791;41390062;41392374;42106761 |  | 2013-06-01 | 8370000 |  |  |  | see above total | 10283386 | refer to TP2008126.xlsx for cost detail | still some w/o open
SWEPCO | 2009 | 2008-2017 | 225 | 10286&89 | S.004 | Rebuild SWEPCO's North Magazine to Entergy's Danville 161 kV Line | North Magazine - Danville | TP2007114 | 000016294 |  |  |  | 2009-06-01 | 19438200 | 7496710.91 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 225 | 10286&89 | S.004 | Rebuild SWEPCO's North Magazine to Entergy's Danville 161 kV Line | North Magazine - Danville | TP2007114 | 000016295 | [5 empty] | 3851829 |  |  |  |  | Shadow to 000016294 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 225 | 10286&89 | S.004 | Rebuild SWEPCO's North Magazine to Entergy's Danville 161 kV Line | North Magazine - Danville ROW | TP2007114 | 000016433 |  |  |  | 2009-06-01 | 106400 | 76204.07 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 225 | 10286&89 | S.004 | Rebuild SWEPCO's North Magazine to Entergy's Danville 161 kV Line | North Magazine - Danville ROW | TP2007114 | 000016434 | [5 empty] | 39146 |  |  |  |  | Shadow to 000016433 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 225 | 10286&89 | S.004 | Rebuild SWEPCO's North Magazine to Entergy's Danville 161 kV Line | Blue Mountain | TP2007114 | 000016436 |  |  |  | 2009-06-01 | 250400 | 76757.4 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 225 | 10286&89 | S.004 | Rebuild SWEPCO's North Magazine to Entergy's Danville 161 kV Line | Blue Mountain | TP2007114 | 000016437 | [5 empty] | 39664 |  |  |  |  | Shadow to 000016436 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 217 | 10276 | S.005 | Greenwood, Arkansas area Improvements | North Huntington - Midland | TP2007120 | 000016616 |  |  |  | 2009-12-01 | 488600 | 305334.81 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 217 | 10276 | S.005 | Greenwood, Arkansas area Improvements | North Huntington - Midland | TP2007120 | 000016617 | [5 empty] | 156838 |  |  |  |  | Shadow to 000016616 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 218 | 10277 | S.005 | Greenwood, Arkansas area Improvements | North Huntington - Waldron | TP2007120 | 000016618 |  |  |  | 2009-12-01 | 609300 | 409561.14 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 218 | 10277 | S.005 | Greenwood, Arkansas area Improvements | North Huntington - Waldron | TP2007120 | 000016619 | [5 empty] | 210339 |  |  |  |  | Shadow to 000016618 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 218 | 10277 | S.005 | Greenwood, Arkansas area Improvements | Huntington Station | TP2007120 | 000016620 |  |  |  | 2009-12-01 | 114300 | 45737.21 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 218 | 10277 | S.005 | Greenwood, Arkansas area Improvements | Huntington Station | TP2007120 | 000016621 | [5 empty] | 23497 |  |  |  |  | Shadow to 000016620 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 219 | 10278 | S.005 | Greenwood, Arkansas area Improvements | Reeves Road Station | TP2007120 | 000016615 |  |  |  | 2009-12-01 | 4865300 | 4395305.37 | 210315.41 |  |  |  | T only cost shown in column Q; Distribution/Transmission - Asset transfer completed to transmission. | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 219 | 10278 | S.005 | Greenwood, Arkansas area Improvements | Reeves Road Station Tap | TP2007120 | 000016622 |  |  |  | 2009-12-01 | 401900 | 279528.64 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 219 | 10278 | S.005 | Greenwood, Arkansas area Improvements | Reeves Road Station Tap | TP2007120 | 000016623 | [5 empty] | 143464 |  |  |  |  | Shadow to 000016622 | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 219 | 10278 | S.005 | Greenwood, Arkansas area Improvements | Greenwood Distribution | TP2007120 | 000016624 |  |  |  | 2009-12-01 | 94800 | 4909.18 | 0 |  |  |  | T only cost shown in column Q; Distribution | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 219 | 10278 | S.005D | Greenwood, Arkansas area Improvements | Excelsior | TP2007120 | 000016693 |  |  |  | 2009-12-01 | 131400 | 7806.32 | 3046.27 |  |  |  | T only cost shown in column Q; Distribution | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 222 | 10281 | S.005 | Greenwood, Arkansas area Improvements | Reconductor Bonanza T-Bonanza | TP2007120 | 000016611 |  |  |  | 2009-12-01 | 1042000 | 788969.41 | [5 empty] | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 222 | 10281 | S.005 | Greenwood, Arkansas area Improvements | Reconductor Bonanza T-Bonanza | TP2007120 | 000016612 | [5 empty] | 405138 |  |  |  |  | Shadow to 000016611 | closed | closed-09
SWEPCO |  | 2008-2017 | 113 | 10140 | S.006 | Convert Haughton-McDade to 138 kV, 1590 ACSR | Haughton Station | TP2007165 | 000014001 |  |  | 25673 | 2011-12-31 | 2788400 | 0 | 2105041.5 |  | 403000 | 403000 | Distribution, Transfer to T verified in PP | closed | X
SWEPCO |  | 2008-2017 | 113 | 10141 | S.006 | New 138 kV line from Port Robson-McDade | McDade Station | TP2007165 | 000014002 |  |  | 25675 | 2011-07-01 | 2043400 | 0 | 2566304.81 |  | 542000 | 542000 | Distribution, Transfer to T verified in PP | closed | X
SWEPCO |  | 2008-2017 | 113 | 10141 | S.006 | Convert Haughton-McDade to 138 kV, 1590 ACSR | McDade-Haughton | TP2007165 | 000014003 |  |  | 25674 | 2011-12-31 | 17938900 | 0 | 8838706.34 | 8517435.23 | 8517435.23 | 8517435.23 |  | closed | X
SWEPCO |  | 2008-2017 | 450 | 10584 | S.033 | Shipe Road 345/161 kV transformer Ckt 1 | All station components | TP2008126 | 000018738/000018739/000018741 |  | 41390791;41390062;41392374;42106761 | SHADOW | [5 empty] | see above total | 5263365 | refer to TP2008126.xlsx for cost detail | still some w/o open
SWEPCO |  | 2008-2017 | 450 | 10585 | S.033 | Flint Creek - Shipe Road 345 kV Ckt 1 | All 345 kV line components | TP2008126 | 000018739/000018742 |  | 41388204;41390064;41392370;41402424 |  | 2014-04-01 | 46514700 |  |  |  |  | 20845185 | refer to TP2008126.xlsx for cost detail | still some w/o open
SWEPCO |  | 2008-2017 | 450 | 10585 | S.033 | Flint Creek - Shipe Road 345 kV Ckt 1 | All 345 kV line components | TP2008126 | 000018739/000018742 |  | 41388204;41390064;41392370;41402424 | SHADOW | 2014-04-01 | [5 empty] | 10716251 | refer to TP2008126.xlsx for cost detail | still some w/o open
SWEPCO |  |  | 502 | 10647 | S.042 | Northwest Henderson - Poynter 69 kV | Northwest Henderson - Poynter | TP2004031 | P04031001/P04031002/P04031003/P04031004 |  |  | 36689/36690/36691/36692 | 2014-06-01 | 4520000 |  |  |  |  | 3503433.65 |  | not closed yet
SWEPCO |  | 2008-2017 | 113 | 10141 | S.006 | Convert Haughton-McDade to 138 kV, 1590 ACSR | McDade-Haughton | TP2007165 | 000014004 |  |  |  | 2011-12-31 |  | 0 | 4575570.1 | 4410287.59 | 4410287.59 | 4410287.59 | Shadow to 000014003 | closed | X
SWEPCO |  | 2008-2017 | 113 | 10140 | S.006 |  | Rebuild Red Point to Haughton, | TP2007165 | 000014006 |  |  | 25672 | 2012-06-01 |  |  |  | 2547981 | 2547981 | 2547981 |  | closed | X
SWEPCO |  | 2008-2017 | 113 | 10140 | S.006 |  |  | TP2007165 | 000014007 |  |  | SHADOW |  |  |  |  | 1313706 | 1313706 | 1313706 |  | closed | X
SWEPCO |  | 2008-2017 | 113 | 10140 | S.006 | Convert Red Point-Haughton to 138 kv | Red Point | TP2007165 | 000014008 |  |  | 25671 | 2012-06-01 | 11572500 |  |  | 3521644 | 4251628 | 4317797.75 | in-service 7/24/2014 | closed 7/30/2014
SWEPCO |  | 2008-2017 | 113 | 10140 | S.006 | Convert Red Point - Haughton to 138 kV | Wallace Lake - Port Robson - Red Point | TP2007165 | 000014008 |  | 41866720, 418626721, 41866722 | 36876/36877/36878 | 2013-05-01 | 5419000 |  |  |  | see above total |  | WO's 41866720, 418626721, 41866722
SWEPCO |  | 2008-2017 | 113 | 10140 | S.006 |  |  | TP2007165 | 000014009 |  |  | SHADOW |  |  |  |  | 1813031 | 2188083 | 2222080.2 | closed 12/30/2014
SWEPCO |  | 2008-2017 | 113 | 10140 | S.006 |  |  | TP2007165 | 000014009 |  |  | SHADOW | [5 empty] | see above total
SWEPCO | 2009 | 2008-2017 | 113 | 10745 | S.006 | Southeast 138 kV Loop | Port Robson - Caplis | TP2007165 | 000014442 |  |  |  | 2009-06-01 | 6302000 | 3178316.28 |  |  |  | 3178316.28 |  | closed | closed-09
SWEPCO | 2009 | 2008-2017 | 113 | 10745 | S.006 | Southeast 138 kV Loop | Port Robson - Caplis | TP2007165 | 000014443 | [5 empty] | 1632229.19 |  |  |  | 1632229.19 | Shadow to 000014442 | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 113 | 10140 | S.006 | Southeast 138 kV Loop | Port Robson | TP2007165 | 000016487 |  |  |  | 2008-10-01 | 523023 | 528473.21 |  |  |  | 0 | Distribution | closed | closed-09
SWEPCO |  |  | 502 | 10647 | S.042 |  |  | TP2004031 | P04031501/P04031502/P04031503/P04031504 |  |  | SHADOW | [6 empty] | 1785759.92 |  | not closed yet
SWEPCO | 2009 | SPP-2006-AG3-AFS-10A | 30151 | 50159 | S.007 | Linwood 138 kV Station Switch Replacement | Linwood 138 kV Station Switch Replacement | TP2008080 | SI159LAPC |  | 41159900 - closed-09 | 29026 | 2009-05-01 | 82200 | 77750.49 |  |  |  |  | Transferred to T | closed | 41159900 - closed-09
SWEPCO | 2008 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | Dyess - S. Fayetteville Line | TP2002085 | 000013339 |  |  |  | 2008-05-05 | 1589050 | 1589296.96 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | Dyess - S. Fayetteville Line | TP2002085 | 000013340 | [5 empty] | 804626.27 |  |  |  |  | Shadow to 000013339 | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | Dyess Station | TP2002085 | 000013341 |  |  |  | 2008-02-04 | 2061620 | 2059650.84 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | Dyess Station | TP2002085 | 000013342 | [5 empty] | 1071631.72 |  |  |  |  | Shadow to 000013341 | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | N. Fayetteville - Fayetteville Line | TP2002085 | 000013343 |  |  |  | 2008-04-11 | 2723708 | 2757834.18 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | N. Fayetteville - Fayetteville Line | TP2002085 | 000013344 | [5 empty] | 1372657.47 |  |  |  |  | Shadow to 000013343 | closed | closed-09
SWEPCO | 2007 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | N. Fayetteville Station | TP2002085 | 000013345 |  |  |  | 2007-12-19 | 4653412 | 4653954.09 |  |  |  |  | Distribution | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | Fayetteville Station | TP2002085 | 000013346 |  |  |  | 2008-05-30 | 4638902 | 4639692.82 |  |  |  |  | Distribution | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 109 | 10133 | S.008 | Dyess-South Fayetteville 161 kV conversion | NFAYTVL & FAYTVL DISTRIB | TP2002085 | 000015866 |  |  |  | 2008-07-20 | 1316004 | 0 |  |  |  |  | Distribution | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 115 | 10145 | S.009 | NW Texarkana-Alumax Tap-Bann reconductor | Northwest Texarkana - Alumax Tap 138 kV | TP2006130 | 000014667 |  |  |  | 2008-03-04 | 1052264 | 1051939.73 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 115 | 10145 | S.009 | NW Texarkana-Alumax Tap-Bann reconductor | Northwest Texarkana - Alumax Tap 138 kV | TP2006130 | 000014668 | [5 empty] | 540527.98 |  |  |  |  | Shadow to 000014667 | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 115 | 10146 | S.009 | NW Texarkana-Alumax Tap-Bann reconductor | Alumax Tap - Bann 138 kV | TP2006130 | 000014669 |  |  |  | 2008-03-26 | 527514 | 526277.21 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 115 | 10146 | S.009 | NW Texarkana-Alumax Tap-Bann reconductor | Alumax Tap - Bann 138 kV | TP2006130 | 000014670 | [5 empty] | 270388.25 |  |  |  |  | Shadow to 000014669 | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 115 | 10146 | S.009 | NW Texarkana-Alumax Tap-Bann reconductor | Bann Station | TP2006130 | 000014672 |  |  |  | 2008-04-23 | 238882 | 238617.62 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 115 | 10146 | S.009 | NW Texarkana-Alumax Tap-Bann reconductor | Bann Station | TP2006130 | 000014673 | [5 empty] | 122596.03 |  |  |  |  | Shadow to 000014672 | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 115 | 10145 | S.009 | NW Texarkana-Alumax Tap-Bann reconductor | Northwest Texarkana Sation | TP2006130 | 000014674 |  |  |  | 2008-03-04 | 46272 | 46271.41 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2006-2016 | 115 | 10145 | S.009 | NW Texarkana-Alumax Tap-Bann reconductor | Northwest Texarkana Sation | TP2006130 | 000014675 | [5 empty] | 23709.59 |  |  |  |  | Shadow to 000014674 | closed | closed-09
SWEPCO |  | 2008 STEP | 641 | 10842 | S.055 | FOREST HILLS REC - QUITMAN 69KV CKT 1 #2 | Replace two switches at Quitman substation. | n/a | n/a |  | n/a | [8 empty] | cancelled
PSO |  | 2009-2018 | 649 | 10853 | P.015 | Rebuild Lone Star-Locus Grove 115 kV | Locus Grove - Lone Star | TP2009093 | TP0909301 |  |  | 30948/36756 | 2014-06-01 | 2295000 |  |  |  |  | 2246628.57 |  | not closed yet
PSO |  | 2009 STEP | 657 | 10862 | P.006 | PRYOR JUNCTION 115/69KV TRANSFORMER CKT 1 | Replace (3) 600 A switches with 1200 A switches. | TP2006090 | n/a |  | n/a | [8 empty] | included in scope of P.006
SWEPCO | 2007 | 2006-2016 | 41 | 10045 | S.012 | SWEPCO Minor Projects II | South Shreveport | TP2004036 | SI194LAPC |  | 40852589 - closed-09 | 24226 | 2007-07-02 | 72374 | 72373 |  |  |  |  | WO 40852589 | closed | 40852589 - closed-09
SWEPCO | 2007 | 2006-2016 | 41 | 10045 | S.012 | SWEPCO Minor Projects II | South Shreveport | TP2004036 | 000007929 |  | 40852589SWP |  |  |  | 35784 |  |  |  |  | Shadow to 24226 (WO 40852589SWP) | closed | closed-09
SWEPCO | 2007 | 2006-2016 | 44 | 10048 | S.012 | SWEPCO Minor Projects II | Knox Lee - Oak Hill #2 138 kV line | TP2004036 | SI194TXPC |  | TC010906 - closed-09 | 18645 | 2007-07-02 | 51674 | 51674 |  |  |  |  | WO TC010906 | closed | TC010906 - closed-09
SWEPCO | 2007 | 2006-2016 | 44 | 10048 | S.012 | SWEPCO Minor Projects II | Knox Lee - Oak Hill #2 138 kV line | TP2004036 | 000007692 |  | TC010906SWP |  |  |  | 25416 |  |  |  |  | Shadow to 18645 (WO TC010906SWP) | closed | closed-09
SWEPCO | 2007 | 2006-2016 | 5 | 10005 | S.013 | Rock Hill to the Carthage three-terminal intersection point (Carthage "T") 138 kV Rebuild | Carthage REC - Rock Hill 138 kV | TP2004139 | ETN102424 | [10 empty] | included in 10007 | closed | closed-09
SWEPCO | 2007 | 2006-2016 | 7 | 10007 | S.013 | Rock Hill to the Carthage three-terminal intersection point (Carthage "T") 138 kV Rebuild | Carthage REC - Carthage T 138 kV | TP2004139 | ETN102424 |  | 40524234 |  | 2006-04-05 | 3884544 | 3884541.74 | [5 empty] | closed | closed-09
SWEPCO | 2007 | 2006-2016 | 7 | 10007 | S.013 | Rock Hill to the Carthage three-terminal intersection point (Carthage "T") 138 kV Rebuild | Carthage REC - Carthage T 138 kV | TP2004139 | 000010786 |  | 40524234SWP |  | 2006-04-05 | 0 | 1847065.26 |  |  |  |  | Shadow to ETN102424 | closed | closed-09
SWEPCO | 2007 | SPP-2005-AG1-AFS-2 | 48 | 10065 | S.014 | NW HENDERSON WAVETRAP | NW Henderson - Oak Hill 138 kV line | TP2006089 | SI194TXPC |  | 40868222 - closed-09 | 25784 | 2007-07-02 | 54301 | 54301 |  |  |  |  | WO 40868222 | closed | 40868222 - closed-09
SWEPCO | 2007 | SPP-2005-AG1-AFS-2 | 48 | 10065 | S.014 | NW HENDERSON WAVETRAP | NW Henderson - Oak Hill 138 kV line | TP2006089 | 000007692 | [5 empty] | 27400 |  |  |  |  | Shadow to 25784 (WO 40866222SWP) | closed | closed-09
SWEPCO | 2007 | 2006-2016 | 30000 | 50000 | S.015 | SWEPCO - Arsenal Hill 138kV Capacitor Bank | Arsenal Hill 138 kV Device | TP2004148 | SI194LAPC |  | 40668182 - closed-09 | 20454 | 2007-07-02 |  | 247950 |  |  |  |  | WO set up against blanket instead of 000007929 (WO 40668182) | closed | 40668182 - closed-09
SWEPCO | 2007 | 2006-2016 | 30000 | 50000 | S.015 | SWEPCO - Arsenal Hill 138kV Capacitor Bank | Arsenal Hill 138 kV Device | TP2004148 | 000007929 | [5 empty] | 124199 |  |  |  |  | Shadow to 20454 (WO 40668182SWP) | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 227 | 10291 | S.016 | Daingerfield breaker Upgrade | Daingerfield - Jenkins REC 69 kV CB Repl | TP2008017 | SI161TXPC |  | 41112837 - closed-09 | 28480 | 2008-12-31 | 384008 | 389325.92 |  |  |  |  | Transferred to T | closed | 41112837 - closed-09
SWEPCO | 2008 | SPP-2006-AG1-AFS-4 | 120 | 10150 | S.017 | Rebuild Linwood Substation to McWillie Street Substation 138 kV Line | Rebuild Linwood-McWillie | TP2007019 | 000014936 |  |  |  | 2008-06-01 | 3274900 | 1288031.83 | [5 empty] | closed | closed-09
SWEPCO | 2008 | SPP-2006-AG1-AFS-4 | 120 | 10150 | S.017 | Rebuild Linwood Substation to McWillie Street Substation 138 kV Line | Rebuild Linwood-McWillie | TP2007019 | 000014937 | [5 empty] | 661804.68 |  |  |  |  | Shadow to 000014936 | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 113 | 10143 | S.019 | Wallace Lake-Port Robson-Red Point 138kV loop. | Wallace Lake | TP2005142 | 000013992 |  |  |  | 2008-05-09 | 1871200 | 1178692.88 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 113 | 10143 | S.019 | Wallace Lake-Port Robson-Red Point 138kV loop. | Wallace Lake | TP2005142 | 000013993 | [5 empty] | 648047.3 |  |  |  |  | Shadow to 000013992 | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 113 | 10143 | S.019 | Wallace Lake-Port Robson-Red Point 138kV loop. | Wallace Lake - Finney Tap | TP2005142 | 000013994 |  |  |  | 2008-05-09 | 3339500 | 1701506.76 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 113 | 10143 | S.019 | Wallace Lake-Port Robson-Red Point 138kV loop. | Wallace Lake - Finney Tap | TP2005142 | 000013995 | [5 empty] | 874275.69 |  |  |  |  | Shadow to 000013994 | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 113 | 10143 | S.019 | Wallace Lake-Port Robson-Red Point 138kV loop. | Wallace Lake - Cleco | TP2005142 | 000014873 |  |  |  | 2008-04-29 | 219100 | 51292.27 | [5 empty] | closed | closed-09
SWEPCO | 2008 | 2008-2017 | 113 | 10143 | S.019 | Wallace Lake-Port Robson-Red Point 138kV loop. | Wallace Lake - Cleco | TP2005142 | 000014874 | [5 empty] | 26352.72 |  |  |  |  | Shadow to 000014873 | closed | closed-09
SWEPCO |  | SPP-2006-AG3-AFS-11 | 349 | 10449/10450 | S.021 | Reconductor 4 miles of Hope-Turk | Hope - Turk | TP2006077 | 000016409 |  |  |  | 2010-06-01 | 2389000 | 1062944 | 1082212.99 | 1084731.06 | 1084752.85 |  |  | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-11 | 349 | 10449/10450 | S.021 | Reconductor 4 miles of Hope-Turk | Hope - Turk | TP2006077 | 000016432 | [5 empty] | 546859 | 556759.08 | 558053.01 | 558064.18 |  | Shadow to 000016409 | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30153 | 50161 | S.022 | Longwood replace switches upgrade bus | Longwood Station | TP2008014 | SI194LAPC |  | 41315313 | 28831 | 2010-06-01 | 187900 | 0 | 136005.49 | 136006 |  |  | WO 41315313 | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30153 | 50161 | S.022 | Longwood replace switches upgrade bus | Longwood Station | TP2008014 | 000006317 |  |  | 28831 |  |  | 0 | 69876.75 | 69877 |  |  | Shadow to 28831 (WO 41315313SWP) | closed | X
SWEPCO |  | 2008-2017 | 292 | 10378 | S.023 | Reconductor Greggton - Lake Lamond 69 kV line | Greggton - Lake Lamond | TP2008015 | 000016986 |  |  |  | 2010-06-01 | 4047100 | 1823248.41 | 1823248.41 |  |  |  |  | closed | closed
SWEPCO |  | 2008-2017 | 292 | 10378 | S.023 | Reconductor Greggton - Lake Lamond 69 kV line | Greggton - Lake Lamond | TP2008015 | 000017384 | [5 empty] | 1030376.77 | 1030376.77 |  |  |  | Shadow to 000016986 | closed | closed
SWEPCO |  | 2008-2017 | 297 | 10383 | S.023 | Reconductor Quitman - Westwood 69 kV | Grand Saline - Quitman | TP2008015 | 000016988 |  |  |  | 2010-06-01 | 3827100 | 1282478.36 | 1282478.36 |  |  |  |  | closed | closed
SWEPCO |  | 2008-2017 | 297 | 10383 | S.023 | Reconductor Quitman - Westwood 69 kV | Grand Saline - Quitman | TP2008015 | 000017385 | [5 empty] | 659035.35 | 659035.35 |  |  |  | Shadow to 000016988 | closed | closed
SWEPCO |  | 2008-2017 | 296 | 10382 | S.024 | Rebuild/reconductor Dyess-Elm Springs REC | Dyess - Flint Creek | TP2008026 | 000017492 |  |  |  | 2010-06-01 | 6216900 | 3291847.02 | 3291847.02 |  |  |  |  | closed | closed
SWEPCO |  | 2008-2017 | 296 | 10382 | S.024 | Rebuild/reconductor Dyess-Elm Springs REC | Dyess - Flint Creek | TP2008026 | 000017494 | [5 empty] | 1692438.37 | 1692438.37 |  |  |  | Shadow to 000017492 | closed | closed
SWEPCO |  | 2008-2017 | 348 | 10445 | S.024 | Rebuild/reconductor Dyess-Elm Springs REC | Dyess Station | TP2008026 | 000017498 |  |  |  | 2010-06-01 | 34800 | 18514.76 | 18514.76 |  |  |  |  | closed | closed
SWEPCO |  | 2008-2017 | 348 | 10445 | S.024 | Rebuild/reconductor Dyess-Elm Springs REC | Dyess Station | TP2008026 | 000017499 | [5 empty] | 9512.96 | 9512.96 |  |  |  | Shadow to 000017498 | closed | closed
SWEPCO |  | SPP-2006-AG3-AFS-11 | 348 | 10445 | S.024 | Rebuild/reconductor Dyess-Elm Springs REC | Dyess Station | TP2008026 | 000017495 |  |  |  | 2010-06-01 | 223600 | 157428.54 | 157428.54 |  |  |  |  | closed | closed
SWEPCO |  | SPP-2006-AG3-AFS-11 | 348 | 10445 | S.024 | Rebuild/reconductor Dyess-Elm Springs REC | Dyess Station | TP2008026 | 000017496 | [5 empty] | 80997.44 | 80997.44 |  |  |  | Shadow to 000017495 | closed | closed
SWEPCO |  |  | 681 | 10898 | S.041 | Rebuild Broadmoor - Fern Street | Broadmoor - Fern | TP2010103 | P10103002/P10103003/P10103005/P10103006 |  |  | 32971/39107/39108/39110 | 2014-12-01 | 3846600 |  |  |  |  | 3091896.24 |  | not all w/o closed yet
SWEPCO |  | 2009-2018 | 613 | 10784 | S.025 | Replace switch at Diana | Diana Substation | TP2009012 | 000018810 |  |  |  | 2010-12-01 | 91500 | 58688.24 | 58688.24 |  |  |  |  | closed | closed
SWEPCO |  | 2009-2018 | 613 | 10784 | S.025 | Replace switch at Diana | Diana Substation | TP2009012 | 000018811 | [5 empty] | 30153.62 | 30153.62 |  |  |  | Shadow to 000018810 | closed | closed
SWEPCO |  | 2009-2018 | 452 | 10586 | S.026 | XFR - Whitney 138/69 kV | Whitney Station | TP2009012 | 000018812 |  |  |  | 2011-06-01 | 279600 | 0 | 164456.72 | 164456.72 | 164456.72 |  |  | closed | X
SWEPCO |  | 2009-2018 | 452 | 10586 | S.026 | XFR - Whitney 138/69 kV | Whitney Station | TP2009012 | 000018813 |  |  |  | 2011-06-01 |  | 0 | 84683.78 | 84683.78 | 84683.78 |  | Shadow to 000018812 | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30152 | 50160 | S.027 | Replace 138KV breaker, switches and jumpers at Linwood | Powell and Linwood Stations | STARP0910 | 000016708 |  | 41740349 | 30509/30510 | 2012-06-01 | 450200 |  |  | 430017 |  | 184849.77 | WO's 41740349 and 41740333 - Submitted | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30152 | 50160 | S.027 | Replace 138KV breaker, switches and jumpers at Linwood | Powell and Linwood Stations | STARP0910 | 000016708 |  | 41740333 | 30509/30510 | 2012-06-01 | 450200 |  |  |  |  | 236667 | WO's 41740349 and 41740333 - Submitted | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30157 | 50165 | S.028 | Rebuild 266 ACSR and replace switches and jumpers at Texarkana plant | Bloomburg-Texarkana Plant | TP2008027 | 000017829 |  | 41568503 | 28965 | 2012-06-01 | 5786100 |  |  | 3478399.92 | 3478914 | 3454115.82 |  | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30157 | 50165 | S.028 |  |  | TP2008027 | 000017830 |  |  | SHADOW |  |  |  |  | 1789309 | 1789573 | 1776832.12 |  | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-11/2008-2017 | 30156/389 | 50164/10507 | S.028 | Changeout 500 CU jumpers at Texarkana/Replace 69 kV jumpers and switches at Texarkana | Texarkana Plant | TP2008027 | 000017829 |  | 41568501 | 28835 | 2011-12-28 | 33200 |  |  |  |  | 37530.89 |  | closed | X
SWEPCO |  | SPP-2009-AGP2-AFS-6 | 30317 | 50363 | S.029 | Replace Knox Lee wave trap | Knox Lee Sub | TP2010062 | TP1006201 |  | 41778096 | 34736 | 2012-12-01 | 235900 |  |  | 1246386.83 | 1243172 | 256687.06 |  | closed | X
SWEPCO |  | SPP-2009-AGP2-AFS-6 | 30319 | 50365 | S.029 | Replace Pirkey wavetrap and Whitney breakers and wavetrap | Whitney Sub | TP2010062 | TP1006201 |  | 41778130 | 34737 | 2012-12-01 | 726300 |  |  |  |  | 1158231.4 |  | closed | X
SWEPCO |  | SPP-2009-AGP2-AFS-6 | 30319 | 50365 | S.029 |  |  | TP2010062 | TP1006251 |  |  | SHADOW |  |  |  |  | 640366 | 638715 |  |  | closed | X
SWEPCO |  | SPP-2009-AGP2-AFS-6 | 30318 | 50364/50365 | S.029 | Replace breaker and wavetrap at Pirkey | Pirkey Sub | TP2010062 | TP1006201 |  | 41778125 | 32957 | 2012-12-01 | 559700 |  |  |  |  | 466968.98 |  | closed | X
SWEPCO |  |  | 681 | 10898 | S.041 |  |  | TP2010103 | P10103502/P10103503/P10103505/P10103506 |  |  | SHADOW | [6 empty] | 1583813.54 |  | not all w/o closed yet
PSO |  | 2009-2018 | 767 | 11011 | P.012, OKT.006 | Convert 17 Mile Canadian River - McAlester City line from 69 kV to 138 kV | Canadian River - McAlester City | TP2009095 | TP0909503/TP0909504 |  | PSO | 32894/32943/33153 | 2013-05-30 | 675000 |  |  |  | 3242134 | 3305767.14 | includes all PSO components | closed 5/29/2014
SWEPCO |  | SPP-2006-AG3-AFS-10 | 30142 | 50149 | S.030 | Add 345 kv terminal at NW Texarkana | NW Texarkana Sub | TP2006077 | 000016418 |  | 41126845 | 27965 | 2012-04-20 | 1755000 |  |  | 1143126.46 | 1143414.44 | 1143414.44 |  | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-10 | 30142 | 50149 | S.030 |  |  | TP2006077 | 000016446 |  | 41126845SWP | SHADOW |  |  |  |  | 588218 | 588365.56 | 588365.56 |  | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-10/SPP-2006-AG3-AFS-11 | 30142/349 | 50150/10456 | S.030 | Add 345 kv terminal at Turk/Add Turk 345/138 kV Transformer | Turk Sub | TP2006077 | 000016411 |  | 41123043,41863322 | 27958 | 2012-08-31 | 7269000 |  |  | 4950541.21 | 4975712.79 | 4975712.79 |  | closed | X
SWEPCO |  | SPP-2006-AG3-AFS-10/SPP-2006-AG3-AFS-11 | 30142/349 | 50150/10456 | S.030 |  |  | TP2006077 | 000016439 |  | 41123043SWP,41863322SWP | SHADOW |  |  |  |  | 2545320 | 2558252.39 | 2558252.39 |  | closed | X
SWEPCO |  | 2008-2017 | 391 | 10509 | S.031 | Replace 138 kv wave traps at both ends | Lone Star S and Pittsburg Subs | TP2009100 | SI194TXPC |  | 41734271 , 41732928 | 28905/34586 | 2012-06-01 | 284100 |  |  | 0 |  |  | WO's 41734271 and 41732928 | closed | X
OK TransCO |  | 2009-2018 | 767 | 11011 | P.012, OKT.006 | Convert 17 Mile Canadian River - McAlester City line from 69 kV to 138 kV | Canadian River - McAlester City | TP2009095 | TP0909501 |  | OKTco | 31174 | 2013-06-01 | 9800000 |  |  |  | see above total
OK TransCO |  | 2009-2018 | 767 | 11012 | P.012, OKT.006 | Tap Pittsburg - Muskogee 345 kV North of Pittsburg Sub | Candian River | TP2009095 | TP0909502 |  | OKTco | 32896 | 2013-06-01 | 8801100 |  |  |  | see above total
PSO |  | SPP-2007-AG2-AFS-11 | 770 | 11015 | S.039, P.014 | Rebuild 2.45 miles of 795 ACSR 1590ACSR and reset relays | Ashdown West - Craig Junction 138KV CKT | TP2009092 | TP0909201 |  |  | 30947/32548/37608 | 2013-02-01 | 5562500 |  |  |  | 1035333 | 1035552 |  | closed 6/13/14
SWEPCO |  | SPP-2007-AG2-AFS-11 | 770 | 11015 | S.039, P.014 |  | Ashdown West - Craig Junction 138KV CKT | TP2009092 | TP0909203 |  |  | 41017 | 2013-02-01 |  |  |  |  | 2851233.62 | 2726090 |  | closed 7/30/14
SWEPCO |  | SPP-2007-AG2-AFS-11 | 770 | 11015 | S.039, P.014 |  |  | TP2009092 | TP0909253 |  |  | SHADOW | [5 empty] | 1464893.61 | 1590578 |  | closed 7/30/14
SWEPCO |  | 2009 STEP | 875 | 11155 | S.056 | SUGAR HILL 138/69KV TRANSFORMER CKT 1 | Replace 69 kV switch 11985 and 1033 AAC jumpers at Sugar Hill. | n/a | 000016677;000016681 |  | 41518934; 41518934SWP |  |  |  | 23215.78 |  |  |  |  | under $100k | closed 7/28/2011
SWEPCO |  |  | 882 | 11171 | S.040 | Rock Hill - Carthage 69 kV Ckt Rebuild | Rockhill - Carthage | TP2010102 | P10102001/P10102002/P10102003 |  |  | 32969/32970/35512 | 2014-06-01 | 9550200 |  |  |  |  | 6375807.81 |  | closed 1/29/15
SWEPCO |  |  | 882 | 11171 | S.040 |  |  | TP2010102 | P10102501/P10102502/P10102503 |  |  | SHADOW | [6 empty] | 3261229.62 |  | closed 1/29/15
PSO |  | 2009-2018 | 767 | 11183 | P.012, OKT.006 | Rebuild McAlester City Tap, double circuit 138 kv line and eliminate the "T" | Canadian River - McAlester City | TP2009095 | TP0909503/TP0909504 |  | PSO | 32897/32898/32942/33491 | 2013-06-01 | 1529000 |  |  |  | see above total
PSO |  |  | 767 | 11184 | P.012, OKT.006 | Rebuild McAlester City Tap, double circuit 138 kv line and eliminate the "T" | McAlester City Tap and Weleetka Sub | TP2009095 | TP0909504 |  | PSO | 32895 | 2012-10-31 | 1132400 |  |  | 504034 | See below total
OK Transco |  |  | 767 | 11184 | P.012, OKT.006 | Rebuild McAlester City Tap, double circuit 138 kv line and eliminate the "T" | McAlester City 138 kV line extension | TP2009095 | TP0909501/TP0909502 |  | OKTco | 32210/32899 | 2012-06-01 | 6627800 |  |  | 9966686 | 28914235.74 |  | includes all OKTCo components | closed 12/30/2014
SWEPCO |  |  | 1012 | 11331 | S.043 | Diana - Perdue 138 kV | Diana - Perdue | TP2011023 | P11023002/P11023003 |  |  | 36212/36213 | 2014-06-01 | 14332500 |  |  |  |  | 14986466.15 | grand total; L1940163 for Linder Storage Yard in question | not all closed
SWEPCO |  |  | 1012 | 11331 | S.043 |  |  | TP2011023 | P11023502/P11023503 |  |  | SHADOW | [8 empty] | not all closed
SWEPCO |  |  | 1012 | 11331 | S.043 | Diana - Perdue 138 kV Reconductor | Diana - Perdue | TP2011023 | P11023001/P11023004 |  |  | 33836/36230 | 2014-06-01 | [7 empty] | not all closed
SWEPCO |  |  | 503 | 10648 | S.043 | Diana - Perdue 138 kV Reconductor | Diana - Perdue | TP2011023 | [11 empty] | included in 11331
SWEPCO |  |  | 30436 | 50531 | S.043 | New Gladewater - Perdue 138 kV | New Gladewater - Perdue 138 kV Ckt 1 | TP2011023 | [10 empty] | included in 11331 | included in 11331
SWEPCO |  |  | 1012 | 11331 | S.043 |  |  | TP2011023 | P11023501/P11023504 |  |  | SHADOW | [8 empty] | not all closed
SWEPCO |  | SPP-2009-AGPI-AFS-5 | 1023 | 11347 | S.037 | Rebuild 7.11 miles of 397.5 ACSR | Southwest Shreveport- Rockhill | TP2010066 | TP1006601 |  |  | 32961/34419 | 2013-06-01 | 4585200 |  |  |  | 3333774.53 | 3333999.52 |  | closed 4/29/14
SWEPCO |  | SPP-2009-AGPI-AFS-5 | 1023 | 11347 | S.037 |  |  | TP2010066 | TP1006651 |  |  | SHADOW | [5 empty] | 1714410.48 | 1714526.04 |  | closed 4/29/14
SWEPCO |  | SPP-2009-AGP1-AFS-5 | 1024 | 11348 | S.038 | Rebuild 2.49 miles with 1590 ACSR. Replace wavetrap at Whitney Replace metering Ct at Eastman | Eastex Switching Station - Whitney | TP2010064 | TP1006401 |  |  | 32959/34204/34205 | 2013-06-01 | 3095000 |  |  |  | 1741647.18 | 1741647.18 |  | closed 1/30/14
SWEPCO |  | SPP-2009-AGP1-AFS-5 | 1024 | 11348 | S.038 |  |  | TP2010064 | TP1006451 |  |  | SHADOW | [5 empty] | 894592.07 | 894592.07 |  | closed 1/30/14
SWEPCO |  | SPP-2006-AG3-AFS-10 | 30142 | 50148 | S.030 | Build 2-954MCM ACSR 54/7 conductors | NW Texarkana - Turk 345 | TP2006077 | 000013692 |  |  | 25619/26293 | 2012-07-20 | 38410000 |  |  | 25052610.48 | 25168949.07 | 25348982.27
SWEPCO |  | SPP-2006-AG3-AFS-10 | 30142 | 50148 | S.030 |  |  | TP2006077 | 000013693 |  |  | SHADOW |  |  |  |  | 12892756 | 12980426.35 | 13045025.16
SWEPCO | 2009 | SPP-2006-AG3-AFS-11 | 30146 | 50154 | S.001 | Arsenal Hill Station SPP Facility Study Projects | Arsenal Hill Auto | TP2007057 | 000015387 | [5 empty] | 2189463.72 |  |  |  |  | Shadow to 000015386 | closed | closed-09
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30147 | 50155 | S.001 | ARSENAL HILL 138/69KV TRANSFORMER CKT 2 | Replace auto and 69 KV breaker and switches. | TP2007057 | n/a |  | n/a | [8 empty] | likely included in S.001; 30146/50154
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30149 | 50157 | S.024 | DYESS - TONTITOWN 161KV CKT 1 | Replace Dyess wavetrap | TP2008026 | n/a | [10 empty] | included in 10445
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30154 | 50162 | S.004 | MAGAZINE REC - NORTH MAGAZINE 161KV CKT 1 #2 | Replace Jumpers at North Magazine | TP2007114 | n/a |  | n/a | [8 empty] | no specific work done on this component
SWEPCO |  | SPP-2006-AG3-AFS-11 | 30155 | 50163 | S.057 | OKAY - TOLLETTE 69KV CKT 1 | Replace 69 kV switches. | n/a | n/a |  | n/a | [8 empty] | cancelled
SWEPCO |  | SPP-2009-AGP2-AFS-6 | 30316 | 50375 | S.035 | Replace auto with new 450 MVA | Diana Substation | TP2010065 | TP1006501 |  | 41732671 | 32960 | 2013-06-01 | 3795000 |  |  |  | 2869536.57 | 2869537.98 |  | closed 1/30/14
SWEPCO |  | SPP-2009-AGP2-AFS-6 | 30316 | 50375 | S.035 |  |  | TP2010065 | TP1006551 |  |  | SHADOW | [5 empty] | 1475310.82 | 1475311.53 |  | closed 1/30/14
OK Transco |  |  | 30354 | 50405 | OKT.008 | Coweta 69 kV Capacitor | Coweta Tap | TP2011156 | P11156001 | TP1115601 | 42048831 | 36012 | 2014-06-01 | 669000 |  |  |  |  | 1865216.7 | in-service 6/2/2014
OK Transco |  |  | 30346 | 50438 | P.016, OKT.007 | Cornville 138 kV Sub | Cornville | TP2011093 | P11093001/P11093015 |  |  | 34918/36519 | 2014-05-21 | 10780000 |  |  |  |  | 10166424.17 |  | not closed yet
PSO |  |  | 30346 | 50438 | P.016, OKT.007 | Cornville 138 kV Sub | Cornville | TP2011093 | P11093002/P11093003/P11093005/P11093010/P11093011/P11093012/P11093013/P11093014/P11093016 |  |  | 35271/36507/36509/36514/36515/36516/36517/36518/36562 |  | 5300000 |  |  |  |  | 4992922.66 |  | not closed yet
SWEPCO |  | 2008-2017 | 450 | 10582/10584/10585 | S.033 | Multi - Flint Creek - Centerton 345 kV and Centerton-East Centerton 161 kV | Flint Creek - Shipe Road | TP2008126 | 000018738/000018739 |  |  | 11336/16225/28889/30370/30367/30365/30364/16224 | 2014-06-01
SWEPCO |  | 2008-2017 | 450 | 10582/10584/10585 | S.033 |  |  | TP2008126 | 000018741/000018742 |  |  | SHADOW
SWEPCO |  | 2010-2019 | 1081/30148 | 11421/50156 | S.034 | Rebuild Line-Hooks-Lone Star Ordinance 69 kV Ckt 1/Line-Bann-Lone Star Ordinance 69 Kv Ckt 1 | Line-Hooks-Lone Star Ordinance 69 kV Ckt 1/Line-Bann-Lone Star Ordinance 69 Kv Ckt 1 | TP2011024 | P11024001/P11024002/P11024003 |  |  | 33837/35279/35337 | 2013-06-01 | 8177700 |  |  |  | 5692416 | 5695701.35 |  | closed 11/25/14
SWEPCO |  | 2010-2019 | 1081/30148 | 11421/50156 | S.034 |  |  | TP2011024 | P11024501/P11024502/P11024503 |  |  | SHADOW | [5 empty] | 2901439 | 2903126.7 |  | closed 11/25/14
OK Transco |  | HPILS | 30770 | 51047 | OKT.015 | Ellis Customer Project | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation. | TP2012055 | P12055002/P12055003/P12055004 |  |  | 36707/36708/36709 | 2013-10-16 | 4028653.39 | [6 empty] | closed 5/29/2014
OK Transco |  | HPILS | 30750 | 51017 | OKT.012 | Wapanucka Customer Project | Wapanucka 138 kV Station and 1st T-line | TP2012141 | P12141001/P12141005/P12141009 |  |  | 37685/37689/37693 | 2013-12-06 | 7311092.4 |  |  |  |  | 7200873.82 |  | not all closed yet
OK Transco |  | HPILS |  |  | OKT.012 | Wapanucka Customer Project | 2nd T-line (not BP, per Alan Ward) | TP2012141 | P12141006/P12141010 |  |  | 37690/37694 | 2015-12-31 | 7053300 | [5 empty] | NOT BASE PLAN (Boggy Creek portion) | not closed yet
OK Transco |  | HPILS | 30747 | 51014 | P.020, OKT.013 | Grady I Customer Project | Grady - Round Creek 138 kV Ckt 1 | TP2013002 | TP1300203 |  |  | 38694;38696;38701;38702;40293 | 2015-06-01 | 12132497 |  |  |  |  | 9016686.66 | 2014 in-svc components
OK Transco |  | HPILS | 30748 | 51015 | P.020, OKT.013 | Grady I Customer Project | Grady - Phillips 138 kV Ckt 1 and 2 | TP2013002 | TP1300203 |  |  | 38699;38703;39963 | 2015-06-01 | 8318584 |  |  |  |  | 9016686.66 | 2014 in-svc components
PSO |  | HPILS | 30747 | 51014 | P.020, OKT.013 | Grady I Customer Project | Grady - Round Creek 138 kV Ckt 1 | TP2013002 | TP1300201 |  |  | 38695;40348 | 2015-06-01 | [6 empty] | 2015 in-svc components
SWEPCO | 2008 | 2008-2017 | 113 | 10140 | S.006 |  | Port Robson Station | TP2007165 | 000016487 |  |  |  | 2009-06-01 |  |  |  |  | 500000 | 500000 | Distribution, Transfer to T verified in PP
SWEPCO |  | 2007 STEP | 294 | 10380 | S.048 | MINEOLA - NORTH MINEOLA 69KV CKT 1 | Replace Mineola 2 Switches & Breaker | TP2007166 | TP0716601 |  | 41396763 | 28885 | 2010-06-01 | 339100 | 160296 | 160296.1 |  |  |  | Submitted | closed | closed
OK Transco |  | ITP10 | 30361 | 50768 | OKT.010 | Chisholm-Gracemont 345 kV | Chisholm 230 kV | TP2011150 |  |  |  |  | 2018-03-01 | 5326722 | [5 empty] | Base Plan
OK Transco |  | ITP10 | 30361 | 50413 | OKT.010 | Chisholm-Gracemont 345 kV | Chisholm-Gracemont 345 kV Ckt 1(AEP) | TP2011150 |  |  |  |  | 2018-03-01 | 93361588 | [5 empty] | Base Plan
OK Transco |  | ITP10 | 30361 | 50414 | OKT.010 | Chisholm-Gracemont 345 kV | Chisholm 345/230 kV Station | TP2011150 |  |  |  |  | 2018-03-01 | 20410547 | [5 empty] | Base Plan
OK Transco |  | Priority Projects | 936 | 11236 | P.018,S.058,OKT.009 | Valliant-NW Texarkana 345 kV | 345 kV from Valliant substation to NW Texarkana substation | TP2009089 | TP0908901;TP0908904 |  |  | 32040;33216;33219 | 2014-10-01 | 131451250 | [5 empty] | Priority Projects
PSO |  | Priority Projects | 936 | 11236 | P.018,S.058,OKT.009 | Valliant-NW Texarkana 345 kV | 345 kV from Valliant substation to NW Texarkana substation | TP2009089 | TP0908906 |  |  | 33412 | 2014-10-01 | 0 | [5 empty] | Priority Projects
SWEPCO |  | Priority Projects | 936 | 11236 | P.018,S.058,OKT.009 | Valliant-NW Texarkana 345 kV | 345 kV from Valliant substation to NW Texarkana substation | TP2009089 | TP0908903;TP0908953 |  |  | 32042;33218;33220;33408;33409 | 2014-10-01 | 0 | [5 empty] | Priority Projects
PSO |  | SPP-2008-AGP1-AFS-9 | 947 | 11261 | P.019 | Broken Arrow North-South Tap-Oneta 138 kV Ckt 1 | Rebuild 4.33 miles of 795 ACSR with 1590 ACSR | TP2010092 |  |  |  |  | 2015-06-01 | 4400000 | [5 empty] | Base Plan
SWEPCO |  | 2013 ITPNT | 504 | 10649 | S.059 | Brownlee-North Market 69 kV | Rebuild 4.7 mile 69 kV line from Brownlee to North Market with 1233.6 ACSR/TW | TP2009104 | TP0910402;TP0910452 |  |  | 16405;39841;39842;39843 | 2013-06-01 | 12424849 | [5 empty] | Base Plan; expected ISD 12/14/2016
SWEPCO |  | 2013 ITPNT | 30449 | 50545 | S.060 | Rock Hill-Springridge Pan-Harr REC 138 kV Ckt 1 | Rebuild 27.6 mile 138 kV ine with 1926.9 ACSR/TW. | TP2010067 | TP1006702;TP1006752 |  |  | 32962;39880;39881;39882;39883;40844;40845;40846 | 2014-06-01 | 25060655 | [5 empty] | Base Plan; expected ISD 6/1/2016
SWEPCO |  |  | 501 | 10646 | S.061 | Evenside-Northwest Henderson 69 kV | Rebuild 6.4 mile 69 kV line; replace breaker at Evenside. | TP2010100 |  |  |  | 32967 | 2018-06-01 | 11980465 | [5 empty] | Base Plan; expected ISD 6/1/2018;Conceptual
SWEPCO |  |  |  |  | S.062 | North Mineola-Mineola | North Mineola-Mineola | TP2010104 |  |  |  |  | 2018-06-02 | [6 empty] | not sure if this is a go or not
SWEPCO |  | 2010 STEP | 30296 | 50334 | S.063 | Winnsboro 138 kV | Install a new 28.8 MVAr capacitor bank at Winnsboro 138 kV substation | TP2013122 | TP1312201;TP1312251 |  |  | 40492 | 2016-06-01 | 1166400 | [5 empty] | Base Plan; expected ISD 6/1/2016
SWEPCO |  | 2010 STEP | 30298 | 50336 | S.064 | Logansport 138 kV | Install a new 28.8 MVAr capacitor bank at Logansport 138 kV substation | TP2011022 | TP1102201;TP1102251 |  |  | 33833;41113 | 2016-06-01 | 1166400 | [5 empty] | Base Plan; expected ISD 6/1/2016
SWEPCO |  | 2013 ITPNT | 30495 | 50607 | S.065 | Messick 500/230 kV | Messick 500/230 kV Transformer Ckt1 | TP2011033 | TP1103303;TP1103353 |  |  | 34077;38807;40478 | 2013-06-01 | 51877771 | [5 empty] | Base Plan; expected ISD 3/31/2016
SWEPCO |  | 2013 ITPNT | 30495 | 50615 | S.065 | Messick 500/230 kV | Messick 500 kV Terminal Upgrades | TP2011033 | [11 empty] | Included in Messick Station UID 50607
SWEPCO |  |  | 451 | 10583 | S.066 | Chamber Springs-Farmington 161 kV | Rebuild and reconductor 11.1-mile 161 kV line; upgrade wavetraps, CT ratios, and relay settings at Chamber Springs | TP2011147 | TP1114701;TP1114751 |  |  | 37648;39347;39348;39350 | 2013-06-01 | 12705537 | [5 empty] | Base Plan; expected ISD 6/1/2017
SWEPCO |  |  | 30471 | 50567 | S.067 | Dekalb-New Boston 69 kV | Rebuild 13.2 mile line; Upgrade CT ratios and relay settings at New Boston. | TP2012144 | TP1214401;TP1214451 |  | need to get work orders for PP | 37651;39795;39796;39797;39798 | 2013-06-01 | 16548317 |  |  |  |  | 49364.11 | Base Plan; expected ISD 6/1/2015
SWEPCO |  |  | 478 | 10615 | S.068 | Forbing Tap-South Shreveport 69 kV | Rebuild 2.3 mile line from Forbing to South Shreveport with 1233.6 ACSR/TW | TP2012145 | see below | see below | see below | see below | 2013-06-01 | 1221505 | [5 empty] | Base Plan; expected ISD 6/1/2016
SWEPCO |  |  | 512 | 10657 | S.068 | Ellerbe Road-Forbing Tap 69 kV | Rebuild 2.0 mile line from Ellerbe Road to Forbing Road with 1233.6 ACSR/TW | TP2012145 | TP1214501;TP1214551 |  |  | 37652;39404;39405;39406;39411 | 2018-06-01 | 8174689 | [5 empty] | Base Plan; expected ISD 6/1/2016
SWEPCO |  |  | 30472 | 50568 | S.069 | Hardy Street-Waterworks 69 kV | Rebuild 1.6 mile line from Hardy Street to Waterworks with 1233.6 ACSR/TW | TP2012146 | TP1214601;TP1214651 |  |  |  | 2013-06-01 | 7519658 |  |  |  |  | 0 | Base Plan; expected ISD 12/22/2015
SWEPCO |  |  | 30473 | 50569 | S.070 | Midland REC-North Huntington 69 kV | Rebuild 4.0 mile line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington. | TP2012164 | see below | see below | see below | see below | 2013-06-01 | 1829026 |  |  |  |  | 0 | Base Plan; expected ISD 6/1/2015
SWEPCO |  |  | 30474 | 50570 | S.070 | Midland-Midland REC 69 kV | Rebuild 1.3 mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | TP2012164 | see below | see below | see below | see below | 2013-06-01 | 5653353 |  |  |  |  | 0 | Base Plan; expected ISD 6/1/2015
SWEPCO |  |  | 30475 | 50571 | S.070 | Howe Interchange-Midland 69 kV | Rebuild 7.0 mile 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of the line to be rebult is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | TP2012164 | TP1216401;TP1216451 |  |  | 38481;39550;39551;39553;39554;39555 | 2013-06-01 | 9145130 |  |  |  |  | 3741684.51 | Base Plan; expected ISD 6/1/2015
OK TransCO |  |  | 879 | 11158 | OKT.011 | Prattville-Bluebell 138 kV | Rebuild 9.0 mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW | TP2010094 | TP1009402 |  |  | 32955 | 2014-06-01 | 10241314 |  |  |  |  | 0 | Base Plan; expected ISD 5/8/15
SWEPCO |  |  | 479 | 10616 | tbd | Georgia Pacific - Keatchie 138 kV Ckt 1 | GEORGIA-PACIFIC - KEATCHIE REC 138KV CKT 1 | TP2010098old |  |  |  |  | 2016-06-01 | [6 empty] | Re-evaluation
SWEPCO |  | 2014 ITPNT | 1083 | 11423 | tbd | Welsh Reserve - Wilkes 138 kV Ckt 1 | Welsh Reserve - Wilkes 138 kV Ckt 1 Rebuild | [5 empty] | 2019-06-01 | 24880495
PSO |  |  | 30381 | 50461 | tbd | SUB - SHIDLER 138KV OG&E Osage Sub work | Shidler 138 kV | [5 empty] | 2014-04-30 | 399000 | [5 empty] | 100% CIAC; net credit on work orders as of Mar-15
SWEPCO |  |  | 30559 | 50697 | tbd | Chapel Hill REC - Welsh Reserve 138 kV Ckt 1 | Chapel Hill REC - Welsh Reserve 138 kV Ckt 1 Rebuild | TP2013169 |  |  |  |  | 2019-06-01 | 6651694 | [5 empty] | Future
SWEPCO |  |  | 30573 | 50718 | tbd | Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | TP2013165 |  |  |  |  | 2019-06-01 | 6695986 | [5 empty] | Future
SWEPCO |  |  | 30574 | 50719 | tbd | Daingerfield - Jenkins Rec 69 kV Ckt 1 Rebuild | Daingerfield - Jenkins REC T 69 kV Ckt 1 Rebuild | [5 empty] | 2019-06-01 | 2819806 | [5 empty] | Future
SWEPCO |  |  | 30575 | 50720 | tbd | Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | [5 empty] | 2017-06-01 | 8851677 | [5 empty] | Future
SWEPCO |  |  | 30576 | 50721 | tbd | Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | [5 empty] | 2017-06-01 | 15248925 | [5 empty] | Future
SWEPCO |  |  | 30598 | 50759 | tbd | Letourneau Tertiary #1 - Letourneau Tap 69 kV Ckt 1 | Letorneau - Air Liquide Tap 69 kV Ckt 1 | [5 empty] | 2017-06-01 | 2358802 | [5 empty] | Future
OK TransCO |  | HPILS | 30619 | 50802 | tbd | Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | TP2015027 | TP1502702 |  |  | P15027001;P15027002 | 2016-12-31 | 11652107
PSO |  | HPILS | 30619 | 50802 | tbd | Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | TP2015027 | TP1502701 |  |  | P15027003;P150027004 | 2016-12-31 | tbd
SWEPCO |  |  | 30731 | 50990 | S.071 | Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | Rebuild 2.75 mile 69 kV line from Mt. Pleasant to West Mt. Pleasant | TP2013081 |  |  |  |  | 2015-11-29 | 4715419 | [5 empty] | Base Plan; expected ISD 11/29/2015
OK TransCO |  |  | 30746 | 51013 | P.021, OKT.014 | Darlington Road Customer Connection | Construct new 8-mile 138 kV line from Red Rock to Darlington | TP2012112 | TP1211202 |  |  | 37406;37407 | 2015-06-01 | 15277233 |  |  |  |  | 13254470.19
PSO |  |  | 30746 | 51013 | P.021, OKT.014 | Darlington Road Customer Connection | Construct new 8-mile 138 kV line from Red Rock to Darlington | TP2012112 | TP1211201 |  |  |  | 2015-06-01 | [5 empty] | 1725646.85
SWEPCO |  | SPP-2010-AGP1-AFS-8 | 30761 | 51033 | tbd | Cedar Grove - South Shreveport 138 kV | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove. | [5 empty] | 2020-06-01 | 6566217 | [5 empty] | Future
SWEPCO |  | HPILS | 30769 | 51045 | S.072 | Benteler - Port Robson 138 kV Ckt 1 and 2 | Build 138 kV line from Benteler to Port Robson (Ckt 1) | TP2012172 | TP1217201;TP1217251 |  |  |  | 2015-06-01 | 2248743
SWEPCO |  | HPILS | 30769 | 51046 | S.072 | Benteler - Port Robson 138 kV Ckt 1 and 2 | Build 138 kV line from Benteler to Port Robson (Ckt 2) | TP2012172 |  |  |  |  | 2015-06-01 | 2548575
SWEPCO |  |  | 30762 | 51034 | tbd | Ellerbe Road-Lucas 69 kV | Rebuild existing 3.2 mile 69 kV line from Ellerbe Road to Lucas | TP2014154 | TP1415401;TP1415451 |  |  |  | 2019-03-01 | 6629465 | [5 empty] | Base Plan; expected ISD 3/1/2019
SWEPCO |  |  | 30762 | 51035 | tbd | Ellerbe Road-Lucas terminal upgrades | Replace jumpers at Elerbe Road and Lucas; Replace relay panel at Ellerbe Road; Change relay settings at Lucas | TP2014154 |  |  |  |  | 2019-03-01 | 652658 | [5 empty] | Base Plan; expected ISD 3/1/2019
Note on J261: Powerplant shows the work orders tied to the Blanket (?).

## Q3 2023 (hidden)
4Q 2022 Project Tracking Initial Extract
| COMPLETE | [10 empty] | Complete and in-service
| CLOSED OUT | [10 empty] | In-service and all required project close-out documentation supplied by TO. Per BP 7060, Section 13, upgrades reported as closed out this quarter will not be included in subsequent reports.
| DELAY - MITIGATION | [10 empty] | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project
| DELAY - MITIGATION WINDOW | [10 empty] | Behind schedule, interim mitigation pending or project may change but time permits the implementation of project
| IDENTIFIED | [10 empty] | Upgrade identified and included in Board approved study results
| IN SERVICE | [10 empty] | Upgrade is in service, but not all project activities are complete
| NTC - COMMITMENT WINDOW | [10 empty] | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
| NTC-C PROJECT ESTIMATE WINDOW | [10 empty] | Within the NTC-C Project Estimate (CPE) window
| ON SCHEDULE < 4 | [10 empty] | On Schedule within 4-year horizon
| ON SCHEDULE > 4 | [10 empty] | On Schedule beyond 4-year horizon
| RE-EVALUATION | [10 empty] | NTC/NTC-C active; pending re-evaluation
| RFP ISSUED | [10 empty] | Responses for competeitive upgrades are being submitted and/or reviewed
| SUSPENDED | [10 empty] | NTC/GIA suspended
Cost Allocation | NTC ID | PROJECT ID | UPGRADE ID | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Manual CPP2 | CPP | OWNER | PROJECT NAME | UPGRADE NAME | UPGRADE TYPE | IN SERVICE DATE | EcoSys ISD (Updated) | RTO DETERMINED NEED DATE | LATEST NTC ISSUE DATE | SOURCE STUDY | BASELINE ESTIMATE | BASELINE YEAR | BASELINE ESTIMATE WITH ESCALATION | CURRENT COST ESTIMATE | EcoSys EAC (Loaded | BEST FINAL COST | FINAL COST SOURCE | PROJECT STATUS TYPE | FROM BUS NUM | FROM BUS NAME | TO BUS NUM | TO BUS NAME | UPGRADE DESCRIPTION | VOLTAGE | NEW MILES | RECONDUCTOR MILES | VOLTAGE CONVERSION MILES | LETTER OF COMMERCIAL OPERATION REC'D | MOD INFO REC'D | FINAL COST REC'D | GIS DATA | PM | Comments
| 200433 | 31144 | 51764 | [6 empty] | 0 | WFEC | Sub - Tupelo - Tupelo Tap 138 kV Terminal Upgrades | Tupelo 138 kV Terminal Upgrades | Economic | 2021-12-31 |  | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 100000 | 2017 | 110381.289 | 410000 |  | 0 |  | Delay - Mitigation | 505600 | Tupelo | 521071 | TUPELO TAP | Upgrade any necessary terminal equipment at Tupelo to increase the rating of the 138 kV line between Tupelo substation and Tupelo Tap substation. | 138
| 210545 | 81550 | 112435 | [6 empty] | 0 | WFEC | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic | 2021-01-01 |  | 2021-01-01 | 2019-11-18 | 2019 ITP | 1000000 | 2020 | 1025000 | 1000000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Rebuild 2.03 miles of 138 kV line from Kingfisher to East Kingfisher and upgrade any necessary terminal equipment at East Kingfisher and/or Kingfisher to increase the summer emergency rating to 286 MVA | 138
| 210586 | 81553 | 112443 | [6 empty] | 0 | WFEC | Line - Russett - South Brown 138 kV | Russett - South Brown 138 kV Ckt 1 Rebuild | Economic | 2027-12-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 10267390.81 | 2021 | 10524075.5803 | 10267390.81 |  | 0 |  | Delay - Mitigation | 505602 | Brown | 521044 | RUSSETT | Rebuild 18.62 miles of 138 kV line from Russett to South Brown and upgrade terminal equipment at South Brown as needed to achieve a summer emergency rating of 234 MVA | 138
| 210543 | 81557 | 112451 | [6 empty] | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Arnold - Ransom 115kV Terminal Upgrades | Economic | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 462000 | 2020 | 485388.75 | 726694 |  | 0 |  | On Schedule < 4 | 531409 | ARNOLD | 531414 | RANSOM | Upgrade any necessary terminal equipment at Arnold and/or Ransom to increase the summer emergency rating to 165 MVA | 115
| 210543 | 81557 | 112452 | [6 empty] | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Pile - Scott City 115kV Terminal Upgrades | Economic | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 1633500 | 2020 | 1716195.9375 | 437574 |  | 0 |  | On Schedule < 4 | 531432 | PILE | 531433 | SCOTT CITY | Upgrade any necessary terminal equipment at Pile and/or Scott City to increase the summer emergency rating to 229 MVA | 115
| 210543 | 81557 | 112453 | [6 empty] | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Scott City - Setab 115kV Terminal Upgrades | Economic | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 1556500 | 2020 | 1635297.8125 | 467574 |  | 0 |  | On Schedule < 4 | 531433 | SCOTT CITY | 531464 | SETAB | Upgrade any necessary terminal equipment at Scott City and/or Setab to increase the summer emergency rating to 230 MVA | 115
Base Plan | 200386 | 31057 | 51560 | #N/A | #N/A | #N/A | No | Do Not Add (Zonal) | TA2011012 | TA2011012 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2022-11-20 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 25128911.6762 | 20716215 |  | 0 |  | Delay - Mitigation Window | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69 |  |  |  | Y | Y |  | Y | Brent Garret | Prev Comments: Waiting for POD to put in service. No final costs. - (A11012545-closed $1,437,431 / A11012198-in-service $0 / A11012444-open $17,092,906) & TP2018017-closed $2,185,878) * Switches at pittsburg not in-service according to SCADA
Direct Assignment | 210611 | 81474 | 112307 | #N/A | #N/A | #N/A | No | Do Not Add (Direct Assigned) | TP2021310 | TP2021310 | AEP | Sub - Oklaunion 345 kV Capacitive Reactive Power Support | Oklaunion 345 kV Capacitive Reactive Power Support | Generation Interconnection | 2024-10-01 | 2025-02-12 | 2023-05-15 | 2021-05-17 | DISIS-2016-002 | 9453182 | 2021 | 9689511.55 | 25800000 | 25800000 | 0 |  | Delay - Mitigation |  |  |  |  | Install +200Mvar Capacitor Bank(s) at the Oklaunion 345kV substation. | 345 |  |  |  |  | Y |  |  |  | MOD number added 102550
|  | 81483 | 112331 | #N/A | #N/A | #N/A | No | Do Not Add | TP2019285 | TP2019285 | AEP | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2024-09-30 | 2024-09-01 |  |  | GI STUDIES |  |  |  | 1175646 |  | 0 |  | In Service |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating | 138 | 0.04 | [5 empty] | Y |  | GIA Oxbow Solar
| 210540 | 81561 | 112504 | [6 empty] | 0 | OGE | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345kV Terminal Upgrades (OGE) | Economic | 2024-01-01 |  | 2026-01-01 | 2019-11-18 | 2019 ITP | 4139615 | 2020 | 4349183.0094 | 4139615 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment to support a 345kV line from Wekiwa to Sooner rated at summer emergency of 1792 MVA | 345
| 210592 | 81547 | 112509 | [6 empty] | 0 | EKC | Line - Wolf Creek - Blackberry 345 kV | Wolf Creek 345kV Terminal Equipment | Economic | 2025-12-31 |  | 2026-01-01 | 2021-01-21 | 2019 ITP | 11618029 | 2021 | 11908479.725 | 12217322 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wolf Creek to support 345kV line from Wolf Creek to Blackberry rated at 1792 MVA | 345
| 210586 | 81617 | 122577 | [6 empty] | 0 | WFEC | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138kV Ckt 1 Rebuild | Economic | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 2850000 | 2020 | 2994281.25 | 5750000 |  | 0 |  | On Schedule < 4 | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Rebuild 5.09-mile 138 kV line from Anadarko to Gracemont as a double circuit and install/upgrade any necessary terminal equipment to increase the summer emergency rating to 353 MVA for each circuit | 138 |  | 5.07
| 210626 | 81547 | 122598 | [6 empty] | 0 | NEET | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic | 2025-01-01 |  | 2026-01-01 | 2021-12-03 | 2019 ITP | 85168938 | 2021 | 87298161.45 | 85168938 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build a new 345kV line from Wolf Creek to Blackberry with a summer emergency rating of 1792 MVA | 345
| 210578 | 81675 | 122717 | [6 empty] | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2022-08-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 374400 | 2021 | 383760 | 374400 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/345
| 210578 | 81675 | 122718 | [6 empty] | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2022-08-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 | 512650 | GRDA1 345 | Upgrade terminal equipment at GRDA1 161 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/161
| 210586 | 81679 | 122722 | [6 empty] | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Dover Switch - O'Keene 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-12-31 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 910000 | 2021 | 932750 | 910000 |  | 0 |  | Delay - Mitigation | 520882 | DOVER SW | 521016 | OKEENE | Upgrade any necessary terminal equipment, increase clearances, and replace conductor to achieve a summer emergency rating of 136 MVA
| 210650 | 81691 | 122733 | [6 empty] | #N/A | BEPC | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock 230 kV Terminal Upgrades | Economic | 2023-10-01 |  | 2025-01-01 | 2022-03-09 | 2021 ITP | 614000 | 2022 | 614000 | 614000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Whitlock 230 kV for Oahe to Sully Buttes to Whitlock to Glenham 230 kV line.
| 210648 | 81691 | 122734 | [6 empty] | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Oahe 230 kV Terminal Upgrades (WAPA) | Economic |  |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 561800 | 2022 | 561800 | 561800 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade terminal equipment at Oahe 230 kV for the Oahe to Sully Buttes 230 kV line. Re-conductor three spans of line between Oahe 230 kV substation and Sully Buttes 230 kV substation..
| 210639 | 81691 | 122735 | [6 empty] | #N/A | EREC | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes 230 kV Terminal Upgrades | Economic | 2023-11-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 587000 | 2022 | 587000 | 587000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Sully Buttes for Oahe - Sully Buttes - Whitlock 230 kV line
| 210645 | 81694 | 122739 | [6 empty] | #N/A | NPPD | XFR - Columbus 230/115 | Columbus East 230/115 kV transformer | Economic | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 5080000 | 2022 | 5080000 | 5080000 |  | 0 |  | Delay - Mitigation | 640127 | Columbus East | 640126 | Columbus East | Replace the 230/115 kV transformer and any necessary terminal equipment at Columbus East. | 230/115
| 210645 | 81769 | 122741 | [6 empty] | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff - Victory Hill 115kV Ckt 2 | Economic | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 7760000 | 2022 | 7760000 | 7760000 |  | 0 |  | Delay - Mitigation | 640338 | Scottsbluff | 640397 | Victory Hill | Build second 9 mile 115 kV line from Scottsbluff to Victory Hill.
| 210586 | 81617 | 122753 | [6 empty] | 0 | WFEC | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138 kV Ckt 2 Rebuild | Economic | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 1750000 | 2021 | 1793750 | 3330000 |  | 0 |  | On Schedule < 4 | 520814 | ANADARKO | 515802 | Gracemont 138 kV | Rebuild 5.09-mile 138kV line from Anadarko to Gracemont as double circuit and add/upgrade any necessary equipment to increase the achieve a summer emergency rating of 353 MVA for each circuit |  |  | 5.07
| 210589 | 81617 | 122755 | [6 empty] | 0 | OGE | Line - Anadarko - Gracemont 138kV | Gracemont 138 kV Ckt 2 Terminal Equipment | Economic | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 6075003 | 2021 | 6226878.075 | 1124593 |  | 0 |  | On Schedule < 4 | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Install terminal equipment at Gracemont 138 kV to support a second 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 353 MVA | NULL
|  | 81483 | 112332 | #N/A | #N/A | #N/A | No | Do Not Add | TP2019285 | TP2019285 | AEP | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2024-09-30 | 2024-09-01 |  |  | GI STUDIES |  |  |  | 9959548.73 |  | 0 |  | In Service |  |  |  |  | Build a 3-breaker ring bus station on the Lieberman-North Benton 138 kV section of the Lieberman-Red Point 138 kV line to facilitate the new generation interconnection. | 138 | 1.32 | [5 empty] | Y |  | GIA Oxbow Solar
| 210578 | 81675 | 122801 | [6 empty] | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-06-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 312000 | 2021 | 319800 | 312000 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | NULL
| 210578 | 81675 | 122802 | [6 empty] | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-06-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | 0 |  | Delay - Mitigation | 512656 | GRDA1 161 |  |  | Upgrade terminal equipment at GRDA1 161 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | 161
| 210628 | 81717 | 122823 | [6 empty] | 0 | OGE | Multi - Border - Woodward 345 kV Tap | Border - Woodward Tap 345 kV Substation | Economic | 2023-04-01 |  | 2022-01-01 | 2021-11-05 | 2020 ITP | 11500000 | 2021 | 11787500 | 11500000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the existing Border to Woodward 345 kV line 19 miles from the Border station and build a new 345 kV substation or switching station
| 210616 | 81741 | 122848 | [6 empty] | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco 345 kV Terminal Equipment | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 1843729 | 2021 | 1889822.225 | 1843729 |  | 0 |  | On Schedule < 4 | 514801 | Minco 345 kv |  |  | Install terminal equipment at Minco substation 345 kV to support a new 345 kV line from Minco with a summer emergency rating of 1792 MVA | 345
| 210616 | 81741 | 122849 | [6 empty] | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (345 kV) | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 30707951 | 2021 | 31475649.775 | 30707951 |  | 0 |  | On Schedule < 4 |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper and terminals to accommodate cut in of existing Cimarron to Draper 345 kV line. Tie into existing Cimarron to Draper 345 kV line. This description is specific to the 345 kV components. | 345
| 210616 | 81741 | 122850 | [6 empty] | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 1 | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 5003830 | 2021 | 5128925.75 | 5003830 |  | 0 |  | On Schedule < 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
| 210616 | 81741 | 122851 | [6 empty] | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 2 | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 4885649 | 2021 | 5007790.225 | 4885649 |  | 0 |  | On Schedule < 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
| 210616 | 81741 | 122858 | [6 empty] | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Cimarron - Draper 345 kV Terminal Upgrades #2 | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 2541200 | 2021 | 2604730 | 2541200 |  | 0 |  | On Schedule < 4 | 514901 | CIMARRON 345 | 514934 | DRAPER LAKE 345 | Upgrade any necessary terminal equipment on the Cimarron to Draper 345 kV line to achieve a summer emergency rating of 1540 MVA
| 210656 | 81741 | 122863 | [6 empty] | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Midwest 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 65000 | 2021 | 66625 | 65000 |  | 0 |  | On Schedule < 4 | 514946 | MIDWEST TAP 138 |  |  | Upgrade any necessary terminal equipment at Midwest 138 kV on the Midwest to Franklin 138 kV line to achieve a summer emergency rating of 308 MVA
| 210586 | 81679 | 122865 | [6 empty] | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Aspen 138 kV Terminal Upgrades | Economic | 2022-04-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 202500 | 2021 | 207562.5 | 202500 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Aspen to Mooreland 138 kV line to achieve a summer emergency rating of 187 MVA rating
| 210586 | 81679 | 122866 | [6 empty] | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Pic 138 kV Terminal Upgrades | Economic | 2022-04-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 405000 | 2021 | 415125 | 405000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Mooreland to Pic 138 kV line to achieve a summer emergency rating of 187 MVA rating
| 210670 | 81741 | 133085 | [6 empty] | #N/A | NEET | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco - Pleasant Valley 345 kV Ckt 1 | Economic |  |  | 2025-01-01 | 2022-04-28 | 2020 ITP |  |  |  | 57512100 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 34.8 miles of 345 kV line from Minco to Pleasant Valley 345 kV to achieve a 1792 MVA summer emergency rating.
| 210670 | 81741 | 133106 | [6 empty] | #N/A | NEET | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper - Pleasant Valley 345 kV Ckt 2 | Economic |  |  | 2025-01-01 | 2022-04-28 | 2020 ITP |  |  |  | 23400139 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build a second 13.2-mile 345 kV line from Draper 345 kV substation to Pleasant Valley 345 kV substation with a summer emergency rating of 1792 MVA
| 210616 | 81741 | 143176 | [6 empty] | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper 345 kV Terminal Equipment | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 6484533 | 2021 | 6646646.325 | 6484533 |  |  |  | On Schedule < 4 |  |  |  |  | Install a new line terminal at Draper 345 kV to accommodate new 345 kV line from Pleasant Valley.
|  | 81489 | 112333 | #N/A | #N/A | #N/A | No | Do Not Add | TP2021760 | TP2021760 | AEP | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (TOIF) (AEPW) | Generation Interconnection |  | 2023-06-01 |  |  | GI STUDIES |  |  |  | 1388819 | 1704279 | 0 |  | On Schedule < 4 |  |  |  |  | : Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 345 | 0.18 | [5 empty] | Y | James Ball | AEP - 100% / P21760001
| 210645 | 81769 | 143599 | [6 empty] | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 1194000 | 2022 | 1194000 | 1194000 |  |  |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Scottsbluff 115 kV to support a second 115 kV line from Victory Hill. | 115
| 210645 | 81769 | 143600 | [6 empty] | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Victory Hill 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 1129000 | 2022 | 1129000 | 1129000 |  |  |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Victory Hill 115 kV to support a second 115 kV line from Scottsbluff with a summer emergency rating of 264 MVA | 115
| 210648 | 81691 | 143613 | [6 empty] | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes - Whitlock 230 kV Line Clearance Increase | Economic | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 1744800 | 2022 | 1744800 | 1744800 |  |  |  | On Schedule < 4 |  |  |  |  | Increase ground clearance of the Sully Buttes to Whitlock 230 kV line. | 230
| 210648 | 81691 | 143614 | [6 empty] | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock - Glenham 230 kV Clearance Increase | Economic | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 5845900 | 2022 | 5845900 | 5845900 |  |  |  | On Schedule < 4 |  |  |  |  | Increase ground clearance of the Whitlock - Glenham 230 kV. | 230
| 210656 | 92184 | 143786 | [6 empty] | #N/A | OGE | Sub - Cleo Corner 69 kV & Cleo Junction 69 kV | Cleo Corner 69 kV Terminal Upgrades | Economic |  |  | 2023-01-01 | 2022-03-11 | 2021 ITP | 168228 | 2022 | 168228 | 168228 |  | 0 |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at the Cleo Corner 69 kV substation | 69
| 210644 | 92238 | 144142 | [6 empty] | #N/A | TSGT | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (TSGT) | Economic | 2023-12-13 |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 380321 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
| 210645 | 92238 | 144143 | [6 empty] | #N/A | NPPD | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (NPPD) | Economic | 2023-12-31 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 281000 | 2022 | 281000 | 281000 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
|  | 30959 | 51338 | [6 empty] | 0 | EKC | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Burns 345kV (GEN-2014-001 NU) | Generation Interconnection | 2021-07-08 |  |  |  | GI STUDIES |  |  |  | 2098946 |  | 0 |  | In Service |  |  |  |  | Construct new terminal extension of the bus north to add another rung to the bus. Equipment includes two (2) 345kV breakers, four (4) 345kV switches, bus work, and all associated yard and conduit work.
|  | 30959 | 51360 | [6 empty] | 0 | EKC | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 TOIF) | Generation Interconnection | 2021-07-28 |  |  |  | GI STUDIES |  |  |  | 1674997 |  | 0 |  | In Service |  |  |  |  | Install three (3) 345 kV arresters, one (1) 345 kV 3000 Amp motor-operated switch, three (3) 345 kV arrester stands, one (1) 345 kV full tension dead-end structure, and one (1) 3-phase bus support into new Transmission Owner GEN-2014-001 Point of Interconnection substation. The estimate also includes three (3) 345 kV VTs, three (3) 345 kV CTs, and revenue interconnection metering plus all other associated yard, cable, grounding, communication, and conduit work.
|  | 51239 | 71933 | [6 empty] | 0 | NPPD | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generation Interconnection | 2024-04-01 |  |  |  | GI STUDIES |  |  |  | 4700000 |  |  |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345kV Substation - Install 345kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformers, potential transformers, and associated and miscellaneous material.; One (1) approximately five (5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Holt County 345 kV substation.
|  | 51239 | 71934 | [6 empty] | 0 | NPPD | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generation Interconnection | 2024-04-01 |  |  |  | GI STUDIES |  |  |  | 5900000 |  |  |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
|  | 51255 | 71970 | [6 empty] | #N/A | WFEC | Sub - Snyder 138kV (WFEC) - GEN-2015-013 Addition | Snyder 138kV (WFEC) - GEN-2015-013 Addition (NU) | Generation Interconnection | 2019-08-15 |  |  |  | GI STUDIES |  |  |  | 1700000 |  |  |  | On Schedule < 4 | 521052 | SNYDER |  |  | Snyder 138kV Substation: Install one (1) new line terminal, one (1) 2000A circuit breaker, line relaying, disconnect switches, additional 4” IPS aluminum buss, and associated equipment. | [5 empty] | #N/A | #N/A
|  | 51261 | 71982 | [6 empty] | 0 | NPPD | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Belvidere – Fairbury 115kV circuit #1 | Generation Interconnection | 2019-11-01 |  |  |  | GI STUDIES |  |  |  | 1700000 |  |  |  | Re-evaluation |  |  | 640169 | Fairbury | NPPD Belvidere – Fairbury 115kV circuit #1: uprate Belvidere – Fairbury to at least 107 MVA | 115/115 |  |  |  | Y
|  | 51261 | 71983 | [6 empty] | 0 | NPPD | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Beatrice – Harbine 115kV circuit #1 | Generation Interconnection | 2019-11-01 |  |  |  | GI STUDIES |  |  |  | 900000 |  |  |  | Re-evaluation | 640076 | Beatrice | 640208 | Harbine | NPPD Beatrice – Harbine 115kV circuit #1: uprate Beatrice – Harbine to at least 102 MVA | 115/115 |  |  |  | Y
|  | 51283 | 72032 | [6 empty] | 0 | EKC | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generation Interconnection | 2019-12-01 |  |  |  | GI STUDIES |  |  |  | 591193 |  | 0 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51283 | 72033 | [6 empty] | 0 | EKC | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU) | Generation Interconnection | 2019-12-01 |  |  |  | GI STUDIES |  |  |  | 13383989 |  | 0 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation - Non-Shared Network Upgrades: Construct three (3) 345kV 4000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Allowance for Funds Used During Construction (AFUDC) and Contingency funds are included in this cost estimate.
|  | 51283 | 72034 | [6 empty] | 0 | OGE | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generation Interconnection | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 20000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Oklahoma Gas and Electric Company – Checking and Verifying Relay Settings
|  | 51332 | 82126 | [6 empty] | 0 | OGE | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (TOIF) | Generation Interconnection | 2022-10-14 |  |  |  | GI STUDIES |  |  |  | 1099958 |  | 0 |  | On Schedule < 4 | 515800 | Gracemont 345kv |  |  | Transmission Owner Gracemont Interconnection Substation: Transmission Owner Interconnection Facilities 345kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51332 | 82127 | [6 empty] | 0 | OGE | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (NU) | Generation Interconnection | 2022-10-14 |  |  |  | GI STUDIES |  |  |  | 1025042 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner Gracemont Interconnection Substation - Non-Shared Network Upgrades install one (1) 3000A circuit breakers, control panel replacement, line relaying, disconnect switches, and all other associated work and materials.
|  | 51333 | 82128 | [6 empty] | 0 | OGE | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generation Interconnection | 2022-10-15 |  |  |  | GI STUDIES |  |  |  | 1099958 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation: Transmission Owner Interconnection Facilities Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51333 | 82129 | [6 empty] | 0 | OGE | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generation Interconnection | 2022-10-15 |  |  |  | GI STUDIES |  |  |  | 9213042 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation - Non-Shared Network Upgrades* Install three (3) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
|  | 81489 | 112334 | #N/A | #N/A | #N/A | No | Do Not Add | TP2021760 | TP2021760 | AEP | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (AEPW) | Generation Interconnection | 2023-05-01 | 2023-06-01 |  |  | GI STUDIES |  |  |  | 17798882 | 7067936.0422 | 0 |  | In Service |  |  |  |  | Construct new 345 kV four (4) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators ,and all other associated work and materials. | 345 | 0.32 | [5 empty] | Y | James Ball | AEP - 39.71% / Treasure Island
|  | 81491 | 112337 | #N/A | #N/A | #N/A | No | Do Not Add | TP2019265 | TP2019265 | AEP | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (TOIF) (AEPW) | Generation Interconnection |  | 2023-05-11 |  |  | GI STUDIES |  |  |  | 918474 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 138 | 0.04 | [5 empty] | Y | Chadwick Bell
|  | 81491 | 112338 | #N/A | #N/A | #N/A | No | Do Not Add | TP2019265 | TP2019265 | AEP | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (Non-Shared NU) (AEPW) | Generation Interconnection |  | 2023-05-11 |  |  | GI STUDIES |  |  |  | 7400346 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct new 138 kV three (3) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 138 | [6 empty] | Y | Chadwick Bell
Base Plan | 210623 | 81500 | 112360 | #N/A | #N/A | #N/A | No | Base Plan - Add in Future (2026) | TP2019245 | TP2019245 | AEP | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | 2026-05-01 | 2026-05-01 | 2021-06-01 | 2021-11-05 | 2019 ITP | 41100000 | 2020 | 43180687.5 | 46270466 | 41667013 | 0 |  | Delay - Mitigation | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 27 breakers at Riverside Station 138 kV with 90 kA breakers and expand substation as necessary to accommodate physically larger breakers | 138 | 1.56 |  |  |  | Y |  | Y | Brad Duvall
Base Plan | 210544 | 81501 | 112361 | TA2019024 | #N/A | TA2019024 | Yes | Base Plan - Add in Future (2025) | TA2019024 | TA2019024 | AEP | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | 2024-10-30 | 2024-10-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4645175.5906 | 4194065 | 3841496 | 0 |  | Delay - Mitigation | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138 |  |  |  |  | Y |  | Y | Nathan Ingram | NTC Work 2 BPIDs Station & Removal - A19024004 & A19024002
Base Plan | 210544 | 81520 | 112389 | TP2020033 | #N/A | TP2020033 | Yes | Already Added | TP2020033 | TP2020033 | AEP | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | 2022-05-27 | 2022-06-23 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 7064651.2565 | 6724237 | 6451699 | 0 |  | In Service | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2 |  |  |  | Y |  | Y | Larry Oden | P20033001, 2, 3, & 6
Base Plan | 210544 | 81523 | 112393 | TP2020033 | #N/A | TP2020033 | Yes | Already Added | TP2020033 | TP2020033 | AEP | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | 2021-11-17 | 2021-11-17 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1340497.05 | 1549008 | 1550669 | 0 |  | Complete | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5 |  |  | Y |  | Y | Larry Oden | P20033005 & P20033005
|  | 81488 | 112339 | [6 empty] | 0 | WAPA | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2023-12-29 |  |  |  | GI STUDIES |  |  |  | 250000 |  | 0 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 81488 | 112340 | [6 empty] | 0 | WAPA | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2023-12-29 |  |  |  | GI STUDIES |  |  |  | 8805000 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 230 kV switchyard on the Oahe - Fort Thompson North 230 kV transmission that will consist of a three (3) breaker ring bus, three (3) 230 kV power circuit breakers, nine (9) 230 kV disconnect switches, instrument transformers, associated control and protection equipment, high voltage bus, three (3) line take-off structures, conductor, overhead optical ground wire, communication equipment, and a control building.
|  | 81495 | 112353 | [6 empty] | 0 | SPS | XTO to Cornell GEN-2016-177 Interconnection Costs | XTO to Cornell GEN-2016-177 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-177 (17.0 MW/Gas Turbine) into the POI at XTO_Cornell 115kV.
| 210609 | 81591 | 122537 | [6 empty] | 0 | OGE | Device - Border 345kV Capacitive Reactive Support | Border 345kV Capacitive Reactive Support | Generation Interconnection | 2024-04-20 |  | 2023-04-20 | 2021-05-17 | DISIS-2016-002 | 3996000 | 2021 | 4095900 | 3996000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Install + 275 MVAR Capacitor Bank(s) at Border 345 kV.
|  | 81594 | 122540 | [6 empty] | 0 | SPS | Device - Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002-1) | Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  |  | GI STUDIES |  |  |  | 7365886 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install + 100 MVAR Capacitor Bank(s) at Crossroads 345 kV. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81600 | 122546 | [6 empty] | 0 | SPS | Line - Crossroads - Tolk 345 kV Ckt 1 | Crossroads - Tolk 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-01 |  |  |  | GI STUDIES |  |  |  | 184651 |  | 0 |  | On Schedule < 4 |  |  |  |  | Replace approximately four structures on the Crossroads - Tolk 345 kV line to achieve a minimum rating of 956 MVA. Network Upgrade shared among four requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81599 | 122547 | [6 empty] | 0 | SPS | Line - Crossroads - Eddy County 345 kV Ckt 1 | Crossroads - Eddy County 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2022-12-15 |  |  |  | GI STUDIES |  |  |  | 210533 |  |  |  | On Schedule < 4 |  |  |  |  | Replace two 345 kV structures, wave traps (3X), and jumpers to achieve minimum emergency rating of 956 MVA. Network Upgrade Shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81606 | 122554 | [6 empty] | 0 | SPS | Roadrunner 115kV GEN-2016-121 Interconnection Costs | Roadrunner 115kV GEN-2016-121 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 483969 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-121 (110.0 MW/Solar) into the POI at Roadrunner 115kV.
|  | 81607 | 122556 | [6 empty] | 0 | SPS | Eddy County to Tolk GEN-2016-123 Interconnection Costs | Eddy County to Tolk GEN-2016-123 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-123 (298.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
|  | 81608 | 122558 | [6 empty] | 0 | SPS | Eddy County to Tolk GEN-2016-124 Interconnection Costs | Eddy County to Tolk GEN-2016-124 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-124 (150.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
|  | 81609 | 122560 | [6 empty] | 0 | SPS | Eddy County to Tolk GEN-2016-125 Interconnection Costs | Eddy County to Tolk GEN-2016-125 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-125 (74.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
|  | 81613 | 122568 | [6 empty] | 0 | SPS | XFR - Tolk 345/230 kV Ckt2 | Tolk 345/230 kV CKT 2 Transformer (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  |  | GI STUDIES |  |  |  | 14055360 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new 345/230 kV Transformer Ckt 2 at Tolk to achieve a minimum emergency rating of 921 MVA on the Crossroads - Tolk 345 kV Ckt 1 line. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  | 0.5
| 210564 | 81489 | 122600 | [6 empty] | 0 | OGE | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (OKGE) | Generation Interconnection | 2021-12-31 |  | 2020-09-22 | 2020-08-11 | DISIS-2016-002 | 10000 | 2020 | 10250 | 10000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Relay settings upgrades
| 210630 | 81490 | 122601 | [6 empty] | 0 | OGE | Multi - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Terminal Equipment | Generation Interconnection | 2023-12-31 |  | 2023-12-31 | 2022-01-31 | DISIS-2016-002 |  |  |  | 10000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Change relay settings to accommodate the construction of the GEN-2016-095 wind farm.
| 210562 | 81628 | 122602 | [6 empty] | 0 | WAPA | Sub - Jamestown 230 kV Redundant Bus Tie | Jamestown 230 kV Redundant Bus Tie | Generation Interconnection | 2024-12-31 |  |  | 2020-06-10 | DISIS-2016-001 | 1510000 | 2020 | 1586443.75 | 1510000 |  | 0 |  | In Service |  |  |  |  | Add a redundant bus to Jamestown 230 kV substation to mitigate for a fault and breaker fail of CB 9182.
| 210565 | 81481 | 122622 | [6 empty] | 0 | EKC | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Substation Upgrades | Generation Interconnection | 2025-12-31 |  |  | 2020-08-28 | DISIS-2016-002 | 139825 | 2020 | 146903.6406 | 136893 |  | 0 |  | In Service |  |  |  |  | Replace one control panel and review and/or apply new relay settings at the Swissvale substation.
|  | 81481 | 122623 | [6 empty] | 0 | EKC | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Terminal Upgrades | Generation Interconnection | 2025-12-31 |  |  |  | GI STUDIES | 10000 | 2020 | 10506.25 | 10000 |  | 0 |  | In Service |  |  |  |  | Reviewing and applying new relaying settings at the Swissvale substation for the interconnection of GEN-2016-158.
|  | 81636 | 122635 | [6 empty] | 0 | OGE | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | GEN-2016-119 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-03-14 |  |  |  | GI STUDIES |  |  |  | 1099871 |  | 0 |  | On Schedule < 4 |  |  |  |  | Add a single 345kV line terminal to a new EHV Substation. Dead end structure, line switch, line relaying, revenue metering including CTs and PTs.
| 210606 | 81636 | 122637 | [6 empty] | 0 | EKC | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | Spring Creek345 kV (GEN-2016-119) | Generation Interconnection |  |  | 2025-03-15 | 2021-03-04 | DISIS-2016-002 | 16624 | 2021 | 17039.6 | 16624.73 |  | 0 |  | On Schedule < 4 |  |  |  |  | Review and/or apply relay protection settings at the Spring Creek substation.
|  | 81639 | 122640 | [6 empty] | 0 | SPS | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-17 |  |  |  | GI STUDIES |  |  |  | 4578401 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum system emergency rating of 430 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81640 | 122641 | [6 empty] | 0 | SPS | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 697513 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum emergency rating of 456 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81641 | 122642 | [6 empty] | 0 | SPS | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125 | [5 empty] | #N/A | #N/A
|  | 81642 | 122643 | [6 empty] | 0 | SPS | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81645 | 122645 | [6 empty] | 0 | SPS | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-15 |  |  |  | GI STUDIES |  |  |  | 4852215 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 90/90 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  |  | 13
|  | 81644 | 122646 | [6 empty] | 0 | SPS | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-15 |  |  |  | GI STUDIES |  |  |  | 968567 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 478 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81646 | 122647 | [6 empty] | 0 | SPS | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 5943138 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Tuco 230 kV Substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81647 | 122648 | [6 empty] | 0 | SPS | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2021-10-28 |  |  |  | GI STUDIES |  |  |  | 3318135 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Deaf Smith 115 kV substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81655 | 122662 | [6 empty] | 0 | OGE | Woodring 345kV GEN-2016-128 Interconnection Costs | Woodring 345kV GEN-2016-128 Interconnection (TOIF) (OKGE) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At an existing EHV substation, update relay settings on an existing Gen-Tie line to accommodate new protection settings.
| 210593 | 81561 | 112458 | #N/A | #N/A | #N/A | No | Do Not Add (2025) - Formula Rates??? | TS2020480 | TS2020480 | TSOK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic | 2026-01-01 | 2025-09-25 | 2026-01-01 | 2021-02-10 | 2019 ITP | 97111851 | 2020 | 102028138.4569 | 97111851 | 119195100 | 0 |  | On Schedule < 4 | 509755 | WEKIWA 345KV | 514803 | SOONER 345 | Build a new 345kV line from Sooner to Wekiwa with a summer emergency rating of 1792 MVA | 345 | 50.5 | [6 empty] | Katherine Vecchiarelli
Base Plan | 210544 | 81561 | 112460 | #N/A | #N/A | #N/A | No | Base Plan - Add in Future (2025) | TP2019146 | TP2019146 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | 2025-05-01 | 2025-02-26 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 770654.45 | 1242638 | 1216324 | 0 |  | On Schedule < 4 | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138 |  |  |  |  | Y |  | Y
| 210631 | 81657 | 122667 | [6 empty] | #N/A | OGE | Multi - Riverside 345 kV Substation | Redbud 345kV | Generation Interconnection | 2025-12-31 |  | 2025-12-31 | 2022-01-31 | DISIS-2016-002 |  |  |  | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Change relay settings to accommodate the Interconnection of the States Edge 1 Wind Farm.
|  | 81658 | 122669 | [6 empty] | 0 | BEPC | GEN-2016-130 Interconnection Costs | Leland Olds 345 kV Substation Reconfiguration (DISIS-2016-002-2) | Generation Interconnection | 2025-06-30 |  |  |  | GI STUDIES |  |  |  | 2776827 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build out of a new line terminal for relocation of LOS Unit 2 main transformer. This includes one (1) 345 kV power circuit breaker, two (2) 345 kV breaker disconnect switches, three (3) 345 kV PTs, three (3) 345 kV surge arrestors, and protection and control package.
|  | 81660 | 122673 | [6 empty] | 0 | EKC | Viola 345kV GEN-2016-153 Interconnection Costs | Viola 345kV GEN-2016-153 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 20000 |  | 0 |  | In Service |  |  |  |  | Review relay settings and apply adjusted settings at Flat Ridge 2 East and Viola 345 kV substations. Install PMU at Viola Substation
| 210612 | 81660 | 122674 | [6 empty] | 0 | OGE | Viola 345kV GEN-2016-153 Interconnection Costs | Renfrow 345 kV Relay Setting Adjustment | Generation Interconnection | 2023-10-01 |  | 2023-10-01 | 2021-06-08 | DISIS-2016-002 | 15000 | 2021 | 15375 | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At the existing Renfrow 345 kV substation, update relay settings to accommodate new protection settings.
|  | 81661 | 122676 | [6 empty] | 0 | EKC | Benton 345kV GEN-2016-162 and 163 Interconnection Costs | Benton 345kV GEN-2016-162 and 163 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 810255 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 345 kV circuit breaker and two (2) new 345 kV disconnect switches.
|  | 81662 | 122677 | [6 empty] | 0 | NPPD | Sweetwater 345kV GEN-2016-074 Interconnection Costs | GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Expanding the existing Sweetwater 345kV Substation to accommodate the GEN-2016-074 interconnection request
|  | 81662 | 122678 | [6 empty] | 0 | NPPD | Sweetwater 345kV GEN-2016-074 Interconnection Costs | Sweetwater 345kV GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Expand the existing Sweetwater 345kV Substation to accommodate GEN-2016-074 interconnection request
|  | 81665 | 122684 | [6 empty] | 0 | TSGT | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (TOIF) (TSGT) | Generation Interconnection | 2023-10-05 |  |  |  | GI STUDIES |  |  |  | 1636796 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 81665 | 122687 | [6 empty] | 0 | TSGT | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (Non-Shared NU) (TSGT) | Generation Interconnection | 2023-10-05 |  |  |  | GI STUDIES |  |  |  | 2155837 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230 kV power circuit breaker, two (2) 115 kV power circuit breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
|  | 81666 | 122688 | [6 empty] | 0 | WAPA | Bismark to Glenham GEN-2016-087 Interconnection Costs | Bismark to Glenham 230kV GEN-2016-087 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2023-08-30 |  |  |  | GI STUDIES |  |  |  | 644488 |  | 0 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and the re-route of the Glenham line to the new 230 kV line bay.
|  | 81670 | 122791 | [6 empty] | 0 | OGE | Viola 345/138 kV Transformer CKT 2 | GEN-2016-119 Tap - Arcadia 345kV (DISIS-2016-002-3) | Generation Interconnection | 2025-12-31 |  |  |  | GI STUDIES |  |  |  | 68725000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new terminal at new substation on Sooner to Spring Creek line being built for Gen-2016-119. Expand Arcadia Substation and re-route four transmission lines to allow for room for new transmission line to be brought in. Build approximately 47 miles of new 345kV line from new substation to Arcadia.
|  | 81670 | 122792 | [6 empty] | 0 | EKC | Viola 345/138 kV Transformer CKT 2 | Viola 345/138 kV Transformer CKT 2 (DISIS-2016-002-2) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 9204586 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install a new 345 kV terminal on a new rung consisting of two (2) breakers, four (4) switches, and two (2) control panels. Install a new 138 kV terminal on an existing rung consisting of one (1) breaker, three (3) switches, three (3) PTs, and one (1) 400/440 MVA 345-138 kV transformer with LTCs. Network Upgrade shared among fourteen requests: GEN-2016-100, GEN-2016-101, GEN-2016-119, GEN-2016-128, GEN-2016-133, GEN-2016-134, GEN-2016-137, GEN-2016-138, GEN-2016-139, GEN-2016-141, GEN-2016-142, GEN-2016-145, GEN-2016-146, GEN-2016-153
| 210643 | 81773 | 143127 | [6 empty] | 0 | OGE | Sub - Chisholm - Gracemont 345 kV | Gracemont 345 kV | Generation Interconnection | 2022-09-01 |  | 2022-09-01 | 2022-02-25 | DISIS-2017-001 | 15000 | 2022 | 15000 | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At the existing Gracmont 345 kV substation, update relay settings to accommodate new protection settings.
|  | 81661 | 143150 | [6 empty] | 0 | EKC | Benton 345kV GEN-2016-162 and 163 Interconnection Costs | Benton 345kV GEN-2016-162 and 163 Interconnection (TOIF) (WERE) | Generation Interconnection | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 1198282 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 345 kV dead-end, one (1) new 345 kV disconnect switch, three (3) new voltage transformers, three (3) new current transformers, and one (1) new line panel.
| 200277 | 30678 | 50889 | [6 empty] | 0 | NPPD | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority | 2025-12-31 |  | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 11338457.3874 | 9797157 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640381 | Thedford | Install new 345/115 kV 400 MVA transformer at Thedford substation. Install any necessary 115 kV terminal equipment. | 345/115
| 200277 | 30678 | 51002 | [6 empty] | 0 | NPPD | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority | 2025-12-31 |  | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1134089.4193 | 913714 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Install any necessary 345 kV terminal equipment at Thedford associated with new 345/115 kV transformer. | 345
| 200397 | 242 | 10308 | [6 empty] | 0 | WFEC | Line - Elmore - Paoli 69 kV Rebuild | Elmore - Paoli 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-03-31 |  | 2009-06-01 | 2016-05-17 | 2016 ITPNT | 3240000 | 2016 | 3757406.6808 | 4339358 |  | 4171494.22 | FORMULA RATE UPDATE | Delay - Mitigation | 520898 | ELMORE | 521022 | PAOLI | Rebuild 10.8-mile 69 kV line from Elmore to Paoli. | 69 |  | 10.8
| 200397 | 844 | 11113 | [6 empty] | 0 | WFEC | Line - Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Regional Reliability | 2020-12-31 |  | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 4725000 | 2016 | 5215515.9052 | 4725000 |  |  | FORMULA RATE UPDATE | Delay - Mitigation | 521005 | MUSTANG | 521058 | SUNSHINE CANYON | Rebuild 10-mile 69 kV line from Sara Road to Sunshine Canyon. | 69 |  | 10 |  |  |  | Y
| 200220 | 30375 | 50442 | [6 empty] | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 204236579 | 2020 | 214576055.8119 | 204236579 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640183 | Gerald Gentleman Station | Build new 110-mile 345 kV line from Gerald Gentleman Station substation to new Cherry County substation. This upgrade is contingent upon approval from Western Area Power Administration ("WAPA") to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 100.7
| 200220 | 30375 | 50444 | [6 empty] | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 13692681 | 2020 | 14385872.9756 | 13692681 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Build new Cherry County 345 kV substation and install necessary terminal equipment. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
| 200220 | 30375 | 50445 | [6 empty] | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 232903698 | 2020 | 244694447.7113 | 232903698 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640503 | Holt County 345 kV | Build new 117-mile 345 kV line from new Cherry County substation to new Holt County substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 124.3
| 210618 | 30375 | 50446 | [6 empty] | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability | 2025-12-31 |  | 2018-01-01 | 2021-11-04 | 2012 ITP10 | 577000 | 2021 | 591425 | 577000 |  | 0 |  | Delay - Mitigation | 640503 | Holt County 345 kV |  |  | Add line bay terminal equipment as necessary to connect, commission and operate the 345 kV line from Thedford to Holt County Substation. | 345
| 200200 | 30491 | 50600 | [6 empty] | 0 | WFEC | Device - Hazelton 69 kV | Hazelton 69 kV Capacitor | Regional Reliability | 2017-03-01 |  | 2013-01-01 | 2013-03-01 | DPA-2012-MAR-143-147 | 237000 | 2013 | 261603.6549 | 735000 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520937 | HAZELTON |  |  | Install two 4.8 Mvar capacitors at Hazelton 69 kV for total of 9.6 Mvar. | 69 |  |  |  | Y
| 200234 | 30503 | 50628 | [6 empty] | 0 | WFEC | Device - Hazelton 69 kV #2 | Hazelton Capacitor 69 kV #2 | Regional Reliability | 2017-03-01 |  | 2017-06-01 | 2013-10-28 | DPA-2012-MAR-151-154-161-JUL-218-SEP-243 | 185004 | 2013 | 204209.7999 | 0 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520937 | HAZELTON |  |  | Install new 69 kV 4.8-Mvar capacitor at Hazelton substation. | 69 |  |  |  | Y
| 200245 | 30563 | 50702 | [6 empty] | 0 | WFEC | Device - Sandy Corner 138 kV | Sandy Corner 138 kV Cap Bank | Regional Reliability | 2017-06-01 |  | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 504000 | 2014 | 542752.8725 | 504000 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520204 | Sandy Corner 138 kV |  |  | Add 20 Mvar of capacitance at Sandy Corner 138 kV. | 138 |  |  |  |  | Y
| 200397 | 31002 | 51445 | [6 empty] | 0 | WFEC | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (WFEC) | Regional Reliability | 2021-05-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6000000 | 2016 | 6788449.26 | 7710000 |  |  |  | Delay - Mitigation | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 8.5-mile 138 kV line from Lincoln to Meeker. | 138
| 200397 | 31065 | 51484 | [6 empty] | 0 | WFEC | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability | 2023-05-31 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 4638773.68 | 4000000 |  | 0 |  | Delay - Mitigation | 520855 | CLEO JCT |  |  | Install 3-breaker ring bus at Cleo Junction to allow load to be moved from 69 kV to 138 kV. | 138
| 200390 | 31025 | 51487 | [6 empty] | 0 | GRDA | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability |  |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2627865.2897 | 2266000 |  | 0 |  | Re-evaluation | 505550 | Sallisaw |  |  | Install ring bus at Sallisaw 161 kV substation. | 161
| 200397 | 31041 | 51526 | [6 empty] | 0 | WFEC | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability | 2022-04-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 637831.381 | 600000 |  | 0 |  | Delay - Mitigation | 520203 |  |  |  | Tap the 138 kV line from Byron to Cherokee City to construct new Driftwood substation. Install any required 138 kV terminal upgrades required to install 138/69 kV transformer. | 138
| 200397 | 31041 | 51527 | [6 empty] | 0 | WFEC | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability | 2022-04-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3479080.26 | 3600000 |  | 0 |  | Delay - Mitigation |  |  | 520938 | HAZELTON JCT | Install new 138/69 kV transformer at new Driftwood substation. Install new 69 kV terminal for 69 kV line from Hazelton Junction. | 138/69
| 200419 | 31042 | 51531 | [6 empty] | 0 | WFEC | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (WFEC) | Regional Reliability | 2026-12-31 |  | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 1400000 | 2017 | 1583971.494 | 5700000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. WFEC and Oklahoma Gas and Electric Company shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138 | 2
| 200420 | 31063 | 51567 | [6 empty] | 0 | SPS | Sub - Carlsbad - Pecos 115 kV Terminal Upgrades | Carlsbad - Pecos 115 kV Terminal Upgrades | Regional Reliability | 2021-06-01 |  | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 767347 | 2017 | 847007.5097 | 0 |  | 0 |  | Complete | 528160 | Carlsbad Interchange 115 kV | 528178 | Pecos Interchange 115 kV | Install terminal upgrades at Carlsbad and/or Pecos to increase the rating of the 115 kV line between the substations. | 115 |  | 0.03
| 200455 | 41198 | 61852 | [6 empty] | 0 | SPS | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #1 | Regional Reliability | 2018-12-31 |  | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 98639 | 2017 | 101104.975 | 98639 |  | 0 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 1 at Texas County. | 115
| 200455 | 41198 | 61853 | [6 empty] | 0 | SPS | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #2 | Regional Reliability | 2018-12-31 |  | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 108430 | 2017 | 111140.75 | 108430 |  | 0 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 2 at Texas County. | 115
| 200479 | 51249 | 71954 | [6 empty] | 0 | KPP | Line - City of Winfield - Oak 69 kV Reconductor | City of Winfield - Rainbow 69 kV Ckt 1 | Regional Reliability | 2020-12-31 |  | 2021-06-01 | 2018-02-27 | SPP-2016-AG2-AFS-2 | 3600000 | 2018 | 3782250 | 5066520 |  | 0 |  | Complete |  |  |  |  | Reconductor 4 miles of 69 kV transmission line from City of Winfield to Rainbow. |  |  | 4
| 200466 | 51249 | 71955 | [6 empty] | 0 | EKC | Line - City of Winfield - Oak 69 kV Reconductor | Oak - Rainbow 69 kV Ckt 1 | Regional Reliability | 2021-04-12 |  | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 7831427 | 2017 | 8644430.0697 | 5156586 |  | 5156585 | QUARTERLY TRACKING | Closed Out |  |  |  |  | Reconductor 5.1 miles of 69 kV transmission line from Oak to Rainbow. | 69 |  | 5.1 |  | Y | Y | Y
| 210536 | 41199 | 71960 | [6 empty] | 0 | SPS | Line - Etter - Moore - 115 kV | Etter - Moore 115 kV Rebuild | Regional Reliability | 2021-10-21 |  | 2018-06-01 | 2019-10-29 | 2017 ITPNT | 9037903 | 2017 | 9976153.83 | 1338161 |  | 0 |  | Delay - Mitigation | 523308 | Moore County Interchange East Bus 115 kV | 523256 | Etter Rural Sub 115 kV | Rebuild 10.83-mile 115 kV line from Etter to Moore. | 115 | 10.25
| 200477 | 51254 | 71963 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 14010573.3857 | 20297796 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
| 200477 | 51254 | 71964 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | 0 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
| 200477 | 51254 | 71965 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | 0 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
| 200477 | 51254 | 71966 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 12441332.2716 | 15279402 |  | 0 |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
| 200477 | 51254 | 71967 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1405712.3383 | 1605462 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
| 200477 | 51254 | 71968 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 4087712.7459 | 5656017 |  | 0 |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
| 200482 | 51280 | 72011 | [6 empty] | 0 | WFEC | Device - Dover SW 69 kV Cap Bank | Dover SW 69 kV Cap Bank | Regional Reliability | 2022-07-01 |  | 2019-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 500000 | 2018 | 551906.445 | 813590 |  | 0 |  | Delay - Mitigation | 520881 | DOVER SW |  |  | Add new 14.4 MVAR capacitor bank at Dover SW 69 kV. | 69
| 200482 | 51281 | 72012 | [6 empty] | 0 | WFEC | Device - Cherokee SW 69 kV Cap Bank | Cherokee SW 69 kV Cap Bank | Regional Reliability | 2023-08-01 |  | 2018-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 1000000 | 2018 | 1103812.89 | 1000000 |  | 0 |  | Delay - Mitigation | 520851 | CHEROKEE SW |  |  | Add new 28.8 MVAR capacitor bank at Cherokee SW 69 kV. | 69
| 210483 | 51282 | 72013 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Park Community 138 kV Substation | Regional Reliability | 2018-06-15 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 2000000 | 2018 | 2000000 | 2000000 |  | 0 |  | Re-evaluation |  |  |  |  | New Park Community 138 kV substation with 3-terminal flat bus. | 138
| 210483 | 51282 | 72014 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Omega - Park Community 138 kV Ckt 1 New Line | Regional Reliability | 2019-07-01 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4700000 | 2018 | 4817500 | 4700000 |  | 0 |  | Delay - Mitigation | 520964 | KINGFISHER |  |  | Construct new 9.4 mile 138 kV line from Omega - Park Community. Complete necessary terminal upgrades at Omega. | 138 | 9.4
| 210483 | 51282 | 72015 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Omega - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-08-31 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 7950000 | 2018 | 8775312.4755 | 12428000 |  | 0 |  | Delay - Mitigation | 520964 | KINGFISHER | 521090 | WATONGA SW | Convert 7.9 mile 69 kV line from Omega - Watonga SW to 138 kV. Complete necessary terminal upgrades at Watonga SW. | 138 |  | 7.9 | 7.9
| 210669 | 51282 | 72016 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Okeene - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2021-08-01 |  | 2019-06-01 | 2022-04-28 | DPA-2017-August-767-774-776 | 8600000 | 2018 | 9261259.332 | 8600000 |  | 0 |  | Delay - Mitigation | 521016 | OKEENE | 521090 | WATONGA SW | Convert 17.2 mile 69 kV line from Okeene - Watonga SW to 138 kV. Complete necessary terminal upgrades at Okeene. | 138 |  | 13.5 | 13.5
| 210483 | 51282 | 72018 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-05-29 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 9272028.276 | 8400000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 521090 | WATONGA SW | Convert 16.8 mile 69 kV line from Calumet - Watonga SW to 138 kV. | 138 |  | 16.8 | 16.8
| 210483 | 51282 | 72019 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-09-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1379766.1125 | 1250000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 520865 | CONCHO | Convert 9.0 mile 69 kV line from Calumet - Concho to 138 kV. Complete necessary terminal upgrades at Concho. | 138 |  |  | 9
| 210483 | 51282 | 72020 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-12-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 5022348.6495 | 4550000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 520502 |  | Convert 9.1 mile 69 kV line from Calumet - Cana to 138 kV. Complete necessary terminal upgrades at Cana. | 138 |  | 9.1 | 9.1
| 210483 | 51282 | 72021 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability | 2022-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4000000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET |  |  | New Calumet 138 kV substation with 4-terminal ring bus. | 138
| 210483 | 51282 | 72022 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 6236542.8285 | 5650000 |  | 0 |  | Delay - Mitigation | 520502 |  | 520899 | EL RENO | Convert 3.3 mile 69 kV line from Cana - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno Jct. | 138 |  | 3.3 | 3.3
| 210483 | 51282 | 72023 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-06-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 3500000 |  | 0 |  | Delay - Mitigation | 520892 | EL RENO SW | 520899 | EL RENO | Convert 6.5 mile 69 kV line from El Reno - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno. | 138
| 210483 | 51282 | 72024 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-05-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 11750000 |  | 0 |  | Delay - Mitigation | 520892 | EL RENO SW | 520412 |  | Convert 21.3 mile 69 kV line from El Reno - Mustang to 138 kV. Complete necessary terminal upgrades at Mustang. | 138 |  | 21.3 | 21.3
| 210483 | 51282 | 72025 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Mustang - Sara Road 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-12-30 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 10650000 | 2018 | 11755607.2785 | 1172000 |  | 0 |  | Delay - Mitigation | 520412 |  | 521005 | MUSTANG | Convert 2.1 mile 69 kV line from Mustang - Sara Road to 138 kV. Complete necessary terminal upgrades at Sara Road. | 138 |  | 2.1 | 2.1
| 210483 | 51282 | 72026 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Sara Road - Sunshine 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-12-30 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1050000 | 2018 | 1159003.5345 | 10380000 |  | 0 |  | Delay - Mitigation | 521005 | MUSTANG | 521059 | SUNSHINE CANYON | Convert 10.0 mile 69 kV line from Sara Road - Sunshine to 138 kV. | 138 |  | 10 | 10
| 210483 | 51282 | 72027 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-01-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 5519064.45 | 5300000 |  | 0 |  | Delay - Mitigation | 520859 | COGAR | 520899 | EL RENO | Convert 10.6 mile 69 kV line from Cogar - El Reno Jct to 138 kV. | 138 |  | 10.6 | 10.6
| 210483 | 51282 | 72030 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Kingfisher SW 138 kV Substation | Regional Reliability | 2023-01-31 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4975000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the East Kingfisher - Reeding 138 kV line and construct new Kingfisher SW 138 kV substation with 4-terminal ring bus. | 138
| 210483 | 51282 | 72031 | [6 empty] | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability | 2022-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4691204.7825 | 4250000 |  | 0 |  | Delay - Mitigation | 520865 | CONCHO |  |  | Construct new 8.5 mile 138 kV line from Concho - Kingfisher SW. | 138 | 8.5
| 210496 | 51316 | 72095 | [6 empty] | 0 | SPS | Carlisle - Murphy 115kV Terminal Upgrades | Carlisle - Murphy 115 kV Terminal Upgrades | Regional Reliability | 2022-03-11 |  | 2022-06-01 | 2018-08-17 | 2018 ITPNT | 232952 | 2018 | 257135.4204 | 232952 |  | 0 |  | Delay - Mitigation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Replace terminal equipment on the Carlisle to Murphy (circuit V40) line and address any line clearance concerns to meet or exceed the conductor rating. | 115
| 210489 | 51327 | 82111 | [6 empty] | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-03-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 10000000 | 2018 | 11038128.9 | 10000000 |  | 0 |  | Delay - Mitigation | 520859 | COGAR | 520509 |  | Convert 12.0 mile 69 kV line from Cogar - Cleveland Junction to 138 kV. | 138
| 210489 | 51327 | 82112 | [6 empty] | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-02-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6900000 | 2018 | 7616308.941 | 6900000 |  | 0 |  | Delay - Mitigation | 520509 |  |  |  | Convert 13.8 mile 69 kV line from Cleveland Jct - Amber Tap to 138 kV. | 138
| 210489 | 51327 | 82113 | [6 empty] | 0 | WFEC | Line - Cogar - OU SW 138 kV | Amber Tap - Blanchard 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-07-15 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 7600000 | 2018 | 8388977.964 | 7019000 |  | 0 |  | NTC - Commitment Window |  |  | 520828 | BLANCHARD | Convert 15.2 mile 69 kV line from Amber Tap - Blanchard to 138 kV. | 138
| 210489 | 51327 | 82114 | [6 empty] | 0 | WFEC | Line - Cogar - OU SW 138 kV | Blanchard - OU SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-11-30 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 300000 | 2018 | 331143.867 | 360000 |  | 0 |  | NTC - Commitment Window | 520828 | BLANCHARD | 521104 | OU SWITCH 4 | Convert 2.1 mile 69 kV line from Blanchard - OU SW to 138 kV. | 138
| 210489 | 51327 | 82115 | [6 empty] | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-02-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6300000 | 2018 | 6954021.207 | 6300000 |  | 0 |  | Delay - Mitigation | 520509 |  | 520814 | ANADARKO | Convert 11.1 miles of double circuit 69 kV line from Cleveland Junction - Anadarko to single circuit 138 kV. | 138
| 210496 | 61346 | 92151 | [6 empty] | 0 | SPS | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Substation | Regional Reliability | 2022-04-16 |  | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 13626695 | 2021 | 13967362.375 | 20859497 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap Moore-Potter 230kV and tap Exell-Fain 115kV and tie into a new substation at McDowell Creek. | 230 | 0.2
| 210496 | 61346 | 92152 | [6 empty] | 0 | SPS | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Transformer | Regional Reliability | 2022-04-16 |  | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 6531679 | 2021 | 6694970.975 | 81052 |  | 0 |  | Delay - Mitigation |  |  |  |  | Install a 230/115 kV transformer at the McDowell Creek substation | 230/115
| 210507 | 61347 | 92153 | [6 empty] | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco - Road Runner 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 29927758 | 2019 | 31442850.7488 | 36646140 |  | 0 |  | In Service |  |  | 528027 | Road Runner 345 kV | Build new 21 mile 345 kV line from Bopco to Road Runner. | 345 | 21
| 210507 | 61347 | 92154 | [6 empty] | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco - China Draw 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 |  | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 30496976 | 2019 | 32040885.41 | 32405135 |  | 0 |  | In Service |  |  | 528223 |  | Build new 19 mile 345 kV line from Bopco to China Draw. | 345 | 19
| 210507 | 61347 | 102153 | [6 empty] | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 1 Transformer | Regional Reliability | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 6205015 | 2019 | 6519143.8844 | 5718715 |  | 0 |  | In Service |  |  | 528020 |  | Construct 345/115 kV transformer at Bopco substation. | 345/115
| 210507 | 61347 | 102154 | [6 empty] | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 2 Transformer | Regional Reliability | 2021-11-15 |  | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 6122043 | 2019 | 6431971.4269 | 5962651 |  | 0 |  | In Service |  |  | 528020 |  | Construct second 345/115 kV transformer at Bopco substation. | 345/115
| 210507 | 61347 | 102157 | [6 empty] | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345 kV Substation | Regional Reliability | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 5153574 | 2019 | 5414473.6837 | 6341420 |  | 0 |  | In Service |  |  |  |  | Build 345 kV portion of new 345/115 kV Bopco substation. | 345
| 210507 | 61347 | 102158 | [6 empty] | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 115 kV Substation | Regional Reliability | 2020-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 11741936 | 2019 | 12035484.4 | 15137218 |  | 0 |  | In Service |  |  |  |  | Build 115 kV portion of new 345/115 kV Bopco substation. This includes work to reterminate the Wood Draw - Red Bluff 115 kV line into the new substation. | 115
| 210548 | 71348 | 102163 | [6 empty] | 0 | OPPD | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability | 2023-05-31 |  | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 3647471 | 2019 | 3927927.3066 | 3647471 |  | 0 |  | Delay - Mitigation | 646209 | Sub 1209 | 646231 | Sub 1231 | Reconductor 3.3 miles of S1209 - S1231 161 kV Ckt 2 | 161 |  | 3.3
| 210505 | 71352 | 102172 | [6 empty] | 0 | WFEC | Device - Clear Creek Tap 69 kV Cap Bank | Clear Creek Tap 69 kV Cap Bank | Regional Reliability | 2020-12-01 |  | 2019-12-01 | 2018-12-06 | DPA-2018-June-902 | 717209 | 2019 | 735139.225 | 717209 |  | 0 |  | Delay - Mitigation |  |  |  |  | New cap bank(s) totaling 18 MVAR at Clear Creek Tap 69kV substation. | 69
| 210540 | 81498 | 112358 | [6 empty] | 0 | OGE | Sub - Westmoore 138 kV | Westmoore 138 kV Breakers | Regional Reliability | 2021-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 271289 | 2020 | 278071.225 | 271289 |  | 0 |  | Complete | 514887 | WESTMOORE 138 |  |  | Replace 2 breakers at Westmoore 138 kV with 40 kA breakers | 138
Base Plan | 210544 | 81571 | 112488 | TP2019132 | #N/A | TP2019132 | Yes | Already Added | TP2019132 | TP2019132 | AEP | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | 2022-06-01 | 2022-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9618647.3294 | 9155167 | 8505279 | 0 |  | Complete | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115 |  |  |  |  | Y |  | Y | Jake Tucker | (EAC calculated for NTC BPID's only: P19132001 & P19132009)
Base Plan | 210544 | 81561 | 112502 | #N/A | #N/A | #N/A | No | Base Plan - Add in Future (2025) | TP2019146 | TP2019146 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | 2025-05-01 | 2025-05-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3409095.4055 | 5329277 | 5374949 | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06 |  |  |  | Y |  | Y
| 210541 | 81503 | 112363 | [6 empty] | 0 | SPS | Sub - Hale Cty Interchange 115 kV | Hale County Interchange 115 kV Breakers | Regional Reliability | 2021-05-30 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 1658004 | 2019 | 1741940.4525 | 257408 |  |  |  | In Service | 525454 | Hale Co Interchange 115 kV |  |  | Replace 3 breakers at Hale County Interchange 115 kV with 40 kA breakers | 115
| 210538 | 81505 | 112366 | [6 empty] | 0 | NPPD | Sub - Canaday 115 kV | Canaday 115 kV Breakers | Regional Reliability | 2020-02-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 2600000 | 2020 | 2600000 | 2555908 |  | 2555908 | QUARTERLY TRACKING | Complete | 640103 | Canaday |  |  | Replace 5 breakers at Canaday 115 kV with 40 kA breakers | 115 | [5 empty] | Y
| 210538 | 81506 | 112367 | [6 empty] | 0 | NPPD | Sub - Hastings 115 kV | Hastings 115 kV Breakers | Regional Reliability | 2021-01-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 550000 | 2020 | 563750 | 434289 |  | 434289 | QUARTERLY TRACKING | Complete | 640215 | Hastings |  |  | Replace 2 breakers at Hastings 115 kV with 40 kA breakers | 115 | [5 empty] | Y
| 210538 | 81507 | 112368 | [6 empty] | 0 | NPPD | Sub - Moore 13.8 kV Breaker | Moore 13.8 kV Breaker | Regional Reliability | 2022-07-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 510000 | 2020 | 535818.75 | 679553 |  | 0 |  | Delay - Mitigation | 640280 | Moore |  |  | Replace 1 breaker at Moore 13.8 kV with 40 kA breakers | 138
| 210539 | 81508 | 112369 | [6 empty] | #N/A | EM | Sub - Craig 161 kV | Craig 161 kV Breaker | Regional Reliability | 2021-06-30 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 311400 | 2019 | 327164.625 | 259864 |  | 0 |  | In Service | 542978 | CRAIG 161 KV |  |  | Replace 1 breaker at Craig 161 kV with 63 kA breakers | 161 |  |  |  | Y | Y | Y
| 210539 | 81509 | 112370 | [6 empty] | 0 | EM | Sub - Leeds 161 kV | Leeds 161 kV Breakers | Regional Reliability | 2020-09-24 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 468500 | 2019 | 480212.5 | 400871 |  | 400871 | QUARTERLY TRACKING | Complete | 542997 | LEEDS 161 KV |  |  | Replace 2 breakers at Leeds 161 kV with 40 kA breakers | 161 |  |  |  | Y |  | Y
| 210539 | 81511 | 112372 | [6 empty] | 0 | EM | Sub - Southtown 161 kV | Southtown 161 kV Breakers | Regional Reliability | 2021-12-31 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 898600 | 2019 | 944091.625 | 1348442 |  | 0 |  | In Service | 542993 | SOUTHTOWN 161 KV |  |  | Replace 4 breakers at Southtown 161 kV with 40 kA breakers | 161 |  |  |  | Y
| 210545 | 81513 | 112377 | [6 empty] | 0 | WFEC | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability | 2027-08-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 870294.6744 | 838500 |  | 0 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Replace 3 breakers at Anadarko 138 kV with 63 kA breakers | 138
| 210545 | 81514 | 112378 | [6 empty] | 0 | WFEC | Sub - Washita 69 kV | Washita 69 kV Breaker | Regional Reliability | 2021-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 52400 | 2020 | 53710 | 52400 |  | 0 |  | Delay - Mitigation | 521088 | WASHITA |  |  | Replace 1 breaker at Washita 69 kV with 40 kA | 69
| 210545 | 81515 | 112379 | [6 empty] | 0 | WFEC | Sub - Mooreland 138/69 kV Breakers | Mooreland 138 kV Breakers #2 | Regional Reliability | 2022-12-29 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 822500 | 2020 | 864139.0625 | 4100000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Replace 12 breakers at Mooreland 138 kV with 40 kA breakers
| 210545 | 81515 | 112380 | [6 empty] | 0 | WFEC | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability | 2022-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 128300 | 2020 | 134795.1875 | 204000 |  | 0 |  | Delay - Mitigation | 520995 | MOORELAND |  |  | Replace 2 breakers at Mooreland 69 kV with 40 kA breakers
| 210542 | 81516 | 112381 | [6 empty] | 0 | EKC | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - South Seneca 115kV Ckt 1 | Regional Reliability | 2022-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 3067168.2 | 2020 | 3222443.5901 | 3393918 |  | 0 |  | Delay - Mitigation | 533322 | BAILEYVILLE N.M. STATION 115 KV (NEMAHA MARSHALL R | 533337 | SOUTH SENECA 115 KV | Rebuild 4 miles of 115 kV line from Baileyville to South Seneca and upgrade any necessary terminal equipment at Baileyville and/or South Seneca to increase the summer emergency rating to 239 MVA | 115 | 4 |  |  | Y | Y
| 210605 | 81516 | 112383 | [6 empty] | 0 | EKC | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Multi-Marshall County - Baileyville - South Seneca 115 kV | Regional Reliability | 2022-06-01 |  | 2021-04-01 | 2021-03-02 | 2019 ITP | 9204123 | 2020 | 9670081.7269 | 10675598 |  | 0 |  | Delay - Mitigation | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Tear down 7.99 miles of 115 kV line from Baileyville to Smittyville, 2.17 miles of 115 kV line from Marshall County to Smittyville, and the Smittyville substation, rebuild 10.16 miles of 115 kV line from Baileyville to Marshall County and upgrade any necessary terminal equipment at Marshall County and/or Baileyville to increase the summer emergency rating to 239 MVA | 115 | 2.2 |  |  | Y | Y
|  | 81657 | 122665 | #N/A | #N/A | #N/A | No | Do Not Add | 0 |  | AEP | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (TOIF) (AEP) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 1388819 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 345 | 0.18 | [5 empty] | Y |  | States Edge (TP2019245 - 05/2026)
|  | 81657 | 122666 | #N/A | #N/A | #N/A | No | Do Not Add | 0 |  | AEP | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (Non-Shared NU) (AEP) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 10361130 |  | 0 |  | On Schedule < 4 |  |  |  |  | Expand the 345 kV breaker and a half scheme, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 345 | [6 empty] | Y |  | States Edge (TP2019245 - 05/2026)
| 210545 | 81525 | 112395 | [6 empty] | 0 | WFEC | Device- Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability | 2025-11-28 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 400000 | 2020 | 420250 | 400000 |  | 0 |  | Delay - Mitigation | 520929 | GYPSUM |  |  | Install a new 12 MVAR capacitor bank at Gypsum 69 kV substation. | 69/69
| 210642 | 81529 | 112399 | [6 empty] | #N/A | SPS | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230 kV Ckt 1 Terminal Upgrades | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 231742 | 2022 | 231742 | 231742 |  | 0 |  | On Schedule < 4 | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230
| 210642 | 81529 | 112401 | [6 empty] | #N/A | SPS | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230kV Ckt 2 Terminal Upgrades | Regional Reliability | 2022-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  | 2022 | 0 |  |  | 0 |  | Delay - Mitigation | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230
| 210540 | 81532 | 112402 | [6 empty] | 0 | OGE | Sub - Cleo Corner - Cleo Junction 69kV | Cleo Corner - Cleo Junction 69kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2019-11-18 | 2019 ITP | 16602 | 2020 | 17442.4762 | 16602 |  | 0 |  | Delay - Mitigation | 514777 | CLEO CORNER 69 | 520855 | CLEO JCT | Upgrade any necessary terminal equipment at Cleo Corner and/or Cleo Junction to increase the summer emergency rating to 48 MVA | 69
| 210538 | 81533 | 112403 | [6 empty] | 0 | NPPD | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability | 2024-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 608900 | 2020 | 639725.5625 | 608900 |  | 0 |  | Delay - Mitigation | 640171 | Firth |  |  | Install new 15 MVAR capacitor bank at Firth 115 kV substation. | 115
| 210538 | 81533 | 112404 | [6 empty] | 0 | NPPD | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability | 2024-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 3600000 | 2020 | 3782250 | 2991100 |  | 0 |  | Delay - Mitigation | 640171 | Firth |  |  | Expand the existing Firth 115 kV substation to accommodate a new 15 MVAR capacitor bank. | 115
Direct Assignment | 210558 | 81673 | 122713 | #N/A | #N/A | #N/A | No | Do Not Add (Direct Assigned) | TP2020077 | TP2020077 | AEP | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | 2022-06-01 | 2022-06-15 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 | 3160967 | 2020 | 3320990.9544 | 2752417 | 3093201 | 0 |  | In Service | 510423 | LOCUST GROVE | 512634 | KERR 115 | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49 |  |  | Y |  |  | Larry Oden
| 210515 | 81581 | 112510 | [6 empty] | 0 | SPS | Multi-Hobbs Interchange-Millen 115kV | Hobbs Interchange to Millen Rebuild 115 kV Ckt1 | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3165684 | 2019 | 3409095.4055 | 0 |  | 0 |  | Delay - Mitigation | 527891 | Hobbs Interchange 115 kV | 528435 | Millen Sub 115 kV | Rebuild 10.5 miles of Hobbs Interchange to Millen 115kV Line |  | 3.5
| 210515 | 81581 | 122510 | [6 empty] | 0 | SPS | Multi-Hobbs Interchange-Millen 115kV | Johnson Draw 115 kV Capacitor Bank | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3749224 | 2019 | 4037504.1579 | 0 |  | 0 |  | Delay - Mitigation | 527362 | Johnson Draw 115 kV |  |  | New 28.8 MVAR capacitor bank addition at Johnson Draw 115kV | 115
| 210560 | 81614 | 122570 | [6 empty] | 0 | BEPC | Multi - Neset - New Town 230 kV | Neset - Northshore 230 kV Ckt 1 | Regional Reliability | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 33155575 | 2020 | 34834075.9844 | 33159000 |  | 0 |  | Delay - Mitigation | 659138 | Neset 230 kV Bus |  |  | Build new 28 mile 230kV line from Neset to Northshore. | 230 | 30
| 210559 | 81614 | 122571 | [6 empty] | 0 | MWE | Multi - Neset - New Town 230 kV | Northshore - New Town 115 kV Ckt 1 | Regional Reliability | 2021-09-05 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 19235485 | 2020 | 19716372.125 | 19235485 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 20 mile 115 kV line from Northshore to New Town. | 115 | 20.5
| 210560 | 81614 | 122572 | [6 empty] | 0 | BEPC | Multi - Neset - New Town 230 kV | North Shore 230/115 kV Transformer | Regional Reliability | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 3176320 | 2020 | 3337121.2 | 3848370 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 230/115 kV Transformer at North Shore substation | 230/115
| 210560 | 81614 | 122575 | [6 empty] | 0 | BEPC | Multi - Neset - New Town 230 kV | Northshore 230 kV Substation | Regional Reliability | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 20938350 | 2020 | 21998353.9688 | 14282000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new Northshore 230/115 kV Substation to replace existing switch
| 210658 | 81627 | 122597 | [6 empty] | 0 | WFEC | SUB - Marietta - Rocky Point 69 kV | Marietta 69 kV | Regional Reliability | 2021-12-01 |  | 2021-12-01 | 2022-03-08 | 2019 ITP | 100000 | 2020 | 102500 | 100000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Install any necessary protection equipment at Marietta to change the operational status from normally open to normally closed | 69
| 210557 | 81652 | 122657 | [6 empty] | 0 | CBPC | Sub-Flint Hills 69 kV Switching Station | Sub - Donald Feldman 69kV Switching Station | Regional Reliability | 2020-06-01 |  | 2020-06-01 | 2020-04-08 | DPA-2019-March-1011 | 1100000 | 2020 | 1100000 | 1227000 |  | 0 |  | Complete |  |  |  |  | Construct a new switching station at Flint Hills connecting the MEC Clarksville line and Corn Belt's Parkersburg and Plainfield line |  |  |  |  | Y |  | Y
| 210552 | 81654 | 122661 | [6 empty] | 0 | NPPD | XFR-Riverdale 230/115 kV Transformer ckt 2 | Riverdale 230/115 kV Transformer ckt 2 | Regional Reliability | 2020-06-01 |  | 2021-06-01 | 2020-09-24 | DPA-2019-June-1058 | 3650000 | 2020 | 3650000 | 3704140 |  | 3704140 | QUARTERLY TRACKING | Complete | 640330 | Riverdale | 640331 | Riverdale | Install a new 230/115 kV 187 MVA transformer located at Riverdale substation | 230/115 | [5 empty] | Y
| 210574 | 81682 | 122725 | [6 empty] | 0 | SPS | Line - Allen - Quaker 115kV | Allen - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 2961075 | 2021 | 3035101.875 | 2961075 |  | 0 |  | Delay - Mitigation | 526213 | Allen Sub 115 kV | 526243 | South Plains REC-Quaker 115 kV | Rebuild 3.6 miles 115 kV line from Allen to Quaker and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA |  |  | 3.5
| 210574 | 81684 | 122727 | [6 empty] | 0 | SPS | Line - Allen - Lubbock South 115kV | Allen - Lubbock South 115 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 7350796 | 2021 | 7534565.9 | 7350796 |  | 0 |  | Delay - Mitigation | 526213 | Allen Sub 115 kV | 526268 | Lubbock South Interchange 115 kV | Rebuild 5.98 miles of 115 kV line from Allen to Lubbock and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA. |  |  | 6
Base Plan | 210575 | 81687 | 122730 | #N/A | TP2020102 | #N/A | Yes | Base Plan - Add in Future (2025) | TP2020102 | TP2020102 | AEP | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | 2024-06-03 | 2024-06-03 | 2024-06-01 | 2020-11-17 | 2020 ITP | 23622577 | 2021 | 24213141.425 | 20597910 | 20736958 | 0 |  | Delay - Mitigation | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA | 138 | 11.2 |  |  |  | Y |  |  | Jeff Koch
| 210581 | 81768 | 122745 | [6 empty] | 0 | BEPC | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 1 (KV1A) | Regional Reliability | 2024-06-30 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 3389739 | 2021 | 3474482.475 | 3910285 |  | 0 |  | Delay - Mitigation |  |  |  |  | Replace the 230/115 kV transformer Ckt 1 at Watford City to achieve a summer emergency rating of 208 MVA | 230/115
| 210581 | 81768 | 122746 | [6 empty] | 0 | BEPC | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 2 (KV2A | Regional Reliability | 2024-06-30 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 173041 | 2021 | 177367.025 | 173041 |  | 0 |  | Delay - Mitigation |  |  |  |  | Upgrade any necessary terminal equipment at Watford City for the 230/115 kV transformer Ckt 2 to achieve a summer emergency rating of 208 MVA | 230/115
| 210582 | 81719 | 122803 | [6 empty] | 0 | SEPC | Device - Russell 115 kV | Russell 115 kV Capacitor Bank | Regional Reliability | 2024-01-01 |  | 2022-06-01 | 2020-11-23 | 2020 ITP | 5306633 | 2021 | 5439298.825 | 5306633 |  | 0 |  | Delay - Mitigation | 539701 | Russell 115 KV |  |  | Add new 24 MVAR capacitor bank at Russell 115 kV
| 210583 | 81720 | 122804 | [6 empty] | 0 | EM | Sub - Northeast 161 kV | Northeast 161 kV Breakers | Regional Reliability | 2025-12-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 887479 | 2021 | 909665.975 | 887481 |  | 0 |  | Delay - Mitigation |  |  |  |  | Replace three breakers at the Northeast 161 kV station with 63 kA breakers
| 210583 | 81722 | 122806 | [6 empty] | 0 | EM | Sub - Leeds 161 kV #2 | Leeds 161 kV Breaker | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 300000 | 2021 | 307500 | 300000 |  | 0 |  | Delay - Mitigation | 542997 | LEEDS 161 KV |  |  | Replace 1 breaker at the Leeds 161 kV station with a 40 kA breaker |  |  |  |  | Y
| 210583 | 81723 | 122807 | [6 empty] | 0 | EM | Sub - Shawnee Mission 161 kV | Shawnee Mission 161 kV Breaker | Regional Reliability | 2023-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 335416 | 2020 | 352396.435 | 355416 |  | 0 |  | Delay - Mitigation | 543031 | SHAWNEE MISSION 161 KV |  |  | Replace 1 breaker at the Shawnee Mission 161 kV station with a 40 kA breaker |  |  |  |  | Y
| 210583 | 81724 | 122808 | [6 empty] | 0 | EM | Sub - Southtown 161 kV #2 | Southtown 161 kV Breaker | Regional Reliability | 2021-12-22 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 244265 | 2021 | 244265 | 389812 |  | 0 |  | In Service | 542993 | SOUTHTOWN 161 KV |  |  | Replace 1 breaker at the Southtown 161 kV station with a 40 kA breaker |  |  |  |  | Y
| 210580 | 81728 | 122812 | [6 empty] | 0 | EKC | Line - Circleville - Goff 115 kV | Circleville - Goff 115 kV Ckt 1 Rebuild | Regional Reliability | 2021-07-02 |  | 2025-06-01 | 2020-11-17 | 2020 ITP | 13028143 | 2021 | 13028143 | 14232227 |  | 14232227 | QUARTERLY TRACKING | Complete | 533152 | CIRCLEVILLE 115 KV | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | Rebuild 14.56 miles of 115 kV line from Circleville to Goff and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  |  | 14.5 |  | Y | Y | Y
| 210580 | 81730 | 122814 | [6 empty] | 0 | EKC | Line - Kelly - Goff 115 kV | Goff - Kelly 115 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-18 |  | 2025-06-01 | 2020-11-17 | 2020 ITP | 5602343 | 2021 | 5602343 | 5483173 |  | 5483173 | QUARTERLY TRACKING | Complete | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | 533217 | KELLY 115 KV | Rebuild 10.0 miles of 115 kV line from Goff to Kelly and upgrade any necessary terminal equipment to achieve a summer emergency rating 239 MVA | 115 |  |  |  | Y | Y | Y
| 210589 | 81733 | 122818 | [6 empty] | 0 | OGE | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Cushing - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 4281150 | 2021 | 4388178.75 | 4281150 |  |  |  | On Schedule < 4 | 515032 | CUSHING 69 | 515022 | PIPELINE 69 | Rebuild 4.71 miles of 69 kV line from Cushing to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 4.71
| 210589 | 81733 | 122819 | [6 empty] | 0 | OGE | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Pipeline - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 1081649 | 2021 | 1108690.225 | 1081649 |  |  |  | On Schedule < 4 | 515022 | PIPELINE 69 |  |  | Rebuild 1.19 miles of 69 kV line from Pipeline to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 1.19
| 210586 | 81751 | 122864 | [6 empty] | 0 | WFEC | Sub - Anadarko 138 kV #2 | Anadarko 138 kV Breakers #2 | Regional Reliability |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 850000 | 2021 | 871250 | 850000 |  | 0 |  | On Schedule < 4 | 520814 | ANADARKO |  |  | Replace 4 breakers at the Anadarko 138 kV station with a 63 kA breakers
| 210574 | 81755 | 122869 | [6 empty] | 0 | SPS | Sub - Bushland - Deaf Smith 230 kV | Bushland - Deaf Smith 230 kV Terminal Upgrades | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 998956 | 2021 | 1023929.9 | 571184 |  | 0 |  | Delay - Mitigation | 524267 | Bushland Interchange 230 kV (POI: Wildorado Wind, 160MW) | 524623 | Deaf Smith County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Bushland and/or Deaf Smith 230 kV to achieve a summer emergency rating of 546 MVA.
| 210574 | 81756 | 122870 | [6 empty] | 0 | SPS | Sub - Newhart - Potter 230 kV | Newhart - Potter 230 kV Terminal Upgrades | Regional Reliability | 2022-04-01 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 735013 | 2021 | 753388.325 | 0 |  | 0 |  | Delay - Mitigation | 525461 | Newhart Interchange 230 kV | 523959 | Potter County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Newhart and/or Potter 230 kV to achieve a summer emergency rating of 540 MVA. |  | 67
| 210574 | 81757 | 122871 | [6 empty] | 0 | SPS | Sub - Deaf Smith #6 - Friona 115 kV | Deaf Smith #6 - Friona 115 kV Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 11609949 | 2021 | 11900197.725 | 11609949 |  | 0 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524655 | Friona Sub 115 kV | Rebuild 18.9 miles of 115 kV line from Deaf Smith #6 to Friona and upgrade any necessary terminal equipment at Deaf Smith #6 and/or Friona to achieve a summer emergency rating of 120 MVA |  | 17.4
| 210574 | 81758 | 122872 | [6 empty] | 0 | SPS | Line - Carlisle - Murphy 115 kV #2 | Carlisle - Murphy 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 4160581 | 2021 | 4264595.525 | 4160581 |  | 0 |  | Delay - Mitigation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Rebuild 4.0 miles of 115 kV line from Carlisle to Murphy and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 4
| 210574 | 81760 | 122876 | [6 empty] | 0 | SPS | Line - Deaf Smith #6 - Hereford 115 kV | Deaf Smith #6 - Hereford 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 6956586 | 2021 | 7130500.65 | 6956586 |  | 0 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524606 | Hereford Interchange 115 kV | Rebuild 2.33 miles of 115 kV line from Deaf Smith #6 to Hereford and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  | 7.3
| 210574 | 81763 | 122883 | [6 empty] | 0 | SPS | Sub - Lubbock South - Wolfforth 230 kV | Lubbock South - Wolfforth 230 kV Ckt 1 Terminal Upgrades #2 | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 944000 | 2021 | 967600 | 835432 |  | 0 |  | Delay - Mitigation | 526269 | Lubbock South Interchange 230 kV | 526525 | Wolfforth Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Lubbock South and/or Wolfforth to achieve a summer emergency rating of 550 MVA |  | 14.6
| 210584 | 81497 | 132893 | [6 empty] | 0 | NWE | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Junction 115 kV Terminal Upgrades | Regional Reliability | 2021-12-31 |  | 2022-12-01 | 2020-11-17 | 2020 ITP | 1182000 | 2021 | 1182000 | 1182000 |  | 989393 | QUARTERLY TRACKING | Complete |  |  |  |  | Install any necessary terminal equipment to support a new 115 kV line from Richmond to achieve a summer emergency rating of 139 MVA | [6 empty] | Y
| 210579 | 91876 | 143157 | [6 empty] | 0 | WAPA | Device - Bismarck 12.47 kV | Bismarck 12.47 kV Reactors | Regional Reliability | 2023-10-01 |  | 2022-04-01 | 2020-11-23 | 2020 ITP | 2143217 | 2021 | 2196797.425 | 2143217 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install 2x35 MVAR reactors at Bismarck to control voltage on the 230 kV transmission system
| 210585 | 91878 | 143159 | [6 empty] | 0 | MRES | Device - Moorehead 230 kV | Moorehead 230 kV Reactor | Regional Reliability | 2024-06-01 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 4358300 | 2022 | 4358300 | 4358300 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 2x40 MVAR reactors at Moorehead to control voltage on the 115 kV and 230 kV transmission systems
| 210591 | 91881 | 143162 | [6 empty] | 0 | CPEC | Device - Agate 115 kV | Agate 115 kV Reactor | Regional Reliability | 2022-07-01 |  | 2022-04-01 | 2020-11-23 | 2020 ITP | 1310400 | 2021 | 1343160 | 1400000 |  |  |  | Delay - Mitigation |  |  |  |  | Install 2x6 MVAR reactors at Agate to control voltage on the 115 kV transmission system
| 210574 | 91884 | 143167 | [6 empty] | 0 | SPS | Line - Cargill - Friona 115 kV | Cargill - Friona 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 1675731 | 2021 | 1717624.275 | 1675731 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 1.15 miles of existing 115 kV line from Cargill to Friona and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 1.15
| 210574 | 91888 | 143168 | [6 empty] | 0 | SPS | Line - Cargill - Deaf Smith #24 115 kV | Cargill - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 5378526 | 2021 | 5512989.15 | 5378526 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 7.74 miles of 115 kV line from Cargill to Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 7.75
| 210574 | 91889 | 143169 | [6 empty] | 0 | SPS | Line - Parmer - Deaf Smith #24 115 kV | Parmer - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 999423 | 2021 | 1024408.575 | 999423 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 1.16 miles of 115 kV line from Parmer - Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 1.16
| 210574 | 91890 | 143170 | [6 empty] | 0 | SPS | Line - Parmer - Deaf Smith #20 115 kV | Parmer - Deaf Smith #20 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 5293163 | 2021 | 5425492.075 | 5293163 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 7.6 miles of 115 kV line from Parmer - Deaf Smith #20 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 7.6
| 210600 | 91885 | 143177 | [6 empty] | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S1260 - S1362 161 kV Ckt 1 Rebuild | Regional Reliability | 2022-08-01 |  | 2023-04-01 | 2021-02-16 | DPA-2018-October-949 | 858928 | 2021 | 880401.2 | 858928 |  | 0 |  | On Schedule < 4 | 646260 |  |  |  | Rebuild 0.9 miles of 161 kV line from S1260 to S1362 line to achieve 243 MVA summer emergency rating. | 161
| 210600 | 91885 | 143178 | [6 empty] | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3456 to S3458 345 kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-08-01 |  | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 100000 | 2021 | 102500 | 100000 |  | 0 |  | On Schedule < 4 | 645456 | Sub 3456 | 645458 | Sub 3458 (Neb Cty) | The upgrade disconnect switch and associated jumpers on S3456 to S3458 345 kV line to achieve at least a 981 MVA summer emergency rating. | 345
| 210600 | 91885 | 143179 | [6 empty] | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3455 to S3740 345 kV CKT1 Rebuild | Regional Reliability | 2024-04-01 |  | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 600000 | 2021 | 615000 | 600000 |  | 0 |  | On Schedule < 4 | 645455 | Sub 3455 | 645740 | Sub 3740 | Replace structures to increase clearance on S3455 to S3740 345 kV CKT1 (approximately 6-7 structures) to achieve a 1112 MVA summer emergency rating. | 345
| 210584 | 81497 | 143181 | [6 empty] | 0 | NWE | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (NWE) | Regional Reliability |  |  | 2022-12-01 | 2020-11-17 | 2020 ITP | 3277500 | 2021 | 3359437.5 | 3277500 |  |  |  | On Schedule < 4 |  |  |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA |  | 14.4
| 210617 | 91939 | 143253 | [6 empty] | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli - Lexington kV 138 kV | Regional Reliability | 2025-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 7865000 | 2021 | 8061625 | 7865000 |  | 0 |  | Delay - Mitigation Window | 521022 | PAOLI | 520973 | LEXINGTON | Rebuild 14.3 miles of 69 kV line from Paoli to Lexington to 138 kV | 69 |  |  |  |  | Y
| 210617 | 91939 | 143254 | [6 empty] | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Lexington - Lil Axe 138 kV | Regional Reliability | 2024-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 5340500 | 2021 | 5474012.5 | 5340500 |  | 0 |  | Delay - Mitigation Window | 520973 | LEXINGTON | 520976 | LITTLE AXE | Rebuild 9.7 miles of 69 kV line from Lexington to Lil Axe to 138 kV | 69 |  |  |  |  | Y
| 210617 | 91939 | 143255 | [6 empty] | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli 138 kV Terminal Upgrades | Regional Reliability | 2025-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 450000 | 2021 | 461250 | 450000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Convert 69 kV terminal equipment at Paoli Switch to 138 kV | [5 empty] | Y
| 210617 | 91939 | 143256 | [6 empty] | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Canadian Switch138 kV Terminal Upgrades | Regional Reliability | 2024-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 500000 | 2021 | 512500 | 500000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Convert 69 kV terminal equipment at Canadian Switch to 138 kV | [5 empty] | Y
| 210655 | 92112 | 143587 | [6 empty] | #N/A | EM | Sub - Platte City 161 kV | Platte City 161 kV Terminal Upgrade | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 55271.78 | 2022 | 55271.78 | 55271.78 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the switch at Platte City 161 kV for the Platte City - Weston 161 kV line. | 161
| 210675 | 92113 | 143588 | [6 empty] | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge - Round Up 345 kV | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 78293357 | 2022 | 78293357 | 78293357 |  |  |  | NTC - Commitment Window |  |  |  |  | Build 33.2 mile new 345 kV line from Kummer Ridge to Round Up | 345
| 210675 | 92113 | 143589 | [6 empty] | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge 345 kV Terminal Upgrades | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 342000 | 2022 | 342000 | 342000 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Kummer Ridge substation 345 kV to support a new 345 kV line from Round Up | 345
| 210675 | 92113 | 143590 | [6 empty] | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Round Up 345 kV Terminal Upgrades | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 342000 | 2022 | 342000 | 342000 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Round Up substation 345 kV to support a new 345 kV line from Kummer Ridge | 345
Base Plan | 210627 | 81717 | 122796 | TP2020266 | #N/A | TP2020266 | Yes | Base Plan - Add in Future (2025) | TP2020266 | TP2020266 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | 2023-04-30 | 2025-01-08 | 2022-01-01 | 2021-11-05 | 2020 ITP | 12210364 | 2021 | 12828513.6775 | 8370000 | 5683773 | 0 |  | Delay - Mitigation | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support a new line 345 kV line from Border - Woodward 345 kV substation with a summer emergency rating of 1792 MVA | 345 | 0.2 |  |  |  | Y |  |  | James Horn | MOD number added 16810 / BPID-P20266001, P20266003, P20266004, P20266005
| 210637 | 92140 | 143663 | [6 empty] | #N/A | EKC | Sub - Jarbalo Junction 115 kV Breaker Upgrade | Jarbalo Junction 115 kV Breaker | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 236539 | 2022 | 236539 | 236539 |  |  |  | On Schedule < 4 |  |  |  |  | Replace breaker 115-483 at the Jarbalo Junction substation | 115
| 210647 | 92144 | 143664 | [6 empty] | #N/A | EM | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 255075 | 255075 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R3-7 breaker at the Shawnee Mission 161 kV substation | 161
| 210647 | 92144 | 143665 | [6 empty] | #N/A | EM | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV Breaker | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 255075 | 255075 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R7-12 breaker at the Shawnee Mission 161 kV substation | 161
| 210647 | 92141 | 143666 | [6 empty] | #N/A | EM | Sub - Craig 161 kV Breaker | Craig 161 kV Breaker #2 | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 319002 | 2022 | 319002 | 319002 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R5-33 breaker at the Craig 161 kV substation | 161
| 210640 | 92142 | 143667 | [6 empty] | #N/A | MRES | Sub - Moorhead 230 kV Substation Reconfiguration | Moorhead 230 kV Substation Reconfiguration | Regional Reliability | 2024-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 9989000 | 2022 | 9989000 | 9989000 |  |  |  | Delay - Mitigation |  |  |  |  | Reconfigure the Moorhead 230 kV substation with a ring bus, expandable to breaker-and-a-half. | 230
| 210654 | 92143 | 143668 | [6 empty] | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th - Stateline 161 kV Rebuild | Regional Reliability | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 10688750 | 2022 | 10688750 | 10688750 |  |  |  | On Schedule < 4 |  |  |  |  | Rebuild approximately 5.5 miles of the existing 161 kV line from Joplin West 7th to Stateline. | 161
| 210654 | 92143 | 143669 | [6 empty] | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th 161 kV Terminal Upgrades | Regional Reliability | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 393232 | 2022 | 393232 | 393232 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at Joplin West 7th 161 kV substation. | 161
| 210654 | 92143 | 143670 | [6 empty] | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Stateline 161 kV Terminal Upgrades | Regional Reliability | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 209518 | 2022 | 209518 | 209518 |  |  |  | On Schedule < 4 |  |  |  |  | : Upgrade any necessary terminal equipment at Stateline 161 kV substation. | 161
| 210619 | 92180 | 143705 | [6 empty] | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Kearney NE - Tower 115 kV Ckt 1 New Line | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 11250834 | 2022 | 11250834 | 11250834 |  | 0 |  | NTC - Commitment Window | 640248 | Kearney Northeast | 640383 | Tower | Build a new 115 kV 10 mile line from Kearney to Tower with a minimum summer emergency rating of 160 MVA |  | 10
| 210675 | 92168 | 143714 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Tande 345 kV New Line | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 67411405 | 2022 | 67411405 | 67411405 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 48 mile 345 kV line from Finstad to Tande. | NULL
| 210656 | 92190 | 143806 | [6 empty] | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Tap (OKGE) – Marietta Switchyard (WFEC) 138 kV Ckt 1 New Line (OGE) | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 1575000 | 2022 | 1575000 | 1575000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new 2.1 mile 138 kV line from Marietta Tap (OKGE) – Marietta Switchyard (WFEC) | 138
| 210656 | 92190 | 143815 | [6 empty] | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta 2 138 kV Voltage Conversion | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 5000000 | 2022 | 5000000 | 5000000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Convert the Marietta 2 substation from 69 kV to 138 kV and install terminal equipment to support a new 138 kV line from Marietta 4 | 69
| 210656 | 92190 | 143816 | [6 empty] | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point - Marietta 2 138 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 8806000 | 2022 | 8806000 | 8806000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild the existing 69 kV line from Rocky Point to Marietta 2 as a 138 kV line | 69
| 210656 | 92190 | 143817 | [6 empty] | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point 69 kV Replace Relays | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 250000 | 2022 | 250000 | 250000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Replace the existing relays at Rocky Point | 69
| 210641 | 92213 | 143980 | [6 empty] | #N/A | NIPCO | Multi - Sioux City - Hinton 69 kV | Hinton 69 kV Terminal Equipment | Regional Reliability | 2023-10-31 |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 277500 |  |  |  | NTC - Commitment Window |  |  |  |  | Upgrade the terminal equipment at Hinton (K412) substation. | NULL
| 210663 | 92178 | 144148 | [6 empty] | #N/A | MWE | Multi - E Newtown 115 kV | E Newtown 115 kV New Statcom | Regional Reliability | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 22213115 | 2022 | 22213115 | 22213115 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install a 150 MVAR statcom and supporting equipment at E Newtown to control voltage on the 115 kV transmission system
| 210663 | 92211 | 144163 | [6 empty] | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | Folvag 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 613746 | 2022 | 613746 | 613746 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Folvag 115 kV sub to accommodate new 115 kV line from NE Williston 115 kV sub.
| 210675 | 92211 | 144171 | [6 empty] | #N/A | BEPC | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Substation | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 17766381 | 2022 | 17766381 | 17766381 |  |  |  | NTC - Commitment Window |  |  |  |  | Bisect the Judson to Tande 345 kV line approximately 18 miles from Judson and build a new 345 kV Substation.
| 210657 | 92190 | 144173 | [6 empty] | #N/A | WFEC | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Switchyard 138 kV Ckt 1 Terminal Equipment | Regional Reliability | 2023-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 736000 | 2022 | 736000 | 736000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at WFEC Marietta Switch to support a new 138 kV line from OG&E Marietta.
| 210663 | 92211 | 144177 | [6 empty] | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston - Folvag 115 kV New Line | Regional Reliability | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 3800000 | 2022 | 3800000 | 6490000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Build a new 4.5 mile 115 kV line from NE Williston to Folvag.
| 210663 | 92211 | 144178 | [6 empty] | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 596597 | 2022 | 596597 | 596597 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at NE Williston 115 kV sub to accommodate new 115 kV line from Folvag 115 kV sub.
| 210675 | 92211 | 144198 | [6 empty] | #N/A | BEPC | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Transformer | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5904650 | 2022 | 5904650 | 5904650 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Transformer at the new East Fork 345/115 kV Substation.
| 210663 | 92211 | 144199 | [6 empty] | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 115 kV Terminal Equipment | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 2511246 | 2022 | 2511246 | 2511246 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 115 kV terminal equipment at MWEC’s East Fork 115 kV substation to accommodate a 115 kV tie line from the East Fork 345/115 kV substation. Construct a 115 kV tie line from the East Fork 115 kV substation to the proposed BEPC East Fork 345/115 kV substation.
| 210663 | 92178 | 144202 | [6 empty] | #N/A | MWE | Multi - E Newtown 115 kV | E Newtown 115 kV Substation | Regional Reliability | 2031-12-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 1087789 | 2022 | 1087789 | 1087789 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Expand existing 115 kV E Newtown substation to accommodate the statcom interconnection. | NULL
| 210659 | 92237 | 144206 | [6 empty] | 0 | SPS | Line - Twist - Wilco 115 kV | Wilco 115 kV Substation | Regional Reliability |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 9225928 | 2022 | 9225928 | 9225928 |  |  |  | NTC - Commitment Window |  |  |  |  | Tap the RB-Exum to Hillmar Cheese Plant 115 kV line 4 miles west of the RB-Exum substation and build the new Wilco 115 kV Substation
| 210659 | 92237 | 144207 | [6 empty] | 0 | SPS | Line - Twist - Wilco 115 kV | Twist 115 kV Substation | Regional Reliability |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 8909901 | 2022 | 8909901 | 8909901 |  |  |  | NTC - Commitment Window |  |  |  |  | Tap the RB-Kemp to Moore 115 kV line 1 mile east of the RB-Kemp substation and build the new Twist 115 kV Substation
| 210659 | 92237 | 144208 | [6 empty] | 0 | SPS | Line - Twist - Wilco 115 kV | Twist - Wilco 115 kV Ckt 1 | Regional Reliability |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 2678226 | 2022 | 2678226 | 2678226 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 115 kV line between the new Twist 115 kV Substation and the Wilco 115 kV Substation
| 210663 | 92168 | 144226 | [6 empty] | #N/A | MWE | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Vanhook 115 kV New Line | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 4702500 | 2022 | 4702500 | 4702500 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 5-mile 115 kV line from Finstad to Vanhook.
| 210675 | 92168 | 144227 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 115 kV Substation | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 4675697 | 2022 | 4675697 | 4675697 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 115 kV Substation with terminal equipment to support a line from Vanhook 115 kV substation.
| 210675 | 92168 | 144230 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345 kV New Substation | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 18822018 | 2022 | 18822018 | 18822018 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV Substation including 345 kV terminals for lines from Leland Olds 345 kV substation, Tande 345 kV substation and high side terminal equipment for Finstad 345/115 kV Ckt 1 transformer and Finstad 345/115 kV Ckt 2 transformer
| 210675 | 92168 | 144231 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad Switched Shunt | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 385021 | 2022 | 385021 | 385021 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a switched shunt at Finstad.
| 210675 | 92168 | 144233 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 1 Transformer | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5315254 | 5315254 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Ckt 1 Transformer at Finstad 345 | 345/115
| 210675 | 92168 | 144235 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 2 Transformer | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5315254 | 5315254 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Ckt 2 transformer at Finstad 115 and upgrade any necessary 115 kV terminal equipment. | 345/115
| 210675 | 92168 | 144236 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds - Finstad - 345 kV New Line | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 200761539 | 2022 | 200761539 | 200761539 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 123 mile 345 kV line from Leland Olds to Finstad.
| 210675 | 92168 | 144237 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds 345 kV Substation | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 9277339 | 2022 | 9277339 | 9277339 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV Substation with terminal equipment to support a new line from Finstad 345 kV substation.
| 210675 | 92168 | 144238 | [6 empty] | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Tande 345 kV Terminal Equipment | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5085047 | 2022 | 5085047 | 5085047 |  |  |  | NTC - Commitment Window |  |  |  |  | Install new terminal equipment at Tande to support a new 345 kV line from Finstad. Install a series compensation device at Finstad or Tande.
| 210663 | 92168 | 144239 | [6 empty] | #N/A | MWE | Multi - Tande - Finstad - Leland Olds 345 kV | Vanhook 115 kV Terminal Equipment | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 3811190 | 2022 | 3811190 | 3811190 |  |  |  | NTC - Commitment Window |  |  |  |  | Install new 115 kV terminal equipment at Vanhook to support a new 115 kV line from Finstad.
| 210619 | 92180 | 144283 | [6 empty] | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Tower 115 kV Terminal Equipment | Regional Reliability |  |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 1288644 | 2022 | 1288644 | 374583 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Tower 115 kV sub to support new line from Kearney 115 kV sub.
| 210619 | 92180 | 144284 | [6 empty] | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Kearney 115 kV Terminal Equipment | Regional Reliability |  |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 2692377 | 2022 | 2692377 | 374583 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 115 kV terminal equipment at Kearney 115 kV sub to support a new line from Tower 115 kV sub. | NULL
| 210486 | 51278 | 72006 | [6 empty] | 0 | WAPA | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | 2023-01-31 |  | 2024-06-01 | 2018-08-17 | SUS-002 | 90000 | 2018 | 99343.1601 | 90000 |  | 0 |  | On Schedule < 4 | 652427 | BISMARK | 655652 |  | Replace CTs at Bismarck 115 kV substation to increase rating of Bismarck - East Bismarck 115 kV line to at least 85 MVA. This is a mitigation upgrade resulting from the Sponsored Upgrade Study #SUS-002 CPEC North Bismarck Breaker. Costs will be Directly Assigned to CPEC. | 115
| 210522 | 81616 | 122599 | [6 empty] | 0 | NWE | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen A-Tap Breaker 115 kV | Sponsored Upgrade | 2019-06-01 |  | 2021-12-31 | 2019-09-06 | SUS-006 | 552668 | 2019 | 552668 | 552668 |  | 555000 | QUARTERLY TRACKING | Complete |  |  |  |  | Add breaker at Aberdeen A-tap for the new Aberdeen City - Aberdeen Industrial Park 115 kV line. | 115 | [5 empty] | Y
| 210563 | 81656 | 122664 | [6 empty] | 0 | NPPD | Line-Pauline-Hastings 115 kV Reconductor | Pauline - Hastings 115 kV Ckt 1 & Ckt 2 Reconductor | Sponsored Upgrade | 2022-12-01 |  | 2022-12-01 | 2020-07-14 | SUS-014 | 6000000 | 2020 | 6303750 | 6000000 |  | 0 |  | On Schedule < 4 | 640313 | Pauline | 640215 | Hastings | A reconductor of the Pauline – Hastings 115 kV transmission lines to achieve 193 MVA for normal and emergency ratings. The Pauline to Hastings 115 kV transmission lines are 13 miles each. |  |  | 13
| 210570 | 81559 | 112456 | [6 empty] | 0 | EDE | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EDE) | Transmission Service | 2023-01-01 |  | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 69054450 | 2022 | 69054450 | 69054450 |  | 0 |  | On Schedule < 4 | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 28.41 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 |  | 25.9
| 200477 | 51254 | 71963 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 14010573.3857 | 20297796 |  |  |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
| 200477 | 51254 | 71964 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  |  |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
| 200477 | 51254 | 71965 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  |  |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
| 200477 | 51254 | 71966 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 12441332.2716 | 15279402 |  |  |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
| 200477 | 51254 | 71967 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1405712.3383 | 1605462 |  |  |  | Delay - Mitigation |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
| 200477 | 51254 | 71968 | [6 empty] | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 4087712.7459 | 5656017 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
| 210569 | 81559 | 112457 | [6 empty] | 0 | EKC | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EKC) | Transmission Service | 2022-12-31 |  | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 4008402 | 2020 | 4211327.3513 | 7617027 |  | 0 |  | On Schedule < 4 | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 2.44 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 | 2.7
Zonal | 210576 | 91875 | 143156 | #N/A | #N/A | #N/A | No | Do Not Add (Zonal) | TP2020234 | TP2020234 | AEP | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Zonal Reliability | 2022-10-28 | 2022-12-13 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1184404 | 2021 | 1214014.1 | 1910669 | 1910669 | 0 |  | In Service |  |  |  |  | Install a new 23 MVAR capacitor bank at Grady 138 kV | 138 |  |  |  |  | Y |  |  | Dara Dixon
| 210590 | 91891 | 143183 | [6 empty] | 0 | EMW | Sub - Greenwood 161 kV Terminal Upgrades | Greenwood 161 kV Terminal Upgrades | Transmission Service | 2022-03-15 |  | 2021-12-31 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 600168 | 2021 | 615172.2 | 600168 |  | 0 |  | In Service | 541218 | Greenwood Energy Center 161 KV | 541233 | Lees Summit East 161 KV | Replace 2 breakers, relays at Greenwood 161 kV substation | 161 |  |  |  | Y | Y
| 210590 | 91892 | 143184 | [6 empty] | 0 | EMW | Sub - Pleasant Hill 161 kV and Lake Winnebago 161 kV Terminal Upgrades | Pleasant Hill 161kV and Lake Winnebago 161 kV Terminal Upgrades | Transmission Service | 2021-04-23 |  | 2021-06-01 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 337005 | 2021 | 337005 | 483586 |  | 483586 | QUARTERLY TRACKING | Complete | 541225 | Pleasant Hill 161 KV | 541243 | Lake Winnebago 161 KV | Replace 2 breakers at Pleasant Hill 161 kV substation and replace 1 switch at Lake Winnebago 161 kV substation in order to increase the limit on the Pleasant Hill - Lake Winnebago 161 kV line. | 161 |  |  |  | Y | Y | Y
Base Plan | 210627 | 81717 | 143182 | TP2020266 | #N/A | TP2020266 | Yes | Base Plan - Add in Future (2025) | TP2020266 | TP2020266 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward - Border 345 kV Ckt 1 (AEP) | Economic | 2024-05-24 | 2025-01-08 | 2022-01-01 | 2021-11-05 | 2020 ITP | 1259660 | 2021 | 1291151.5 | 5264319 | 5064769 | 0 |  | Delay - Mitigation |  |  |  |  | Build 0.84-miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm with a summer emergency rating of 1792 MVA. Oklahoma Gas and Electric Co. and American Electric Power shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC | 345 | 0.84 | [6 empty] | James Horn | P20266002 -T Line Costs minus dead ends
Base Plan | 210633 | 92114 | 143591 | TP2021281 | #N/A | #N/A | Yes | Added | TP2021281 | TP2021281 | AEP | Line- Catoosa - Blue Circle 69 kV | Blue Circle - Catoosa 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-05-01 | 2024-06-04 | 2023-06-01 | 2022-03-09 | 2021 ITP | 9020000 | 2022 | 9020000 | 9020000 | 8113212 | 0 |  | Delay - Mitigation |  |  |  |  | Rebuild 3.5 miles of 69 kV line from Catoosa to Blue Circle and upgrade any necessary terminal equipment at Catoosa and/or Blue Circle | 69 |  | 3.5
| 210708 | 92393 | 156293 | #N/A | TP2022737 | #N/A | Yes | Added | TP2022737 | TP2022737 | AEP | Multi - Siloam Springs-Siloam Springs City 161 kV Terminal Upgrades | Siloam Springs 161 kV Terminal Upgrade | Regional Reliability |  | 2024-06-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 698030 | 2023 | 698030 | 698030 | 693140 | 0 |  | On Schedule < 4 |  |  |  |  | Upgrade terminal equipment at Siloam Springs 161 kV substation | 161
| 210708 | 92386 | 156299 | #N/A | #N/A | #N/A | No | Base Plan - Add in Future (2027) | TP2022736 | TP2022736 | AEP | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis - 52nd & Delaware Tap 138 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2027-06-01 | 2022-12-09 | 2022 ITP | 951250 | 2023 | 951250 | 4951250 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild 138 kV line from 36th & Lewis to 52nd & Delaware Tap | 138
| 210708 | 92386 | 156300 | #N/A | #N/A | #N/A | No | Base Plan - Add in Future (2027) | TP2022736 | TP2022736 | AEP | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis 138 kV Ckt 1 Terminal Upgrade | Regional Reliability |  |  | 2027-06-01 | 2022-12-09 | 2022 ITP | 540691 | 2023 | 540691 | 540691 |  | 0 |  | On Schedule < 4 | 509800 | 36th & LEWIS |  |  | Replace wave traps at 36th & Lewis 138 kV substation | 138
Note on Y76: s306055: EcoSys = 2,984,870

## Q4 2023 (hidden)
4Q 2022 Project Tracking Initial Extract
| COMPLETE |  |  |  |  | Complete and in-service
| CLOSED OUT |  |  |  |  | In-service and all required project close-out documentation supplied by TO. Per BP 7060, Section 13, upgrades reported as closed out this quarter will not be included in subsequent reports.
| DELAY - MITIGATION |  |  |  |  | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project
| DELAY - MITIGATION WINDOW |  |  |  |  | Behind schedule, interim mitigation pending or project may change but time permits the implementation of project
| IDENTIFIED |  |  |  |  | Upgrade identified and included in Board approved study results
| IN SERVICE |  |  |  |  | Upgrade is in service, but not all project activities are complete
| NTC - COMMITMENT WINDOW |  |  |  |  | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
| NTC-C PROJECT ESTIMATE WINDOW |  |  |  |  | Within the NTC-C Project Estimate (CPE) window
| ON SCHEDULE < 4 |  |  |  |  | On Schedule within 4-year horizon
| ON SCHEDULE > 4 |  |  |  |  | On Schedule beyond 4-year horizon
| RE-EVALUATION |  |  |  |  | NTC/NTC-C active; pending re-evaluation
| RFP ISSUED |  |  |  |  | Responses for competeitive upgrades are being submitted and/or reviewed
| SUSPENDED |  |  |  |  | NTC/GIA suspended
Cost Allocation | NTC ID | PROJECT ID | UPGRADE ID | CPP | OWNER | PROJECT NAME | UPGRADE NAME | UPGRADE TYPE | Verified? | IN SERVICE DATE | EcoSys ISD (Updated) | RTO DETERMINED NEED DATE | LATEST NTC ISSUE DATE | SOURCE STUDY | BASELINE ESTIMATE | BASELINE YEAR | BASELINE ESTIMATE WITH ESCALATION | CURRENT COST ESTIMATE | EcoSys EAC (Loaded | BEST FINAL COST | FINAL COST SOURCE | PROJECT STATUS TYPE | FROM BUS NUM | FROM BUS NAME | TO BUS NUM | TO BUS NAME | UPGRADE DESCRIPTION | VOLTAGE | NEW MILES | RECONDUCTOR MILES | VOLTAGE CONVERSION MILES | LETTER OF COMMERCIAL OPERATION REC'D | MOD INFO REC'D | FINAL COST REC'D | GIS DATA | PM | Comments | FLC Comments
| 200433 | 31144 | 51764 | 0 | WFEC | Sub - Tupelo - Tupelo Tap 138 kV Terminal Upgrades | Tupelo 138 kV Terminal Upgrades | Economic |  | 2021-12-31 |  | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 100000 | 2017 | 110381.289 | 410000 |  | 0 |  | Delay - Mitigation | 505600 | Tupelo | 521071 | TUPELO TAP | Upgrade any necessary terminal equipment at Tupelo to increase the rating of the 138 kV line between Tupelo substation and Tupelo Tap substation. | 138
| 210545 | 81550 | 112435 | 0 | WFEC | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic |  | 2021-01-01 |  | 2021-01-01 | 2019-11-18 | 2019 ITP | 1000000 | 2020 | 1025000 | 1000000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Rebuild 2.03 miles of 138 kV line from Kingfisher to East Kingfisher and upgrade any necessary terminal equipment at East Kingfisher and/or Kingfisher to increase the summer emergency rating to 286 MVA | 138
| 210586 | 81553 | 112443 | 0 | WFEC | Line - Russett - South Brown 138 kV | Russett - South Brown 138 kV Ckt 1 Rebuild | Economic |  | 2027-12-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 10267390.81 | 2021 | 10524075.5803 | 10267390.81 |  | 0 |  | Delay - Mitigation | 505602 | Brown | 521044 | RUSSETT | Rebuild 18.62 miles of 138 kV line from Russett to South Brown and upgrade terminal equipment at South Brown as needed to achieve a summer emergency rating of 234 MVA | 138
| 210543 | 81557 | 112451 | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Arnold - Ransom 115kV Terminal Upgrades | Economic |  | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 462000 | 2020 | 485388.75 | 726694 |  | 0 |  | On Schedule < 4 | 531409 | ARNOLD | 531414 | RANSOM | Upgrade any necessary terminal equipment at Arnold and/or Ransom to increase the summer emergency rating to 165 MVA | 115
| 210543 | 81557 | 112452 | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Pile - Scott City 115kV Terminal Upgrades | Economic |  | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 1633500 | 2020 | 1716195.9375 | 437574 |  | 0 |  | On Schedule < 4 | 531432 | PILE | 531433 | SCOTT CITY | Upgrade any necessary terminal equipment at Pile and/or Scott City to increase the summer emergency rating to 229 MVA | 115
| 210543 | 81557 | 112453 | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Scott City - Setab 115kV Terminal Upgrades | Economic |  | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 1556500 | 2020 | 1635297.8125 | 467574 |  | 0 |  | On Schedule < 4 | 531433 | SCOTT CITY | 531464 | SETAB | Upgrade any necessary terminal equipment at Scott City and/or Setab to increase the summer emergency rating to 230 MVA | 115
Base Plan | 200386 | 31057 | 51560 | TA2011012 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | Do Not Add (Zonal) | 2022-11-20 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 25128911.6762 | 20716215 | 23741278 | 0 |  | Delay - Mitigation Window | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69 |  |  |  | Y | Y |  | Y | Brent Garret | Prev Comments: Waiting for POD to put in service. No final costs. - (A11012545-closed $1,437,431 / A11012198-closed $173 / A11012444-open $17,213,598) & TP2018017-closed $2,147,490) * Switches at pittsburg not in-service according to SCADA | CPP - TA2020053 / BPIDs A20053023, A20053010, A20053009, and A20053014 added to complete needed tap switch work
Direct Assignment | 210611 | 81474 | 112307 | TP2021310 | AEP | Sub - Oklaunion 345 kV Capacitive Reactive Power Support | Oklaunion 345 kV Capacitive Reactive Power Support | Generation Interconnection | Do Not Add (Direct Assigned) | 2024-10-01 | 2025-10-31 | 2023-05-15 | 2021-05-17 | DISIS-2016-002 | 9453182 | 2021 | 9931749.3387 | 25800000 | 26767089 | 0 |  | Delay - Mitigation |  |  |  |  | Install +200Mvar Capacitor Bank(s) at the Oklaunion 345kV substation. | 345 |  |  |  |  | Y |  |  |  | MOD number added 102550 | Includes all BPIDs on TP2021310
|  | 81483 | 112331 | TP2019285 | AEP | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (TOIF) (AEPW) | Generation Interconnection |  | 2024-09-30 | 2024-09-01 |  |  | GI STUDIES |  |  |  | 1175646 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating | 138 | 0.04 | [5 empty] | Y |  | GIA Oxbow Solar | Projects is on hold. Nothing to report at this time.
| 210540 | 81561 | 112504 | 0 | OGE | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345kV Terminal Upgrades (OGE) | Economic |  | 2024-01-01 |  | 2026-01-01 | 2019-11-18 | 2019 ITP | 4139615 | 2020 | 4349183.0094 | 4139615 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment to support a 345kV line from Wekiwa to Sooner rated at summer emergency of 1792 MVA | 345
| 210592 | 81547 | 112509 | 0 | EKC | Line - Wolf Creek - Blackberry 345 kV | Wolf Creek 345kV Terminal Equipment | Economic |  | 2025-12-31 |  | 2026-01-01 | 2021-01-21 | 2019 ITP | 11618029 | 2021 | 11908479.725 | 12217322 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wolf Creek to support 345kV line from Wolf Creek to Blackberry rated at 1792 MVA | 345
| 210586 | 81617 | 122577 | 0 | WFEC | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138kV Ckt 1 Rebuild | Economic |  | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 2850000 | 2020 | 2994281.25 | 5750000 |  | 0 |  | On Schedule < 4 | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Rebuild 5.09-mile 138 kV line from Anadarko to Gracemont as a double circuit and install/upgrade any necessary terminal equipment to increase the summer emergency rating to 353 MVA for each circuit | 138 |  | 5.07
| 210626 | 81547 | 122598 | 0 | NEET | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic |  | 2025-01-01 |  | 2026-01-01 | 2021-12-03 | 2019 ITP | 85168938 | 2021 | 87298161.45 | 85168938 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build a new 345kV line from Wolf Creek to Blackberry with a summer emergency rating of 1792 MVA | 345
| 210578 | 81675 | 122717 | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 1 | Economic |  | 2022-08-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 374400 | 2021 | 383760 | 374400 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/345
| 210578 | 81675 | 122718 | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 1 | Economic |  | 2022-08-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 | 512650 | GRDA1 345 | Upgrade terminal equipment at GRDA1 161 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/161
| 210586 | 81679 | 122722 | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Dover Switch - O'Keene 138 kV Ckt 1 Terminal Upgrades | Economic |  | 2025-12-31 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 910000 | 2021 | 932750 | 910000 |  | 0 |  | Delay - Mitigation | 520882 | DOVER SW | 521016 | OKEENE | Upgrade any necessary terminal equipment, increase clearances, and replace conductor to achieve a summer emergency rating of 136 MVA
| 210650 | 81691 | 122733 | #N/A | BEPC | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock 230 kV Terminal Upgrades | Economic |  | 2023-10-01 |  | 2025-01-01 | 2022-03-09 | 2021 ITP | 614000 | 2022 | 614000 | 614000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Whitlock 230 kV for Oahe to Sully Buttes to Whitlock to Glenham 230 kV line.
| 210648 | 81691 | 122734 | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Oahe 230 kV Terminal Upgrades (WAPA) | Economic |  |  |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 561800 | 2022 | 561800 | 561800 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade terminal equipment at Oahe 230 kV for the Oahe to Sully Buttes 230 kV line. Re-conductor three spans of line between Oahe 230 kV substation and Sully Buttes 230 kV substation..
| 210639 | 81691 | 122735 | #N/A | EREC | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes 230 kV Terminal Upgrades | Economic |  | 2023-11-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 587000 | 2022 | 587000 | 587000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Sully Buttes for Oahe - Sully Buttes - Whitlock 230 kV line
| 210645 | 81694 | 122739 | #N/A | NPPD | XFR - Columbus 230/115 | Columbus East 230/115 kV transformer | Economic |  | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 5080000 | 2022 | 5080000 | 5080000 |  | 0 |  | Delay - Mitigation | 640127 | Columbus East | 640126 | Columbus East | Replace the 230/115 kV transformer and any necessary terminal equipment at Columbus East. | 230/115
| 210645 | 81769 | 122741 | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff - Victory Hill 115kV Ckt 2 | Economic |  | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 7760000 | 2022 | 7760000 | 7760000 |  | 0 |  | Delay - Mitigation | 640338 | Scottsbluff | 640397 | Victory Hill | Build second 9 mile 115 kV line from Scottsbluff to Victory Hill.
| 210586 | 81617 | 122753 | 0 | WFEC | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138 kV Ckt 2 Rebuild | Economic |  | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 1750000 | 2021 | 1793750 | 3330000 |  | 0 |  | On Schedule < 4 | 520814 | ANADARKO | 515802 | Gracemont 138 kV | Rebuild 5.09-mile 138kV line from Anadarko to Gracemont as double circuit and add/upgrade any necessary equipment to increase the achieve a summer emergency rating of 353 MVA for each circuit |  |  | 5.07
| 210589 | 81617 | 122755 | 0 | OGE | Line - Anadarko - Gracemont 138kV | Gracemont 138 kV Ckt 2 Terminal Equipment | Economic |  | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 6075003 | 2021 | 6226878.075 | 1124593 |  | 0 |  | On Schedule < 4 | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Install terminal equipment at Gracemont 138 kV to support a second 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 353 MVA | NULL
|  | 81483 | 112332 | TP2019285 | AEP | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection |  | 2024-09-30 | 2024-09-01 |  |  | GI STUDIES |  |  |  | 9959548.73 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build a 3-breaker ring bus station on the Lieberman-North Benton 138 kV section of the Lieberman-Red Point 138 kV line to facilitate the new generation interconnection. | 138 | 1.32 | [5 empty] | Y |  | GIA Oxbow Solar | Projects is on hold. Nothing to report at this time.
| 210578 | 81675 | 122801 | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 2 | Economic |  | 2022-06-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 312000 | 2021 | 319800 | 312000 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | NULL
| 210578 | 81675 | 122802 | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 2 | Economic |  | 2022-06-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | 0 |  | Delay - Mitigation | 512656 | GRDA1 161 |  |  | Upgrade terminal equipment at GRDA1 161 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | 161
| 210628 | 81717 | 122823 | 0 | OGE | Multi - Border - Woodward 345 kV Tap | Border - Woodward Tap 345 kV Substation | Economic |  | 2023-04-01 |  | 2022-01-01 | 2021-11-05 | 2020 ITP | 11500000 | 2021 | 11787500 | 11500000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the existing Border to Woodward 345 kV line 19 miles from the Border station and build a new 345 kV substation or switching station
| 210616 | 81741 | 122848 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco 345 kV Terminal Equipment | Economic |  | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 1843729 | 2021 | 1889822.225 | 1843729 |  | 0 |  | On Schedule < 4 | 514801 | Minco 345 kv |  |  | Install terminal equipment at Minco substation 345 kV to support a new 345 kV line from Minco with a summer emergency rating of 1792 MVA | 345
| 210616 | 81741 | 122849 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (345 kV) | Economic |  | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 30707951 | 2021 | 31475649.775 | 30707951 |  | 0 |  | On Schedule < 4 |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper and terminals to accommodate cut in of existing Cimarron to Draper 345 kV line. Tie into existing Cimarron to Draper 345 kV line. This description is specific to the 345 kV components. | 345
| 210616 | 81741 | 122850 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 1 | Economic |  | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 5003830 | 2021 | 5128925.75 | 5003830 |  | 0 |  | On Schedule < 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
| 210616 | 81741 | 122851 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 2 | Economic |  | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 4885649 | 2021 | 5007790.225 | 4885649 |  | 0 |  | On Schedule < 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
| 210616 | 81741 | 122858 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Cimarron - Draper 345 kV Terminal Upgrades #2 | Economic |  | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 2541200 | 2021 | 2604730 | 2541200 |  | 0 |  | On Schedule < 4 | 514901 | CIMARRON 345 | 514934 | DRAPER LAKE 345 | Upgrade any necessary terminal equipment on the Cimarron to Draper 345 kV line to achieve a summer emergency rating of 1540 MVA
| 210656 | 81741 | 122863 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Midwest 138 kV Ckt 1 Terminal Upgrades | Economic |  | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 65000 | 2021 | 66625 | 65000 |  | 0 |  | On Schedule < 4 | 514946 | MIDWEST TAP 138 |  |  | Upgrade any necessary terminal equipment at Midwest 138 kV on the Midwest to Franklin 138 kV line to achieve a summer emergency rating of 308 MVA
| 210586 | 81679 | 122865 | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Aspen 138 kV Terminal Upgrades | Economic |  | 2022-04-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 202500 | 2021 | 207562.5 | 202500 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Aspen to Mooreland 138 kV line to achieve a summer emergency rating of 187 MVA rating
| 210586 | 81679 | 122866 | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Pic 138 kV Terminal Upgrades | Economic |  | 2022-04-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 405000 | 2021 | 415125 | 405000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Mooreland to Pic 138 kV line to achieve a summer emergency rating of 187 MVA rating
| 210670 | 81741 | 133085 | #N/A | NEET | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco - Pleasant Valley 345 kV Ckt 1 | Economic |  |  |  | 2025-01-01 | 2022-04-28 | 2020 ITP |  |  |  | 57512100 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 34.8 miles of 345 kV line from Minco to Pleasant Valley 345 kV to achieve a 1792 MVA summer emergency rating.
| 210670 | 81741 | 133106 | #N/A | NEET | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper - Pleasant Valley 345 kV Ckt 2 | Economic |  |  |  | 2025-01-01 | 2022-04-28 | 2020 ITP |  |  |  | 23400139 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build a second 13.2-mile 345 kV line from Draper 345 kV substation to Pleasant Valley 345 kV substation with a summer emergency rating of 1792 MVA
| 210616 | 81741 | 143176 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper 345 kV Terminal Equipment | Economic |  | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 6484533 | 2021 | 6646646.325 | 6484533 |  |  |  | On Schedule < 4 |  |  |  |  | Install a new line terminal at Draper 345 kV to accommodate new 345 kV line from Pleasant Valley.
|  | 81489 | 112333 | TP2021760 | AEP | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (TOIF) (AEPW) | Generation Interconnection |  |  | 2023-10-31 |  |  | GI STUDIES |  |  |  | 1704279 | 1934406 | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 345 | 0.18 | [5 empty] | Y | James Ball | AEP - 100% / P21760001 - In Construction | Confirm need to report cost.
| 210645 | 81769 | 143599 | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff 115 kV Ckt 2 Terminal Upgrades | Economic |  | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 1194000 | 2022 | 1194000 | 1194000 |  |  |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Scottsbluff 115 kV to support a second 115 kV line from Victory Hill. | 115
| 210645 | 81769 | 143600 | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Victory Hill 115 kV Ckt 2 Terminal Upgrades | Economic |  | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 1129000 | 2022 | 1129000 | 1129000 |  |  |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Victory Hill 115 kV to support a second 115 kV line from Scottsbluff with a summer emergency rating of 264 MVA | 115
| 210648 | 81691 | 143613 | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes - Whitlock 230 kV Line Clearance Increase | Economic |  | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 1744800 | 2022 | 1744800 | 1744800 |  |  |  | On Schedule < 4 |  |  |  |  | Increase ground clearance of the Sully Buttes to Whitlock 230 kV line. | 230
| 210648 | 81691 | 143614 | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock - Glenham 230 kV Clearance Increase | Economic |  | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 5845900 | 2022 | 5845900 | 5845900 |  |  |  | On Schedule < 4 |  |  |  |  | Increase ground clearance of the Whitlock - Glenham 230 kV. | 230
| 210656 | 92184 | 143786 | #N/A | OGE | Sub - Cleo Corner 69 kV & Cleo Junction 69 kV | Cleo Corner 69 kV Terminal Upgrades | Economic |  |  |  | 2023-01-01 | 2022-03-11 | 2021 ITP | 168228 | 2022 | 168228 | 168228 |  | 0 |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at the Cleo Corner 69 kV substation | 69
| 210644 | 92238 | 144142 | #N/A | TSGT | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (TSGT) | Economic |  | 2023-12-13 |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 380321 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
| 210645 | 92238 | 144143 | #N/A | NPPD | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (NPPD) | Economic |  | 2023-12-31 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 281000 | 2022 | 281000 | 281000 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
|  | 30959 | 51338 | 0 | EKC | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Burns 345kV (GEN-2014-001 NU) | Generation Interconnection |  | 2021-07-08 |  |  |  | GI STUDIES |  |  |  | 2098946 |  | 0 |  | In Service |  |  |  |  | Construct new terminal extension of the bus north to add another rung to the bus. Equipment includes two (2) 345kV breakers, four (4) 345kV switches, bus work, and all associated yard and conduit work.
|  | 30959 | 51360 | 0 | EKC | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 TOIF) | Generation Interconnection |  | 2021-07-28 |  |  |  | GI STUDIES |  |  |  | 1674997 |  | 0 |  | In Service |  |  |  |  | Install three (3) 345 kV arresters, one (1) 345 kV 3000 Amp motor-operated switch, three (3) 345 kV arrester stands, one (1) 345 kV full tension dead-end structure, and one (1) 3-phase bus support into new Transmission Owner GEN-2014-001 Point of Interconnection substation. The estimate also includes three (3) 345 kV VTs, three (3) 345 kV CTs, and revenue interconnection metering plus all other associated yard, cable, grounding, communication, and conduit work.
|  | 51239 | 71933 | 0 | NPPD | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generation Interconnection |  | 2024-04-01 |  |  |  | GI STUDIES |  |  |  | 4700000 |  |  |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345kV Substation - Install 345kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformers, potential transformers, and associated and miscellaneous material.; One (1) approximately five (5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Holt County 345 kV substation.
|  | 51239 | 71934 | 0 | NPPD | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generation Interconnection |  | 2024-04-01 |  |  |  | GI STUDIES |  |  |  | 5900000 |  |  |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
|  | 51255 | 71970 | #N/A | WFEC | Sub - Snyder 138kV (WFEC) - GEN-2015-013 Addition | Snyder 138kV (WFEC) - GEN-2015-013 Addition (NU) | Generation Interconnection |  | 2019-08-15 |  |  |  | GI STUDIES |  |  |  | 1700000 |  |  |  | On Schedule < 4 | 521052 | SNYDER |  |  | Snyder 138kV Substation: Install one (1) new line terminal, one (1) 2000A circuit breaker, line relaying, disconnect switches, additional 4” IPS aluminum buss, and associated equipment. | [5 empty] | #N/A | #N/A
|  | 51261 | 71982 | 0 | NPPD | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Belvidere – Fairbury 115kV circuit #1 | Generation Interconnection |  | 2019-11-01 |  |  |  | GI STUDIES |  |  |  | 1700000 |  |  |  | Re-evaluation |  |  | 640169 | Fairbury | NPPD Belvidere – Fairbury 115kV circuit #1: uprate Belvidere – Fairbury to at least 107 MVA | 115/115 |  |  |  | Y
|  | 51261 | 71983 | 0 | NPPD | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Beatrice – Harbine 115kV circuit #1 | Generation Interconnection |  | 2019-11-01 |  |  |  | GI STUDIES |  |  |  | 900000 |  |  |  | Re-evaluation | 640076 | Beatrice | 640208 | Harbine | NPPD Beatrice – Harbine 115kV circuit #1: uprate Beatrice – Harbine to at least 102 MVA | 115/115 |  |  |  | Y
|  | 51283 | 72032 | 0 | EKC | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generation Interconnection |  | 2019-12-01 |  |  |  | GI STUDIES |  |  |  | 591193 |  | 0 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51283 | 72033 | 0 | EKC | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU) | Generation Interconnection |  | 2019-12-01 |  |  |  | GI STUDIES |  |  |  | 13383989 |  | 0 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation - Non-Shared Network Upgrades: Construct three (3) 345kV 4000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Allowance for Funds Used During Construction (AFUDC) and Contingency funds are included in this cost estimate.
|  | 51283 | 72034 | 0 | OGE | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generation Interconnection |  | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 20000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Oklahoma Gas and Electric Company – Checking and Verifying Relay Settings
|  | 51332 | 82126 | 0 | OGE | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (TOIF) | Generation Interconnection |  | 2022-10-14 |  |  |  | GI STUDIES |  |  |  | 1099958 |  | 0 |  | On Schedule < 4 | 515800 | Gracemont 345kv |  |  | Transmission Owner Gracemont Interconnection Substation: Transmission Owner Interconnection Facilities 345kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51332 | 82127 | 0 | OGE | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (NU) | Generation Interconnection |  | 2022-10-14 |  |  |  | GI STUDIES |  |  |  | 1025042 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner Gracemont Interconnection Substation - Non-Shared Network Upgrades install one (1) 3000A circuit breakers, control panel replacement, line relaying, disconnect switches, and all other associated work and materials.
|  | 51333 | 82128 | 0 | OGE | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generation Interconnection |  | 2022-10-15 |  |  |  | GI STUDIES |  |  |  | 1099958 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation: Transmission Owner Interconnection Facilities Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51333 | 82129 | 0 | OGE | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generation Interconnection |  | 2022-10-15 |  |  |  | GI STUDIES |  |  |  | 9213042 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation - Non-Shared Network Upgrades* Install three (3) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
|  | 81489 | 112334 | TP2021760 | AEP | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (AEPW) | Generation Interconnection |  | 2023-05-01 | 2023-10-31 |  |  | GI STUDIES |  |  |  | 17798882 | 7067936.0422 | 0 |  | On Schedule < 4 |  |  |  |  | Construct new 345 kV four (4) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators ,and all other associated work and materials. | 345 | 0.32 | [5 empty] | Y | James Ball | AEP - 39.71% / Treasure Island - In Construction | Confirm need to report cost.
|  | 81491 | 112337 | TP2019265 | AEP | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (TOIF) (AEPW) | Generation Interconnection |  |  | 2023-05-11 |  |  | GI STUDIES |  |  |  | 918474 | 680247 | 0 |  | In Service |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 138 | 0.04 | [5 empty] | Y | Chadwick Bell | Tonkawa | Confirm need to report cost.
|  | 81491 | 112338 | TP2019265 | AEP | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (Non-Shared NU) (AEPW) | Generation Interconnection |  |  | 2023-05-11 |  |  | GI STUDIES |  |  |  | 7400346 | 3741126 | 0 |  | In Service |  |  |  |  | Construct new 138 kV three (3) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 138 | [6 empty] | Y | Chadwick Bell | White Rock Wind West - Station | Confirm need to report cost.
Base Plan | 210623 | 81500 | 112360 | TP2019245 | AEP | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | Base Plan - Add in Future (2026) | 2026-05-01 | 2026-05-01 | 2021-06-01 | 2021-11-05 | 2019 ITP | 41100000 | 2020 | 44260204.48 | 46270466 | 46079373 | 0 |  | Delay - Mitigation | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 27 breakers at Riverside Station 138 kV with 90 kA breakers and expand substation as necessary to accommodate physically larger breakers | 138 | 1.56 |  |  |  | Y |  | Y | Brad Duvall | All BPIDs | Includes all BPIDs on TP2019245
Base Plan | 210544 | 81501 | 112361 | TA2019024 | AEP | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | Base Plan - Add in Future (2025) | 2024-10-30 | 2025-01-08 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4761304.958 | 4194065 | 4123280 | 0 |  | Delay - Mitigation | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138 |  |  |  |  | Y |  | Y | Nathan Ingram | NTC Work 2 BPIDs Station & Removal - A19024004 & A19024002
Base Plan | 210544 | 81520 | 112389 | TP2020033 | AEP | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | Already Added | 2022-05-27 | 2022-06-23 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 7064651.2565 | 6724237 | 6452547 | 0 |  | In Service | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2 |  |  |  | Y |  | Y | Larry Oden | P20033001, 2, 3, & 6
Base Plan | 210544 | 81523 | 112393 | TP2020033 | AEP | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | Already Added | 2021-11-17 | 2021-11-17 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1340497.05 | 1549008 | 1868658 | 0 |  | In Service | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5 |  |  | Y |  | Y | Larry Oden | P20033004, P20033005 & P20033007
|  | 81488 | 112339 | 0 | WAPA | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (TOIF) (WAPA) | Generation Interconnection |  | 2023-12-29 |  |  |  | GI STUDIES |  |  |  | 250000 |  | 0 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 81488 | 112340 | 0 | WAPA | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection |  | 2023-12-29 |  |  |  | GI STUDIES |  |  |  | 8805000 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 230 kV switchyard on the Oahe - Fort Thompson North 230 kV transmission that will consist of a three (3) breaker ring bus, three (3) 230 kV power circuit breakers, nine (9) 230 kV disconnect switches, instrument transformers, associated control and protection equipment, high voltage bus, three (3) line take-off structures, conductor, overhead optical ground wire, communication equipment, and a control building.
|  | 81495 | 112353 | 0 | SPS | XTO to Cornell GEN-2016-177 Interconnection Costs | XTO to Cornell GEN-2016-177 Interconnection (TOIF) (SPS) | Generation Interconnection | [5 empty] | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-177 (17.0 MW/Gas Turbine) into the POI at XTO_Cornell 115kV.
| 210609 | 81591 | 122537 | 0 | OGE | Device - Border 345kV Capacitive Reactive Support | Border 345kV Capacitive Reactive Support | Generation Interconnection |  | 2024-04-20 |  | 2023-04-20 | 2021-05-17 | DISIS-2016-002 | 3996000 | 2021 | 4095900 | 3996000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Install + 275 MVAR Capacitor Bank(s) at Border 345 kV.
|  | 81594 | 122540 | 0 | SPS | Device - Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002-1) | Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002) | Generation Interconnection |  | 2021-12-31 |  |  |  | GI STUDIES |  |  |  | 7365886 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install + 100 MVAR Capacitor Bank(s) at Crossroads 345 kV. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81600 | 122546 | 0 | SPS | Line - Crossroads - Tolk 345 kV Ckt 1 | Crossroads - Tolk 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  | 2020-12-01 |  |  |  | GI STUDIES |  |  |  | 184651 |  | 0 |  | On Schedule < 4 |  |  |  |  | Replace approximately four structures on the Crossroads - Tolk 345 kV line to achieve a minimum rating of 956 MVA. Network Upgrade shared among four requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81599 | 122547 | 0 | SPS | Line - Crossroads - Eddy County 345 kV Ckt 1 | Crossroads - Eddy County 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  | 2022-12-15 |  |  |  | GI STUDIES |  |  |  | 210533 |  |  |  | On Schedule < 4 |  |  |  |  | Replace two 345 kV structures, wave traps (3X), and jumpers to achieve minimum emergency rating of 956 MVA. Network Upgrade Shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81606 | 122554 | 0 | SPS | Roadrunner 115kV GEN-2016-121 Interconnection Costs | Roadrunner 115kV GEN-2016-121 Interconnection (TOIF) (SPS) | Generation Interconnection | [5 empty] | GI STUDIES |  |  |  | 483969 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-121 (110.0 MW/Solar) into the POI at Roadrunner 115kV.
|  | 81607 | 122556 | 0 | SPS | Eddy County to Tolk GEN-2016-123 Interconnection Costs | Eddy County to Tolk GEN-2016-123 Interconnection (TOIF) (SPS) | Generation Interconnection | [5 empty] | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-123 (298.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
|  | 81608 | 122558 | 0 | SPS | Eddy County to Tolk GEN-2016-124 Interconnection Costs | Eddy County to Tolk GEN-2016-124 Interconnection (TOIF) (SPS) | Generation Interconnection | [5 empty] | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-124 (150.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
|  | 81609 | 122560 | 0 | SPS | Eddy County to Tolk GEN-2016-125 Interconnection Costs | Eddy County to Tolk GEN-2016-125 Interconnection (TOIF) (SPS) | Generation Interconnection | [5 empty] | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-125 (74.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
|  | 81613 | 122568 | 0 | SPS | XFR - Tolk 345/230 kV Ckt2 | Tolk 345/230 kV CKT 2 Transformer (DISIS-2016-002) | Generation Interconnection |  | 2021-12-31 |  |  |  | GI STUDIES |  |  |  | 14055360 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new 345/230 kV Transformer Ckt 2 at Tolk to achieve a minimum emergency rating of 921 MVA on the Crossroads - Tolk 345 kV Ckt 1 line. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  | 0.5
| 210564 | 81489 | 122600 | 0 | OGE | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (OKGE) | Generation Interconnection |  | 2021-12-31 |  | 2020-09-22 | 2020-08-11 | DISIS-2016-002 | 10000 | 2020 | 10250 | 10000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Relay settings upgrades
| 210630 | 81490 | 122601 | 0 | OGE | Multi - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Terminal Equipment | Generation Interconnection |  | 2023-12-31 |  | 2023-12-31 | 2022-01-31 | DISIS-2016-002 |  |  |  | 10000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Change relay settings to accommodate the construction of the GEN-2016-095 wind farm.
| 210562 | 81628 | 122602 | 0 | WAPA | Sub - Jamestown 230 kV Redundant Bus Tie | Jamestown 230 kV Redundant Bus Tie | Generation Interconnection |  | 2024-12-31 |  |  | 2020-06-10 | DISIS-2016-001 | 1510000 | 2020 | 1586443.75 | 1510000 |  | 0 |  | In Service |  |  |  |  | Add a redundant bus to Jamestown 230 kV substation to mitigate for a fault and breaker fail of CB 9182.
| 210565 | 81481 | 122622 | 0 | EKC | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Substation Upgrades | Generation Interconnection |  | 2025-12-31 |  |  | 2020-08-28 | DISIS-2016-002 | 139825 | 2020 | 146903.6406 | 136893 |  | 0 |  | In Service |  |  |  |  | Replace one control panel and review and/or apply new relay settings at the Swissvale substation.
|  | 81481 | 122623 | 0 | EKC | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Terminal Upgrades | Generation Interconnection |  | 2025-12-31 |  |  |  | GI STUDIES | 10000 | 2020 | 10506.25 | 10000 |  | 0 |  | In Service |  |  |  |  | Reviewing and applying new relaying settings at the Swissvale substation for the interconnection of GEN-2016-158.
|  | 81636 | 122635 | 0 | OGE | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | GEN-2016-119 Interconnection (TOIF) (OKGE) | Generation Interconnection |  | 2025-03-14 |  |  |  | GI STUDIES |  |  |  | 1099871 |  | 0 |  | On Schedule < 4 |  |  |  |  | Add a single 345kV line terminal to a new EHV Substation. Dead end structure, line switch, line relaying, revenue metering including CTs and PTs.
| 210606 | 81636 | 122637 | 0 | EKC | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | Spring Creek345 kV (GEN-2016-119) | Generation Interconnection |  |  |  | 2025-03-15 | 2021-03-04 | DISIS-2016-002 | 16624 | 2021 | 17039.6 | 16624.73 |  | 0 |  | On Schedule < 4 |  |  |  |  | Review and/or apply relay protection settings at the Spring Creek substation.
|  | 81639 | 122640 | 0 | SPS | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  | 2021-12-17 |  |  |  | GI STUDIES |  |  |  | 4578401 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum system emergency rating of 430 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81640 | 122641 | 0 | SPS | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 697513 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum emergency rating of 456 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81641 | 122642 | 0 | SPS | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | [5 empty] | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125 | [5 empty] | #N/A | #N/A
|  | 81642 | 122643 | 0 | SPS | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Generation Interconnection | [5 empty] | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81645 | 122645 | 0 | SPS | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  | 2021-12-15 |  |  |  | GI STUDIES |  |  |  | 4852215 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 90/90 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  |  | 13
|  | 81644 | 122646 | 0 | SPS | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  | 2020-12-15 |  |  |  | GI STUDIES |  |  |  | 968567 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 478 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81646 | 122647 | 0 | SPS | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection |  | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 5943138 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Tuco 230 kV Substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81647 | 122648 | 0 | SPS | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection |  | 2021-10-28 |  |  |  | GI STUDIES |  |  |  | 3318135 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Deaf Smith 115 kV substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
|  | 81655 | 122662 | 0 | OGE | Woodring 345kV GEN-2016-128 Interconnection Costs | Woodring 345kV GEN-2016-128 Interconnection (TOIF) (OKGE) | Generation Interconnection | [5 empty] | GI STUDIES |  |  |  | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At an existing EHV substation, update relay settings on an existing Gen-Tie line to accommodate new protection settings.
| 210593 | 81561 | 112458 | TS2020480 | TSOK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic | Do Not Add (2025) - Formula Rates??? | 2026-01-01 | 2025-10-08 | 2026-01-01 | 2021-02-10 | 2019 ITP | 97111851 | 2020 | 104578841.4 | 97111851 | 104642958 | 0 |  | On Schedule < 4 | 509755 | WEKIWA 345KV | 514803 | SOONER 345 | Build a new 345kV line from Sooner to Wekiwa with a summer emergency rating of 1792 MVA | 345 | 50.5 | [6 empty] | Katherine Vecchiarelli
Base Plan | 210544 | 81561 | 112460 | TP2019146 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | Base Plan - Add in Future (2025) | 2025-05-01 | 2025-02-26 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 789920.8076 | 1242638 | 0 | 0 |  | On Schedule < 4 | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138 |  |  |  |  | Y |  | Y |  |  | There is no work being completed on this UID. What is being reported?
| 210631 | 81657 | 122667 | #N/A | OGE | Multi - Riverside 345 kV Substation | Redbud 345kV | Generation Interconnection |  | 2025-12-31 |  | 2025-12-31 | 2022-01-31 | DISIS-2016-002 |  |  |  | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Change relay settings to accommodate the Interconnection of the States Edge 1 Wind Farm.
|  | 81658 | 122669 | 0 | BEPC | GEN-2016-130 Interconnection Costs | Leland Olds 345 kV Substation Reconfiguration (DISIS-2016-002-2) | Generation Interconnection |  | 2025-06-30 |  |  |  | GI STUDIES |  |  |  | 2776827 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build out of a new line terminal for relocation of LOS Unit 2 main transformer. This includes one (1) 345 kV power circuit breaker, two (2) 345 kV breaker disconnect switches, three (3) 345 kV PTs, three (3) 345 kV surge arrestors, and protection and control package.
|  | 81660 | 122673 | 0 | EKC | Viola 345kV GEN-2016-153 Interconnection Costs | Viola 345kV GEN-2016-153 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection |  | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 20000 |  | 0 |  | In Service |  |  |  |  | Review relay settings and apply adjusted settings at Flat Ridge 2 East and Viola 345 kV substations. Install PMU at Viola Substation
| 210612 | 81660 | 122674 | 0 | OGE | Viola 345kV GEN-2016-153 Interconnection Costs | Renfrow 345 kV Relay Setting Adjustment | Generation Interconnection |  | 2023-10-01 |  | 2023-10-01 | 2021-06-08 | DISIS-2016-002 | 15000 | 2021 | 15375 | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At the existing Renfrow 345 kV substation, update relay settings to accommodate new protection settings.
|  | 81661 | 122676 | 0 | EKC | Benton 345kV GEN-2016-162 and 163 Interconnection Costs | Benton 345kV GEN-2016-162 and 163 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection |  | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 810255 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 345 kV circuit breaker and two (2) new 345 kV disconnect switches.
|  | 81662 | 122677 | 0 | NPPD | Sweetwater 345kV GEN-2016-074 Interconnection Costs | GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection |  | 2024-02-01 |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Expanding the existing Sweetwater 345kV Substation to accommodate the GEN-2016-074 interconnection request
|  | 81662 | 122678 | 0 | NPPD | Sweetwater 345kV GEN-2016-074 Interconnection Costs | Sweetwater 345kV GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection |  | 2024-02-01 |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Expand the existing Sweetwater 345kV Substation to accommodate GEN-2016-074 interconnection request
|  | 81665 | 122684 | 0 | TSGT | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (TOIF) (TSGT) | Generation Interconnection |  | 2023-10-05 |  |  |  | GI STUDIES |  |  |  | 1636796 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 81665 | 122687 | 0 | TSGT | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (Non-Shared NU) (TSGT) | Generation Interconnection |  | 2023-10-05 |  |  |  | GI STUDIES |  |  |  | 2155837 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230 kV power circuit breaker, two (2) 115 kV power circuit breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
|  | 81666 | 122688 | 0 | WAPA | Bismark to Glenham GEN-2016-087 Interconnection Costs | Bismark to Glenham 230kV GEN-2016-087 Interconnection (TOIF) (WAPA) | Generation Interconnection |  | 2023-08-30 |  |  |  | GI STUDIES |  |  |  | 644488 |  | 0 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and the re-route of the Glenham line to the new 230 kV line bay.
|  | 81670 | 122791 | 0 | OGE | Viola 345/138 kV Transformer CKT 2 | GEN-2016-119 Tap - Arcadia 345kV (DISIS-2016-002-3) | Generation Interconnection |  | 2025-12-31 |  |  |  | GI STUDIES |  |  |  | 68725000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new terminal at new substation on Sooner to Spring Creek line being built for Gen-2016-119. Expand Arcadia Substation and re-route four transmission lines to allow for room for new transmission line to be brought in. Build approximately 47 miles of new 345kV line from new substation to Arcadia.
|  | 81670 | 122792 | 0 | EKC | Viola 345/138 kV Transformer CKT 2 | Viola 345/138 kV Transformer CKT 2 (DISIS-2016-002-2) | Generation Interconnection | [5 empty] | GI STUDIES |  |  |  | 9204586 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install a new 345 kV terminal on a new rung consisting of two (2) breakers, four (4) switches, and two (2) control panels. Install a new 138 kV terminal on an existing rung consisting of one (1) breaker, three (3) switches, three (3) PTs, and one (1) 400/440 MVA 345-138 kV transformer with LTCs. Network Upgrade shared among fourteen requests: GEN-2016-100, GEN-2016-101, GEN-2016-119, GEN-2016-128, GEN-2016-133, GEN-2016-134, GEN-2016-137, GEN-2016-138, GEN-2016-139, GEN-2016-141, GEN-2016-142, GEN-2016-145, GEN-2016-146, GEN-2016-153
| 210643 | 81773 | 143127 | 0 | OGE | Sub - Chisholm - Gracemont 345 kV | Gracemont 345 kV | Generation Interconnection |  | 2022-09-01 |  | 2022-09-01 | 2022-02-25 | DISIS-2017-001 | 15000 | 2022 | 15000 | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At the existing Gracmont 345 kV substation, update relay settings to accommodate new protection settings.
|  | 81661 | 143150 | 0 | EKC | Benton 345kV GEN-2016-162 and 163 Interconnection Costs | Benton 345kV GEN-2016-162 and 163 Interconnection (TOIF) (WERE) | Generation Interconnection |  | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 1198282 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 345 kV dead-end, one (1) new 345 kV disconnect switch, three (3) new voltage transformers, three (3) new current transformers, and one (1) new line panel.
| 200277 | 30678 | 50889 | 0 | NPPD | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority |  | 2025-12-31 |  | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 11338457.3874 | 9797157 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640381 | Thedford | Install new 345/115 kV 400 MVA transformer at Thedford substation. Install any necessary 115 kV terminal equipment. | 345/115
| 200277 | 30678 | 51002 | 0 | NPPD | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority |  | 2025-12-31 |  | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1134089.4193 | 913714 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Install any necessary 345 kV terminal equipment at Thedford associated with new 345/115 kV transformer. | 345
| 200397 | 242 | 10308 | 0 | WFEC | Line - Elmore - Paoli 69 kV Rebuild | Elmore - Paoli 69 kV Ckt 1 Rebuild | Regional Reliability |  | 2024-03-31 |  | 2009-06-01 | 2016-05-17 | 2016 ITPNT | 3240000 | 2016 | 3757406.6808 | 4339358 |  | 4171494.22 | FORMULA RATE UPDATE | Delay - Mitigation | 520898 | ELMORE | 521022 | PAOLI | Rebuild 10.8-mile 69 kV line from Elmore to Paoli. | 69 |  | 10.8
| 200397 | 844 | 11113 | 0 | WFEC | Line - Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Regional Reliability |  | 2020-12-31 |  | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 4725000 | 2016 | 5215515.9052 | 4725000 |  |  | FORMULA RATE UPDATE | Delay - Mitigation | 521005 | MUSTANG | 521058 | SUNSHINE CANYON | Rebuild 10-mile 69 kV line from Sara Road to Sunshine Canyon. | 69 |  | 10 |  |  |  | Y
| 200220 | 30375 | 50442 | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability |  | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 204236579 | 2020 | 214576055.8119 | 204236579 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640183 | Gerald Gentleman Station | Build new 110-mile 345 kV line from Gerald Gentleman Station substation to new Cherry County substation. This upgrade is contingent upon approval from Western Area Power Administration ("WAPA") to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 100.7
| 200220 | 30375 | 50444 | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability |  | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 13692681 | 2020 | 14385872.9756 | 13692681 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Build new Cherry County 345 kV substation and install necessary terminal equipment. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
| 200220 | 30375 | 50445 | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability |  | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 232903698 | 2020 | 244694447.7113 | 232903698 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640503 | Holt County 345 kV | Build new 117-mile 345 kV line from new Cherry County substation to new Holt County substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 124.3
| 210618 | 30375 | 50446 | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability |  | 2025-12-31 |  | 2018-01-01 | 2021-11-04 | 2012 ITP10 | 577000 | 2021 | 591425 | 577000 |  | 0 |  | Delay - Mitigation | 640503 | Holt County 345 kV |  |  | Add line bay terminal equipment as necessary to connect, commission and operate the 345 kV line from Thedford to Holt County Substation. | 345
| 200200 | 30491 | 50600 | 0 | WFEC | Device - Hazelton 69 kV | Hazelton 69 kV Capacitor | Regional Reliability |  | 2017-03-01 |  | 2013-01-01 | 2013-03-01 | DPA-2012-MAR-143-147 | 237000 | 2013 | 261603.6549 | 735000 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520937 | HAZELTON |  |  | Install two 4.8 Mvar capacitors at Hazelton 69 kV for total of 9.6 Mvar. | 69 |  |  |  | Y
| 200234 | 30503 | 50628 | 0 | WFEC | Device - Hazelton 69 kV #2 | Hazelton Capacitor 69 kV #2 | Regional Reliability |  | 2017-03-01 |  | 2017-06-01 | 2013-10-28 | DPA-2012-MAR-151-154-161-JUL-218-SEP-243 | 185004 | 2013 | 204209.7999 | 0 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520937 | HAZELTON |  |  | Install new 69 kV 4.8-Mvar capacitor at Hazelton substation. | 69 |  |  |  | Y
| 200245 | 30563 | 50702 | 0 | WFEC | Device - Sandy Corner 138 kV | Sandy Corner 138 kV Cap Bank | Regional Reliability |  | 2017-06-01 |  | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 504000 | 2014 | 542752.8725 | 504000 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520204 | Sandy Corner 138 kV |  |  | Add 20 Mvar of capacitance at Sandy Corner 138 kV. | 138 |  |  |  |  | Y
| 200397 | 31002 | 51445 | 0 | WFEC | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (WFEC) | Regional Reliability |  | 2021-05-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6000000 | 2016 | 6788449.26 | 7710000 |  |  |  | Delay - Mitigation | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 8.5-mile 138 kV line from Lincoln to Meeker. | 138
| 200397 | 31065 | 51484 | 0 | WFEC | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability |  | 2023-05-31 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 4638773.68 | 4000000 |  | 0 |  | Delay - Mitigation | 520855 | CLEO JCT |  |  | Install 3-breaker ring bus at Cleo Junction to allow load to be moved from 69 kV to 138 kV. | 138
| 200390 | 31025 | 51487 | 0 | GRDA | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability |  |  |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2627865.2897 | 2266000 |  | 0 |  | Re-evaluation | 505550 | Sallisaw |  |  | Install ring bus at Sallisaw 161 kV substation. | 161
| 200397 | 31041 | 51526 | 0 | WFEC | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability |  | 2022-04-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 637831.381 | 600000 |  | 0 |  | Delay - Mitigation | 520203 |  |  |  | Tap the 138 kV line from Byron to Cherokee City to construct new Driftwood substation. Install any required 138 kV terminal upgrades required to install 138/69 kV transformer. | 138
| 200397 | 31041 | 51527 | 0 | WFEC | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability |  | 2022-04-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3479080.26 | 3600000 |  | 0 |  | Delay - Mitigation |  |  | 520938 | HAZELTON JCT | Install new 138/69 kV transformer at new Driftwood substation. Install new 69 kV terminal for 69 kV line from Hazelton Junction. | 138/69
| 200419 | 31042 | 51531 | 0 | WFEC | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (WFEC) | Regional Reliability |  | 2026-12-31 |  | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 1400000 | 2017 | 1583971.494 | 5700000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. WFEC and Oklahoma Gas and Electric Company shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138 | 2
| 200420 | 31063 | 51567 | 0 | SPS | Sub - Carlsbad - Pecos 115 kV Terminal Upgrades | Carlsbad - Pecos 115 kV Terminal Upgrades | Regional Reliability |  | 2021-06-01 |  | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 767347 | 2017 | 847007.5097 | 0 |  | 0 |  | Complete | 528160 | Carlsbad Interchange 115 kV | 528178 | Pecos Interchange 115 kV | Install terminal upgrades at Carlsbad and/or Pecos to increase the rating of the 115 kV line between the substations. | 115 |  | 0.03
| 200455 | 41198 | 61852 | 0 | SPS | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #1 | Regional Reliability |  | 2018-12-31 |  | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 98639 | 2017 | 101104.975 | 98639 |  | 0 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 1 at Texas County. | 115
| 200455 | 41198 | 61853 | 0 | SPS | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #2 | Regional Reliability |  | 2018-12-31 |  | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 108430 | 2017 | 111140.75 | 108430 |  | 0 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 2 at Texas County. | 115
| 200479 | 51249 | 71954 | 0 | KPP | Line - City of Winfield - Oak 69 kV Reconductor | City of Winfield - Rainbow 69 kV Ckt 1 | Regional Reliability |  | 2020-12-31 |  | 2021-06-01 | 2018-02-27 | SPP-2016-AG2-AFS-2 | 3600000 | 2018 | 3782250 | 5066520 |  | 0 |  | Complete |  |  |  |  | Reconductor 4 miles of 69 kV transmission line from City of Winfield to Rainbow. |  |  | 4
| 200466 | 51249 | 71955 | 0 | EKC | Line - City of Winfield - Oak 69 kV Reconductor | Oak - Rainbow 69 kV Ckt 1 | Regional Reliability |  | 2021-04-12 |  | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 7831427 | 2017 | 8644430.0697 | 5156586 |  | 5156585 | QUARTERLY TRACKING | Closed Out |  |  |  |  | Reconductor 5.1 miles of 69 kV transmission line from Oak to Rainbow. | 69 |  | 5.1 |  | Y | Y | Y
| 210536 | 41199 | 71960 | 0 | SPS | Line - Etter - Moore - 115 kV | Etter - Moore 115 kV Rebuild | Regional Reliability |  | 2021-10-21 |  | 2018-06-01 | 2019-10-29 | 2017 ITPNT | 9037903 | 2017 | 9976153.83 | 1338161 |  | 0 |  | Delay - Mitigation | 523308 | Moore County Interchange East Bus 115 kV | 523256 | Etter Rural Sub 115 kV | Rebuild 10.83-mile 115 kV line from Etter to Moore. | 115 | 10.25
| 200477 | 51254 | 71963 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 14010573.3857 | 20297796 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
| 200477 | 51254 | 71964 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | 0 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
| 200477 | 51254 | 71965 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | 0 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
| 200477 | 51254 | 71966 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 12441332.2716 | 15279402 |  | 0 |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
| 200477 | 51254 | 71967 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1405712.3383 | 1605462 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
| 200477 | 51254 | 71968 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 4087712.7459 | 5656017 |  | 0 |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
| 200482 | 51280 | 72011 | 0 | WFEC | Device - Dover SW 69 kV Cap Bank | Dover SW 69 kV Cap Bank | Regional Reliability |  | 2022-07-01 |  | 2019-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 500000 | 2018 | 551906.445 | 813590 |  | 0 |  | Delay - Mitigation | 520881 | DOVER SW |  |  | Add new 14.4 MVAR capacitor bank at Dover SW 69 kV. | 69
| 200482 | 51281 | 72012 | 0 | WFEC | Device - Cherokee SW 69 kV Cap Bank | Cherokee SW 69 kV Cap Bank | Regional Reliability |  | 2023-08-01 |  | 2018-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 1000000 | 2018 | 1103812.89 | 1000000 |  | 0 |  | Delay - Mitigation | 520851 | CHEROKEE SW |  |  | Add new 28.8 MVAR capacitor bank at Cherokee SW 69 kV. | 69
| 210483 | 51282 | 72013 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Park Community 138 kV Substation | Regional Reliability |  | 2018-06-15 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 2000000 | 2018 | 2000000 | 2000000 |  | 0 |  | Re-evaluation |  |  |  |  | New Park Community 138 kV substation with 3-terminal flat bus. | 138
| 210483 | 51282 | 72014 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Omega - Park Community 138 kV Ckt 1 New Line | Regional Reliability |  | 2019-07-01 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4700000 | 2018 | 4817500 | 4700000 |  | 0 |  | Delay - Mitigation | 520964 | KINGFISHER |  |  | Construct new 9.4 mile 138 kV line from Omega - Park Community. Complete necessary terminal upgrades at Omega. | 138 | 9.4
| 210483 | 51282 | 72015 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Omega - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2022-08-31 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 7950000 | 2018 | 8775312.4755 | 12428000 |  | 0 |  | Delay - Mitigation | 520964 | KINGFISHER | 521090 | WATONGA SW | Convert 7.9 mile 69 kV line from Omega - Watonga SW to 138 kV. Complete necessary terminal upgrades at Watonga SW. | 138 |  | 7.9 | 7.9
| 210669 | 51282 | 72016 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Okeene - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2021-08-01 |  | 2019-06-01 | 2022-04-28 | DPA-2017-August-767-774-776 | 8600000 | 2018 | 9261259.332 | 8600000 |  | 0 |  | Delay - Mitigation | 521016 | OKEENE | 521090 | WATONGA SW | Convert 17.2 mile 69 kV line from Okeene - Watonga SW to 138 kV. Complete necessary terminal upgrades at Okeene. | 138 |  | 13.5 | 13.5
| 210483 | 51282 | 72018 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2026-05-29 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 9272028.276 | 8400000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 521090 | WATONGA SW | Convert 16.8 mile 69 kV line from Calumet - Watonga SW to 138 kV. | 138 |  | 16.8 | 16.8
| 210483 | 51282 | 72019 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2022-09-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1379766.1125 | 1250000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 520865 | CONCHO | Convert 9.0 mile 69 kV line from Calumet - Concho to 138 kV. Complete necessary terminal upgrades at Concho. | 138 |  |  | 9
| 210483 | 51282 | 72020 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2023-12-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 5022348.6495 | 4550000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 520502 |  | Convert 9.1 mile 69 kV line from Calumet - Cana to 138 kV. Complete necessary terminal upgrades at Cana. | 138 |  | 9.1 | 9.1
| 210483 | 51282 | 72021 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability |  | 2022-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4000000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET |  |  | New Calumet 138 kV substation with 4-terminal ring bus. | 138
| 210483 | 51282 | 72022 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2023-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 6236542.8285 | 5650000 |  | 0 |  | Delay - Mitigation | 520502 |  | 520899 | EL RENO | Convert 3.3 mile 69 kV line from Cana - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno Jct. | 138 |  | 3.3 | 3.3
| 210483 | 51282 | 72023 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2022-06-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 3500000 |  | 0 |  | Delay - Mitigation | 520892 | EL RENO SW | 520899 | EL RENO | Convert 6.5 mile 69 kV line from El Reno - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno. | 138
| 210483 | 51282 | 72024 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2022-05-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 11750000 |  | 0 |  | Delay - Mitigation | 520892 | EL RENO SW | 520412 |  | Convert 21.3 mile 69 kV line from El Reno - Mustang to 138 kV. Complete necessary terminal upgrades at Mustang. | 138 |  | 21.3 | 21.3
| 210483 | 51282 | 72025 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Mustang - Sara Road 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2022-12-30 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 10650000 | 2018 | 11755607.2785 | 1172000 |  | 0 |  | Delay - Mitigation | 520412 |  | 521005 | MUSTANG | Convert 2.1 mile 69 kV line from Mustang - Sara Road to 138 kV. Complete necessary terminal upgrades at Sara Road. | 138 |  | 2.1 | 2.1
| 210483 | 51282 | 72026 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Sara Road - Sunshine 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2022-12-30 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1050000 | 2018 | 1159003.5345 | 10380000 |  | 0 |  | Delay - Mitigation | 521005 | MUSTANG | 521059 | SUNSHINE CANYON | Convert 10.0 mile 69 kV line from Sara Road - Sunshine to 138 kV. | 138 |  | 10 | 10
| 210483 | 51282 | 72027 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2024-01-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 5519064.45 | 5300000 |  | 0 |  | Delay - Mitigation | 520859 | COGAR | 520899 | EL RENO | Convert 10.6 mile 69 kV line from Cogar - El Reno Jct to 138 kV. | 138 |  | 10.6 | 10.6
| 210483 | 51282 | 72030 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Kingfisher SW 138 kV Substation | Regional Reliability |  | 2023-01-31 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4975000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the East Kingfisher - Reeding 138 kV line and construct new Kingfisher SW 138 kV substation with 4-terminal ring bus. | 138
| 210483 | 51282 | 72031 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability |  | 2022-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4691204.7825 | 4250000 |  | 0 |  | Delay - Mitigation | 520865 | CONCHO |  |  | Construct new 8.5 mile 138 kV line from Concho - Kingfisher SW. | 138 | 8.5
| 210496 | 51316 | 72095 | 0 | SPS | Carlisle - Murphy 115kV Terminal Upgrades | Carlisle - Murphy 115 kV Terminal Upgrades | Regional Reliability |  | 2022-03-11 |  | 2022-06-01 | 2018-08-17 | 2018 ITPNT | 232952 | 2018 | 257135.4204 | 232952 |  | 0 |  | Delay - Mitigation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Replace terminal equipment on the Carlisle to Murphy (circuit V40) line and address any line clearance concerns to meet or exceed the conductor rating. | 115
| 210489 | 51327 | 82111 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2024-03-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 10000000 | 2018 | 11038128.9 | 10000000 |  | 0 |  | Delay - Mitigation | 520859 | COGAR | 520509 |  | Convert 12.0 mile 69 kV line from Cogar - Cleveland Junction to 138 kV. | 138
| 210489 | 51327 | 82112 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2024-02-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6900000 | 2018 | 7616308.941 | 6900000 |  | 0 |  | Delay - Mitigation | 520509 |  |  |  | Convert 13.8 mile 69 kV line from Cleveland Jct - Amber Tap to 138 kV. | 138
| 210489 | 51327 | 82113 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Amber Tap - Blanchard 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2022-07-15 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 7600000 | 2018 | 8388977.964 | 7019000 |  | 0 |  | NTC - Commitment Window |  |  | 520828 | BLANCHARD | Convert 15.2 mile 69 kV line from Amber Tap - Blanchard to 138 kV. | 138
| 210489 | 51327 | 82114 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Blanchard - OU SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2023-11-30 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 300000 | 2018 | 331143.867 | 360000 |  | 0 |  | NTC - Commitment Window | 520828 | BLANCHARD | 521104 | OU SWITCH 4 | Convert 2.1 mile 69 kV line from Blanchard - OU SW to 138 kV. | 138
| 210489 | 51327 | 82115 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2024-02-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6300000 | 2018 | 6954021.207 | 6300000 |  | 0 |  | Delay - Mitigation | 520509 |  | 520814 | ANADARKO | Convert 11.1 miles of double circuit 69 kV line from Cleveland Junction - Anadarko to single circuit 138 kV. | 138
| 210496 | 61346 | 92151 | 0 | SPS | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Substation | Regional Reliability |  | 2022-04-16 |  | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 13626695 | 2021 | 13967362.375 | 20859497 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap Moore-Potter 230kV and tap Exell-Fain 115kV and tie into a new substation at McDowell Creek. | 230 | 0.2
| 210496 | 61346 | 92152 | 0 | SPS | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Transformer | Regional Reliability |  | 2022-04-16 |  | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 6531679 | 2021 | 6694970.975 | 81052 |  | 0 |  | Delay - Mitigation |  |  |  |  | Install a 230/115 kV transformer at the McDowell Creek substation | 230/115
| 210507 | 61347 | 92153 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco - Road Runner 345 kV Ckt 1 New Line | Regional Reliability |  | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 29927758 | 2019 | 31442850.7488 | 36646140 |  | 0 |  | In Service |  |  | 528027 | Road Runner 345 kV | Build new 21 mile 345 kV line from Bopco to Road Runner. | 345 | 21
| 210507 | 61347 | 92154 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco - China Draw 345 kV Ckt 1 New Line | Regional Reliability |  | 2021-11-15 |  | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 30496976 | 2019 | 32040885.41 | 32405135 |  | 0 |  | In Service |  |  | 528223 |  | Build new 19 mile 345 kV line from Bopco to China Draw. | 345 | 19
| 210507 | 61347 | 102153 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 1 Transformer | Regional Reliability |  | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 6205015 | 2019 | 6519143.8844 | 5718715 |  | 0 |  | In Service |  |  | 528020 |  | Construct 345/115 kV transformer at Bopco substation. | 345/115
| 210507 | 61347 | 102154 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 2 Transformer | Regional Reliability |  | 2021-11-15 |  | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 6122043 | 2019 | 6431971.4269 | 5962651 |  | 0 |  | In Service |  |  | 528020 |  | Construct second 345/115 kV transformer at Bopco substation. | 345/115
| 210507 | 61347 | 102157 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345 kV Substation | Regional Reliability |  | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 5153574 | 2019 | 5414473.6837 | 6341420 |  | 0 |  | In Service |  |  |  |  | Build 345 kV portion of new 345/115 kV Bopco substation. | 345
| 210507 | 61347 | 102158 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 115 kV Substation | Regional Reliability |  | 2020-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 11741936 | 2019 | 12035484.4 | 15137218 |  | 0 |  | In Service |  |  |  |  | Build 115 kV portion of new 345/115 kV Bopco substation. This includes work to reterminate the Wood Draw - Red Bluff 115 kV line into the new substation. | 115
| 210548 | 71348 | 102163 | 0 | OPPD | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability |  | 2023-05-31 |  | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 3647471 | 2019 | 3927927.3066 | 3647471 |  | 0 |  | Delay - Mitigation | 646209 | Sub 1209 | 646231 | Sub 1231 | Reconductor 3.3 miles of S1209 - S1231 161 kV Ckt 2 | 161 |  | 3.3
| 210505 | 71352 | 102172 | 0 | WFEC | Device - Clear Creek Tap 69 kV Cap Bank | Clear Creek Tap 69 kV Cap Bank | Regional Reliability |  | 2020-12-01 |  | 2019-12-01 | 2018-12-06 | DPA-2018-June-902 | 717209 | 2019 | 735139.225 | 717209 |  | 0 |  | Delay - Mitigation |  |  |  |  | New cap bank(s) totaling 18 MVAR at Clear Creek Tap 69kV substation. | 69
| 210540 | 81498 | 112358 | 0 | OGE | Sub - Westmoore 138 kV | Westmoore 138 kV Breakers | Regional Reliability |  | 2021-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 271289 | 2020 | 278071.225 | 271289 |  | 0 |  | Complete | 514887 | WESTMOORE 138 |  |  | Replace 2 breakers at Westmoore 138 kV with 40 kA breakers | 138
Base Plan | 210544 | 81571 | 112488 | TP2019132 | AEP | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | Already Added | 2022-06-01 | 2022-05-24 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9618647.3294 | 9155167 | 8507034 | 0 |  | In Service | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115 |  |  |  |  | Y |  | Y | Jake Tucker | BPID's P19132001, P19132006, & P19132009
Base Plan | 210544 | 81561 | 112502 | TP2019146 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | Base Plan - Add in Future (2025) | 2025-05-01 | 2025-02-26 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 5383105 | 5329277 | 6445708 | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06 |  |  |  | Y |  | Y |  | BPID's P19146001, 02, 04, 05
| 210541 | 81503 | 112363 | 0 | SPS | Sub - Hale Cty Interchange 115 kV | Hale County Interchange 115 kV Breakers | Regional Reliability |  | 2021-05-30 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 1658004 | 2019 | 1741940.4525 | 257408 |  |  |  | In Service | 525454 | Hale Co Interchange 115 kV |  |  | Replace 3 breakers at Hale County Interchange 115 kV with 40 kA breakers | 115
| 210538 | 81505 | 112366 | 0 | NPPD | Sub - Canaday 115 kV | Canaday 115 kV Breakers | Regional Reliability |  | 2020-02-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 2600000 | 2020 | 2600000 | 2555908 |  | 2555908 | QUARTERLY TRACKING | Complete | 640103 | Canaday |  |  | Replace 5 breakers at Canaday 115 kV with 40 kA breakers | 115 | [5 empty] | Y
| 210538 | 81506 | 112367 | 0 | NPPD | Sub - Hastings 115 kV | Hastings 115 kV Breakers | Regional Reliability |  | 2021-01-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 550000 | 2020 | 563750 | 434289 |  | 434289 | QUARTERLY TRACKING | Complete | 640215 | Hastings |  |  | Replace 2 breakers at Hastings 115 kV with 40 kA breakers | 115 | [5 empty] | Y
| 210538 | 81507 | 112368 | 0 | NPPD | Sub - Moore 13.8 kV Breaker | Moore 13.8 kV Breaker | Regional Reliability |  | 2022-07-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 510000 | 2020 | 535818.75 | 679553 |  | 0 |  | Delay - Mitigation | 640280 | Moore |  |  | Replace 1 breaker at Moore 13.8 kV with 40 kA breakers | 138
| 210539 | 81508 | 112369 | #N/A | EM | Sub - Craig 161 kV | Craig 161 kV Breaker | Regional Reliability |  | 2021-06-30 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 311400 | 2019 | 327164.625 | 259864 |  | 0 |  | In Service | 542978 | CRAIG 161 KV |  |  | Replace 1 breaker at Craig 161 kV with 63 kA breakers | 161 |  |  |  | Y | Y | Y
| 210539 | 81509 | 112370 | 0 | EM | Sub - Leeds 161 kV | Leeds 161 kV Breakers | Regional Reliability |  | 2020-09-24 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 468500 | 2019 | 480212.5 | 400871 |  | 400871 | QUARTERLY TRACKING | Complete | 542997 | LEEDS 161 KV |  |  | Replace 2 breakers at Leeds 161 kV with 40 kA breakers | 161 |  |  |  | Y |  | Y
| 210539 | 81511 | 112372 | 0 | EM | Sub - Southtown 161 kV | Southtown 161 kV Breakers | Regional Reliability |  | 2021-12-31 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 898600 | 2019 | 944091.625 | 1348442 |  | 0 |  | In Service | 542993 | SOUTHTOWN 161 KV |  |  | Replace 4 breakers at Southtown 161 kV with 40 kA breakers | 161 |  |  |  | Y
| 210545 | 81513 | 112377 | 0 | WFEC | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability |  | 2027-08-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 870294.6744 | 838500 |  | 0 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Replace 3 breakers at Anadarko 138 kV with 63 kA breakers | 138
| 210545 | 81514 | 112378 | 0 | WFEC | Sub - Washita 69 kV | Washita 69 kV Breaker | Regional Reliability |  | 2021-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 52400 | 2020 | 53710 | 52400 |  | 0 |  | Delay - Mitigation | 521088 | WASHITA |  |  | Replace 1 breaker at Washita 69 kV with 40 kA | 69
| 210545 | 81515 | 112379 | 0 | WFEC | Sub - Mooreland 138/69 kV Breakers | Mooreland 138 kV Breakers #2 | Regional Reliability |  | 2022-12-29 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 822500 | 2020 | 864139.0625 | 4100000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Replace 12 breakers at Mooreland 138 kV with 40 kA breakers
| 210545 | 81515 | 112380 | 0 | WFEC | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability |  | 2022-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 128300 | 2020 | 134795.1875 | 204000 |  | 0 |  | Delay - Mitigation | 520995 | MOORELAND |  |  | Replace 2 breakers at Mooreland 69 kV with 40 kA breakers
| 210542 | 81516 | 112381 | 0 | EKC | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - South Seneca 115kV Ckt 1 | Regional Reliability |  | 2022-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 3067168.2 | 2020 | 3222443.5901 | 3393918 |  | 0 |  | Delay - Mitigation | 533322 | BAILEYVILLE N.M. STATION 115 KV (NEMAHA MARSHALL R | 533337 | SOUTH SENECA 115 KV | Rebuild 4 miles of 115 kV line from Baileyville to South Seneca and upgrade any necessary terminal equipment at Baileyville and/or South Seneca to increase the summer emergency rating to 239 MVA | 115 | 4 |  |  | Y | Y
| 210605 | 81516 | 112383 | 0 | EKC | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Multi-Marshall County - Baileyville - South Seneca 115 kV | Regional Reliability |  | 2022-06-01 |  | 2021-04-01 | 2021-03-02 | 2019 ITP | 9204123 | 2020 | 9670081.7269 | 10675598 |  | 0 |  | Delay - Mitigation | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Tear down 7.99 miles of 115 kV line from Baileyville to Smittyville, 2.17 miles of 115 kV line from Marshall County to Smittyville, and the Smittyville substation, rebuild 10.16 miles of 115 kV line from Baileyville to Marshall County and upgrade any necessary terminal equipment at Marshall County and/or Baileyville to increase the summer emergency rating to 239 MVA | 115 | 2.2 |  |  | Y | Y
|  | 81657 | 122665 |  | AEP | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (TOIF) (AEP) | Generation Interconnection |  |  | 2025-12-12 |  |  | GI STUDIES |  |  |  | 1388819 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 345 | 0.18 | [5 empty] | Y |  | States Edge (TP2019245 - 05/2026) P19245010 & P19245014 | Projects is on hold. Nothing to report at this time.
|  | 81657 | 122666 |  | AEP | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (Non-Shared NU) (AEP) | Generation Interconnection | [5 empty] | GI STUDIES |  |  |  | 10361130 |  | 0 |  | On Schedule < 4 |  |  |  |  | Expand the 345 kV breaker and a half scheme, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 345 | [6 empty] | Y |  | States Edge (TP2019245 - 05/2026) All other BPIDs | Projects is on hold. Nothing to report at this time.
| 210545 | 81525 | 112395 | 0 | WFEC | Device- Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability |  | 2025-11-28 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 400000 | 2020 | 420250 | 400000 |  | 0 |  | Delay - Mitigation | 520929 | GYPSUM |  |  | Install a new 12 MVAR capacitor bank at Gypsum 69 kV substation. | 69/69
| 210642 | 81529 | 112399 | #N/A | SPS | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230 kV Ckt 1 Terminal Upgrades | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 231742 | 2022 | 231742 | 231742 |  | 0 |  | On Schedule < 4 | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230
| 210642 | 81529 | 112401 | #N/A | SPS | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230kV Ckt 2 Terminal Upgrades | Regional Reliability |  | 2022-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  | 2022 | 0 |  |  | 0 |  | Delay - Mitigation | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230
| 210540 | 81532 | 112402 | 0 | OGE | Sub - Cleo Corner - Cleo Junction 69kV | Cleo Corner - Cleo Junction 69kV Ckt 1 Terminal Upgrades | Regional Reliability |  | 2022-06-01 |  | 2022-06-01 | 2019-11-18 | 2019 ITP | 16602 | 2020 | 17442.4762 | 16602 |  | 0 |  | Delay - Mitigation | 514777 | CLEO CORNER 69 | 520855 | CLEO JCT | Upgrade any necessary terminal equipment at Cleo Corner and/or Cleo Junction to increase the summer emergency rating to 48 MVA | 69
| 210538 | 81533 | 112403 | 0 | NPPD | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability |  | 2024-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 608900 | 2020 | 639725.5625 | 608900 |  | 0 |  | Delay - Mitigation | 640171 | Firth |  |  | Install new 15 MVAR capacitor bank at Firth 115 kV substation. | 115
| 210538 | 81533 | 112404 | 0 | NPPD | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability |  | 2024-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 3600000 | 2020 | 3782250 | 2991100 |  | 0 |  | Delay - Mitigation | 640171 | Firth |  |  | Expand the existing Firth 115 kV substation to accommodate a new 15 MVAR capacitor bank. | 115
Direct Assignment | 210558 | 81673 | 122713 | TP2020077 | AEP | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | Do Not Add (Direct Assigned) | 2022-06-01 | 2022-06-15 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 | 3160967 | 2020 | 3320990.9544 | 2752417 | 3093373 | 0 |  | In Service | 510423 | LOCUST GROVE | 512634 | KERR 115 | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49 |  |  | Y |  |  | Larry Oden | All BPIDs on TP2020077
| 210515 | 81581 | 112510 | 0 | SPS | Multi-Hobbs Interchange-Millen 115kV | Hobbs Interchange to Millen Rebuild 115 kV Ckt1 | Regional Reliability |  | 2022-06-01 |  | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3165684 | 2019 | 3409095.4055 | 0 |  | 0 |  | Delay - Mitigation | 527891 | Hobbs Interchange 115 kV | 528435 | Millen Sub 115 kV | Rebuild 10.5 miles of Hobbs Interchange to Millen 115kV Line |  | 3.5
| 210515 | 81581 | 122510 | 0 | SPS | Multi-Hobbs Interchange-Millen 115kV | Johnson Draw 115 kV Capacitor Bank | Regional Reliability |  | 2022-06-01 |  | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3749224 | 2019 | 4037504.1579 | 0 |  | 0 |  | Delay - Mitigation | 527362 | Johnson Draw 115 kV |  |  | New 28.8 MVAR capacitor bank addition at Johnson Draw 115kV | 115
| 210560 | 81614 | 122570 | 0 | BEPC | Multi - Neset - New Town 230 kV | Neset - Northshore 230 kV Ckt 1 | Regional Reliability |  | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 33155575 | 2020 | 34834075.9844 | 33159000 |  | 0 |  | Delay - Mitigation | 659138 | Neset 230 kV Bus |  |  | Build new 28 mile 230kV line from Neset to Northshore. | 230 | 30
| 210559 | 81614 | 122571 | 0 | MWE | Multi - Neset - New Town 230 kV | Northshore - New Town 115 kV Ckt 1 | Regional Reliability |  | 2021-09-05 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 19235485 | 2020 | 19716372.125 | 19235485 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 20 mile 115 kV line from Northshore to New Town. | 115 | 20.5
| 210560 | 81614 | 122572 | 0 | BEPC | Multi - Neset - New Town 230 kV | North Shore 230/115 kV Transformer | Regional Reliability |  | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 3176320 | 2020 | 3337121.2 | 3848370 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 230/115 kV Transformer at North Shore substation | 230/115
| 210560 | 81614 | 122575 | 0 | BEPC | Multi - Neset - New Town 230 kV | Northshore 230 kV Substation | Regional Reliability |  | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 20938350 | 2020 | 21998353.9688 | 14282000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new Northshore 230/115 kV Substation to replace existing switch
| 210658 | 81627 | 122597 | 0 | WFEC | SUB - Marietta - Rocky Point 69 kV | Marietta 69 kV | Regional Reliability |  | 2021-12-01 |  | 2021-12-01 | 2022-03-08 | 2019 ITP | 100000 | 2020 | 102500 | 100000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Install any necessary protection equipment at Marietta to change the operational status from normally open to normally closed | 69
| 210557 | 81652 | 122657 | 0 | CBPC | Sub-Flint Hills 69 kV Switching Station | Sub - Donald Feldman 69kV Switching Station | Regional Reliability |  | 2020-06-01 |  | 2020-06-01 | 2020-04-08 | DPA-2019-March-1011 | 1100000 | 2020 | 1100000 | 1227000 |  | 0 |  | Complete |  |  |  |  | Construct a new switching station at Flint Hills connecting the MEC Clarksville line and Corn Belt's Parkersburg and Plainfield line |  |  |  |  | Y |  | Y
| 210552 | 81654 | 122661 | 0 | NPPD | XFR-Riverdale 230/115 kV Transformer ckt 2 | Riverdale 230/115 kV Transformer ckt 2 | Regional Reliability |  | 2020-06-01 |  | 2021-06-01 | 2020-09-24 | DPA-2019-June-1058 | 3650000 | 2020 | 3650000 | 3704140 |  | 3704140 | QUARTERLY TRACKING | Complete | 640330 | Riverdale | 640331 | Riverdale | Install a new 230/115 kV 187 MVA transformer located at Riverdale substation | 230/115 | [5 empty] | Y
| 210574 | 81682 | 122725 | 0 | SPS | Line - Allen - Quaker 115kV | Allen - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability |  |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 2961075 | 2021 | 3035101.875 | 2961075 |  | 0 |  | Delay - Mitigation | 526213 | Allen Sub 115 kV | 526243 | South Plains REC-Quaker 115 kV | Rebuild 3.6 miles 115 kV line from Allen to Quaker and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA |  |  | 3.5
| 210574 | 81684 | 122727 | 0 | SPS | Line - Allen - Lubbock South 115kV | Allen - Lubbock South 115 kV Ckt 1 Rebuild | Regional Reliability |  |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 7350796 | 2021 | 7534565.9 | 7350796 |  | 0 |  | Delay - Mitigation | 526213 | Allen Sub 115 kV | 526268 | Lubbock South Interchange 115 kV | Rebuild 5.98 miles of 115 kV line from Allen to Lubbock and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA. |  |  | 6
Base Plan | 210575 | 81687 | 122730 | TP2020102 | AEP | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | Base Plan - Add in Future (2025) | 2024-06-03 | 2025-03-20 | 2024-06-01 | 2020-11-17 | 2020 ITP | 23622577 | 2021 | 24818469.96 | 20597910 | 21548952 | 0 |  | Delay - Mitigation | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA | 138 | 11.2 |  |  |  | Y |  |  | Jeff Koch | All BPIDs on TP2020102
| 210581 | 81768 | 122745 | 0 | BEPC | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 1 (KV1A) | Regional Reliability |  | 2024-06-30 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 3389739 | 2021 | 3474482.475 | 3910285 |  | 0 |  | Delay - Mitigation |  |  |  |  | Replace the 230/115 kV transformer Ckt 1 at Watford City to achieve a summer emergency rating of 208 MVA | 230/115
| 210581 | 81768 | 122746 | 0 | BEPC | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 2 (KV2A | Regional Reliability |  | 2024-06-30 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 173041 | 2021 | 177367.025 | 173041 |  | 0 |  | Delay - Mitigation |  |  |  |  | Upgrade any necessary terminal equipment at Watford City for the 230/115 kV transformer Ckt 2 to achieve a summer emergency rating of 208 MVA | 230/115
| 210582 | 81719 | 122803 | 0 | SEPC | Device - Russell 115 kV | Russell 115 kV Capacitor Bank | Regional Reliability |  | 2024-01-01 |  | 2022-06-01 | 2020-11-23 | 2020 ITP | 5306633 | 2021 | 5439298.825 | 5306633 |  | 0 |  | Delay - Mitigation | 539701 | Russell 115 KV |  |  | Add new 24 MVAR capacitor bank at Russell 115 kV
| 210583 | 81720 | 122804 | 0 | EM | Sub - Northeast 161 kV | Northeast 161 kV Breakers | Regional Reliability |  | 2025-12-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 887479 | 2021 | 909665.975 | 887481 |  | 0 |  | Delay - Mitigation |  |  |  |  | Replace three breakers at the Northeast 161 kV station with 63 kA breakers
| 210583 | 81722 | 122806 | 0 | EM | Sub - Leeds 161 kV #2 | Leeds 161 kV Breaker | Regional Reliability |  | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 300000 | 2021 | 307500 | 300000 |  | 0 |  | Delay - Mitigation | 542997 | LEEDS 161 KV |  |  | Replace 1 breaker at the Leeds 161 kV station with a 40 kA breaker |  |  |  |  | Y
| 210583 | 81723 | 122807 | 0 | EM | Sub - Shawnee Mission 161 kV | Shawnee Mission 161 kV Breaker | Regional Reliability |  | 2023-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 335416 | 2020 | 352396.435 | 355416 |  | 0 |  | Delay - Mitigation | 543031 | SHAWNEE MISSION 161 KV |  |  | Replace 1 breaker at the Shawnee Mission 161 kV station with a 40 kA breaker |  |  |  |  | Y
| 210583 | 81724 | 122808 | 0 | EM | Sub - Southtown 161 kV #2 | Southtown 161 kV Breaker | Regional Reliability |  | 2021-12-22 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 244265 | 2021 | 244265 | 389812 |  | 0 |  | In Service | 542993 | SOUTHTOWN 161 KV |  |  | Replace 1 breaker at the Southtown 161 kV station with a 40 kA breaker |  |  |  |  | Y
| 210580 | 81728 | 122812 | 0 | EKC | Line - Circleville - Goff 115 kV | Circleville - Goff 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2021-07-02 |  | 2025-06-01 | 2020-11-17 | 2020 ITP | 13028143 | 2021 | 13028143 | 14232227 |  | 14232227 | QUARTERLY TRACKING | Complete | 533152 | CIRCLEVILLE 115 KV | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | Rebuild 14.56 miles of 115 kV line from Circleville to Goff and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  |  | 14.5 |  | Y | Y | Y
| 210580 | 81730 | 122814 | 0 | EKC | Line - Kelly - Goff 115 kV | Goff - Kelly 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2021-06-18 |  | 2025-06-01 | 2020-11-17 | 2020 ITP | 5602343 | 2021 | 5602343 | 5483173 |  | 5483173 | QUARTERLY TRACKING | Complete | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | 533217 | KELLY 115 KV | Rebuild 10.0 miles of 115 kV line from Goff to Kelly and upgrade any necessary terminal equipment to achieve a summer emergency rating 239 MVA | 115 |  |  |  | Y | Y | Y
| 210589 | 81733 | 122818 | 0 | OGE | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Cushing - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  |  |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 4281150 | 2021 | 4388178.75 | 4281150 |  |  |  | On Schedule < 4 | 515032 | CUSHING 69 | 515022 | PIPELINE 69 | Rebuild 4.71 miles of 69 kV line from Cushing to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 4.71
| 210589 | 81733 | 122819 | 0 | OGE | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Pipeline - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  |  |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 1081649 | 2021 | 1108690.225 | 1081649 |  |  |  | On Schedule < 4 | 515022 | PIPELINE 69 |  |  | Rebuild 1.19 miles of 69 kV line from Pipeline to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 1.19
| 210586 | 81751 | 122864 | 0 | WFEC | Sub - Anadarko 138 kV #2 | Anadarko 138 kV Breakers #2 | Regional Reliability |  |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 850000 | 2021 | 871250 | 850000 |  | 0 |  | On Schedule < 4 | 520814 | ANADARKO |  |  | Replace 4 breakers at the Anadarko 138 kV station with a 63 kA breakers
| 210574 | 81755 | 122869 | 0 | SPS | Sub - Bushland - Deaf Smith 230 kV | Bushland - Deaf Smith 230 kV Terminal Upgrades | Regional Reliability |  | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 998956 | 2021 | 1023929.9 | 571184 |  | 0 |  | Delay - Mitigation | 524267 | Bushland Interchange 230 kV (POI: Wildorado Wind, 160MW) | 524623 | Deaf Smith County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Bushland and/or Deaf Smith 230 kV to achieve a summer emergency rating of 546 MVA.
| 210574 | 81756 | 122870 | 0 | SPS | Sub - Newhart - Potter 230 kV | Newhart - Potter 230 kV Terminal Upgrades | Regional Reliability |  | 2022-04-01 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 735013 | 2021 | 753388.325 | 0 |  | 0 |  | Delay - Mitigation | 525461 | Newhart Interchange 230 kV | 523959 | Potter County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Newhart and/or Potter 230 kV to achieve a summer emergency rating of 540 MVA. |  | 67
| 210574 | 81757 | 122871 | 0 | SPS | Sub - Deaf Smith #6 - Friona 115 kV | Deaf Smith #6 - Friona 115 kV Rebuild | Regional Reliability |  | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 11609949 | 2021 | 11900197.725 | 11609949 |  | 0 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524655 | Friona Sub 115 kV | Rebuild 18.9 miles of 115 kV line from Deaf Smith #6 to Friona and upgrade any necessary terminal equipment at Deaf Smith #6 and/or Friona to achieve a summer emergency rating of 120 MVA |  | 17.4
| 210574 | 81758 | 122872 | 0 | SPS | Line - Carlisle - Murphy 115 kV #2 | Carlisle - Murphy 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 4160581 | 2021 | 4264595.525 | 4160581 |  | 0 |  | Delay - Mitigation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Rebuild 4.0 miles of 115 kV line from Carlisle to Murphy and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 4
| 210574 | 81760 | 122876 | 0 | SPS | Line - Deaf Smith #6 - Hereford 115 kV | Deaf Smith #6 - Hereford 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 6956586 | 2021 | 7130500.65 | 6956586 |  | 0 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524606 | Hereford Interchange 115 kV | Rebuild 2.33 miles of 115 kV line from Deaf Smith #6 to Hereford and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  | 7.3
| 210574 | 81763 | 122883 | 0 | SPS | Sub - Lubbock South - Wolfforth 230 kV | Lubbock South - Wolfforth 230 kV Ckt 1 Terminal Upgrades #2 | Regional Reliability |  | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 944000 | 2021 | 967600 | 835432 |  | 0 |  | Delay - Mitigation | 526269 | Lubbock South Interchange 230 kV | 526525 | Wolfforth Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Lubbock South and/or Wolfforth to achieve a summer emergency rating of 550 MVA |  | 14.6
| 210584 | 81497 | 132893 | 0 | NWE | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Junction 115 kV Terminal Upgrades | Regional Reliability |  | 2021-12-31 |  | 2022-12-01 | 2020-11-17 | 2020 ITP | 1182000 | 2021 | 1182000 | 1182000 |  | 989393 | QUARTERLY TRACKING | Complete |  |  |  |  | Install any necessary terminal equipment to support a new 115 kV line from Richmond to achieve a summer emergency rating of 139 MVA | [6 empty] | Y
| 210579 | 91876 | 143157 | 0 | WAPA | Device - Bismarck 12.47 kV | Bismarck 12.47 kV Reactors | Regional Reliability |  | 2023-10-01 |  | 2022-04-01 | 2020-11-23 | 2020 ITP | 2143217 | 2021 | 2196797.425 | 2143217 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install 2x35 MVAR reactors at Bismarck to control voltage on the 230 kV transmission system
| 210585 | 91878 | 143159 | 0 | MRES | Device - Moorehead 230 kV | Moorehead 230 kV Reactor | Regional Reliability |  | 2024-06-01 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 4358300 | 2022 | 4358300 | 4358300 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 2x40 MVAR reactors at Moorehead to control voltage on the 115 kV and 230 kV transmission systems
| 210591 | 91881 | 143162 | 0 | CPEC | Device - Agate 115 kV | Agate 115 kV Reactor | Regional Reliability |  | 2022-07-01 |  | 2022-04-01 | 2020-11-23 | 2020 ITP | 1310400 | 2021 | 1343160 | 1400000 |  |  |  | Delay - Mitigation |  |  |  |  | Install 2x6 MVAR reactors at Agate to control voltage on the 115 kV transmission system
| 210574 | 91884 | 143167 | 0 | SPS | Line - Cargill - Friona 115 kV | Cargill - Friona 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 1675731 | 2021 | 1717624.275 | 1675731 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 1.15 miles of existing 115 kV line from Cargill to Friona and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 1.15
| 210574 | 91888 | 143168 | 0 | SPS | Line - Cargill - Deaf Smith #24 115 kV | Cargill - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 5378526 | 2021 | 5512989.15 | 5378526 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 7.74 miles of 115 kV line from Cargill to Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 7.75
| 210574 | 91889 | 143169 | 0 | SPS | Line - Parmer - Deaf Smith #24 115 kV | Parmer - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 999423 | 2021 | 1024408.575 | 999423 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 1.16 miles of 115 kV line from Parmer - Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 1.16
| 210574 | 91890 | 143170 | 0 | SPS | Line - Parmer - Deaf Smith #20 115 kV | Parmer - Deaf Smith #20 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 5293163 | 2021 | 5425492.075 | 5293163 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 7.6 miles of 115 kV line from Parmer - Deaf Smith #20 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 7.6
| 210600 | 91885 | 143177 | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S1260 - S1362 161 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-08-01 |  | 2023-04-01 | 2021-02-16 | DPA-2018-October-949 | 858928 | 2021 | 880401.2 | 858928 |  | 0 |  | On Schedule < 4 | 646260 |  |  |  | Rebuild 0.9 miles of 161 kV line from S1260 to S1362 line to achieve 243 MVA summer emergency rating. | 161
| 210600 | 91885 | 143178 | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3456 to S3458 345 kV Ckt 1 Terminal Upgrades | Regional Reliability |  | 2022-08-01 |  | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 100000 | 2021 | 102500 | 100000 |  | 0 |  | On Schedule < 4 | 645456 | Sub 3456 | 645458 | Sub 3458 (Neb Cty) | The upgrade disconnect switch and associated jumpers on S3456 to S3458 345 kV line to achieve at least a 981 MVA summer emergency rating. | 345
| 210600 | 91885 | 143179 | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3455 to S3740 345 kV CKT1 Rebuild | Regional Reliability |  | 2024-04-01 |  | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 600000 | 2021 | 615000 | 600000 |  | 0 |  | On Schedule < 4 | 645455 | Sub 3455 | 645740 | Sub 3740 | Replace structures to increase clearance on S3455 to S3740 345 kV CKT1 (approximately 6-7 structures) to achieve a 1112 MVA summer emergency rating. | 345
| 210584 | 81497 | 143181 | 0 | NWE | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (NWE) | Regional Reliability |  |  |  | 2022-12-01 | 2020-11-17 | 2020 ITP | 3277500 | 2021 | 3359437.5 | 3277500 |  |  |  | On Schedule < 4 |  |  |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA |  | 14.4
| 210617 | 91939 | 143253 | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli - Lexington kV 138 kV | Regional Reliability |  | 2025-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 7865000 | 2021 | 8061625 | 7865000 |  | 0 |  | Delay - Mitigation Window | 521022 | PAOLI | 520973 | LEXINGTON | Rebuild 14.3 miles of 69 kV line from Paoli to Lexington to 138 kV | 69 |  |  |  |  | Y
| 210617 | 91939 | 143254 | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Lexington - Lil Axe 138 kV | Regional Reliability |  | 2024-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 5340500 | 2021 | 5474012.5 | 5340500 |  | 0 |  | Delay - Mitigation Window | 520973 | LEXINGTON | 520976 | LITTLE AXE | Rebuild 9.7 miles of 69 kV line from Lexington to Lil Axe to 138 kV | 69 |  |  |  |  | Y
| 210617 | 91939 | 143255 | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli 138 kV Terminal Upgrades | Regional Reliability |  | 2025-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 450000 | 2021 | 461250 | 450000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Convert 69 kV terminal equipment at Paoli Switch to 138 kV | [5 empty] | Y
| 210617 | 91939 | 143256 | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Canadian Switch138 kV Terminal Upgrades | Regional Reliability |  | 2024-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 500000 | 2021 | 512500 | 500000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Convert 69 kV terminal equipment at Canadian Switch to 138 kV | [5 empty] | Y
| 210655 | 92112 | 143587 | #N/A | EM | Sub - Platte City 161 kV | Platte City 161 kV Terminal Upgrade | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 55271.78 | 2022 | 55271.78 | 55271.78 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the switch at Platte City 161 kV for the Platte City - Weston 161 kV line. | 161
| 210675 | 92113 | 143588 | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge - Round Up 345 kV | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 78293357 | 2022 | 78293357 | 78293357 |  |  |  | NTC - Commitment Window |  |  |  |  | Build 33.2 mile new 345 kV line from Kummer Ridge to Round Up | 345
| 210675 | 92113 | 143589 | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge 345 kV Terminal Upgrades | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 342000 | 2022 | 342000 | 342000 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Kummer Ridge substation 345 kV to support a new 345 kV line from Round Up | 345
| 210675 | 92113 | 143590 | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Round Up 345 kV Terminal Upgrades | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 342000 | 2022 | 342000 | 342000 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Round Up substation 345 kV to support a new 345 kV line from Kummer Ridge | 345
Base Plan | 210627 | 81717 | 122796 | TP2020266 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | Added | 2023-04-30 | 2024-05-31 | 2022-01-01 | 2021-11-05 | 2020 ITP | 12210364 | 2021 | 12828513.6775 | 8370000 | 6864531 | 0 |  | Delay - Mitigation | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support a new line 345 kV line from Border - Woodward 345 kV substation with a summer emergency rating of 1792 MVA | 345 | 0.2 |  |  |  | Y |  |  | James Horn | MOD number added 16810 / BPID-P20266001, P20266004, P20266005
| 210637 | 92140 | 143663 | #N/A | EKC | Sub - Jarbalo Junction 115 kV Breaker Upgrade | Jarbalo Junction 115 kV Breaker | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 236539 | 2022 | 236539 | 236539 |  |  |  | On Schedule < 4 |  |  |  |  | Replace breaker 115-483 at the Jarbalo Junction substation | 115
| 210647 | 92144 | 143664 | #N/A | EM | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 255075 | 255075 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R3-7 breaker at the Shawnee Mission 161 kV substation | 161
| 210647 | 92144 | 143665 | #N/A | EM | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV Breaker | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 255075 | 255075 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R7-12 breaker at the Shawnee Mission 161 kV substation | 161
| 210647 | 92141 | 143666 | #N/A | EM | Sub - Craig 161 kV Breaker | Craig 161 kV Breaker #2 | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 319002 | 2022 | 319002 | 319002 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R5-33 breaker at the Craig 161 kV substation | 161
| 210640 | 92142 | 143667 | #N/A | MRES | Sub - Moorhead 230 kV Substation Reconfiguration | Moorhead 230 kV Substation Reconfiguration | Regional Reliability |  | 2024-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 9989000 | 2022 | 9989000 | 9989000 |  |  |  | Delay - Mitigation |  |  |  |  | Reconfigure the Moorhead 230 kV substation with a ring bus, expandable to breaker-and-a-half. | 230
| 210654 | 92143 | 143668 | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th - Stateline 161 kV Rebuild | Regional Reliability |  | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 10688750 | 2022 | 10688750 | 10688750 |  |  |  | On Schedule < 4 |  |  |  |  | Rebuild approximately 5.5 miles of the existing 161 kV line from Joplin West 7th to Stateline. | 161
| 210654 | 92143 | 143669 | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th 161 kV Terminal Upgrades | Regional Reliability |  | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 393232 | 2022 | 393232 | 393232 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at Joplin West 7th 161 kV substation. | 161
| 210654 | 92143 | 143670 | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Stateline 161 kV Terminal Upgrades | Regional Reliability |  | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 209518 | 2022 | 209518 | 209518 |  |  |  | On Schedule < 4 |  |  |  |  | : Upgrade any necessary terminal equipment at Stateline 161 kV substation. | 161
| 210619 | 92180 | 143705 | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Kearney NE - Tower 115 kV Ckt 1 New Line | Regional Reliability |  | 2022-06-01 |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 11250834 | 2022 | 11250834 | 11250834 |  | 0 |  | NTC - Commitment Window | 640248 | Kearney Northeast | 640383 | Tower | Build a new 115 kV 10 mile line from Kearney to Tower with a minimum summer emergency rating of 160 MVA |  | 10
| 210675 | 92168 | 143714 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Tande 345 kV New Line | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 67411405 | 2022 | 67411405 | 67411405 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 48 mile 345 kV line from Finstad to Tande. | NULL
| 210656 | 92190 | 143806 | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Tap (OKGE) – Marietta Switchyard (WFEC) 138 kV Ckt 1 New Line (OGE) | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 1575000 | 2022 | 1575000 | 1575000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new 2.1 mile 138 kV line from Marietta Tap (OKGE) – Marietta Switchyard (WFEC) | 138
| 210656 | 92190 | 143815 | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta 2 138 kV Voltage Conversion | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 5000000 | 2022 | 5000000 | 5000000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Convert the Marietta 2 substation from 69 kV to 138 kV and install terminal equipment to support a new 138 kV line from Marietta 4 | 69
| 210656 | 92190 | 143816 | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point - Marietta 2 138 kV Ckt 1 Rebuild | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 8806000 | 2022 | 8806000 | 8806000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild the existing 69 kV line from Rocky Point to Marietta 2 as a 138 kV line | 69
| 210656 | 92190 | 143817 | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point 69 kV Replace Relays | Regional Reliability |  |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 250000 | 2022 | 250000 | 250000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Replace the existing relays at Rocky Point | 69
| 210641 | 92213 | 143980 | #N/A | NIPCO | Multi - Sioux City - Hinton 69 kV | Hinton 69 kV Terminal Equipment | Regional Reliability |  | 2023-10-31 |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 277500 |  |  |  | NTC - Commitment Window |  |  |  |  | Upgrade the terminal equipment at Hinton (K412) substation. | NULL
| 210663 | 92178 | 144148 | #N/A | MWE | Multi - E Newtown 115 kV | E Newtown 115 kV New Statcom | Regional Reliability |  | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 22213115 | 2022 | 22213115 | 22213115 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install a 150 MVAR statcom and supporting equipment at E Newtown to control voltage on the 115 kV transmission system
| 210663 | 92211 | 144163 | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | Folvag 115 kV Terminal Equipment | Regional Reliability |  | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 613746 | 2022 | 613746 | 613746 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Folvag 115 kV sub to accommodate new 115 kV line from NE Williston 115 kV sub.
| 210675 | 92211 | 144171 | #N/A | BEPC | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Substation | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 17766381 | 2022 | 17766381 | 17766381 |  |  |  | NTC - Commitment Window |  |  |  |  | Bisect the Judson to Tande 345 kV line approximately 18 miles from Judson and build a new 345 kV Substation.
| 210657 | 92190 | 144173 | #N/A | WFEC | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Switchyard 138 kV Ckt 1 Terminal Equipment | Regional Reliability |  | 2023-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 736000 | 2022 | 736000 | 736000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at WFEC Marietta Switch to support a new 138 kV line from OG&E Marietta.
| 210663 | 92211 | 144177 | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston - Folvag 115 kV New Line | Regional Reliability |  | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 3800000 | 2022 | 3800000 | 6490000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Build a new 4.5 mile 115 kV line from NE Williston to Folvag.
| 210663 | 92211 | 144178 | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston 115 kV Terminal Equipment | Regional Reliability |  | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 596597 | 2022 | 596597 | 596597 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at NE Williston 115 kV sub to accommodate new 115 kV line from Folvag 115 kV sub.
| 210675 | 92211 | 144198 | #N/A | BEPC | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Transformer | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5904650 | 2022 | 5904650 | 5904650 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Transformer at the new East Fork 345/115 kV Substation.
| 210663 | 92211 | 144199 | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 115 kV Terminal Equipment | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 2511246 | 2022 | 2511246 | 2511246 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 115 kV terminal equipment at MWEC’s East Fork 115 kV substation to accommodate a 115 kV tie line from the East Fork 345/115 kV substation. Construct a 115 kV tie line from the East Fork 115 kV substation to the proposed BEPC East Fork 345/115 kV substation.
| 210663 | 92178 | 144202 | #N/A | MWE | Multi - E Newtown 115 kV | E Newtown 115 kV Substation | Regional Reliability |  | 2031-12-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 1087789 | 2022 | 1087789 | 1087789 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Expand existing 115 kV E Newtown substation to accommodate the statcom interconnection. | NULL
| 210659 | 92237 | 144206 | 0 | SPS | Line - Twist - Wilco 115 kV | Wilco 115 kV Substation | Regional Reliability |  |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 9225928 | 2022 | 9225928 | 9225928 |  |  |  | NTC - Commitment Window |  |  |  |  | Tap the RB-Exum to Hillmar Cheese Plant 115 kV line 4 miles west of the RB-Exum substation and build the new Wilco 115 kV Substation
| 210659 | 92237 | 144207 | 0 | SPS | Line - Twist - Wilco 115 kV | Twist 115 kV Substation | Regional Reliability |  |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 8909901 | 2022 | 8909901 | 8909901 |  |  |  | NTC - Commitment Window |  |  |  |  | Tap the RB-Kemp to Moore 115 kV line 1 mile east of the RB-Kemp substation and build the new Twist 115 kV Substation
| 210659 | 92237 | 144208 | 0 | SPS | Line - Twist - Wilco 115 kV | Twist - Wilco 115 kV Ckt 1 | Regional Reliability |  |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 2678226 | 2022 | 2678226 | 2678226 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 115 kV line between the new Twist 115 kV Substation and the Wilco 115 kV Substation
| 210663 | 92168 | 144226 | #N/A | MWE | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Vanhook 115 kV New Line | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 4702500 | 2022 | 4702500 | 4702500 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 5-mile 115 kV line from Finstad to Vanhook.
| 210675 | 92168 | 144227 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 115 kV Substation | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 4675697 | 2022 | 4675697 | 4675697 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 115 kV Substation with terminal equipment to support a line from Vanhook 115 kV substation.
| 210675 | 92168 | 144230 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345 kV New Substation | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 18822018 | 2022 | 18822018 | 18822018 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV Substation including 345 kV terminals for lines from Leland Olds 345 kV substation, Tande 345 kV substation and high side terminal equipment for Finstad 345/115 kV Ckt 1 transformer and Finstad 345/115 kV Ckt 2 transformer
| 210675 | 92168 | 144231 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad Switched Shunt | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 385021 | 2022 | 385021 | 385021 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a switched shunt at Finstad.
| 210675 | 92168 | 144233 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 1 Transformer | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5315254 | 5315254 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Ckt 1 Transformer at Finstad 345 | 345/115
| 210675 | 92168 | 144235 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 2 Transformer | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5315254 | 5315254 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Ckt 2 transformer at Finstad 115 and upgrade any necessary 115 kV terminal equipment. | 345/115
| 210675 | 92168 | 144236 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds - Finstad - 345 kV New Line | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 200761539 | 2022 | 200761539 | 200761539 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 123 mile 345 kV line from Leland Olds to Finstad.
| 210675 | 92168 | 144237 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds 345 kV Substation | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 9277339 | 2022 | 9277339 | 9277339 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV Substation with terminal equipment to support a new line from Finstad 345 kV substation.
| 210675 | 92168 | 144238 | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Tande 345 kV Terminal Equipment | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5085047 | 2022 | 5085047 | 5085047 |  |  |  | NTC - Commitment Window |  |  |  |  | Install new terminal equipment at Tande to support a new 345 kV line from Finstad. Install a series compensation device at Finstad or Tande.
| 210663 | 92168 | 144239 | #N/A | MWE | Multi - Tande - Finstad - Leland Olds 345 kV | Vanhook 115 kV Terminal Equipment | Regional Reliability |  |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 3811190 | 2022 | 3811190 | 3811190 |  |  |  | NTC - Commitment Window |  |  |  |  | Install new 115 kV terminal equipment at Vanhook to support a new 115 kV line from Finstad.
| 210619 | 92180 | 144283 | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Tower 115 kV Terminal Equipment | Regional Reliability |  |  |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 1288644 | 2022 | 1288644 | 374583 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Tower 115 kV sub to support new line from Kearney 115 kV sub.
| 210619 | 92180 | 144284 | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Kearney 115 kV Terminal Equipment | Regional Reliability |  |  |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 2692377 | 2022 | 2692377 | 374583 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 115 kV terminal equipment at Kearney 115 kV sub to support a new line from Tower 115 kV sub. | NULL
| 210486 | 51278 | 72006 | 0 | WAPA | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade |  | 2023-01-31 |  | 2024-06-01 | 2018-08-17 | SUS-002 | 90000 | 2018 | 99343.1601 | 90000 |  | 0 |  | On Schedule < 4 | 652427 | BISMARK | 655652 |  | Replace CTs at Bismarck 115 kV substation to increase rating of Bismarck - East Bismarck 115 kV line to at least 85 MVA. This is a mitigation upgrade resulting from the Sponsored Upgrade Study #SUS-002 CPEC North Bismarck Breaker. Costs will be Directly Assigned to CPEC. | 115
| 210522 | 81616 | 122599 | 0 | NWE | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen A-Tap Breaker 115 kV | Sponsored Upgrade |  | 2019-06-01 |  | 2021-12-31 | 2019-09-06 | SUS-006 | 552668 | 2019 | 552668 | 552668 |  | 555000 | QUARTERLY TRACKING | Complete |  |  |  |  | Add breaker at Aberdeen A-tap for the new Aberdeen City - Aberdeen Industrial Park 115 kV line. | 115 | [5 empty] | Y
| 210563 | 81656 | 122664 | 0 | NPPD | Line-Pauline-Hastings 115 kV Reconductor | Pauline - Hastings 115 kV Ckt 1 & Ckt 2 Reconductor | Sponsored Upgrade |  | 2022-12-01 |  | 2022-12-01 | 2020-07-14 | SUS-014 | 6000000 | 2020 | 6303750 | 6000000 |  | 0 |  | On Schedule < 4 | 640313 | Pauline | 640215 | Hastings | A reconductor of the Pauline – Hastings 115 kV transmission lines to achieve 193 MVA for normal and emergency ratings. The Pauline to Hastings 115 kV transmission lines are 13 miles each. |  |  | 13
| 210570 | 81559 | 112456 | 0 | EDE | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EDE) | Transmission Service |  | 2023-01-01 |  | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 69054450 | 2022 | 69054450 | 69054450 |  | 0 |  | On Schedule < 4 | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 28.41 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 |  | 25.9
| 200477 | 51254 | 71963 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 14010573.3857 | 20297796 |  |  |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
| 200477 | 51254 | 71964 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  |  |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
| 200477 | 51254 | 71965 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  |  |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
| 200477 | 51254 | 71966 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 12441332.2716 | 15279402 |  |  |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
| 200477 | 51254 | 71967 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1405712.3383 | 1605462 |  |  |  | Delay - Mitigation |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
| 200477 | 51254 | 71968 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability |  | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 4087712.7459 | 5656017 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
| 210569 | 81559 | 112457 | 0 | EKC | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EKC) | Transmission Service |  | 2022-12-31 |  | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 4008402 | 2020 | 4211327.3513 | 7617027 |  | 0 |  | On Schedule < 4 | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 2.44 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 | 2.7
Zonal | 210576 | 91875 | 143156 | TP2020234 | AEP | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Zonal Reliability | Do Not Add (Zonal) | 2022-10-28 | 2022-12-13 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1184404 | 2021 | 1214014.1 | 1910669 | 1460280 | 0 |  | Closed Out |  |  |  |  | Install a new 23 MVAR capacitor bank at Grady 138 kV | 138 |  |  |  |  | Y |  |  | Dara Dixon
| 210590 | 91891 | 143183 | 0 | EMW | Sub - Greenwood 161 kV Terminal Upgrades | Greenwood 161 kV Terminal Upgrades | Transmission Service |  | 2022-03-15 |  | 2021-12-31 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 600168 | 2021 | 615172.2 | 600168 |  | 0 |  | In Service | 541218 | Greenwood Energy Center 161 KV | 541233 | Lees Summit East 161 KV | Replace 2 breakers, relays at Greenwood 161 kV substation | 161 |  |  |  | Y | Y
| 210590 | 91892 | 143184 | 0 | EMW | Sub - Pleasant Hill 161 kV and Lake Winnebago 161 kV Terminal Upgrades | Pleasant Hill 161kV and Lake Winnebago 161 kV Terminal Upgrades | Transmission Service |  | 2021-04-23 |  | 2021-06-01 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 337005 | 2021 | 337005 | 483586 |  | 483586 | QUARTERLY TRACKING | Complete | 541225 | Pleasant Hill 161 KV | 541243 | Lake Winnebago 161 KV | Replace 2 breakers at Pleasant Hill 161 kV substation and replace 1 switch at Lake Winnebago 161 kV substation in order to increase the limit on the Pleasant Hill - Lake Winnebago 161 kV line. | 161 |  |  |  | Y | Y | Y
Base Plan | 210627 | 81717 | 143182 | TP2020266 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward - Border 345 kV Ckt 1 (AEP) | Economic | Base Plan - Add in Future (2025) | 2024-05-24 | 2025-05-27 | 2022-01-01 | 2021-11-05 | 2020 ITP | 1259660 | 2021 | 1323430.288 | 5264319 | 9807331 | 0 |  | Delay - Mitigation |  |  |  |  | Build 0.84-miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm with a summer emergency rating of 1792 MVA. Oklahoma Gas and Electric Co. and American Electric Power shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC | 345 | 0.84 | [6 empty] | James Horn | P20266002 & P20266003
Base Plan | 210633 | 92114 | 143591 | TP2021281 | AEP | Line- Catoosa - Blue Circle 69 kV | Blue Circle - Catoosa 69 kV Ckt 1 Rebuild | Regional Reliability | Added | 2024-05-01 | 2024-12-15 | 2023-06-01 | 2022-03-09 | 2021 ITP | 9020000 | 2022 | 9245500 | 9020000 | 10586881 | 0 |  | Delay - Mitigation |  |  |  |  | Rebuild 3.5 miles of 69 kV line from Catoosa to Blue Circle and upgrade any necessary terminal equipment at Catoosa and/or Blue Circle | 69 |  | 3.5 | [6 empty] | All BPIDs on TP2021281
Base Plan | 210708 | 92393 | 156293 | TP2022737 | AEP | Multi - Siloam Springs-Siloam Springs City 161 kV Terminal Upgrades | Siloam Springs 161 kV Terminal Upgrade | Regional Reliability | Added |  | 2024-10-11 | 2024-06-01 | 2022-12-09 | 2022 ITP | 698030 | 2023 | 698030 | 698030 | 424065 | 0 |  | On Schedule < 4 |  |  |  |  | Upgrade terminal equipment at Siloam Springs 161 kV substation | 161 | [8 empty] | All BPIDs on TP2022737
Base Plan | 210708 | 92386 | 156299 | TA2022022 | AEP | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis - 52nd & Delaware Tap 138 kV Ckt 1 Rebuild | Regional Reliability | Base Plan - Add in Future (2027) | 2027-06-01 | 2027-06-01 | 2027-06-01 | 2022-12-09 | 2022 ITP | 4951250 | 2023 | 4951250 | 4951250 | 4951250 | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild 138 kV line from 36th & Lewis to 52nd & Delaware Tap | 138 | [8 empty] | BPIDs: A22022017, A22022018, A22022019
Base Plan | 210708 | 92386 | 156300 | TA2022022 | AEP | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis 138 kV Ckt 1 Terminal Upgrade | Regional Reliability | Base Plan - Add in Future (2027) | 2027-06-01 | 2027-06-01 | 2027-06-01 | 2022-12-09 | 2022 ITP | 540691 | 2023 | 540691 | 540691 | 540691 | 0 |  | On Schedule < 4 | 509800 | 36th & LEWIS |  |  | Replace wave traps at 36th & Lewis 138 kV substation | 138 | [8 empty] | BPID: A22022011
Note on L15: s306055: If project skips summer peak
Note on T76: s306055: 60% costs of Treasure Island Station
Note on S322: s306055: Use these numbers

## Sheet1 (hidden)
UPGRADE TYPE
If it says zonal, even for the base plan ones, do not include these

## Q4 2022 Initial (hidden)
4Q 2022 Project Tracking Initial Extract
| COMPLETE | [11 empty] | Complete and in-service
| CLOSED OUT | [11 empty] | In-service and all required project close-out documentation supplied by TO. Per BP 7060, Section 13, upgrades reported as closed out this quarter will not be included in subsequent reports.
| DELAY - MITIGATION | [11 empty] | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project
| DELAY - MITIGATION WINDOW | [11 empty] | Behind schedule, interim mitigation pending or project may change but time permits the implementation of project
| IDENTIFIED | [11 empty] | Upgrade identified and included in Board approved study results
| IN SERVICE | [11 empty] | Upgrade is in service, but not all project activities are complete
| NTC - COMMITMENT WINDOW | [11 empty] | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
| NTC-C PROJECT ESTIMATE WINDOW | [11 empty] | Within the NTC-C Project Estimate (CPE) window
| ON SCHEDULE < 4 | [11 empty] | On Schedule within 4-year horizon
| ON SCHEDULE > 4 | [11 empty] | On Schedule beyond 4-year horizon
| RE-EVALUATION | [11 empty] | NTC/NTC-C active; pending re-evaluation
| RFP ISSUED | [11 empty] | Responses for competeitive upgrades are being submitted and/or reviewed
| SUSPENDED | [11 empty] | NTC/GIA suspended
Cost Allocation | NTC ID | PROJECT ID | UPGRADE ID | Column4 | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Manual CPP2 | CPP | OWNER | PROJECT NAME | UPGRADE NAME | UPGRADE TYPE | IN SERVICE DATE | EcoSys ISD (Updated) | RTO DETERMINED NEED DATE | LATEST NTC ISSUE DATE | SOURCE STUDY | BASELINE ESTIMATE | BASELINE YEAR | BASELINE ESTIMATE WITH ESCALATION | CURRENT COST ESTIMATE | EcoSys EAC (Loaded | BEST FINAL COST | FINAL COST SOURCE | PROJECT STATUS TYPE | FROM BUS NUM | FROM BUS NAME | TO BUS NUM | TO BUS NAME | UPGRADE DESCRIPTION | VOLTAGE | NEW MILES | RECONDUCTOR MILES | VOLTAGE CONVERSION MILES | LETTER OF COMMERCIAL OPERATION REC'D | MOD INFO REC'D | FINAL COST REC'D | GIS DATA | PM | Comments
| 200433 | 31144 | 51764 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Sub - Tupelo - Tupelo Tap 138 kV Terminal Upgrades | Tupelo 138 kV Terminal Upgrades | Economic | 2021-12-31 |  | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 100000 | 2017 | 110381.289 | 410000 |  | 0 |  | Delay - Mitigation | 505600 | Tupelo | 521071 | TUPELO TAP | Upgrade any necessary terminal equipment at Tupelo to increase the rating of the 138 kV line between Tupelo substation and Tupelo Tap substation. | 138
| 210545 | 81550 | 112435 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic | 2021-01-01 |  | 2021-01-01 | 2019-11-18 | 2019 ITP | 1000000 | 2020 | 1025000 | 1000000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Rebuild 2.03 miles of 138 kV line from Kingfisher to East Kingfisher and upgrade any necessary terminal equipment at East Kingfisher and/or Kingfisher to increase the summer emergency rating to 286 MVA | 138
| 210586 | 81553 | 112443 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Russett - South Brown 138 kV | Russett - South Brown 138 kV Ckt 1 Rebuild | Economic | 2027-12-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 10267390.81 | 2021 | 10524075.5803 | 10267390.81 |  | 0 |  | Delay - Mitigation | 505602 | Brown | 521044 | RUSSETT | Rebuild 18.62 miles of 138 kV line from Russett to South Brown and upgrade terminal equipment at South Brown as needed to achieve a summer emergency rating of 234 MVA | 138
| 210543 | 81557 | 112451 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Arnold - Ransom 115kV Terminal Upgrades | Economic | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 462000 | 2020 | 485388.75 | 726694 |  | 0 |  | On Schedule < 4 | 531409 | ARNOLD | 531414 | RANSOM | Upgrade any necessary terminal equipment at Arnold and/or Ransom to increase the summer emergency rating to 165 MVA | 115
| 210543 | 81557 | 112452 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Pile - Scott City 115kV Terminal Upgrades | Economic | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 1633500 | 2020 | 1716195.9375 | 437574 |  | 0 |  | On Schedule < 4 | 531432 | PILE | 531433 | SCOTT CITY | Upgrade any necessary terminal equipment at Pile and/or Scott City to increase the summer emergency rating to 229 MVA | 115
| 210543 | 81557 | 112453 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SEPC | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Scott City - Setab 115kV Terminal Upgrades | Economic | 2025-01-01 |  | 2025-01-01 | 2019-11-18 | 2019 ITP | 1556500 | 2020 | 1635297.8125 | 467574 |  | 0 |  | On Schedule < 4 | 531433 | SCOTT CITY | 531464 | SETAB | Upgrade any necessary terminal equipment at Scott City and/or Setab to increase the summer emergency rating to 230 MVA | 115
Base Plan | 200386 | 31057 | 51560 |  | #N/A | #N/A | #N/A | No | Do Not Add (Zonal) | TA2011012 | TA2011012 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2022-11-20 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 25128911.6762 | 20716215 |  | 0 |  | Delay - Mitigation | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69 |  |  |  | Y | Y |  | Y | Brent Garret | Prev Comments: Waiting for POD to put in service. No final costs. - (A11012545-closed $1,437,431 / A11012198-in-service $0 / A11012444-open $17,092,906) & TP2018017-closed $2,185,878)
Direct Assignment | 210611 | 81474 | 112307 |  | #N/A | #N/A | #N/A | No | Do Not Add | TP2021310 | TP2021310 | AEP | Sub - Oklaunion 345 kV Capacitive Reactive Power Support | Oklaunion 345 kV Capacitive Reactive Power Support | Generation Interconnection | 2023-05-15 | 2024-10-01 | 2023-05-15 | 2021-05-17 | DISIS-2016-002 | 9453182 | 2021 | 9689511.55 | 12400000 | 25800000 | 0 |  | On Schedule < 4 |  |  |  |  | Install +200Mvar Capacitor Bank(s) at the Oklaunion 345kV substation. | 345 |  |  |  |  | Y |  |  |  | MOD number added 102550
|  | 81483 | 112331 |  | #N/A | #N/A | #N/A | No | Do Not Add | TP2019285 | TP2019285 | AEP | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (TOIF) (AEPW) | Generation Interconnection |  | 2024-09-01 |  |  | GI STUDIES |  |  |  | 1175646 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating | 138 | 0.04 | [5 empty] | Y |  | GIA Oxbow Solar
| 210540 | 81561 | 112504 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345kV Terminal Upgrades (OGE) | Economic | 2024-01-01 |  | 2026-01-01 | 2019-11-18 | 2019 ITP | 4139615 | 2020 | 4349183.0094 | 4139615 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment to support a 345kV line from Wekiwa to Sooner rated at summer emergency of 1792 MVA | 345
| 210592 | 81547 | 112509 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Line - Wolf Creek - Blackberry 345 kV | Wolf Creek 345kV Terminal Equipment | Economic | 2025-12-31 |  | 2026-01-01 | 2021-01-21 | 2019 ITP | 11618029 | 2021 | 11908479.725 | 12217322 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wolf Creek to support 345kV line from Wolf Creek to Blackberry rated at 1792 MVA | 345
| 210586 | 81617 | 122577 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138kV Ckt 1 Rebuild | Economic | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 2850000 | 2020 | 2994281.25 | 5750000 |  | 0 |  | On Schedule < 4 | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Rebuild 5.09-mile 138 kV line from Anadarko to Gracemont as a double circuit and install/upgrade any necessary terminal equipment to increase the summer emergency rating to 353 MVA for each circuit | 138 |  | 5.07
| 210626 | 81547 | 122598 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NEET | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic | 2025-01-01 |  | 2026-01-01 | 2021-12-03 | 2019 ITP | 85168938 | 2021 | 87298161.45 | 85168938 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build a new 345kV line from Wolf Creek to Blackberry with a summer emergency rating of 1792 MVA | 345
| 210578 | 81675 | 122717 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2022-08-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 374400 | 2021 | 383760 | 374400 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/345
| 210578 | 81675 | 122718 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2022-08-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 | 512650 | GRDA1 345 | Upgrade terminal equipment at GRDA1 161 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/161
| 210586 | 81679 | 122722 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Dover Switch - O'Keene 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-12-31 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 910000 | 2021 | 932750 | 910000 |  | 0 |  | Delay - Mitigation | 520882 | DOVER SW | 521016 | OKEENE | Upgrade any necessary terminal equipment, increase clearances, and replace conductor to achieve a summer emergency rating of 136 MVA
| 210650 | 81691 | 122733 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock 230 kV Terminal Upgrades | Economic | 2023-10-01 |  | 2025-01-01 | 2022-03-09 | 2021 ITP | 614000 | 2022 | 614000 | 614000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Whitlock 230 kV for Oahe to Sully Buttes to Whitlock to Glenham 230 kV line.
| 210648 | 81691 | 122734 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Oahe 230 kV Terminal Upgrades (WAPA) | Economic |  |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 561800 | 2022 | 561800 | 561800 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade terminal equipment at Oahe 230 kV for the Oahe to Sully Buttes 230 kV line. Re-conductor three spans of line between Oahe 230 kV substation and Sully Buttes 230 kV substation..
| 210639 | 81691 | 122735 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EREC | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes 230 kV Terminal Upgrades | Economic | 2023-11-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 587000 | 2022 | 587000 | 587000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Sully Buttes for Oahe - Sully Buttes - Whitlock 230 kV line
| 210645 | 81694 | 122739 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | NPPD | XFR - Columbus 230/115 | Columbus East 230/115 kV transformer | Economic | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 5080000 | 2022 | 5080000 | 5080000 |  | 0 |  | Delay - Mitigation | 640127 | Columbus East | 640126 | Columbus East | Replace the 230/115 kV transformer and any necessary terminal equipment at Columbus East. | 230/115
| 210645 | 81769 | 122741 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff - Victory Hill 115kV Ckt 2 | Economic | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 7760000 | 2022 | 7760000 | 7760000 |  | 0 |  | Delay - Mitigation | 640338 | Scottsbluff | 640397 | Victory Hill | Build second 9 mile 115 kV line from Scottsbluff to Victory Hill.
| 210586 | 81617 | 122753 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138 kV Ckt 2 Rebuild | Economic | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 1750000 | 2021 | 1793750 | 3330000 |  | 0 |  | On Schedule < 4 | 520814 | ANADARKO | 515802 | Gracemont 138 kV | Rebuild 5.09-mile 138kV line from Anadarko to Gracemont as double circuit and add/upgrade any necessary equipment to increase the achieve a summer emergency rating of 353 MVA for each circuit |  |  | 5.07
| 210589 | 81617 | 122755 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Line - Anadarko - Gracemont 138kV | Gracemont 138 kV Ckt 2 Terminal Equipment | Economic | 2023-01-01 |  | 2023-01-01 | 2020-11-17 | 2020 ITP | 6075003 | 2021 | 6226878.075 | 1124593 |  | 0 |  | On Schedule < 4 | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Install terminal equipment at Gracemont 138 kV to support a second 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 353 MVA | NULL
|  | 81483 | 112332 |  | #N/A | #N/A | #N/A | No | Do Not Add | TP2019285 | TP2019285 | AEP | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection |  | 2024-09-01 |  |  | GI STUDIES |  |  |  | 9959548.73 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build a 3-breaker ring bus station on the Lieberman-North Benton 138 kV section of the Lieberman-Red Point 138 kV line to facilitate the new generation interconnection. | 138 | 1.32 | [5 empty] | Y |  | GIA Oxbow Solar
| 210578 | 81675 | 122801 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-06-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 312000 | 2021 | 319800 | 312000 |  | 0 |  | Delay - Mitigation | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | NULL
| 210578 | 81675 | 122802 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | GRDA | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-06-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | 0 |  | Delay - Mitigation | 512656 | GRDA1 161 |  |  | Upgrade terminal equipment at GRDA1 161 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | 161
| 210628 | 81717 | 122823 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Border - Woodward 345 kV Tap | Border - Woodward Tap 345 kV Substation | Economic | 2023-04-01 |  | 2022-01-01 | 2021-11-05 | 2020 ITP | 11500000 | 2021 | 11787500 | 11500000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the existing Border to Woodward 345 kV line 19 miles from the Border station and build a new 345 kV substation or switching station
| 210616 | 81741 | 122848 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco 345 kV Terminal Equipment | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 1843729 | 2021 | 1889822.225 | 1843729 |  | 0 |  | On Schedule < 4 | 514801 | Minco 345 kv |  |  | Install terminal equipment at Minco substation 345 kV to support a new 345 kV line from Minco with a summer emergency rating of 1792 MVA | 345
| 210616 | 81741 | 122849 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (345 kV) | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 30707951 | 2021 | 31475649.775 | 30707951 |  | 0 |  | On Schedule < 4 |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper and terminals to accommodate cut in of existing Cimarron to Draper 345 kV line. Tie into existing Cimarron to Draper 345 kV line. This description is specific to the 345 kV components. | 345
| 210616 | 81741 | 122850 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 1 | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 5003830 | 2021 | 5128925.75 | 5003830 |  | 0 |  | On Schedule < 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
| 210616 | 81741 | 122851 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 2 | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 4885649 | 2021 | 5007790.225 | 4885649 |  | 0 |  | On Schedule < 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
| 210616 | 81741 | 122858 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Cimarron - Draper 345 kV Terminal Upgrades #2 | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 2541200 | 2021 | 2604730 | 2541200 |  | 0 |  | On Schedule < 4 | 514901 | CIMARRON 345 | 514934 | DRAPER LAKE 345 | Upgrade any necessary terminal equipment on the Cimarron to Draper 345 kV line to achieve a summer emergency rating of 1540 MVA
| 210656 | 81741 | 122863 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Midwest 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 65000 | 2021 | 66625 | 65000 |  | 0 |  | On Schedule < 4 | 514946 | MIDWEST TAP 138 |  |  | Upgrade any necessary terminal equipment at Midwest 138 kV on the Midwest to Franklin 138 kV line to achieve a summer emergency rating of 308 MVA
| 210586 | 81679 | 122865 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Aspen 138 kV Terminal Upgrades | Economic | 2022-04-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 202500 | 2021 | 207562.5 | 202500 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Aspen to Mooreland 138 kV line to achieve a summer emergency rating of 187 MVA rating
| 210586 | 81679 | 122866 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Pic 138 kV Terminal Upgrades | Economic | 2022-04-01 |  | 2022-01-01 | 2020-11-17 | 2020 ITP | 405000 | 2021 | 415125 | 405000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Mooreland to Pic 138 kV line to achieve a summer emergency rating of 187 MVA rating
| 210670 | 81741 | 133085 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | NEET | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco - Pleasant Valley 345 kV Ckt 1 | Economic |  |  | 2025-01-01 | 2022-04-28 | 2020 ITP |  |  |  | 57512100 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 34.8 miles of 345 kV line from Minco to Pleasant Valley 345 kV to achieve a 1792 MVA summer emergency rating.
| 210670 | 81741 | 133106 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | NEET | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper - Pleasant Valley 345 kV Ckt 2 | Economic |  |  | 2025-01-01 | 2022-04-28 | 2020 ITP |  |  |  | 23400139 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build a second 13.2-mile 345 kV line from Draper 345 kV substation to Pleasant Valley 345 kV substation with a summer emergency rating of 1792 MVA
| 210616 | 81741 | 143176 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper 345 kV Terminal Equipment | Economic | 2025-01-01 |  | 2025-01-01 | 2021-06-04 | 2020 ITP | 6484533 | 2021 | 6646646.325 | 6484533 |  |  |  | On Schedule < 4 |  |  |  |  | Install a new line terminal at Draper 345 kV to accommodate new 345 kV line from Pleasant Valley.
|  | 81489 | 112333 |  | #N/A | #N/A | #N/A | No | Do Not Add | TP2021760 | TP2021760 | AEP | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (TOIF) (AEPW) | Generation Interconnection |  | 2023-05-01 |  |  | GI STUDIES |  |  |  | 1388819 | 1704279 | 0 |  | On Schedule < 4 |  |  |  |  | : Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 345 | 0.18 | [5 empty] | Y | James Ball | AEP - 100% / P21760001
| 210645 | 81769 | 143599 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 1194000 | 2022 | 1194000 | 1194000 |  |  |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Scottsbluff 115 kV to support a second 115 kV line from Victory Hill. | 115
| 210645 | 81769 | 143600 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | NPPD | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Victory Hill 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 1129000 | 2022 | 1129000 | 1129000 |  |  |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Victory Hill 115 kV to support a second 115 kV line from Scottsbluff with a summer emergency rating of 264 MVA | 115
| 210648 | 81691 | 143613 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes - Whitlock 230 kV Line Clearance Increase | Economic | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 1744800 | 2022 | 1744800 | 1744800 |  |  |  | On Schedule < 4 |  |  |  |  | Increase ground clearance of the Sully Buttes to Whitlock 230 kV line. | 230
| 210648 | 81691 | 143614 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | WAPA | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock - Glenham 230 kV Clearance Increase | Economic | 2025-01-01 |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 5845900 | 2022 | 5845900 | 5845900 |  |  |  | On Schedule < 4 |  |  |  |  | Increase ground clearance of the Whitlock - Glenham 230 kV. | 230
| 210656 | 92184 | 143786 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | OGE | Sub - Cleo Corner 69 kV & Cleo Junction 69 kV | Cleo Corner 69 kV Terminal Upgrades | Economic |  |  | 2023-01-01 | 2022-03-11 | 2021 ITP | 168228 | 2022 | 168228 | 168228 |  | 0 |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at the Cleo Corner 69 kV substation | 69
| 210644 | 92238 | 144142 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | TSGT | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (TSGT) | Economic | 2023-12-13 |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 380321 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
| 210645 | 92238 | 144143 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | NPPD | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (NPPD) | Economic | 2023-12-31 |  | 2023-01-01 | 2022-03-09 | 2021 ITP | 281000 | 2022 | 281000 | 281000 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
|  | 30959 | 51338 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Burns 345kV (GEN-2014-001 NU) | Generation Interconnection | 2021-07-08 |  |  |  | GI STUDIES |  |  |  | 2098946 |  | 0 |  | In Service |  |  |  |  | Construct new terminal extension of the bus north to add another rung to the bus. Equipment includes two (2) 345kV breakers, four (4) 345kV switches, bus work, and all associated yard and conduit work.
|  | 30959 | 51360 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 TOIF) | Generation Interconnection | 2021-07-28 |  |  |  | GI STUDIES |  |  |  | 1674997 |  | 0 |  | In Service |  |  |  |  | Install three (3) 345 kV arresters, one (1) 345 kV 3000 Amp motor-operated switch, three (3) 345 kV arrester stands, one (1) 345 kV full tension dead-end structure, and one (1) 3-phase bus support into new Transmission Owner GEN-2014-001 Point of Interconnection substation. The estimate also includes three (3) 345 kV VTs, three (3) 345 kV CTs, and revenue interconnection metering plus all other associated yard, cable, grounding, communication, and conduit work.
|  | 51239 | 71933 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generation Interconnection | 2024-04-01 |  |  |  | GI STUDIES |  |  |  | 4700000 |  |  |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345kV Substation - Install 345kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformers, potential transformers, and associated and miscellaneous material.; One (1) approximately five (5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Holt County 345 kV substation.
|  | 51239 | 71934 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generation Interconnection | 2024-04-01 |  |  |  | GI STUDIES |  |  |  | 5900000 |  |  |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
|  | 51255 | 71970 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | WFEC | Sub - Snyder 138kV (WFEC) - GEN-2015-013 Addition | Snyder 138kV (WFEC) - GEN-2015-013 Addition (NU) | Generation Interconnection | 2019-08-15 |  |  |  | GI STUDIES |  |  |  | 1700000 |  |  |  | On Schedule < 4 | 521052 | SNYDER |  |  | Snyder 138kV Substation: Install one (1) new line terminal, one (1) 2000A circuit breaker, line relaying, disconnect switches, additional 4” IPS aluminum buss, and associated equipment. | [5 empty] | #N/A | #N/A
|  | 51261 | 71982 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Belvidere – Fairbury 115kV circuit #1 | Generation Interconnection | 2019-11-01 |  |  |  | GI STUDIES |  |  |  | 1700000 |  |  |  | Re-evaluation |  |  | 640169 | Fairbury | NPPD Belvidere – Fairbury 115kV circuit #1: uprate Belvidere – Fairbury to at least 107 MVA | 115/115 |  |  |  | Y
|  | 51261 | 71983 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Beatrice – Harbine 115kV circuit #1 | Generation Interconnection | 2019-11-01 |  |  |  | GI STUDIES |  |  |  | 900000 |  |  |  | Re-evaluation | 640076 | Beatrice | 640208 | Harbine | NPPD Beatrice – Harbine 115kV circuit #1: uprate Beatrice – Harbine to at least 102 MVA | 115/115 |  |  |  | Y
|  | 51283 | 72032 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generation Interconnection | 2019-12-01 |  |  |  | GI STUDIES |  |  |  | 591193 |  | 0 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51283 | 72033 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU) | Generation Interconnection | 2019-12-01 |  |  |  | GI STUDIES |  |  |  | 13383989 |  | 0 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation - Non-Shared Network Upgrades: Construct three (3) 345kV 4000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Allowance for Funds Used During Construction (AFUDC) and Contingency funds are included in this cost estimate.
|  | 51283 | 72034 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generation Interconnection | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 20000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Oklahoma Gas and Electric Company – Checking and Verifying Relay Settings
|  | 51332 | 82126 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (TOIF) | Generation Interconnection | 2022-10-14 |  |  |  | GI STUDIES |  |  |  | 1099958 |  | 0 |  | On Schedule < 4 | 515800 | Gracemont 345kv |  |  | Transmission Owner Gracemont Interconnection Substation: Transmission Owner Interconnection Facilities 345kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51332 | 82127 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (NU) | Generation Interconnection | 2022-10-14 |  |  |  | GI STUDIES |  |  |  | 1025042 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner Gracemont Interconnection Substation - Non-Shared Network Upgrades install one (1) 3000A circuit breakers, control panel replacement, line relaying, disconnect switches, and all other associated work and materials.
|  | 51333 | 82128 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generation Interconnection | 2022-10-15 |  |  |  | GI STUDIES |  |  |  | 1099958 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation: Transmission Owner Interconnection Facilities Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
|  | 51333 | 82129 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generation Interconnection | 2022-10-15 |  |  |  | GI STUDIES |  |  |  | 9213042 |  | 0 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation - Non-Shared Network Upgrades* Install three (3) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
|  | 81489 | 112334 |  | #N/A | #N/A | #N/A | No | Do Not Add | TP2021760 | TP2021760 | AEP | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (AEPW) | Generation Interconnection | 2023-05-01 | 2023-05-01 |  |  | GI STUDIES |  |  |  | 17798882 | 7067936.0422 | 0 |  | On Schedule < 4 |  |  |  |  | Construct new 345 kV four (4) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators ,and all other associated work and materials. | 345 | 0.32 | [5 empty] | Y | James Ball | AEP - 39.71% / Treasure Island
|  | 81491 | 112337 |  | #N/A | #N/A | #N/A | No | Do Not Add | TP2019265 | TP2019265 | AEP | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (TOIF) (AEPW) | Generation Interconnection |  | 2023-04-25 |  |  | GI STUDIES |  |  |  | 918474 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 138 | 0.04 | [5 empty] | Y | Chadwick Bell
|  | 81491 | 112338 |  | #N/A | #N/A | #N/A | No | Do Not Add | TP2019265 | TP2019265 | AEP | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (Non-Shared NU) (AEPW) | Generation Interconnection |  | 2023-04-25 |  |  | GI STUDIES |  |  |  | 7400346 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct new 138 kV three (3) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 138 | [6 empty] | Y | Chadwick Bell
Base Plan | 210623 | 81500 | 112360 |  | #N/A | #N/A | #N/A | No | Do Not Add (2026) | TP2019245 | TP2019245 | AEP | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | 2026-05-01 | 2026-05-01 | 2021-06-01 | 2021-11-05 | 2019 ITP | 41100000 | 2020 | 43180687.5 | 46270466 | 41667013 | 0 |  | Delay - Mitigation | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 27 breakers at Riverside Station 138 kV with 90 kA breakers and expand substation as necessary to accommodate physically larger breakers | 138 | 1.56 |  |  |  | Y |  | Y | Brad Duvall
Base Plan | 210544 | 81501 | 112361 |  | TA2019024 | #N/A | TA2019024 | Yes | Do Not Add (2024) | TA2019024 | TA2019024 | AEP | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | 2023-12-15 | 2024-10-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4645175.5906 | 4194065 | 3841496 | 0 |  | Delay - Mitigation | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138 |  |  |  |  | Y |  | Y | Nathan Ingram | NTC Work 2 BPIDs Station & Removal - A19024004 & A19024002
Base Plan | 210544 | 81520 | 112389 |  | TP2020033 | #N/A | TP2020033 | Yes | Already Added | TP2020033 | TP2020033 | AEP | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | 2022-05-27 | 2022-06-23 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 7064651.2565 | 6724237 | 6071666 | 0 |  | Delay - Mitigation | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2 |  |  |  | Y |  | Y | Larry Oden | P20033001 & P20033006
Base Plan | 210544 | 81523 | 112393 |  | TP2020033 | #N/A | TP2020033 | Yes | Already Added | TP2020033 | TP2020033 | AEP | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | 2021-11-17 | 2021-11-17 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1340497.05 | 1497509 | 1549008 | 0 |  | Complete | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5 |  |  | Y |  | Y | Larry Oden
0 |  | 81488 | 112339 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WAPA | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2023-12-29 |  |  |  | GI STUDIES |  |  |  | 250000 |  | 0 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
0 |  | 81488 | 112340 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WAPA | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2023-12-29 |  |  |  | GI STUDIES |  |  |  | 8805000 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 230 kV switchyard on the Oahe - Fort Thompson North 230 kV transmission that will consist of a three (3) breaker ring bus, three (3) 230 kV power circuit breakers, nine (9) 230 kV disconnect switches, instrument transformers, associated control and protection equipment, high voltage bus, three (3) line take-off structures, conductor, overhead optical ground wire, communication equipment, and a control building.
0 |  | 81495 | 112353 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | XTO to Cornell GEN-2016-177 Interconnection Costs | XTO to Cornell GEN-2016-177 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-177 (17.0 MW/Gas Turbine) into the POI at XTO_Cornell 115kV.
0 | 210609 | 81591 | 122537 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Device - Border 345kV Capacitive Reactive Support | Border 345kV Capacitive Reactive Support | Generation Interconnection | 2024-04-20 |  | 2023-04-20 | 2021-05-17 | DISIS-2016-002 | 3996000 | 2021 | 4095900 | 3996000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Install + 275 MVAR Capacitor Bank(s) at Border 345 kV.
0 |  | 81594 | 122540 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Device - Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002-1) | Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  |  | GI STUDIES |  |  |  | 7365886 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install + 100 MVAR Capacitor Bank(s) at Crossroads 345 kV. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81600 | 122546 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Crossroads - Tolk 345 kV Ckt 1 | Crossroads - Tolk 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-01 |  |  |  | GI STUDIES |  |  |  | 184651 |  | 0 |  | On Schedule < 4 |  |  |  |  | Replace approximately four structures on the Crossroads - Tolk 345 kV line to achieve a minimum rating of 956 MVA. Network Upgrade shared among four requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81599 | 122547 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Crossroads - Eddy County 345 kV Ckt 1 | Crossroads - Eddy County 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2022-12-15 |  |  |  | GI STUDIES |  |  |  | 210533 |  |  |  | On Schedule < 4 |  |  |  |  | Replace two 345 kV structures, wave traps (3X), and jumpers to achieve minimum emergency rating of 956 MVA. Network Upgrade Shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81606 | 122554 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Roadrunner 115kV GEN-2016-121 Interconnection Costs | Roadrunner 115kV GEN-2016-121 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 483969 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-121 (110.0 MW/Solar) into the POI at Roadrunner 115kV.
0 |  | 81607 | 122556 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Eddy County to Tolk GEN-2016-123 Interconnection Costs | Eddy County to Tolk GEN-2016-123 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-123 (298.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
0 |  | 81608 | 122558 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Eddy County to Tolk GEN-2016-124 Interconnection Costs | Eddy County to Tolk GEN-2016-124 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-124 (150.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
0 |  | 81609 | 122560 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Eddy County to Tolk GEN-2016-125 Interconnection Costs | Eddy County to Tolk GEN-2016-125 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 413496 |  |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-125 (74.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
0 |  | 81613 | 122568 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | XFR - Tolk 345/230 kV Ckt2 | Tolk 345/230 kV CKT 2 Transformer (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  |  | GI STUDIES |  |  |  | 14055360 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new 345/230 kV Transformer Ckt 2 at Tolk to achieve a minimum emergency rating of 921 MVA on the Crossroads - Tolk 345 kV Ckt 1 line. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  | 0.5
0 | 210564 | 81489 | 122600 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (OKGE) | Generation Interconnection | 2021-12-31 |  | 2020-09-22 | 2020-08-11 | DISIS-2016-002 | 10000 | 2020 | 10250 | 10000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Relay settings upgrades
0 | 210630 | 81490 | 122601 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Multi - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Terminal Equipment | Generation Interconnection | 2023-12-31 |  | 2023-12-31 | 2022-01-31 | DISIS-2016-002 |  |  |  | 10000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Change relay settings to accommodate the construction of the GEN-2016-095 wind farm.
0 | 210562 | 81628 | 122602 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WAPA | Sub - Jamestown 230 kV Redundant Bus Tie | Jamestown 230 kV Redundant Bus Tie | Generation Interconnection | 2024-12-31 |  |  | 2020-06-10 | DISIS-2016-001 | 1510000 | 2020 | 1586443.75 | 1510000 |  | 0 |  | In Service |  |  |  |  | Add a redundant bus to Jamestown 230 kV substation to mitigate for a fault and breaker fail of CB 9182.
0 | 210565 | 81481 | 122622 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Substation Upgrades | Generation Interconnection | 2025-12-31 |  |  | 2020-08-28 | DISIS-2016-002 | 139825 | 2020 | 146903.6406 | 136893 |  | 0 |  | In Service |  |  |  |  | Replace one control panel and review and/or apply new relay settings at the Swissvale substation.
0 |  | 81481 | 122623 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Terminal Upgrades | Generation Interconnection | 2025-12-31 |  |  |  | GI STUDIES | 10000 | 2020 | 10506.25 | 10000 |  | 0 |  | In Service |  |  |  |  | Reviewing and applying new relaying settings at the Swissvale substation for the interconnection of GEN-2016-158.
0 |  | 81636 | 122635 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | GEN-2016-119 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-03-14 |  |  |  | GI STUDIES |  |  |  | 1099871 |  | 0 |  | On Schedule < 4 |  |  |  |  | Add a single 345kV line terminal to a new EHV Substation. Dead end structure, line switch, line relaying, revenue metering including CTs and PTs.
0 | 210606 | 81636 | 122637 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | Spring Creek345 kV (GEN-2016-119) | Generation Interconnection |  |  | 2025-03-15 | 2021-03-04 | DISIS-2016-002 | 16624 | 2021 | 17039.6 | 16624.73 |  | 0 |  | On Schedule < 4 |  |  |  |  | Review and/or apply relay protection settings at the Spring Creek substation.
0 |  | 81639 | 122640 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-17 |  |  |  | GI STUDIES |  |  |  | 4578401 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum system emergency rating of 430 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81640 | 122641 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 697513 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum emergency rating of 456 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81641 | 122642 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125 | [5 empty] | #N/A | #N/A
0 |  | 81642 | 122643 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81645 | 122645 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-15 |  |  |  | GI STUDIES |  |  |  | 4852215 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 90/90 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  |  | 13
0 |  | 81644 | 122646 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-15 |  |  |  | GI STUDIES |  |  |  | 968567 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 478 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81646 | 122647 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  |  | GI STUDIES |  |  |  | 5943138 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Tuco 230 kV Substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81647 | 122648 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2021-10-28 |  |  |  | GI STUDIES |  |  |  | 3318135 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Deaf Smith 115 kV substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
0 |  | 81655 | 122662 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Woodring 345kV GEN-2016-128 Interconnection Costs | Woodring 345kV GEN-2016-128 Interconnection (TOIF) (OKGE) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At an existing EHV substation, update relay settings on an existing Gen-Tie line to accommodate new protection settings.
0 | 210593 | 81561 | 112458 |  | #N/A | #N/A | #N/A | No | Do Not Add (2026) | TS2020480 | TS2020480 | TSOK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic | 2026-01-01 | 2025-12-31 | 2026-01-01 | 2021-02-10 | 2019 ITP | 97111851 | 2020 | 102028138.4569 | 97111851 | 114481758 | 0 |  | On Schedule < 4 | 509755 | WEKIWA 345KV | 514803 | SOONER 345 | Build a new 345kV line from Sooner to Wekiwa with a summer emergency rating of 1792 MVA | 345 | 50.5 | [6 empty] | Katherine Vecchiarelli
Base Plan | 210544 | 81561 | 112460 |  | #N/A | #N/A | #N/A | No | Do Not Add (2025) | TP2019146 | TP2019146 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | 2025-05-01 | 2025-05-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 770654.45 | 1242638 | 1216324 | 0 |  | On Schedule < 4 | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138 |  |  |  |  | Y |  | Y
0 | 210631 | 81657 | 122667 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | OGE | Multi - Riverside 345 kV Substation | Redbud 345kV | Generation Interconnection | 2025-12-31 |  | 2025-12-31 | 2022-01-31 | DISIS-2016-002 |  |  |  | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Change relay settings to accommodate the Interconnection of the States Edge 1 Wind Farm.
0 |  | 81658 | 122669 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | BEPC | GEN-2016-130 Interconnection Costs | Leland Olds 345 kV Substation Reconfiguration (DISIS-2016-002-2) | Generation Interconnection | 2025-06-30 |  |  |  | GI STUDIES |  |  |  | 2776827 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build out of a new line terminal for relocation of LOS Unit 2 main transformer. This includes one (1) 345 kV power circuit breaker, two (2) 345 kV breaker disconnect switches, three (3) 345 kV PTs, three (3) 345 kV surge arrestors, and protection and control package.
0 |  | 81660 | 122673 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Viola 345kV GEN-2016-153 Interconnection Costs | Viola 345kV GEN-2016-153 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 20000 |  | 0 |  | In Service |  |  |  |  | Review relay settings and apply adjusted settings at Flat Ridge 2 East and Viola 345 kV substations. Install PMU at Viola Substation
0 | 210612 | 81660 | 122674 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Viola 345kV GEN-2016-153 Interconnection Costs | Renfrow 345 kV Relay Setting Adjustment | Generation Interconnection | 2023-10-01 |  | 2023-10-01 | 2021-06-08 | DISIS-2016-002 | 15000 | 2021 | 15375 | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At the existing Renfrow 345 kV substation, update relay settings to accommodate new protection settings.
0 |  | 81661 | 122676 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Benton 345kV GEN-2016-162 and 163 Interconnection Costs | Benton 345kV GEN-2016-162 and 163 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 810255 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 345 kV circuit breaker and two (2) new 345 kV disconnect switches.
0 |  | 81662 | 122677 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sweetwater 345kV GEN-2016-074 Interconnection Costs | GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Expanding the existing Sweetwater 345kV Substation to accommodate the GEN-2016-074 interconnection request
0 |  | 81662 | 122678 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sweetwater 345kV GEN-2016-074 Interconnection Costs | Sweetwater 345kV GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  |  | GI STUDIES | [7 empty] | On Schedule < 4 |  |  |  |  | Expand the existing Sweetwater 345kV Substation to accommodate GEN-2016-074 interconnection request
0 |  | 81665 | 122684 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | TSGT | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (TOIF) (TSGT) | Generation Interconnection | 2023-10-05 |  |  |  | GI STUDIES |  |  |  | 1636796 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
0 |  | 81665 | 122687 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | TSGT | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (Non-Shared NU) (TSGT) | Generation Interconnection | 2023-10-05 |  |  |  | GI STUDIES |  |  |  | 2155837 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230 kV power circuit breaker, two (2) 115 kV power circuit breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
0 |  | 81666 | 122688 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WAPA | Bismark to Glenham GEN-2016-087 Interconnection Costs | Bismark to Glenham 230kV GEN-2016-087 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2023-08-30 |  |  |  | GI STUDIES |  |  |  | 644488 |  | 0 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and the re-route of the Glenham line to the new 230 kV line bay.
0 |  | 81670 | 122791 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Viola 345/138 kV Transformer CKT 2 | GEN-2016-119 Tap - Arcadia 345kV (DISIS-2016-002-3) | Generation Interconnection | 2025-12-31 |  |  |  | GI STUDIES |  |  |  | 68725000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new terminal at new substation on Sooner to Spring Creek line being built for Gen-2016-119. Expand Arcadia Substation and re-route four transmission lines to allow for room for new transmission line to be brought in. Build approximately 47 miles of new 345kV line from new substation to Arcadia.
0 |  | 81670 | 122792 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Viola 345/138 kV Transformer CKT 2 | Viola 345/138 kV Transformer CKT 2 (DISIS-2016-002-2) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 9204586 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install a new 345 kV terminal on a new rung consisting of two (2) breakers, four (4) switches, and two (2) control panels. Install a new 138 kV terminal on an existing rung consisting of one (1) breaker, three (3) switches, three (3) PTs, and one (1) 400/440 MVA 345-138 kV transformer with LTCs. Network Upgrade shared among fourteen requests: GEN-2016-100, GEN-2016-101, GEN-2016-119, GEN-2016-128, GEN-2016-133, GEN-2016-134, GEN-2016-137, GEN-2016-138, GEN-2016-139, GEN-2016-141, GEN-2016-142, GEN-2016-145, GEN-2016-146, GEN-2016-153
0 | 210643 | 81773 | 143127 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Chisholm - Gracemont 345 kV | Gracemont 345 kV | Generation Interconnection | 2022-09-01 |  | 2022-09-01 | 2022-02-25 | DISIS-2017-001 | 15000 | 2022 | 15000 | 15000 |  | 0 |  | On Schedule < 4 |  |  |  |  | At the existing Gracmont 345 kV substation, update relay settings to accommodate new protection settings.
0 |  | 81661 | 143150 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Benton 345kV GEN-2016-162 and 163 Interconnection Costs | Benton 345kV GEN-2016-162 and 163 Interconnection (TOIF) (WERE) | Generation Interconnection | 2022-06-21 |  |  |  | GI STUDIES |  |  |  | 1198282 |  | 0 |  | In Service |  |  |  |  | Construct one (1) new 345 kV dead-end, one (1) new 345 kV disconnect switch, three (3) new voltage transformers, three (3) new current transformers, and one (1) new line panel.
0 | 200277 | 30678 | 50889 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority | 2025-12-31 |  | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 11338457.3874 | 9797157 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640381 | Thedford | Install new 345/115 kV 400 MVA transformer at Thedford substation. Install any necessary 115 kV terminal equipment. | 345/115
0 | 200277 | 30678 | 51002 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority | 2025-12-31 |  | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1134089.4193 | 913714 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Install any necessary 345 kV terminal equipment at Thedford associated with new 345/115 kV transformer. | 345
0 | 200397 | 242 | 10308 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Elmore - Paoli 69 kV Rebuild | Elmore - Paoli 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-03-31 |  | 2009-06-01 | 2016-05-17 | 2016 ITPNT | 3240000 | 2016 | 3757406.6808 | 4339358 |  | 4171494.22 | FORMULA RATE UPDATE | Delay - Mitigation | 520898 | ELMORE | 521022 | PAOLI | Rebuild 10.8-mile 69 kV line from Elmore to Paoli. | 69 |  | 10.8
0 | 200397 | 844 | 11113 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Regional Reliability | 2020-12-31 |  | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 4725000 | 2016 | 5215515.9052 | 4725000 |  |  | FORMULA RATE UPDATE | Delay - Mitigation | 521005 | MUSTANG | 521058 | SUNSHINE CANYON | Rebuild 10-mile 69 kV line from Sara Road to Sunshine Canyon. | 69 |  | 10 |  |  |  | Y
0 | 200220 | 30375 | 50442 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 204236579 | 2020 | 214576055.8119 | 204236579 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640183 | Gerald Gentleman Station | Build new 110-mile 345 kV line from Gerald Gentleman Station substation to new Cherry County substation. This upgrade is contingent upon approval from Western Area Power Administration ("WAPA") to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 100.7
0 | 200220 | 30375 | 50444 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 13692681 | 2020 | 14385872.9756 | 13692681 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Build new Cherry County 345 kV substation and install necessary terminal equipment. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
0 | 200220 | 30375 | 50445 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability | 2025-12-31 |  | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 232903698 | 2020 | 244694447.7113 | 232903698 |  | 0 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640503 | Holt County 345 kV | Build new 117-mile 345 kV line from new Cherry County substation to new Holt County substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 124.3
0 | 210618 | 30375 | 50446 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability | 2025-12-31 |  | 2018-01-01 | 2021-11-04 | 2012 ITP10 | 577000 | 2021 | 591425 | 577000 |  | 0 |  | Delay - Mitigation | 640503 | Holt County 345 kV |  |  | Add line bay terminal equipment as necessary to connect, commission and operate the 345 kV line from Thedford to Holt County Substation. | 345
0 | 200200 | 30491 | 50600 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Device - Hazelton 69 kV | Hazelton 69 kV Capacitor | Regional Reliability | 2017-03-01 |  | 2013-01-01 | 2013-03-01 | DPA-2012-MAR-143-147 | 237000 | 2013 | 261603.6549 | 735000 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520937 | HAZELTON |  |  | Install two 4.8 Mvar capacitors at Hazelton 69 kV for total of 9.6 Mvar. | 69 |  |  |  | Y
0 | 200234 | 30503 | 50628 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Device - Hazelton 69 kV #2 | Hazelton Capacitor 69 kV #2 | Regional Reliability | 2017-03-01 |  | 2017-06-01 | 2013-10-28 | DPA-2012-MAR-151-154-161-JUL-218-SEP-243 | 185004 | 2013 | 204209.7999 | 0 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520937 | HAZELTON |  |  | Install new 69 kV 4.8-Mvar capacitor at Hazelton substation. | 69 |  |  |  | Y
0 | 200245 | 30563 | 50702 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Device - Sandy Corner 138 kV | Sandy Corner 138 kV Cap Bank | Regional Reliability | 2017-06-01 |  | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 504000 | 2014 | 542752.8725 | 504000 |  |  | FORMULA RATE UPDATE | Re-evaluation | 520204 | Sandy Corner 138 kV |  |  | Add 20 Mvar of capacitance at Sandy Corner 138 kV. | 138 |  |  |  |  | Y
0 | 200397 | 31002 | 51445 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (WFEC) | Regional Reliability | 2021-05-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6000000 | 2016 | 6788449.26 | 7710000 |  |  |  | Delay - Mitigation | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 8.5-mile 138 kV line from Lincoln to Meeker. | 138
0 | 200397 | 31065 | 51484 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability | 2023-05-31 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 4638773.68 | 4000000 |  | 0 |  | Delay - Mitigation | 520855 | CLEO JCT |  |  | Install 3-breaker ring bus at Cleo Junction to allow load to be moved from 69 kV to 138 kV. | 138
0 | 200390 | 31025 | 51487 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | GRDA | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability |  |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2627865.2897 | 2266000 |  | 0 |  | Re-evaluation | 505550 | Sallisaw |  |  | Install ring bus at Sallisaw 161 kV substation. | 161
0 | 200397 | 31041 | 51526 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability | 2022-04-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 637831.381 | 600000 |  | 0 |  | Delay - Mitigation | 520203 |  |  |  | Tap the 138 kV line from Byron to Cherokee City to construct new Driftwood substation. Install any required 138 kV terminal upgrades required to install 138/69 kV transformer. | 138
0 | 200397 | 31041 | 51527 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability | 2022-04-01 |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3479080.26 | 3600000 |  | 0 |  | Delay - Mitigation |  |  | 520938 | HAZELTON JCT | Install new 138/69 kV transformer at new Driftwood substation. Install new 69 kV terminal for 69 kV line from Hazelton Junction. | 138/69
0 | 200419 | 31042 | 51531 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (WFEC) | Regional Reliability | 2026-12-31 |  | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 1400000 | 2017 | 1583971.494 | 5700000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. WFEC and Oklahoma Gas and Electric Company shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138 | 2
0 | 200420 | 31063 | 51567 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Sub - Carlsbad - Pecos 115 kV Terminal Upgrades | Carlsbad - Pecos 115 kV Terminal Upgrades | Regional Reliability | 2021-06-01 |  | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 767347 | 2017 | 847007.5097 | 0 |  | 0 |  | Complete | 528160 | Carlsbad Interchange 115 kV | 528178 | Pecos Interchange 115 kV | Install terminal upgrades at Carlsbad and/or Pecos to increase the rating of the 115 kV line between the substations. | 115 |  | 0.03
0 | 200455 | 41198 | 61852 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #1 | Regional Reliability | 2018-12-31 |  | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 98639 | 2017 | 101104.975 | 98639 |  | 0 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 1 at Texas County. | 115
0 | 200455 | 41198 | 61853 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #2 | Regional Reliability | 2018-12-31 |  | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 108430 | 2017 | 111140.75 | 108430 |  | 0 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 2 at Texas County. | 115
0 | 200479 | 51249 | 71954 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | KPP | Line - City of Winfield - Oak 69 kV Reconductor | City of Winfield - Rainbow 69 kV Ckt 1 | Regional Reliability | 2020-12-31 |  | 2021-06-01 | 2018-02-27 | SPP-2016-AG2-AFS-2 | 3600000 | 2018 | 3782250 | 5066520 |  | 0 |  | Complete |  |  |  |  | Reconductor 4 miles of 69 kV transmission line from City of Winfield to Rainbow. |  |  | 4
0 | 200466 | 51249 | 71955 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Line - City of Winfield - Oak 69 kV Reconductor | Oak - Rainbow 69 kV Ckt 1 | Regional Reliability | 2021-04-12 |  | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 7831427 | 2017 | 8644430.0697 | 5156586 |  | 5156585 | QUARTERLY TRACKING | Closed Out |  |  |  |  | Reconductor 5.1 miles of 69 kV transmission line from Oak to Rainbow. | 69 |  | 5.1 |  | Y | Y | Y
0 | 210536 | 41199 | 71960 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Etter - Moore - 115 kV | Etter - Moore 115 kV Rebuild | Regional Reliability | 2021-10-21 |  | 2018-06-01 | 2019-10-29 | 2017 ITPNT | 9037903 | 2017 | 9976153.83 | 1338161 |  | 0 |  | Delay - Mitigation | 523308 | Moore County Interchange East Bus 115 kV | 523256 | Etter Rural Sub 115 kV | Rebuild 10.83-mile 115 kV line from Etter to Moore. | 115 | 10.25
0 | 200477 | 51254 | 71963 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 14010573.3857 | 20297796 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
0 | 200477 | 51254 | 71964 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | 0 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
0 | 200477 | 51254 | 71965 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | 0 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
0 | 200477 | 51254 | 71966 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 12441332.2716 | 15279402 |  | 0 |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
0 | 200477 | 51254 | 71967 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1405712.3383 | 1605462 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
0 | 200477 | 51254 | 71968 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 4087712.7459 | 5656017 |  | 0 |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
0 | 200482 | 51280 | 72011 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Device - Dover SW 69 kV Cap Bank | Dover SW 69 kV Cap Bank | Regional Reliability | 2022-07-01 |  | 2019-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 500000 | 2018 | 551906.445 | 813590 |  | 0 |  | Delay - Mitigation | 520881 | DOVER SW |  |  | Add new 14.4 MVAR capacitor bank at Dover SW 69 kV. | 69
0 | 200482 | 51281 | 72012 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Device - Cherokee SW 69 kV Cap Bank | Cherokee SW 69 kV Cap Bank | Regional Reliability | 2023-08-01 |  | 2018-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 1000000 | 2018 | 1103812.89 | 1000000 |  | 0 |  | Delay - Mitigation | 520851 | CHEROKEE SW |  |  | Add new 28.8 MVAR capacitor bank at Cherokee SW 69 kV. | 69
0 | 210483 | 51282 | 72013 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Park Community 138 kV Substation | Regional Reliability | 2018-06-15 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 2000000 | 2018 | 2000000 | 2000000 |  | 0 |  | Re-evaluation |  |  |  |  | New Park Community 138 kV substation with 3-terminal flat bus. | 138
0 | 210483 | 51282 | 72014 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Omega - Park Community 138 kV Ckt 1 New Line | Regional Reliability | 2019-07-01 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4700000 | 2018 | 4817500 | 4700000 |  | 0 |  | Delay - Mitigation | 520964 | KINGFISHER |  |  | Construct new 9.4 mile 138 kV line from Omega - Park Community. Complete necessary terminal upgrades at Omega. | 138 | 9.4
0 | 210483 | 51282 | 72015 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Omega - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-08-31 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 7950000 | 2018 | 8775312.4755 | 12428000 |  | 0 |  | Delay - Mitigation | 520964 | KINGFISHER | 521090 | WATONGA SW | Convert 7.9 mile 69 kV line from Omega - Watonga SW to 138 kV. Complete necessary terminal upgrades at Watonga SW. | 138 |  | 7.9 | 7.9
0 | 210669 | 51282 | 72016 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Okeene - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2021-08-01 |  | 2019-06-01 | 2022-04-28 | DPA-2017-August-767-774-776 | 8600000 | 2018 | 9261259.332 | 8600000 |  | 0 |  | Delay - Mitigation | 521016 | OKEENE | 521090 | WATONGA SW | Convert 17.2 mile 69 kV line from Okeene - Watonga SW to 138 kV. Complete necessary terminal upgrades at Okeene. | 138 |  | 13.5 | 13.5
0 | 210483 | 51282 | 72018 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-05-29 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 9272028.276 | 8400000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 521090 | WATONGA SW | Convert 16.8 mile 69 kV line from Calumet - Watonga SW to 138 kV. | 138 |  | 16.8 | 16.8
0 | 210483 | 51282 | 72019 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-09-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1379766.1125 | 1250000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 520865 | CONCHO | Convert 9.0 mile 69 kV line from Calumet - Concho to 138 kV. Complete necessary terminal upgrades at Concho. | 138 |  |  | 9
0 | 210483 | 51282 | 72020 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-12-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 5022348.6495 | 4550000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET | 520502 |  | Convert 9.1 mile 69 kV line from Calumet - Cana to 138 kV. Complete necessary terminal upgrades at Cana. | 138 |  | 9.1 | 9.1
0 | 210483 | 51282 | 72021 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability | 2022-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4000000 |  | 0 |  | Delay - Mitigation | 520839 | CALUMET |  |  | New Calumet 138 kV substation with 4-terminal ring bus. | 138
0 | 210483 | 51282 | 72022 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 6236542.8285 | 5650000 |  | 0 |  | Delay - Mitigation | 520502 |  | 520899 | EL RENO | Convert 3.3 mile 69 kV line from Cana - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno Jct. | 138 |  | 3.3 | 3.3
0 | 210483 | 51282 | 72023 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-06-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 3500000 |  | 0 |  | Delay - Mitigation | 520892 | EL RENO SW | 520899 | EL RENO | Convert 6.5 mile 69 kV line from El Reno - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno. | 138
0 | 210483 | 51282 | 72024 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-05-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 11750000 |  | 0 |  | Delay - Mitigation | 520892 | EL RENO SW | 520412 |  | Convert 21.3 mile 69 kV line from El Reno - Mustang to 138 kV. Complete necessary terminal upgrades at Mustang. | 138 |  | 21.3 | 21.3
0 | 210483 | 51282 | 72025 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Mustang - Sara Road 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-12-30 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 10650000 | 2018 | 11755607.2785 | 1172000 |  | 0 |  | Delay - Mitigation | 520412 |  | 521005 | MUSTANG | Convert 2.1 mile 69 kV line from Mustang - Sara Road to 138 kV. Complete necessary terminal upgrades at Sara Road. | 138 |  | 2.1 | 2.1
0 | 210483 | 51282 | 72026 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Sara Road - Sunshine 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-12-30 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1050000 | 2018 | 1159003.5345 | 10380000 |  | 0 |  | Delay - Mitigation | 521005 | MUSTANG | 521059 | SUNSHINE CANYON | Convert 10.0 mile 69 kV line from Sara Road - Sunshine to 138 kV. | 138 |  | 10 | 10
0 | 210483 | 51282 | 72027 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-01-01 |  | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 5519064.45 | 5300000 |  | 0 |  | Delay - Mitigation | 520859 | COGAR | 520899 | EL RENO | Convert 10.6 mile 69 kV line from Cogar - El Reno Jct to 138 kV. | 138 |  | 10.6 | 10.6
0 | 210483 | 51282 | 72030 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Kingfisher SW 138 kV Substation | Regional Reliability | 2023-01-31 |  | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4975000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap the East Kingfisher - Reeding 138 kV line and construct new Kingfisher SW 138 kV substation with 4-terminal ring bus. | 138
0 | 210483 | 51282 | 72031 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability | 2022-11-01 |  | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4691204.7825 | 4250000 |  | 0 |  | Delay - Mitigation | 520865 | CONCHO |  |  | Construct new 8.5 mile 138 kV line from Concho - Kingfisher SW. | 138 | 8.5
0 | 210496 | 51316 | 72095 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Carlisle - Murphy 115kV Terminal Upgrades | Carlisle - Murphy 115 kV Terminal Upgrades | Regional Reliability | 2022-03-11 |  | 2022-06-01 | 2018-08-17 | 2018 ITPNT | 232952 | 2018 | 257135.4204 | 232952 |  | 0 |  | Delay - Mitigation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Replace terminal equipment on the Carlisle to Murphy (circuit V40) line and address any line clearance concerns to meet or exceed the conductor rating. | 115
0 | 210489 | 51327 | 82111 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-03-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 10000000 | 2018 | 11038128.9 | 10000000 |  | 0 |  | Delay - Mitigation | 520859 | COGAR | 520509 |  | Convert 12.0 mile 69 kV line from Cogar - Cleveland Junction to 138 kV. | 138
0 | 210489 | 51327 | 82112 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-02-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6900000 | 2018 | 7616308.941 | 6900000 |  | 0 |  | Delay - Mitigation | 520509 |  |  |  | Convert 13.8 mile 69 kV line from Cleveland Jct - Amber Tap to 138 kV. | 138
0 | 210489 | 51327 | 82113 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Amber Tap - Blanchard 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-07-15 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 7600000 | 2018 | 8388977.964 | 7019000 |  | 0 |  | NTC - Commitment Window |  |  | 520828 | BLANCHARD | Convert 15.2 mile 69 kV line from Amber Tap - Blanchard to 138 kV. | 138
0 | 210489 | 51327 | 82114 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Blanchard - OU SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-11-30 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 300000 | 2018 | 331143.867 | 360000 |  | 0 |  | NTC - Commitment Window | 520828 | BLANCHARD | 521104 | OU SWITCH 4 | Convert 2.1 mile 69 kV line from Blanchard - OU SW to 138 kV. | 138
0 | 210489 | 51327 | 82115 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-02-01 |  | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6300000 | 2018 | 6954021.207 | 6300000 |  | 0 |  | Delay - Mitigation | 520509 |  | 520814 | ANADARKO | Convert 11.1 miles of double circuit 69 kV line from Cleveland Junction - Anadarko to single circuit 138 kV. | 138
0 | 210496 | 61346 | 92151 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Substation | Regional Reliability | 2022-04-16 |  | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 13626695 | 2021 | 13967362.375 | 20859497 |  | 0 |  | Delay - Mitigation |  |  |  |  | Tap Moore-Potter 230kV and tap Exell-Fain 115kV and tie into a new substation at McDowell Creek. | 230 | 0.2
0 | 210496 | 61346 | 92152 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Transformer | Regional Reliability | 2022-04-16 |  | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 6531679 | 2021 | 6694970.975 | 81052 |  | 0 |  | Delay - Mitigation |  |  |  |  | Install a 230/115 kV transformer at the McDowell Creek substation | 230/115
0 | 210507 | 61347 | 92153 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco - Road Runner 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 29927758 | 2019 | 31442850.7488 | 36646140 |  | 0 |  | In Service |  |  | 528027 | Road Runner 345 kV | Build new 21 mile 345 kV line from Bopco to Road Runner. | 345 | 21
0 | 210507 | 61347 | 92154 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco - China Draw 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 |  | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 30496976 | 2019 | 32040885.41 | 32405135 |  | 0 |  | In Service |  |  | 528223 |  | Build new 19 mile 345 kV line from Bopco to China Draw. | 345 | 19
0 | 210507 | 61347 | 102153 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 1 Transformer | Regional Reliability | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 6205015 | 2019 | 6519143.8844 | 5718715 |  | 0 |  | In Service |  |  | 528020 |  | Construct 345/115 kV transformer at Bopco substation. | 345/115
0 | 210507 | 61347 | 102154 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 2 Transformer | Regional Reliability | 2021-11-15 |  | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 6122043 | 2019 | 6431971.4269 | 5962651 |  | 0 |  | In Service |  |  | 528020 |  | Construct second 345/115 kV transformer at Bopco substation. | 345/115
0 | 210507 | 61347 | 102157 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 345 kV Substation | Regional Reliability | 2021-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 5153574 | 2019 | 5414473.6837 | 6341420 |  | 0 |  | In Service |  |  |  |  | Build 345 kV portion of new 345/115 kV Bopco substation. | 345
0 | 210507 | 61347 | 102158 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Multi - China Draw - Road Runner 345 kV | Bopco 115 kV Substation | Regional Reliability | 2020-11-15 |  | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 11741936 | 2019 | 12035484.4 | 15137218 |  | 0 |  | In Service |  |  |  |  | Build 115 kV portion of new 345/115 kV Bopco substation. This includes work to reterminate the Wood Draw - Red Bluff 115 kV line into the new substation. | 115
0 | 210548 | 71348 | 102163 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OPPD | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability | 2023-05-31 |  | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 3647471 | 2019 | 3927927.3066 | 3647471 |  | 0 |  | Delay - Mitigation | 646209 | Sub 1209 | 646231 | Sub 1231 | Reconductor 3.3 miles of S1209 - S1231 161 kV Ckt 2 | 161 |  | 3.3
0 | 210505 | 71352 | 102172 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Device - Clear Creek Tap 69 kV Cap Bank | Clear Creek Tap 69 kV Cap Bank | Regional Reliability | 2020-12-01 |  | 2019-12-01 | 2018-12-06 | DPA-2018-June-902 | 717209 | 2019 | 735139.225 | 717209 |  | 0 |  | Delay - Mitigation |  |  |  |  | New cap bank(s) totaling 18 MVAR at Clear Creek Tap 69kV substation. | 69
0 | 210540 | 81498 | 112358 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Westmoore 138 kV | Westmoore 138 kV Breakers | Regional Reliability | 2021-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 271289 | 2020 | 278071.225 | 271289 |  | 0 |  | Complete | 514887 | WESTMOORE 138 |  |  | Replace 2 breakers at Westmoore 138 kV with 40 kA breakers | 138
Base Plan | 210544 | 81571 | 112488 |  | TP2019132 | #N/A | TP2019132 | Yes | Already Added | TP2019132 | TP2019132 | AEP | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | 2022-06-01 | 2022-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9618647.3294 | 9155167 | 7840356 | 0 |  | In Service | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115 |  |  |  |  | Y |  | Y | Jake Tucker | (EAC calculated for NTC BPID's only: P19132001 & P19132009)
Base Plan | 210544 | 81561 | 112502 |  | #N/A | #N/A | #N/A | No | Do Not Add (2025) | TP2019146 | TP2019146 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | 2025-05-01 | 2025-05-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3409095.4055 | 5329277 | 5374949 | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06 |  |  |  | Y |  | Y
0 | 210541 | 81503 | 112363 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Sub - Hale Cty Interchange 115 kV | Hale County Interchange 115 kV Breakers | Regional Reliability | 2021-05-30 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 1658004 | 2019 | 1741940.4525 | 257408 |  |  |  | In Service | 525454 | Hale Co Interchange 115 kV |  |  | Replace 3 breakers at Hale County Interchange 115 kV with 40 kA breakers | 115
0 | 210538 | 81505 | 112366 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sub - Canaday 115 kV | Canaday 115 kV Breakers | Regional Reliability | 2020-02-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 2600000 | 2020 | 2600000 | 2555908 |  | 2555908 | QUARTERLY TRACKING | Complete | 640103 | Canaday |  |  | Replace 5 breakers at Canaday 115 kV with 40 kA breakers | 115 | [5 empty] | Y
0 | 210538 | 81506 | 112367 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sub - Hastings 115 kV | Hastings 115 kV Breakers | Regional Reliability | 2021-01-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 550000 | 2020 | 563750 | 434289 |  | 434289 | QUARTERLY TRACKING | Complete | 640215 | Hastings |  |  | Replace 2 breakers at Hastings 115 kV with 40 kA breakers | 115 | [5 empty] | Y
0 | 210538 | 81507 | 112368 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sub - Moore 13.8 kV Breaker | Moore 13.8 kV Breaker | Regional Reliability | 2022-07-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 510000 | 2020 | 535818.75 | 679553 |  | 0 |  | Delay - Mitigation | 640280 | Moore |  |  | Replace 1 breaker at Moore 13.8 kV with 40 kA breakers | 138
0 | 210539 | 81508 | 112369 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EM | Sub - Craig 161 kV | Craig 161 kV Breaker | Regional Reliability | 2021-06-30 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 311400 | 2019 | 327164.625 | 259864 |  | 0 |  | In Service | 542978 | CRAIG 161 KV |  |  | Replace 1 breaker at Craig 161 kV with 63 kA breakers | 161 |  |  |  | Y | Y | Y
0 | 210539 | 81509 | 112370 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EM | Sub - Leeds 161 kV | Leeds 161 kV Breakers | Regional Reliability | 2020-09-24 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 468500 | 2019 | 480212.5 | 400871 |  | 400871 | QUARTERLY TRACKING | Complete | 542997 | LEEDS 161 KV |  |  | Replace 2 breakers at Leeds 161 kV with 40 kA breakers | 161 |  |  |  | Y |  | Y
0 | 210539 | 81511 | 112372 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EM | Sub - Southtown 161 kV | Southtown 161 kV Breakers | Regional Reliability | 2021-12-31 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 898600 | 2019 | 944091.625 | 1348442 |  | 0 |  | In Service | 542993 | SOUTHTOWN 161 KV |  |  | Replace 4 breakers at Southtown 161 kV with 40 kA breakers | 161 |  |  |  | Y
0 | 210545 | 81513 | 112377 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability | 2027-08-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 870294.6744 | 838500 |  | 0 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Replace 3 breakers at Anadarko 138 kV with 63 kA breakers | 138
0 | 210545 | 81514 | 112378 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Sub - Washita 69 kV | Washita 69 kV Breaker | Regional Reliability | 2021-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 52400 | 2020 | 53710 | 52400 |  | 0 |  | Delay - Mitigation | 521088 | WASHITA |  |  | Replace 1 breaker at Washita 69 kV with 40 kA | 69
0 | 210545 | 81515 | 112379 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Sub - Mooreland 138/69 kV Breakers | Mooreland 138 kV Breakers #2 | Regional Reliability | 2022-12-29 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 822500 | 2020 | 864139.0625 | 4100000 |  | 0 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Replace 12 breakers at Mooreland 138 kV with 40 kA breakers
0 | 210545 | 81515 | 112380 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability | 2022-06-01 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 128300 | 2020 | 134795.1875 | 204000 |  | 0 |  | Delay - Mitigation | 520995 | MOORELAND |  |  | Replace 2 breakers at Mooreland 69 kV with 40 kA breakers
0 | 210542 | 81516 | 112381 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - South Seneca 115kV Ckt 1 | Regional Reliability | 2022-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 3067168.2 | 2020 | 3222443.5901 | 3393918 |  | 0 |  | Delay - Mitigation | 533322 | BAILEYVILLE N.M. STATION 115 KV (NEMAHA MARSHALL R | 533337 | SOUTH SENECA 115 KV | Rebuild 4 miles of 115 kV line from Baileyville to South Seneca and upgrade any necessary terminal equipment at Baileyville and/or South Seneca to increase the summer emergency rating to 239 MVA | 115 | 4 |  |  | Y | Y
0 | 210605 | 81516 | 112383 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Multi-Marshall County - Baileyville - South Seneca 115 kV | Regional Reliability | 2022-06-01 |  | 2021-04-01 | 2021-03-02 | 2019 ITP | 9204123 | 2020 | 9670081.7269 | 10675598 |  | 0 |  | Delay - Mitigation | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Tear down 7.99 miles of 115 kV line from Baileyville to Smittyville, 2.17 miles of 115 kV line from Marshall County to Smittyville, and the Smittyville substation, rebuild 10.16 miles of 115 kV line from Baileyville to Marshall County and upgrade any necessary terminal equipment at Marshall County and/or Baileyville to increase the summer emergency rating to 239 MVA | 115 | 2.2 |  |  | Y | Y
|  | 81657 | 122665 |  | #N/A | #N/A | #N/A | No | Do Not Add | 0 |  | AEP | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (TOIF) (AEP) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 1388819 |  | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. | 345 | 0.18 | [5 empty] | Y |  | States Edge
|  | 81657 | 122666 |  | #N/A | #N/A | #N/A | No | Do Not Add | 0 |  | AEP | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (Non-Shared NU) (AEP) | Generation Interconnection |  |  |  |  | GI STUDIES |  |  |  | 10361130 |  | 0 |  | On Schedule < 4 |  |  |  |  | Expand the 345 kV breaker and a half scheme, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 345 | [6 empty] | Y |  | States Edge
0 | 210545 | 81525 | 112395 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Device- Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability | 2025-11-28 |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 400000 | 2020 | 420250 | 400000 |  | 0 |  | Delay - Mitigation | 520929 | GYPSUM |  |  | Install a new 12 MVAR capacitor bank at Gypsum 69 kV substation. | 69/69
0 | 210642 | 81529 | 112399 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | SPS | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230 kV Ckt 1 Terminal Upgrades | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 231742 | 2022 | 231742 | 231742 |  | 0 |  | On Schedule < 4 | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230
0 | 210642 | 81529 | 112401 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | SPS | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230kV Ckt 2 Terminal Upgrades | Regional Reliability | 2022-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  | 2022 | 0 |  |  | 0 |  | Delay - Mitigation | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230
0 | 210540 | 81532 | 112402 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Sub - Cleo Corner - Cleo Junction 69kV | Cleo Corner - Cleo Junction 69kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2019-11-18 | 2019 ITP | 16602 | 2020 | 17442.4762 | 16602 |  | 0 |  | Delay - Mitigation | 514777 | CLEO CORNER 69 | 520855 | CLEO JCT | Upgrade any necessary terminal equipment at Cleo Corner and/or Cleo Junction to increase the summer emergency rating to 48 MVA | 69
0 | 210538 | 81533 | 112403 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability | 2024-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 608900 | 2020 | 639725.5625 | 608900 |  | 0 |  | Delay - Mitigation | 640171 | Firth |  |  | Install new 15 MVAR capacitor bank at Firth 115 kV substation. | 115
0 | 210538 | 81533 | 112404 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability | 2024-06-01 |  | 2021-04-01 | 2019-11-18 | 2019 ITP | 3600000 | 2020 | 3782250 | 2991100 |  | 0 |  | Delay - Mitigation | 640171 | Firth |  |  | Expand the existing Firth 115 kV substation to accommodate a new 15 MVAR capacitor bank. | 115
Direct Assignment | 210558 | 81673 | 122713 |  | #N/A | #N/A | #N/A | No | Do Not Add (Direct Assigned) | TP2020077 | TP2020077 | AEP | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | 2022-06-01 | 2022-06-15 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 | 3160967 | 2020 | 3320990.9544 | 3160967 | 3413931 | 0 |  | Delay - Mitigation | 510423 | LOCUST GROVE | 512634 | KERR 115 | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49 |  |  | Y |  |  | Larry Oden
0 | 210515 | 81581 | 112510 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Multi-Hobbs Interchange-Millen 115kV | Hobbs Interchange to Millen Rebuild 115 kV Ckt1 | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3165684 | 2019 | 3409095.4055 | 0 |  | 0 |  | Delay - Mitigation | 527891 | Hobbs Interchange 115 kV | 528435 | Millen Sub 115 kV | Rebuild 10.5 miles of Hobbs Interchange to Millen 115kV Line |  | 3.5
0 | 210515 | 81581 | 122510 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Multi-Hobbs Interchange-Millen 115kV | Johnson Draw 115 kV Capacitor Bank | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3749224 | 2019 | 4037504.1579 | 0 |  | 0 |  | Delay - Mitigation | 527362 | Johnson Draw 115 kV |  |  | New 28.8 MVAR capacitor bank addition at Johnson Draw 115kV | 115
0 | 210560 | 81614 | 122570 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | BEPC | Multi - Neset - New Town 230 kV | Neset - Northshore 230 kV Ckt 1 | Regional Reliability | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 33155575 | 2020 | 34834075.9844 | 33159000 |  | 0 |  | Delay - Mitigation | 659138 | Neset 230 kV Bus |  |  | Build new 28 mile 230kV line from Neset to Northshore. | 230 | 30
0 | 210559 | 81614 | 122571 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | MWE | Multi - Neset - New Town 230 kV | Northshore - New Town 115 kV Ckt 1 | Regional Reliability | 2021-09-05 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 19235485 | 2020 | 19716372.125 | 19235485 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 20 mile 115 kV line from Northshore to New Town. | 115 | 20.5
0 | 210560 | 81614 | 122572 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | BEPC | Multi - Neset - New Town 230 kV | North Shore 230/115 kV Transformer | Regional Reliability | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 3176320 | 2020 | 3337121.2 | 3848370 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new 230/115 kV Transformer at North Shore substation | 230/115
0 | 210560 | 81614 | 122575 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | BEPC | Multi - Neset - New Town 230 kV | Northshore 230 kV Substation | Regional Reliability | 2022-12-31 |  | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 20938350 | 2020 | 21998353.9688 | 14282000 |  | 0 |  | Delay - Mitigation |  |  |  |  | Build new Northshore 230/115 kV Substation to replace existing switch
0 | 210658 | 81627 | 122597 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | SUB - Marietta - Rocky Point 69 kV | Marietta 69 kV | Regional Reliability | 2021-12-01 |  | 2021-12-01 | 2022-03-08 | 2019 ITP | 100000 | 2020 | 102500 | 100000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Install any necessary protection equipment at Marietta to change the operational status from normally open to normally closed | 69
0 | 210557 | 81652 | 122657 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | CBPC | Sub-Flint Hills 69 kV Switching Station | Sub - Donald Feldman 69kV Switching Station | Regional Reliability | 2020-06-01 |  | 2020-06-01 | 2020-04-08 | DPA-2019-March-1011 | 1100000 | 2020 | 1100000 | 1227000 |  | 0 |  | Complete |  |  |  |  | Construct a new switching station at Flint Hills connecting the MEC Clarksville line and Corn Belt's Parkersburg and Plainfield line |  |  |  |  | Y |  | Y
0 | 210552 | 81654 | 122661 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | XFR-Riverdale 230/115 kV Transformer ckt 2 | Riverdale 230/115 kV Transformer ckt 2 | Regional Reliability | 2020-06-01 |  | 2021-06-01 | 2020-09-24 | DPA-2019-June-1058 | 3650000 | 2020 | 3650000 | 3704140 |  | 3704140 | QUARTERLY TRACKING | Complete | 640330 | Riverdale | 640331 | Riverdale | Install a new 230/115 kV 187 MVA transformer located at Riverdale substation | 230/115 | [5 empty] | Y
0 | 210574 | 81682 | 122725 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Allen - Quaker 115kV | Allen - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 2961075 | 2021 | 3035101.875 | 2961075 |  | 0 |  | Delay - Mitigation | 526213 | Allen Sub 115 kV | 526243 | South Plains REC-Quaker 115 kV | Rebuild 3.6 miles 115 kV line from Allen to Quaker and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA |  |  | 3.5
0 | 210574 | 81684 | 122727 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Allen - Lubbock South 115kV | Allen - Lubbock South 115 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 7350796 | 2021 | 7534565.9 | 7350796 |  | 0 |  | Delay - Mitigation | 526213 | Allen Sub 115 kV | 526268 | Lubbock South Interchange 115 kV | Rebuild 5.98 miles of 115 kV line from Allen to Lubbock and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA. |  |  | 6
Base Plan | 210575 | 81687 | 122730 |  | #N/A | TP2020102 | #N/A | Yes | Do Not Add (2024) | TP2020102 | TP2020102 | AEP | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | 2024-06-03 | 2024-06-03 | 2024-06-01 | 2020-11-17 | 2020 ITP | 23622577 | 2021 | 24213141.425 | 20597910 | 20736958 | 0 |  | Delay - Mitigation Window | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA | 138 | 11.2 |  |  |  | Y |  |  | Jeff Koch
0 | 210581 | 81768 | 122745 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | BEPC | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 1 (KV1A) | Regional Reliability | 2024-06-30 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 3389739 | 2021 | 3474482.475 | 3910285 |  | 0 |  | Delay - Mitigation |  |  |  |  | Replace the 230/115 kV transformer Ckt 1 at Watford City to achieve a summer emergency rating of 208 MVA | 230/115
0 | 210581 | 81768 | 122746 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | BEPC | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 2 (KV2A | Regional Reliability | 2024-06-30 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 173041 | 2021 | 177367.025 | 173041 |  | 0 |  | Delay - Mitigation |  |  |  |  | Upgrade any necessary terminal equipment at Watford City for the 230/115 kV transformer Ckt 2 to achieve a summer emergency rating of 208 MVA | 230/115
0 | 210582 | 81719 | 122803 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SEPC | Device - Russell 115 kV | Russell 115 kV Capacitor Bank | Regional Reliability | 2024-01-01 |  | 2022-06-01 | 2020-11-23 | 2020 ITP | 5306633 | 2021 | 5439298.825 | 5306633 |  | 0 |  | Delay - Mitigation | 539701 | Russell 115 KV |  |  | Add new 24 MVAR capacitor bank at Russell 115 kV
0 | 210583 | 81720 | 122804 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EM | Sub - Northeast 161 kV | Northeast 161 kV Breakers | Regional Reliability | 2025-12-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 887479 | 2021 | 909665.975 | 887481 |  | 0 |  | Delay - Mitigation |  |  |  |  | Replace three breakers at the Northeast 161 kV station with 63 kA breakers
0 | 210583 | 81722 | 122806 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EM | Sub - Leeds 161 kV #2 | Leeds 161 kV Breaker | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 300000 | 2021 | 307500 | 300000 |  | 0 |  | Delay - Mitigation | 542997 | LEEDS 161 KV |  |  | Replace 1 breaker at the Leeds 161 kV station with a 40 kA breaker |  |  |  |  | Y
0 | 210583 | 81723 | 122807 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EM | Sub - Shawnee Mission 161 kV | Shawnee Mission 161 kV Breaker | Regional Reliability | 2023-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 335416 | 2020 | 352396.435 | 355416 |  | 0 |  | Delay - Mitigation | 543031 | SHAWNEE MISSION 161 KV |  |  | Replace 1 breaker at the Shawnee Mission 161 kV station with a 40 kA breaker |  |  |  |  | Y
0 | 210583 | 81724 | 122808 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EM | Sub - Southtown 161 kV #2 | Southtown 161 kV Breaker | Regional Reliability | 2021-12-22 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 244265 | 2021 | 244265 | 389812 |  | 0 |  | In Service | 542993 | SOUTHTOWN 161 KV |  |  | Replace 1 breaker at the Southtown 161 kV station with a 40 kA breaker |  |  |  |  | Y
0 | 210580 | 81728 | 122812 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Line - Circleville - Goff 115 kV | Circleville - Goff 115 kV Ckt 1 Rebuild | Regional Reliability | 2021-07-02 |  | 2025-06-01 | 2020-11-17 | 2020 ITP | 13028143 | 2021 | 13028143 | 14232227 |  | 14232227 | QUARTERLY TRACKING | Complete | 533152 | CIRCLEVILLE 115 KV | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | Rebuild 14.56 miles of 115 kV line from Circleville to Goff and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  |  | 14.5 |  | Y | Y | Y
0 | 210580 | 81730 | 122814 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Line - Kelly - Goff 115 kV | Goff - Kelly 115 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-18 |  | 2025-06-01 | 2020-11-17 | 2020 ITP | 5602343 | 2021 | 5602343 | 5483173 |  | 5483173 | QUARTERLY TRACKING | Complete | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | 533217 | KELLY 115 KV | Rebuild 10.0 miles of 115 kV line from Goff to Kelly and upgrade any necessary terminal equipment to achieve a summer emergency rating 239 MVA | 115 |  |  |  | Y | Y | Y
0 | 210589 | 81733 | 122818 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Cushing - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 4281150 | 2021 | 4388178.75 | 4281150 |  |  |  | On Schedule < 4 | 515032 | CUSHING 69 | 515022 | PIPELINE 69 | Rebuild 4.71 miles of 69 kV line from Cushing to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 4.71
0 | 210589 | 81733 | 122819 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OGE | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Pipeline - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 1081649 | 2021 | 1108690.225 | 1081649 |  |  |  | On Schedule < 4 | 515022 | PIPELINE 69 |  |  | Rebuild 1.19 miles of 69 kV line from Pipeline to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 1.19
0 | 210586 | 81751 | 122864 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Sub - Anadarko 138 kV #2 | Anadarko 138 kV Breakers #2 | Regional Reliability |  |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 850000 | 2021 | 871250 | 850000 |  | 0 |  | On Schedule < 4 | 520814 | ANADARKO |  |  | Replace 4 breakers at the Anadarko 138 kV station with a 63 kA breakers
0 | 210574 | 81755 | 122869 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Sub - Bushland - Deaf Smith 230 kV | Bushland - Deaf Smith 230 kV Terminal Upgrades | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 998956 | 2021 | 1023929.9 | 571184 |  | 0 |  | Delay - Mitigation | 524267 | Bushland Interchange 230 kV (POI: Wildorado Wind, 160MW) | 524623 | Deaf Smith County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Bushland and/or Deaf Smith 230 kV to achieve a summer emergency rating of 546 MVA.
0 | 210574 | 81756 | 122870 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Sub - Newhart - Potter 230 kV | Newhart - Potter 230 kV Terminal Upgrades | Regional Reliability | 2022-04-01 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 735013 | 2021 | 753388.325 | 0 |  | 0 |  | Delay - Mitigation | 525461 | Newhart Interchange 230 kV | 523959 | Potter County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Newhart and/or Potter 230 kV to achieve a summer emergency rating of 540 MVA. |  | 67
0 | 210574 | 81757 | 122871 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Sub - Deaf Smith #6 - Friona 115 kV | Deaf Smith #6 - Friona 115 kV Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 11609949 | 2021 | 11900197.725 | 11609949 |  | 0 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524655 | Friona Sub 115 kV | Rebuild 18.9 miles of 115 kV line from Deaf Smith #6 to Friona and upgrade any necessary terminal equipment at Deaf Smith #6 and/or Friona to achieve a summer emergency rating of 120 MVA |  | 17.4
0 | 210574 | 81758 | 122872 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Carlisle - Murphy 115 kV #2 | Carlisle - Murphy 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 4160581 | 2021 | 4264595.525 | 4160581 |  | 0 |  | Delay - Mitigation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Rebuild 4.0 miles of 115 kV line from Carlisle to Murphy and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 4
0 | 210574 | 81760 | 122876 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Deaf Smith #6 - Hereford 115 kV | Deaf Smith #6 - Hereford 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 6956586 | 2021 | 7130500.65 | 6956586 |  | 0 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524606 | Hereford Interchange 115 kV | Rebuild 2.33 miles of 115 kV line from Deaf Smith #6 to Hereford and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  | 7.3
0 | 210574 | 81763 | 122883 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Sub - Lubbock South - Wolfforth 230 kV | Lubbock South - Wolfforth 230 kV Ckt 1 Terminal Upgrades #2 | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 944000 | 2021 | 967600 | 835432 |  | 0 |  | Delay - Mitigation | 526269 | Lubbock South Interchange 230 kV | 526525 | Wolfforth Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Lubbock South and/or Wolfforth to achieve a summer emergency rating of 550 MVA |  | 14.6
0 | 210584 | 81497 | 132893 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NWE | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Junction 115 kV Terminal Upgrades | Regional Reliability | 2021-12-31 |  | 2022-12-01 | 2020-11-17 | 2020 ITP | 1182000 | 2021 | 1182000 | 1182000 |  | 989393 | QUARTERLY TRACKING | Complete |  |  |  |  | Install any necessary terminal equipment to support a new 115 kV line from Richmond to achieve a summer emergency rating of 139 MVA | [6 empty] | Y
0 | 210579 | 91876 | 143157 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WAPA | Device - Bismarck 12.47 kV | Bismarck 12.47 kV Reactors | Regional Reliability | 2023-10-01 |  | 2022-04-01 | 2020-11-23 | 2020 ITP | 2143217 | 2021 | 2196797.425 | 2143217 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install 2x35 MVAR reactors at Bismarck to control voltage on the 230 kV transmission system
0 | 210585 | 91878 | 143159 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | MRES | Device - Moorehead 230 kV | Moorehead 230 kV Reactor | Regional Reliability | 2024-06-01 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 4358300 | 2022 | 4358300 | 4358300 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 2x40 MVAR reactors at Moorehead to control voltage on the 115 kV and 230 kV transmission systems
0 | 210591 | 91881 | 143162 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | CPEC | Device - Agate 115 kV | Agate 115 kV Reactor | Regional Reliability | 2022-07-01 |  | 2022-04-01 | 2020-11-23 | 2020 ITP | 1310400 | 2021 | 1343160 | 1400000 |  |  |  | Delay - Mitigation |  |  |  |  | Install 2x6 MVAR reactors at Agate to control voltage on the 115 kV transmission system
0 | 210574 | 91884 | 143167 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Cargill - Friona 115 kV | Cargill - Friona 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 1675731 | 2021 | 1717624.275 | 1675731 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 1.15 miles of existing 115 kV line from Cargill to Friona and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 1.15
0 | 210574 | 91888 | 143168 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Cargill - Deaf Smith #24 115 kV | Cargill - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 5378526 | 2021 | 5512989.15 | 5378526 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 7.74 miles of 115 kV line from Cargill to Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 7.75
0 | 210574 | 91889 | 143169 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Parmer - Deaf Smith #24 115 kV | Parmer - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 999423 | 2021 | 1024408.575 | 999423 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 1.16 miles of 115 kV line from Parmer - Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 1.16
0 | 210574 | 91890 | 143170 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Parmer - Deaf Smith #20 115 kV | Parmer - Deaf Smith #20 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 |  | 2022-04-01 | 2020-11-17 | 2020 ITP | 5293163 | 2021 | 5425492.075 | 5293163 |  |  |  | Delay - Mitigation |  |  |  |  | Rebuild 7.6 miles of 115 kV line from Parmer - Deaf Smith #20 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 7.6
0 | 210600 | 91885 | 143177 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S1260 - S1362 161 kV Ckt 1 Rebuild | Regional Reliability | 2022-08-01 |  | 2023-04-01 | 2021-02-16 | DPA-2018-October-949 | 858928 | 2021 | 880401.2 | 858928 |  | 0 |  | On Schedule < 4 | 646260 |  |  |  | Rebuild 0.9 miles of 161 kV line from S1260 to S1362 line to achieve 243 MVA summer emergency rating. | 161
0 | 210600 | 91885 | 143178 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3456 to S3458 345 kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-08-01 |  | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 100000 | 2021 | 102500 | 100000 |  | 0 |  | On Schedule < 4 | 645456 | Sub 3456 | 645458 | Sub 3458 (Neb Cty) | The upgrade disconnect switch and associated jumpers on S3456 to S3458 345 kV line to achieve at least a 981 MVA summer emergency rating. | 345
0 | 210600 | 91885 | 143179 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | OPPD | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3455 to S3740 345 kV CKT1 Rebuild | Regional Reliability | 2024-04-01 |  | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 600000 | 2021 | 615000 | 600000 |  | 0 |  | On Schedule < 4 | 645455 | Sub 3455 | 645740 | Sub 3740 | Replace structures to increase clearance on S3455 to S3740 345 kV CKT1 (approximately 6-7 structures) to achieve a 1112 MVA summer emergency rating. | 345
0 | 210584 | 81497 | 143181 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NWE | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (NWE) | Regional Reliability |  |  | 2022-12-01 | 2020-11-17 | 2020 ITP | 3277500 | 2021 | 3359437.5 | 3277500 |  |  |  | On Schedule < 4 |  |  |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA |  | 14.4
0 | 210617 | 91939 | 143253 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli - Lexington kV 138 kV | Regional Reliability | 2025-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 7865000 | 2021 | 8061625 | 7865000 |  | 0 |  | Delay - Mitigation Window | 521022 | PAOLI | 520973 | LEXINGTON | Rebuild 14.3 miles of 69 kV line from Paoli to Lexington to 138 kV | 69 |  |  |  |  | Y
0 | 210617 | 91939 | 143254 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Lexington - Lil Axe 138 kV | Regional Reliability | 2024-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 5340500 | 2021 | 5474012.5 | 5340500 |  | 0 |  | Delay - Mitigation Window | 520973 | LEXINGTON | 520976 | LITTLE AXE | Rebuild 9.7 miles of 69 kV line from Lexington to Lil Axe to 138 kV | 69 |  |  |  |  | Y
0 | 210617 | 91939 | 143255 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli 138 kV Terminal Upgrades | Regional Reliability | 2025-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 450000 | 2021 | 461250 | 450000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Convert 69 kV terminal equipment at Paoli Switch to 138 kV | [5 empty] | Y
0 | 210617 | 91939 | 143256 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WFEC | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Canadian Switch138 kV Terminal Upgrades | Regional Reliability | 2024-12-31 |  | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 500000 | 2021 | 512500 | 500000 |  | 0 |  | Delay - Mitigation Window |  |  |  |  | Convert 69 kV terminal equipment at Canadian Switch to 138 kV | [5 empty] | Y
0 | 210655 | 92112 | 143587 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EM | Sub - Platte City 161 kV | Platte City 161 kV Terminal Upgrade | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 55271.78 | 2022 | 55271.78 | 55271.78 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the switch at Platte City 161 kV for the Platte City - Weston 161 kV line. | 161
0 | 210675 | 92113 | 143588 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge - Round Up 345 kV | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 78293357 | 2022 | 78293357 | 78293357 |  |  |  | NTC - Commitment Window |  |  |  |  | Build 33.2 mile new 345 kV line from Kummer Ridge to Round Up | 345
0 | 210675 | 92113 | 143589 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge 345 kV Terminal Upgrades | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 342000 | 2022 | 342000 | 342000 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Kummer Ridge substation 345 kV to support a new 345 kV line from Round Up | 345
0 | 210675 | 92113 | 143590 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Line - Kummer Ridge - Round Up 345 kV | Round Up 345 kV Terminal Upgrades | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 342000 | 2022 | 342000 | 342000 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Round Up substation 345 kV to support a new 345 kV line from Kummer Ridge | 345
Base Plan | 210627 | 81717 | 122796 |  | TP2020266 | #N/A | TP2020266 | Yes | Do Not Add (2024) | TP2020266 | TP2020266 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | 2023-04-30 | 2024-05-24 | 2022-01-01 | 2021-11-05 | 2020 ITP |  |  |  |  | 5067275 |  |  | Delay - Mitigation | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support a new line 345 kV line from Border - Woodward 345 kV substation with a summer emergency rating of 1792 MVA | 345 | 0.2 |  |  |  | Y |  |  | James Horn | MOD number added 16810 / BPID-P20266001, P20266003, P20266004, P20266005
0 | 210637 | 92140 | 143663 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EKC | Sub - Jarbalo Junction 115 kV Breaker Upgrade | Jarbalo Junction 115 kV Breaker | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 236539 | 2022 | 236539 | 236539 |  |  |  | On Schedule < 4 |  |  |  |  | Replace breaker 115-483 at the Jarbalo Junction substation | 115
0 | 210647 | 92144 | 143664 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EM | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 255075 | 255075 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R3-7 breaker at the Shawnee Mission 161 kV substation | 161
0 | 210647 | 92144 | 143665 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EM | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV Breaker | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 255075 | 255075 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R7-12 breaker at the Shawnee Mission 161 kV substation | 161
0 | 210647 | 92141 | 143666 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EM | Sub - Craig 161 kV Breaker | Craig 161 kV Breaker #2 | Regional Reliability |  |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 319002 | 2022 | 319002 | 319002 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade the R5-33 breaker at the Craig 161 kV substation | 161
0 | 210640 | 92142 | 143667 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MRES | Sub - Moorhead 230 kV Substation Reconfiguration | Moorhead 230 kV Substation Reconfiguration | Regional Reliability | 2024-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 9989000 | 2022 | 9989000 | 9989000 |  |  |  | Delay - Mitigation |  |  |  |  | Reconfigure the Moorhead 230 kV substation with a ring bus, expandable to breaker-and-a-half. | 230
0 | 210654 | 92143 | 143668 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th - Stateline 161 kV Rebuild | Regional Reliability | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 10688750 | 2022 | 10688750 | 10688750 |  |  |  | On Schedule < 4 |  |  |  |  | Rebuild approximately 5.5 miles of the existing 161 kV line from Joplin West 7th to Stateline. | 161
0 | 210654 | 92143 | 143669 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th 161 kV Terminal Upgrades | Regional Reliability | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 393232 | 2022 | 393232 | 393232 |  |  |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at Joplin West 7th 161 kV substation. | 161
0 | 210654 | 92143 | 143670 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | EDE | Multi - Joplin West 7th - Stateline 161 kV | Stateline 161 kV Terminal Upgrades | Regional Reliability | 2026-06-01 |  | 2026-06-01 | 2022-03-11 | 2021 ITP | 209518 | 2022 | 209518 | 209518 |  |  |  | On Schedule < 4 |  |  |  |  | : Upgrade any necessary terminal equipment at Stateline 161 kV substation. | 161
0 | 210619 | 92180 | 143705 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Kearney NE - Tower 115 kV Ckt 1 New Line | Regional Reliability | 2022-06-01 |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 11250834 | 2022 | 11250834 | 11250834 |  | 0 |  | NTC - Commitment Window | 640248 | Kearney Northeast | 640383 | Tower | Build a new 115 kV 10 mile line from Kearney to Tower with a minimum summer emergency rating of 160 MVA |  | 10
0 | 210675 | 92168 | 143714 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Tande 345 kV New Line | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 67411405 | 2022 | 67411405 | 67411405 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 48 mile 345 kV line from Finstad to Tande. | NULL
0 | 210656 | 92190 | 143806 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Tap (OKGE) – Marietta Switchyard (WFEC) 138 kV Ckt 1 New Line (OGE) | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 1575000 | 2022 | 1575000 | 1575000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Build new 2.1 mile 138 kV line from Marietta Tap (OKGE) – Marietta Switchyard (WFEC) | 138
0 | 210656 | 92190 | 143815 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta 2 138 kV Voltage Conversion | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 5000000 | 2022 | 5000000 | 5000000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Convert the Marietta 2 substation from 69 kV to 138 kV and install terminal equipment to support a new 138 kV line from Marietta 4 | 69
0 | 210656 | 92190 | 143816 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point - Marietta 2 138 kV Ckt 1 Rebuild | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 8806000 | 2022 | 8806000 | 8806000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Rebuild the existing 69 kV line from Rocky Point to Marietta 2 as a 138 kV line | 69
0 | 210656 | 92190 | 143817 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | OGE | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point 69 kV Replace Relays | Regional Reliability |  |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 250000 | 2022 | 250000 | 250000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Replace the existing relays at Rocky Point | 69
0 | 210641 | 92213 | 143980 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | NIPCO | Multi - Sioux City - Hinton 69 kV | Hinton 69 kV Terminal Equipment | Regional Reliability | 2023-10-31 |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 277500 |  |  |  | NTC - Commitment Window |  |  |  |  | Upgrade the terminal equipment at Hinton (K412) substation. | NULL
0 | 210663 | 92178 | 144148 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MWE | Multi - E Newtown 115 kV | E Newtown 115 kV New Statcom | Regional Reliability | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 22213115 | 2022 | 22213115 | 22213115 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install a 150 MVAR statcom and supporting equipment at E Newtown to control voltage on the 115 kV transmission system
0 | 210663 | 92211 | 144163 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | Folvag 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 613746 | 2022 | 613746 | 613746 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Folvag 115 kV sub to accommodate new 115 kV line from NE Williston 115 kV sub.
0 | 210675 | 92211 | 144171 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Substation | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 17766381 | 2022 | 17766381 | 17766381 |  |  |  | NTC - Commitment Window |  |  |  |  | Bisect the Judson to Tande 345 kV line approximately 18 miles from Judson and build a new 345 kV Substation.
0 | 210657 | 92190 | 144173 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | WFEC | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Switchyard 138 kV Ckt 1 Terminal Equipment | Regional Reliability | 2023-06-01 |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 736000 | 2022 | 736000 | 736000 |  | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at WFEC Marietta Switch to support a new 138 kV line from OG&E Marietta.
0 | 210663 | 92211 | 144177 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston - Folvag 115 kV New Line | Regional Reliability | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 3800000 | 2022 | 3800000 | 6490000 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Build a new 4.5 mile 115 kV line from NE Williston to Folvag.
0 | 210663 | 92211 | 144178 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 596597 | 2022 | 596597 | 596597 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at NE Williston 115 kV sub to accommodate new 115 kV line from Folvag 115 kV sub.
0 | 210675 | 92211 | 144198 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Transformer | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5904650 | 2022 | 5904650 | 5904650 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Transformer at the new East Fork 345/115 kV Substation.
0 | 210663 | 92211 | 144199 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MWE | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 115 kV Terminal Equipment | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 2511246 | 2022 | 2511246 | 2511246 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 115 kV terminal equipment at MWEC’s East Fork 115 kV substation to accommodate a 115 kV tie line from the East Fork 345/115 kV substation. Construct a 115 kV tie line from the East Fork 115 kV substation to the proposed BEPC East Fork 345/115 kV substation.
0 | 210663 | 92178 | 144202 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MWE | Multi - E Newtown 115 kV | E Newtown 115 kV Substation | Regional Reliability | 2031-12-01 |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 1087789 | 2022 | 1087789 | 1087789 |  | 0 |  | NTC - Commitment Window |  |  |  |  | Expand existing 115 kV E Newtown substation to accommodate the statcom interconnection. | NULL
0 | 210659 | 92237 | 144206 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Twist - Wilco 115 kV | Wilco 115 kV Substation | Regional Reliability |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 9225928 | 2022 | 9225928 | 9225928 |  |  |  | NTC - Commitment Window |  |  |  |  | Tap the RB-Exum to Hillmar Cheese Plant 115 kV line 4 miles west of the RB-Exum substation and build the new Wilco 115 kV Substation
0 | 210659 | 92237 | 144207 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Twist - Wilco 115 kV | Twist 115 kV Substation | Regional Reliability |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 8909901 | 2022 | 8909901 | 8909901 |  |  |  | NTC - Commitment Window |  |  |  |  | Tap the RB-Kemp to Moore 115 kV line 1 mile east of the RB-Kemp substation and build the new Twist 115 kV Substation
0 | 210659 | 92237 | 144208 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | SPS | Line - Twist - Wilco 115 kV | Twist - Wilco 115 kV Ckt 1 | Regional Reliability |  |  | 2022-06-01 | 2022-03-08 | DPA-2021-Feb-1279-1280 | 2678226 | 2022 | 2678226 | 2678226 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 115 kV line between the new Twist 115 kV Substation and the Wilco 115 kV Substation
0 | 210663 | 92168 | 144226 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MWE | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Vanhook 115 kV New Line | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 4702500 | 2022 | 4702500 | 4702500 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 5-mile 115 kV line from Finstad to Vanhook.
0 | 210675 | 92168 | 144227 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 115 kV Substation | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 4675697 | 2022 | 4675697 | 4675697 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 115 kV Substation with terminal equipment to support a line from Vanhook 115 kV substation.
0 | 210675 | 92168 | 144230 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345 kV New Substation | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 18822018 | 2022 | 18822018 | 18822018 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV Substation including 345 kV terminals for lines from Leland Olds 345 kV substation, Tande 345 kV substation and high side terminal equipment for Finstad 345/115 kV Ckt 1 transformer and Finstad 345/115 kV Ckt 2 transformer
0 | 210675 | 92168 | 144231 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad Switched Shunt | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 385021 | 2022 | 385021 | 385021 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a switched shunt at Finstad.
0 | 210675 | 92168 | 144233 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 1 Transformer | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5315254 | 5315254 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Ckt 1 Transformer at Finstad 345 | 345/115
0 | 210675 | 92168 | 144235 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 2 Transformer | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5315254 | 5315254 |  |  |  | NTC - Commitment Window |  |  |  |  | Install a 345/115 kV Ckt 2 transformer at Finstad 115 and upgrade any necessary 115 kV terminal equipment. | 345/115
0 | 210675 | 92168 | 144236 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds - Finstad - 345 kV New Line | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 200761539 | 2022 | 200761539 | 200761539 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a 123 mile 345 kV line from Leland Olds to Finstad.
0 | 210675 | 92168 | 144237 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds 345 kV Substation | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 9277339 | 2022 | 9277339 | 9277339 |  |  |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV Substation with terminal equipment to support a new line from Finstad 345 kV substation.
0 | 210675 | 92168 | 144238 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | BEPC | Multi - Tande - Finstad - Leland Olds 345 kV | Tande 345 kV Terminal Equipment | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 5085047 | 2022 | 5085047 | 5085047 |  |  |  | NTC - Commitment Window |  |  |  |  | Install new terminal equipment at Tande to support a new 345 kV line from Finstad. Install a series compensation device at Finstad or Tande.
0 | 210663 | 92168 | 144239 |  | #N/A | #N/A | #N/A | No | #N/A | #N/A | #N/A | MWE | Multi - Tande - Finstad - Leland Olds 345 kV | Vanhook 115 kV Terminal Equipment | Regional Reliability |  |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 3811190 | 2022 | 3811190 | 3811190 |  |  |  | NTC - Commitment Window |  |  |  |  | Install new 115 kV terminal equipment at Vanhook to support a new 115 kV line from Finstad.
0 | 210619 | 92180 | 144283 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Tower 115 kV Terminal Equipment | Regional Reliability |  |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 1288644 | 2022 | 1288644 | 374583 |  |  |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Tower 115 kV sub to support new line from Kearney 115 kV sub.
0 | 210619 | 92180 | 144284 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Line - Kearney NE - Tower 115 kV | Kearney 115 kV Terminal Equipment | Regional Reliability |  |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 2692377 | 2022 | 2692377 | 374583 |  |  |  | NTC - Commitment Window |  |  |  |  | Install 115 kV terminal equipment at Kearney 115 kV sub to support a new line from Tower 115 kV sub. | NULL
0 | 210486 | 51278 | 72006 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | WAPA | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | 2023-01-31 |  | 2024-06-01 | 2018-08-17 | SUS-002 | 90000 | 2018 | 99343.1601 | 90000 |  | 0 |  | On Schedule < 4 | 652427 | BISMARK | 655652 |  | Replace CTs at Bismarck 115 kV substation to increase rating of Bismarck - East Bismarck 115 kV line to at least 85 MVA. This is a mitigation upgrade resulting from the Sponsored Upgrade Study #SUS-002 CPEC North Bismarck Breaker. Costs will be Directly Assigned to CPEC. | 115
0 | 210522 | 81616 | 122599 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NWE | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen A-Tap Breaker 115 kV | Sponsored Upgrade | 2019-06-01 |  | 2021-12-31 | 2019-09-06 | SUS-006 | 552668 | 2019 | 552668 | 552668 |  | 555000 | QUARTERLY TRACKING | Complete |  |  |  |  | Add breaker at Aberdeen A-tap for the new Aberdeen City - Aberdeen Industrial Park 115 kV line. | 115 | [5 empty] | Y
0 | 210563 | 81656 | 122664 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Line-Pauline-Hastings 115 kV Reconductor | Pauline - Hastings 115 kV Ckt 1 & Ckt 2 Reconductor | Sponsored Upgrade | 2022-12-01 |  | 2022-12-01 | 2020-07-14 | SUS-014 | 6000000 | 2020 | 6303750 | 6000000 |  | 0 |  | On Schedule < 4 | 640313 | Pauline | 640215 | Hastings | A reconductor of the Pauline – Hastings 115 kV transmission lines to achieve 193 MVA for normal and emergency ratings. The Pauline to Hastings 115 kV transmission lines are 13 miles each. |  |  | 13
0 | 210570 | 81559 | 112456 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EDE | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EDE) | Transmission Service | 2023-01-01 |  | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 69054450 | 2022 | 69054450 | 69054450 |  | 0 |  | On Schedule < 4 | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 28.41 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 |  | 25.9
0 | 200477 | 51254 | 71963 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 14010573.3857 | 20297796 |  |  |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
0 | 200477 | 51254 | 71964 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  |  |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
0 | 200477 | 51254 | 71965 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  |  |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
0 | 200477 | 51254 | 71966 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 12441332.2716 | 15279402 |  |  |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
0 | 200477 | 51254 | 71967 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1405712.3383 | 1605462 |  |  |  | Delay - Mitigation |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
0 | 200477 | 51254 | 71968 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | NPPD | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | 2023-06-01 |  | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 4087712.7459 | 5656017 |  |  |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
0 | 210569 | 81559 | 112457 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EKC | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EKC) | Transmission Service | 2022-12-31 |  | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 4008402 | 2020 | 4211327.3513 | 7617027 |  | 0 |  | On Schedule < 4 | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 2.44 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 | 2.7
Zonal Project | 210576 | 91875 | 143156 |  | #N/A | #N/A | #N/A | No | Do Not Add (Zonal) | TP2020234 | TP2020234 | AEP | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Zonal Reliability | 2022-10-28 | 2022-10-28 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1184404 | 2021 | 1214014.1 | 1184404 | 1910669 | 0 |  | On Schedule < 4 |  |  |  |  | Install a new 23 MVAR capacitor bank at Grady 138 kV | 138 |  |  |  |  | Y |  |  | Dara Dixon
0 | 210590 | 91891 | 143183 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EMW | Sub - Greenwood 161 kV Terminal Upgrades | Greenwood 161 kV Terminal Upgrades | Transmission Service | 2022-03-15 |  | 2021-12-31 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 600168 | 2021 | 615172.2 | 600168 |  | 0 |  | In Service | 541218 | Greenwood Energy Center 161 KV | 541233 | Lees Summit East 161 KV | Replace 2 breakers, relays at Greenwood 161 kV substation | 161 |  |  |  | Y | Y
0 | 210590 | 91892 | 143184 |  | #N/A | #N/A | #N/A | No | 0 | 0 | 0 | EMW | Sub - Pleasant Hill 161 kV and Lake Winnebago 161 kV Terminal Upgrades | Pleasant Hill 161kV and Lake Winnebago 161 kV Terminal Upgrades | Transmission Service | 2021-04-23 |  | 2021-06-01 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 337005 | 2021 | 337005 | 483586 |  | 483586 | QUARTERLY TRACKING | Complete | 541225 | Pleasant Hill 161 KV | 541243 | Lake Winnebago 161 KV | Replace 2 breakers at Pleasant Hill 161 kV substation and replace 1 switch at Lake Winnebago 161 kV substation in order to increase the limit on the Pleasant Hill - Lake Winnebago 161 kV line. | 161 |  |  |  | Y | Y | Y
Base Plan | 210627 | 81717 | 143182 |  | TP2020266 | #N/A | TP2020266 | Yes | Do Not Add (2024) | TP2020266 | TP2020266 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward - Border 345 kV Ckt 1 (AEP) | Economic | 2023-04-30 | 2024-05-24 | 2022-01-01 | 2021-11-05 | 2020 ITP | 1259660 | 2021 | 1291151.5 | 5264319 | 5839252 | 0 |  | Delay - Mitigation |  |  |  |  | Build 0.84-miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm with a summer emergency rating of 1792 MVA. Oklahoma Gas and Electric Co. and American Electric Power shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC | 345 | 0.84 | [6 empty] | James Horn | P20266002 -T Line Costs minus dead ends
Base Plan | 210633 | 92114 | 143591 |  | TP2021281 | #N/A | #N/A | Yes | Do Not Add (2024) | TP2021281 | TP2021281 | AEP | Line- Catoosa - Blue Circle 69 kV | Blue Circle - Catoosa 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-05-01 | 2024-05-01 | 2023-06-01 | 2022-03-09 | 2021 ITP | 9020000 | 2022 | 9020000 | 9020000 | 9040257 |  |  | Delay - Mitigation |  |  |  |  | Rebuild 3.5 miles of 69 kV line from Catoosa to Blue Circle and upgrade any necessary terminal equipment at Catoosa and/or Blue Circle | 69 |  | 3.5
Note on Z76: s306055: EcoSys = 2,984,870

## Q4 2021 Initial Extract (hidden)
UID Lookup | UID | Cost Allocation | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Manual Super | CPP | NTC ID | PID | Project Owner | Project Name | Upgrade Name | Project Type | STEP Project Type | Project Owner Indicated In-Service Date | RTO Determined Need Date | Latest NTC Issue Date | NTC Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Final Cost Source | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/Comments | Voltages (kV) | Number of New | Number of Rebuild/ Reconductor | Number of Voltage Conversion | Letter of Commercial Operation | MODInformation | Amount to-date Cost | GIS Data | AEP comments | PM | old comments
#N/A | 51558 | Zonal | #N/A | #N/A | #REF! | Yes | Do Not Add (Zonal) | TA2011012 | TP2015169 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2019-12-18 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 13512896.75 | 2016 | 14551911.7591 | 11805970.48 | 8544022 | QUARTERLY TRACKING | Closed Out | 510912 | ARMY AMMUNITION DEPOT | 510899 | McALESTER 69KV | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester. | 69 |  |  |  | Y | Y | Y | Y | ok to close out |  | Completed and in service
#N/A | 51559 | Zonal | #N/A | #N/A | #REF! | Yes | Do Not Add (Zonal) | TA2011012 | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15146463.7 | 2016 | 17136833.3826 | 15595092.29 | 0 |  | Delay - Mitigation | 510912 | ARMY AMMUNITION DEPOT | 510885 | PITTSBURG 69KV | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg. | 69 |  |  |  |  | Y |  |  | Final proportionalized cost provided last quarterly update and shows correctly in TRAC but not in this report. Waiting for line switches replacement to put in service. |  | No PM assigned yet. Waiting for outages. Mitigation plan since 2017 No PM assigned to the last portion. Note from Frances: "After further discussion with Brent and the t-line engineer I have confirmed that the line sections from McAlester City to Army Ammo Plant Tap and Army Ammo Plant Tap to Savanna have been fully rebuilt. The section of line from Savanna to Pittsburg and Pittsburg to Atoka Pump will not be completed until the line switches are replaced as part of TA2020053.
#N/A | 51560 | Zonal | #N/A | #N/A | #REF! | Yes | Do Not Add (Zonal) | TA2011012 | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 24516011.291 | 21981547.8 | 0 |  | Delay - Mitigation | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69 |  |  |  |  | Y |  |  | Waiting for POD to put in service. No final costs. |  | No PM assigned yet. Waiting for outages. Mitigation plan since 2017 Note from Frances: "After further discussion with Brent and the t-line engineer I have confirmed that the line sections from McAlester City to Army Ammo Plant Tap and Army Ammo Plant Tap to Savanna have been fully rebuilt. There is a box bay being added at Atoka Pump Tap under TA2018017. EcoSys shows a planned ISD of 11/2020. I assume the section of line from Atoka Pump to Atoka will not be fully rebuilt until the Box Bay is installed. "
#N/A | 82137 | Not Base Plan | #N/A | #N/A | #REF! | Yes | Do Not Add (Not Base Plan) | TP2017247 | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | GI | 2020-09-30 |  |  | GI STUDIES |  |  |  | 700000 | 405916 | QUARTERLY TRACKING | Closed Out |  |  |  |  | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation. | [6 empty] | Y | Y | LOC sent to SPP and confirmed in February 21. OK to close out | Tommy Vannoy
#N/A | 82138 | Not Base Plan | #N/A | #N/A | #REF! | Yes | Do Not Add (Not Base Plan) | TP2017247 | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | GI | 2020-09-30 |  |  | GI STUDIES |  |  |  | 8700000 | 6103003 | QUARTERLY TRACKING | Closed Out |  |  |  |  | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer. | [6 empty] | Y | Y | LOC sent to SPP and confirmed in February 21. OK to close out | Tommy Vannoy
#N/A | 112307 | Direct Assigned | #N/A | #N/A | #REF! | Yes |  | 0 |  | 210611 | 81474 | AEP | Sub - Oklaunion 345 kV Capacitive Reactive Power Support | Oklaunion 345 kV Capacitive Reactive Power Support | Generation Interconnection | GI | 2023-05-15 | 2023-05-15 | 2021-05-17 | DISIS-2016-002 |  |  |  | 9453182 | 0 |  | NTC - Commitment Window |  |  |  |  | Install +200Mvar Capacitor Bank(s) at the Oklaunion 345kV substation. | [8 empty] | MOD number added 102550
#N/A | 112331 |  | #N/A | #N/A | #REF! | Yes |  | 0 |  |  | 81483 | AEP | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (TOIF) (AEPW) | Generation Interconnection | GI |  |  |  | GI STUDIES |  |  |  | 1175646 | 0 |  | On Schedule > 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating |  | 0.04 | [6 empty] | In-service dates will be provided after GIA
#N/A | 112332 |  | #N/A | #N/A | #REF! | Yes |  | 0 |  |  | 81483 | AEP | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | GI |  |  |  | GI STUDIES |  |  |  | 9959548.73 | 0 |  | On Schedule > 4 |  |  |  |  | Build a 3-breaker ring bus station on the Lieberman-North Benton 138 kV section of the Lieberman-Red Point 138 kV line to facilitate the new generation interconnection. |  | 1.32 | [6 empty] | In-service dates will be provided after GIA
#N/A | 112333 |  | #N/A | #N/A | #REF! | Yes |  | 0 |  |  | 81489 | AEP | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (TOIF) (AEPW) | Generation Interconnection | GI |  |  |  | GI STUDIES |  |  |  | 1388819 | 0 |  | On Schedule < 4 |  |  |  |  | : Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.18 | [6 empty] | In-service dates will be provided after GIA
#N/A | 112334 |  | #N/A | #N/A | #REF! | Yes |  | 0 |  |  | 81489 | AEP | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (AEPW) | Generation Interconnection | GI |  |  |  | GI STUDIES |  |  |  | 17798882 | 0 |  | On Schedule < 4 |  |  |  |  | Construct new 345 kV four (4) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators ,and all other associated work and materials. |  | 0.32 | [6 empty] | In-service dates will be provided after GIA
#N/A | 112337 |  | #N/A | #N/A | #REF! | Yes |  | 0 |  |  | 81491 | AEP | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (TOIF) (AEPW) | Generation Interconnection | GI |  |  |  | GI STUDIES |  |  |  | 918474 | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.04 | [6 empty] | In-service dates will be provided after GIA
#N/A | 112338 |  | #N/A | #N/A | #REF! | Yes |  | 0 |  |  | 81491 | AEP | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (Non-Shared NU) (AEPW) | Generation Interconnection | GI |  |  |  | GI STUDIES |  |  |  | 7400346 | 0 |  | On Schedule < 4 |  |  |  |  | Construct new 138 kV three (3) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | [8 empty] | In-service dates will be provided after GIA
#N/A | 112360 | Base Plan | #N/A | #N/A | #REF! | Yes | Do Not Add (2023) | TP2019245 | TP2019245 | 210544 | 81500 | AEP | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | ITP | 2023-05-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 16288000 | 2020 | 16695200 | 33619929 | 0 |  | Re-evaluation | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 21 breakers at Riverside Station 138 kV with 80 kA breakers | 138 | 1.56 |  |  |  | Y |  |  | no change | Anita Hartman | Received and updated TAGIT with new dollars on 9/17/20520 for the additional rehab of all the remaining breakers and other new equipment.
#N/A | 112361 | Base Plan | #N/A | #N/A | #REF! | Yes | Do Not Add (2023) | TA2019024 | TA2019024 | 210544 | 81501 | AEP | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | ITP | 2023-12-15 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4531878.625 | 4194065 | 0 |  | Delay - Mitigation | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138 |  |  |  |  | Y |  |  | no change | Nathan Ingram | Per Nathan, we must wait for engineering's detailed estimate to get correct dollars, 08/10/20 estimate is $2.464M
#N/A | 112389 | Base Plan | #N/A | #N/A | #REF! | Yes | Need To Add (2022) | TP2020033 | TP2020033 | 210544 | 81520 | AEP | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | ITP | 2022-05-27 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 6892342.6892 | 6724237 | 0 |  | Delay - Mitigation | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2 |  |  |  | Y |  |  | no change | Larry Oden | Per PM: "Working on detail estimate. Per the overview scoping document, Functional non loaded cost is estimated to be ~$4.37M ."
#N/A | 112393 | Base Plan | #N/A | #N/A | #REF! | Yes | Need To Add (2022) | TP2020033 | TP2020033 | 210544 | 81523 | AEP | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | ITP | 2022-05-27 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1340497.05 | 1307802 | 0 |  | Delay - Mitigation | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5 |  |  | Y |  |  | no change | Larry Oden | Per PM: "Working on detail estimate. Per the overview scoping document, Functional non loaded cost is estimated to be ~$2.98M . High risk is the existing building to be purchased and lies beneath our existing 138kV line"
#N/A | 112460 | Base Plan | #N/A | #N/A | #REF! | Yes | Do Not Add (2026) | TS2020480 | TS2020480 | 210544 | 81561 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | ITP | 2026-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 751858 | 733520 | 0 |  | On Schedule < 4 | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138/138 |  |  |  |  | Y |  |  | no change |  | No information yet
#N/A | 112488 | Base Plan | #N/A | #N/A | #REF! | Yes | Need To Add (06/2022 per EcoSys) | TP2019132 | TP2019132 | 210544 | 81571 | AEP | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | ITP | 2021-11-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9384046.175 | 9155167 | 0 |  | Delay - Mitigation | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115 |  |  |  |  | Y |  |  | no change | Jake Tucker | New dates and dollars from PM updated 8/10/20. Leaving dollars as they were last quarter until we get final estimates. Per Jake Tucker, "For the NTC work we have two bpid’s, one for removal and one for install. The loaded costs on those are $8,090,001(functional costs), we have detailed scopes, but not detailed estimates yet. ISD for NTC portion will be October 2021 as we cannot get the xfrmr until May and then will lose our outages end of May and not get them back til mid September. We expect to have most everything ready by end of May, commission the xfrmr over the summer, and then do final install last half of Sept."
#N/A | 112502 | Base Plan | #N/A | #N/A | #REF! | Yes | Do Not Add (2026) | TS2020480 | TS2020480 | 210544 | 81561 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | ITP | 2026-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3325946.7525 | 5383105 | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06 |  |  |  | Y |  |  | no change |  | No information yet
#N/A | 122665 |  | #N/A | #N/A | #REF! | Yes |  | 0 |  |  | 81657 | AEP | Riverside GEN-2016-133 thru 146 Interconnection Costs | Riverside 345kV GEN-2016-133 thru 146 Interconnection (TOIF) (AEP) | Generation Interconnection | GI |  |  |  | GI STUDIES |  |  |  | 1388819 | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.18 | [6 empty] | In-service dates will be provided after GIA
#N/A | 122666 |  | #N/A | #N/A | #REF! | Yes |  | 0 |  |  | 81657 | AEP | Riverside GEN-2016-133 thru 146 Interconnection Costs | Riverside 345kV GEN-2016-133 thru 146 Interconnection (Non-Shared NU) (AEP) | Generation Interconnection | GI |  |  |  | GI STUDIES |  |  |  | 10361130 | 0 |  | On Schedule < 4 |  |  |  |  | Expand the 345 kV breaker and a half scheme, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | [8 empty] | In-service dates will be provided after GIA
#N/A | 122713 | Direct Assigned | #N/A | #N/A | #REF! | Yes | Do Not Add (Direct Assigned) | TP2020077 | TP2020077 | 210558 | 81673 | AEP | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | TS | 2022-06-01 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 | 3160967 | 2020 | 3239991.175 | 3160967 | 0 |  | On Schedule < 4 | 510423 | LOCUST GROVE | 512634 | KERR 115 | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49 |  |  | Y |  |  | no change | Larry Oden | Per PM: "project just kicked off. Detail scope development underway. Project is no longer a box bay but an "in-out". TFS interested in doing the line work"
#N/A | 122730 | Base Plan | #N/A | #N/A | #REF! | Yes | Do Not Add (2024) | TP2020102 | TP2020102 | 210575 | 81687 | AEP | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | ITP | 2024-06-01 | 2024-06-01 | 2020-11-17 | 2020 ITP | 23622577 | 2021 | 23622577 | 23622577 | 0 |  | On Schedule < 4 | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA |  | 11.2 | [6 empty] | MOD number added 13153 |  | No PM assigned yet
#N/A | 122796 | Base Plan | #N/A | #N/A | #REF! | Yes | Do Not Add (2023) | TP2020266 | TP2020266 | 210575 | 81717 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | ITP | 2023-04-30 | 2022-01-01 | 2020-11-17 | 2020 ITP | 12210634 | 2021 | 12210634 | 12210634 | 0 |  | NTC-C Project Estimate Window | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support an in and out tap of the existing Woodward to Border 345 kV line to achieve a summer emergency of 1792 MVA |  | 0.2 | [6 empty] | MOD number added 16810 |  | On hold Waiting for SPP decision
#N/A | 143156 | Base Plan (This project was incorrectly listed, it is ZONAL) | #N/A | #N/A | #REF! | Yes | Need To Add (2022) - REMOVED in R1 | TP2020234 | TP2020234 | 210576 | 91875 | AEP | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Zonal Reliability | ITP | 2022-12-01 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1184404 | 2021 | 1184404 | 1184404 | 0 |  | On Schedule < 4 |  |  |  |  | Install a new 23 MVAR capacitor bank at Grady 138 kV | [8 empty] | MOD number added 100179 | Dara Dixon | Detailed estimate matches NTC

## Q2 2021 Initial PTP (hidden)
UID Lookup | UID | Cost Allocation | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Manual Super | TPID | NTC ID | RFP ID | PID | Project Owner | Project Name | Upgrade Name | Project Type | STEP Project Type | Project Owner Indicated In-Service Date | Q4 2020 Project Owner Indicated In-Service Date | RTO Determined Need Date | Latest NTC Issue Date | NTC Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Final Cost Source | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion | Letter of Commercial Operation | Mod Information | Amount to-date Cost | GIS Data
11261 | 11261 |  | #N/A | #N/A | #REF! | No | Direct Assigned | TP2010092 | TP2010092 | 20104 |  | 947 | AEP | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | TS | 2016-05-25 | 2016-05-25 | 2015-06-01 | 2010-08-25 | SPP-2008-AGP1-AFS-9 | 6072000 | 2014 | 6379395 | 6072000 | 3994146.59 |  | Complete | 509806 | ONETA 138KV | 509786 | BROKEN ARROW NORTH - SOUTH TAP | Rebuild 4.33 of 795 ACSR with 1590 ACSR. | 138 |  | 4.33 |  | Y | Y | Y | Y
50718 | 50718 | BasePlan | #N/A | TP2013165 | #REF! | Yes |  | TP2013165 | TP2013165 | 200246 |  | 30573 | AEP | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-06-21 | 2017-06-21 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 6695985.9 | 2014 | 7210844.4074 | 6695985.9 | 4352349 |  | Complete | 507716 | BROADMOOR | 507730 | FORT HUMBUG 69KV | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor. | 69 |  | 1.7 |  | Y | Y | Y | Y
#N/A | 51096 |  | TP2015118 | #N/A | #REF! | Yes |  | TP2015118 | TP2015118 | 200382 |  | 30809 | AEP | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | TS | 2020-06-11 | 2020-06-11 | 2021-06-01 | 2016-04-12 | SPP-2014-AG1-AFS-6 | 4319501 | 2016 | 4767920.8822 | 6445009 | 6193883 |  | Complete | 505610 | Keystone Dam | 509757 | WEKIWA 138KV | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation. | 138 | 2 | 2 | 2 | Y | Y | Y | Y
#N/A | 51446 | BasePlan | TP2015169 | #N/A | #REF! | Yes |  | TP2015169 | TP2015169 TFS/failure | 200386 |  | 31003 | AEP | Sub - Northeastern Station 138 kV Terminal Upgrades | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | ITP | 2016-10-05 | 2016-10-05 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 518011.16 | 2016 | 518011.16 | 518011.16 | 183230.63 |  | Complete | 510396 | NORTHEAST STATION 138KV |  |  | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah. | 138 |  |  |  | Y | Y | Y | Y
#N/A | 51558 |  | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | TA2011012 | 200386 |  | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2019-12-18 | 2019-12-18 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 13512896.75 | 2016 | 14551911.7591 | 11805970.48 | 8544022.08 | proportionalized | Complete | 510912 | ARMY AMMUNITION DEPOT | 510899 | McALESTER 69KV | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester. | 69 |  |  |  | Y | Y | Y | Y
#N/A | 51559 |  | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | TA2011012 | 200386 |  | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2022-11-20 | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15146463.7 | 2016 | 17136833.3826 | 15595092.29 | 9226023.92 | proportionalized | Delay - Mitigation | 510912 | ARMY AMMUNITION DEPOT | 510885 | PITTSBURG 69KV | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg. | 69 |  |  |  |  | Y |  | Y
#N/A | 51560 |  | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | TA2011012 | 200386 |  | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2022-11-20 | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 24516011.291 | 21981547.8 |  |  | Delay - Mitigation | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69 |  |  |  |  | Y |  | Y
#N/A | 61858 | BasePlan | TP2017011 | #N/A | #REF! | Yes |  | TP2017011 | TP2017011 | 200446 |  | 41202 | AEP | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | ITP | 2019-12-20 | 2019-12-20 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 6014381.13 | 2017 | 6318859.1747 | 7238795 | 8151314 |  | Complete | 509811 | TULSA SOUTHEAST 138KV | 509831 | EAST 61st STREET | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line. | 138 | 1.8 |  |  | Y | Y | Y | Y
#N/A | 72066 | BasePlan | #N/A | TA2016806 | #REF! | Yes |  | TA2016806 | TA2016806 P16806004 | 210491 |  | 51300 | AEP | Multi - Fig Five - VBI 69kV | Fig Five - VBI North 69kV Ckt 1 | Regional Reliability | ITP | 2019-04-11 | 2019-04-11 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 3357600 | 2018 | 3441540 | 3357600 | 1922898.94 | proportionalized | Complete | 504185 | Figure Five | 504032 | VBI NORTH | Rebuild 4.2 miles of 69 kV line from Fig Five to VBI. | 69 |  |  |  | Y | Y | Y | Y
#N/A | 82137 |  | #N/A | #N/A | #REF! | No | Not Base Plan | TP2017247 | TP2017247 |  |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | GI | 2020-09-30 | 2020-12-31 |  |  | GI STUDIES |  |  |  | 700000 | 0 |  | Complete |  |  |  |  | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation. | [5 empty] | Y |  | Y
#N/A | 82138 |  | #N/A | #N/A | #REF! | No | Not Base Plan | TP2017247 | TP2017247 |  |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | GI | 2020-09-30 | 2020-12-31 |  |  | GI STUDIES |  |  |  | 8700000 | 0 |  | Complete |  |  |  |  | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer. | [5 empty] | Y |  | Y
#N/A | 112360 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2023) | TP2019245 | TP2019245 | 210544 |  | 81500 | AEP | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | ITP | 2023-05-01 | 2022-11-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 16288000 | 2020 | 16695200 | 33619929 | 0 |  | Re-evaluation | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 21 breakers at Riverside Station 138 kV with 80 kA breakers | 138 | 1.56 |  |  |  | Y |  | Y
#N/A | 112361 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2023) | TA2019024 | TA2019024 | 210544 |  | 81501 | AEP | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | ITP | 2023-12-15 | 2023-12-15 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4531878.625 | 4194065 | 0 |  | Delay - Mitigation | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138 |  |  |  |  | Y |  | Y
#N/A | 112389 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2022) | TP2020033 | TP2020033 | 210544 |  | 81520 | AEP | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | ITP | 2022-05-27 | 2022-05-27 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 6892342.6892 | 6724237 | 0 |  | Delay - Mitigation | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2 |  |  |  | Y |  | Y
#N/A | 112393 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2022) | TP2020033 | TP2020033 | 210544 |  | 81523 | AEP | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | ITP | 2022-05-27 | 2022-05-27 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1340497.05 | 1307802 | 0 |  | Delay - Mitigation | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5 |  |  | Y |  | Y
#N/A | 112460 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2026) | 0 |  | 210544 |  | 81561 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | ITP | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 751858 | 733520 | 0 |  | On Schedule < 4 | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138/138 | [6 empty] | Y
#N/A | 112488 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (06/2022 per EcoSys) | TP2019132 | TP2019132 | 210544 |  | 81571 | AEP | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | ITP | 2021-11-30 | 2021-11-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9384046.175 | 9155167 | 0 |  | Delay - Mitigation | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115 |  |  |  |  | Y |  | Y
#N/A | 112502 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2026) | 0 |  | 210544 |  | 81561 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | ITP | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3325946.7525 | 5383105 | 0 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06 | [5 empty] | Y
#N/A | 122713 | Directly assigned | #N/A | #N/A | #REF! | No | Direct Assigned | TP2019243 | TP2019243 | 210558 |  | 81673 | AEP | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | TS | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 | 3160967 | 2020 | 3239991.175 | 3160967 | 0 |  | Delay - Mitigation | 510423 | LOCUST GROVE | 512634 | KERR 115 | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49
#N/A | 122730 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2024) | TP2020102 | TP2020102 | 210575 |  | 81687 | AEP | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | ITP | 2024-06-01 | Not Found | 2024-06-01 | 2020-11-17 | 2020 ITP | 23622577 | 2020 |  | 23622577 | 0 |  | NTC-C Project Estimate Window | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA |  | 11.2
#N/A | 122796 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2023) | TP2020266 | TP2020266 | 210575 |  | 81717 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | ITP | 2023-04-30 | Not Found | 2022-01-01 | 2020-11-17 | 2020 ITP | 11999273.11 | 2020 |  | 12210634 | 0 |  | NTC-C Project Estimate Window | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support an in and out tap of the existing Woodward to Border 345 kV line to achieve a summer emergency of 1792 MVA |  | 0.2
#N/A | 143156 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2022) | TP2020234 | TP2020234 | 210576 |  | 91875 | AEP | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Regional Reliability | ITP | 2022-12-01 | Not Found | 2022-12-01 | 2020-11-17 | 2020 ITP | 688788.07 | 2020 |  | 1184404 | 0 |  | NTC - Commitment Window |  |  |  |  | Install a new 23 MVAR capacitor bank at Grady 138 kV
#N/A | 143182 | BasePlan | #N/A | #N/A | #REF! | No | Do Not Add (2023) | TP2020266 | TP2020266 | 210575 |  | 81717 | AEP | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward Border 345 kV Ckt 1 (AEP) | Economic | ITP | 2023-04-30 | Not Found | 2022-01-01 | 2020-11-17 | 2020 ITP | 1000000 | 2020 |  | 3358894 | 0 |  | NTC-C Project Estimate Window |  |  |  |  | Build 0.84-miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm to achieve a summer emergency rating of 1792 MVA. Oklahoma Gas and Electric Co. and American Electric Power shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC

## Q4 2020 Initial PTP (hidden)
UID Lookup | UID | Cost Allocation | MPID | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Superproject | PM Name | MOD_ID | NTC_ID | PID | ProjectOwner | Project Name | Upgrade Name | Project Type | Project Owner Indicated In-Service Date | Q4 2019 Project Owner Indicated ISD | RTO Determined Need Date | Letter of Notification to Construct Issue Date | Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | % compare | Final Cost | Final Cost Source | Project Status | Project Description/ Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion | Letter of Commercial Operation | Mod Information | Amount to-date Cost | GIS Data | AEP comments
#N/A | 51558 |  |  | #N/A | #N/A | #REF! | Yes | Zonal | TA2011012 | Brent Harris | 13823-25 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-18 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 13512896.75 | 2016 | 14551911.7591 | 11805970.48 |  | 0 |  | Complete | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester. | 69 |  |  |  |  | Y |  | Y
#N/A | 51559 | BasePlan | MP0004303 | #N/A | #N/A | #REF! | Yes | Zonal | TA2011012 | Brent Harris/Todd Rind | 13824 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2022-11-20 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15146463.7 | 2016 | 16718861.87 | 15595092.29 | 93.28% | 0 |  | Delay - Mitigation | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg. | 69 | [6 empty] | Y | Waiting for outages. Mitigation plan since 2017 No PM assigned to the last portion. Note from Frances: "After further discussion with Brent and the t-line engineer I have confirmed that the line sections from McAlester City to Army Ammo Plant Tap and Army Ammo Plant Tap to Savanna have been fully rebuilt. The section of line from Savanna to Pittsburg and Pittsburg to Atoka Pump will not be completed until the line switches are replaced as part of TA2020053. There is a box bay being added at Atoka Pump Tap under TA2018017. EcoSys shows a planned ISD of 11/2020. I assume the section of line from Atoka Pump to Atoka will not be fully rebuilt until the Box Bay is installed. "
#N/A | 51560 | BasePlan | MP0004303 | #N/A | #N/A | #REF! | Yes | Zonal | TA2011012 | Brent Harris/Todd Rind | 13825 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2022-11-20 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 23918059.8437 | 21981547.8 | 91.9% | 0 |  | Delay - Mitigation | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69 | [6 empty] | Y | Same as UID 51560 above
#N/A | 72066 | BasePlan |  | #N/A | TA2016806 | #REF! | Yes |  | TA2016806 | Tucker, Jake | 17135 | 210491 | 51300 | AEP | Multi - Fig Five - VBI 69kV | Fig Five - VBI North 69kV Ckt 1 | Regional Reliability | 2019-04-11 | 2019-04-11 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 3357600 | 2018 | 3441540 | 3357600 |  | 0 |  | Complete | Rebuild 4.2 miles of 69 kV line from Fig Five to VBI. | 69 |  |  |  | Y | Y |  | Y
#N/A | 112361 | BasePlan | MP1959604 | #N/A | #N/A | #REF! | Yes | Do Not Add (2023) | TA2019024 | Nathan Ingram |  | 210544 | 81501 | AEP | Sub - Southwestern Station 138 kV BPID's A19024002&4 | Southwestern Station 138 kV Breakers | Regional Reliability | 2023-12-15 | Not Found | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4421345 | 4194065 | 94.86% | 0 |  | Delay - Mitigation | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138 | [6 empty] | Y | Per Nathan, we must wait for engineering's detailed estimate to get correct dollars, DICM was added on the wrong BPID. 08/10/20 estimate is $2.464M
50545 | 50545 |  |  | #N/A | TP2010067 | #REF! | Yes |  | TP2010067 | Goetz, Dave | 11336 | 200231 | 30449 | AEP | Line - Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Regional Reliability | 2016-09-19 | 2016-09-19 | 2014-06-01 | 2013-09-23 | 2013 ITPNT | 25060655.37 | 2013 | 26987584.699 | 25060655.37 |  | 25330929 | FORMULA RATE UPDATE | Complete | Rebuild 27.6-mile 138 kV line from Rock Hill to Springridge Pan-Harr REC with 1926.9 ACSR/TW conductor. | 138 | 27.6 |  |  | Y | Y |  | Y
11261 | 11261 | Directly Assigned |  | #N/A | #N/A | #REF! | Yes | Direct Assigned | TP2010092 | Brent Garrett | 6232 | 20104 | 947 | AEP | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | 2016-05-25 | 2016-05-25 | 2015-06-01 | 2010-08-25 | SPP-2008-AGP1-AFS-9 | 6072000 | 2014 | 6379395 | 6072000 | 95.18% | 0 |  | In Service | Rebuild 4.33 of 795 ACSR with 1590 ACSR. | 138 |  | 4.33 |  | Y | Y |  | Y | Needs to be closed out? Check with Brent Garrett for final dollars.
10615 | 10615 | BasePlan |  | #N/A | TP2012145 | #REF! | Yes |  | TP2012145 | Goetz, Dave |  | 200216 | 478 | AEP | Line - Forbing Tap - South Shreveport 69 kV | Forbing Tap - South Shreveport 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 1221505.45 | 2013 | 1315427.7614 | 1221505.45 |  | 0 |  | Complete | Rebuild 2.3-mile 69 kV line from Forbing to South Shreveport with 1233.6 ACSR/TW. | 69 |  | 2.3 |  | Y | Y |  | Y
10657 | 10657 | BasePlan |  | #N/A | TP2012145 | #REF! | Yes |  | TP2012145 | Goetz, Dave |  | 200246 | 512 | AEP | Line - Ellerbe Road - Forbing Tap 69 kV Ckt 1 | Ellerbe Road - Forbing T 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 8174689.3 | 2014 | 8588532.9458 | 8174689.3 |  | 0 |  | Complete | Rebuild 2.0-mile 69 kV line from Ellerbe Road to Forbing T with 1233.6 ACSR/TW conductor. | 69 | 2 |  |  | Y | Y |  | Y
50718 | 50718 | BasePlan |  | #N/A | TP2013165 | #REF! | Yes |  | TP2013165 | Goetz, Dave |  | 200246 | 30573 | AEP | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-21 | 2017-06-21 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 6695985.9 | 2014 | 7210844.4074 | 6695985.9 |  | 0 |  | Complete | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor. | 69 |  | 1.7 |  | Y | Y |  | Y
50720 | 50720 | BasePlan |  | #N/A | TP2013167 | #REF! | Yes |  | TP2013167 | Goetz, Dave | 12312 | 200246 | 30575 | AEP | Line - Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-03-02 | 2018-03-02 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 8851676.64 | 2014 | 9770594.7733 | 11872448 |  | 9930039 | FORMULA RATE UPDATE | Complete | Rebuild 6.6-mile 69 kV line from Longview Heights to Hallsville with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Longview Heights. | 69 |  | 6.6 |  | Y | Y |  | Y
50721 | 50721 | BasePlan |  | #N/A | TP2013167 | #REF! | Yes |  | TP2013167 | Goetz, Dave | 10759 | 200246 | 30576 | AEP | Line - Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-02 | 2017-06-02 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 15248925.46 | 2014 | 16421424.793 | 19864843 |  | 10670271 | FORMULA RATE UPDATE | Complete | Rebuild 11.2-mile 69 kV line from Hallsville to Marshall with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Marshall. | 69 |  | 11.2 |  | Y | Y |  | Y
#N/A | 51096 | BasePlan | MP0010898 | TP2015118 | #N/A | #REF! | Yes |  | TP2015118 | 0 | 14087 | 200382 | 30809 | AEP | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | 2020-06-11 | 2021-06-01 | 2021-06-01 | 2016-04-12 | SPP-2014-AG1-AFS-6 | 4319501 | 2016 | 4767920.8822 | 6445009 | 135.2% | 0 |  | In Service | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation. | 138 | 2 | 2 | 2 |  |  |  | Y | In service. Gathering remaining information. Dollars above estimate, Jeff is preparing paperwork
#N/A | 61858 | BasePlan |  | TP2017011 | #N/A | #REF! | Yes |  | TP2017011 | 0 | 15516 | 200446 | 41202 | AEP | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | 2019-12-20 | 2019-12-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 6014381.13 | 2017 | 6318859.1747 | 7238795 |  | 0 |  | Complete | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line. | 138 | 1.8 |  |  |  | Y |  | Y
#N/A | 82137 |  | MP1922928 | #N/A | #N/A | #REF! | Yes | Not Base Plan | TP2017247 | Tommy Vannoy | 16818 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | 2020-12-31 | 2019-08-09 |  |  | GI STUDIES |  |  |  | 700000 | 0% | 0 |  | On Schedule < 4 | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation. | [7 empty] | Y | IPP project, put in service when Tommy reports that it went into service. Check on new date with Linda. Tied up with lawyers. Need new dollars, Tommy cannot separate this portion.
#N/A | 82138 |  | MP1922928 | #N/A | #N/A | #REF! | Yes | Not Base Plan | TP2017247 | 0 | 16818 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | 2020-12-31 | 2019-08-09 |  |  | GI STUDIES |  |  |  | 8700000 | 0% | 0 |  | On Schedule < 4 | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer. | [7 empty] | Y | IPP project, put in service when Tommy reports that it went into service. Check on new date with Linda. Tied up with lawyers. Need new dollars, Tommy cannot separate this portion.
#N/A | 112488 | BasePlan | MP1959952 | #N/A | #N/A | #REF! | Yes | Do Not Add (06/2022 per EcoSys) | TP2019132 | Jake Tucker |  | 210544 | 81571 | AEP | XFR - Pryor Junction 138/115 BPID's P19132001 removal, 09 install | Pryor Junction 138/115 kV Transformer | Regional Reliability | 2021-11-30 | Not Found | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9155167 | 9155167 | 100% | 0 |  | Delay - Mitigation | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115 | [6 empty] | Y | new dates and dollars from PM updated 8/10/20. Leaving dollars as they were last quarter until we get final estimates. Per Jake Tucker, "For the NTC work we have two bpid’s, one for removal and one for install. The loaded costs on those are $8,090,001(functional costs), we have detailed scopes, but not detailed estimates yet. ISD for NTC portion will be October 2021 as we cannot get the xfrmr until May and then will lose our outages end of May and not get them back til mid September. We expect to have most everything ready by end of May, commission the xfrmr over the summer, and then do final install last half of Sept."
#N/A | 122713 | Directly assigned | MP1959942 | #N/A | #N/A | #REF! | Yes | Direct Assigned | TP2019243 | TBD |  | 210558 | 81673 | AEP | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | 2022-06-01 | Not Found | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 |  |  |  | 3160967 | 0% | 0 |  | Delay - Mitigation | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49 | [5 empty] | No PM assigned, ask Ashley Beasley
#N/A | 112360 | BasePlan | MP1959941 | #N/A | #N/A | #REF! | Yes | Do Not Add (2022) | TP2019245 | Anita Hartman |  | 210544 | 81500 | AEP | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | 2022-11-01 | Not Found | 2021-06-01 | 2019-11-18 | 2019 ITP | 16288000 | 2020 | 16288000 | 16288000 | 100% | 0 |  | Delay - Mitigation | Replace 21 breakers at Riverside Station 138 kV with 80 kA breakers | 138 | [6 empty] | Y | Needs updated dollars and date from Jeff.
#N/A | 112389 | BasePlan | MP1960212 | #N/A | #N/A | #REF! | Yes | Do Not Add (2022) | TP2020033 | Larry Oden |  | 210544 | 81520 | AEP | Line - Tulsa SE - S Hudson 138kV Ckt 1 BPID's P20033001,02,03&06 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | 2022-05-27 | Not Found | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 6724236.77 | 6724236.77 | 100% | 0 |  | Delay - Mitigation | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2 | [5 empty] | Y | Need new dates and dollars from PM updated 8/10/20 are not detailed. Leaving dollars as they were last quarter
#N/A | 112393 | BasePlan | MP1960212 | #N/A | #N/A | #REF! | Yes | Do Not Add (2022) | TP2020033 | Larry Oden |  | 210544 | 81523 | AEP | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 BPID's P20033004&05 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | 2022-05-27 | Not Found | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1307802 | 1307802 | 100% | 0 |  | Delay - Mitigation | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5 |  |  |  |  | Y | Need new dates and dollars from PM updated 8/10/20 are not detailed. Leaving dollars as they were last quarter
#N/A | 51446 | BasePlan |  | TP2015169 | #N/A | #REF! | Yes |  | TP2015169 | Balo, Donald |  | 200386 | 31003 | AEP | Sub - Northeastern Station 138 kV Terminal Upgrades | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | 2016-10-05 | 2016-10-05 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 518011.16 | 2016 | 518011.16 | 518011.16 |  | 0 |  | Complete | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah. | 138 |  |  |  | Y | Y |  | Y
#N/A | 50769 |  |  | #N/A | #N/A | #REF! | Yes | Do Not Add (2033) |  | #N/A |  |  | 30599 | AEP | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | South Fayetteville 345/161 kV Transformer Ckt1 | ITP20 |  | Not Found | 2033-01-01 |  | 2013 ITP20 | 0 |  |  | 12600000 | 0% |  |  | Identified | Install new 345/161 kV Transformer at South Fayetteville. | 345/161 | [7 empty] | Not a real project (??), ISD is 2033 so we won't be working on it for a while…
51033 | 51033 |  |  | #N/A | TP2014139 | #REF! | Yes |  | TP2014139 | #N/A |  | 200298 | 30761 | AEP | Line - Cedar Grove - South Shreveport 138 kV | Cedar Grove - South Shreveport 138 kV | Transmission Service | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2014-09-30 | SPP-2010-AGP1-AFS-8 | 6566218 | 2014 | 7614799.8089 | 6566217.77 | 86.23% | 0 |  | On Schedule < 4 | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove. | 138 | [6 empty] | Y | Done under another UID, shouldn't be showing up
#N/A | 112460 | BasePlan |  | #N/A | #N/A | #REF! | Yes | Do Not Add (2026) |  | #N/A |  | 210544 | 81561 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | 2026-01-01 | Not Found | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 733520 | 733520 | 100% | 0 |  | On Schedule < 4 | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138/138 | [6 empty] | Y | Competitive project, also very distant ISD, no changes to these. May not get awarded
#N/A | 112502 | BasePlan |  | #N/A | #N/A | #REF! | Yes | Do Not Add (2026) |  | #N/A |  | 210544 | 81561 | AEP | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | 2026-01-01 | Not Found | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3244826.1 | 5383105 | 165.9% | 0 |  | On Schedule < 4 | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06 | [5 empty] | Y | Competitive project, also very distant ISD, no changes Wekiwa atse
Formulas:
Q4 2019 Project Owner Indicated ISD = IFNA(VLOOKUP([UID],'Q4 2019 Initial PTP'!$B2:P57,15,0),"Not Found")

## Q4 2019 Initial PTP (hidden)
UID Lookup | UID | Cost Allocation | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Superproject | NTC ID | PID | Project Owner | Project Name | Upgrade Name | Project Type | Project Owner Indicated In-Service Date | Q4 2018 Project Owner Indicated ISD | RTO Determined Need Date | Latest NTC Issue Date | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Final Cost Source | Project Status | Project Description/Comments
#N/A | 51558 |  | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (BPID's A11012198&A11012075) | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 13512897 | 2016 | 14551912 | 13512897 |  |  | DELAY - MITIGATION | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester.
#N/A | 51559 |  | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (BPID A11012444) | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 15146464 | 2016 | 16311085 | 13767520 |  |  | DELAY - MITIGATION | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg.
#N/A | 51560 |  | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (BPID's A11012445&46) | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 21668582 | 2016 | 23334693 | 23047526 |  |  | DELAY - MITIGATION | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg.
#N/A | 72066 | BasePlan | #N/A | #N/A | #REF! | No | Need to Add | TA2016806 | 210491 | 51300 | AEP | Multi - Fig Five - VBI 69kV | Fig Five - VBI North 69kV Ckt 1 | Regional Reliability | 2019-04-11 | Not Found | 2019-06-01 | 2018-08-17 | 3357600 | 2018 | 3441540 | 3357600 |  |  | ON SCHEDULE < 4 | Rebuild 4.2 miles of 69 kV line from Fig Five to VBI.
#N/A | 51446 | BasePlan | TP2015169 | #N/A | #REF! | Yes |  | TP2015169 | 200386 | 31003 | AEP | Sub - Northeastern Station 138 kV Terminal Upgrades | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | 2016-10-05 | 2016-10-05 | 2017-06-01 | 2016-05-17 | 518011 | 2016 | 557841 | 518011 |  |  | COMPLETE | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah.
51017 | 51017 | TBD | #N/A | #N/A | #REF! | Yes |  | TP2012141 | 200272 | 30750 | AEP | Line - Stonewall - Wapanucka 138 kV Ckt 1 | Stonewall - Wapanucka 138 kV Ckt 1 | High Priority | 2013-12-31 | 2013-12-31 | 2015-06-01 | 2014-05-19 | 8934149 | 2014 | 10108169 | 8934149 | 7200874 | Formula Rate Update | COMPLETE | Construct new 6.4-mile 138 kV line from Stonewall to Wapanucka.
11236 | 11236 |  | TP2009089 | TP2009089 | #REF! | Yes |  | TP2009089 | 20096 | 936 | AEP | Line - Valliant - NW Texarkana 345 kV | NORTHWEST TEXARKANA - VALLIANT 345KV CKT 1 | High Priority | 2016-12-16 | 2016-12-16 | 2014-10-01 | 2010-06-30 | 185751250 | 2016 | 200033780 | 185751250 |  |  | COMPLETE | Build a new 76 mile 345 kV line from Valliant to NW Texarkana with at least 3000 A capacity. Upgrade the Valliant and NW Texarkana substations with the necessary breakers and terminal equipment.
10649 | 10649 | BasePlan | #N/A | TP2009104 | #REF! | Yes |  | TP2009104 | 200216 | 504 | AEP | Line - Brownlee - North Market 69 kV | Brownlee - North Market 69 kV Ckt 1 | Regional Reliability | 2017-03-22 | 2017-03-22 | 2013-06-01 | 2013-02-20 | 12424849 | 2013 | 14409016 | 17162457 |  |  | COMPLETE | Rebuild 4.7-mile 69 kV line from Brownlee to North Market with 1233.6 ACSR/TW.
50607 | 50607 |  | #N/A | TP2011033 | #REF! | Yes |  | TP2011033 | 200231 | 30495 | AEP | Sub - Messick 500/230 kV | Layfield 500/230 kV Transformer Ckt 1 | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 30369537 | 2013 | 35219352 | 22851755 |  |  | COMPLETE | Build Messick 500/230 kV substation. Connect to Carrol, Clarence, and Western Kraft 230 kV lines. Install 500/230 kV 675 MVA transformer. This upgrade is contingent upon approval from Cleco Power LLC.
50615 | 50615 |  | #N/A | TP2011033 | #REF! | Yes |  | TP2011033 | 200231 | 30495 | AEP | Sub - Messick 500/230 kV | Layfield 500 kV Terminal Upgrades | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 21508234 | 2013 | 24942957 | 32212715 |  |  | COMPLETE | Install terminal equipment on 500 kV side of new Messick substation. Connect to Mt. Olive - Hartburg 500 kV line. This upgrade is contingent upon approval from Cleco Power LLC for Upgrade ID 50607.
50545 | 50545 |  | #N/A | TP2010067 | #REF! | Yes |  | TP2010067 | 200231 | 30449 | AEP | Line - Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Regional Reliability | 2016-09-19 | 2016-09-19 | 2014-06-01 | 2013-09-23 | 25060655 | 2013 | 29062677 | 25060655 |  |  | COMPLETE | Rebuild 27.6-mile 138 kV line from Rock Hill to Springridge Pan-Harr REC with 1926.9 ACSR/TW conductor.
11261 | 11261 |  | #N/A | #N/A | #REF! | No | Direct Assigned | TP2010092 | 20104 | 947 | AEP | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | 2016-05-25 | 2016-05-25 | 2015-06-01 | 2010-08-25 | 6072000 | 2014 | 6869911 | 6072000 |  |  | COMPLETE | Rebuild 4.33 of 795 ACSR with 1590 ACSR.
11158 | 11158 | BasePlan | #N/A | #N/A | #REF! | Yes |  | TP2010094 | 200216 | 879 | AEP | Line - Bluebell - Prattville 138 kV | Bluebell - Prattville 138 kV Ckt 1 | Regional Reliability | 2015-06-02 | 2015-06-02 | 2014-06-01 | 2013-02-20 | 10241314 | 2013 | 11876785 | 10241314 |  |  | COMPLETE | Rebuild 9.0-mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW.
10646 | 10646 | BasePlan | #N/A | TP2010100 | #REF! | Yes |  | TP2010100 | 200216 | 501 | AEP | Line - Evenside - Northwest Henderson 69 kV | Evenside - Northwest Henderson 69 kV Ckt 1 | Regional Reliability | 2018-05-11 | 2018-05-11 | 2018-06-01 | 2013-02-20 | 11980465 | 2013 | 13893666 | 11980465 |  |  | COMPLETE | Rebuild 6.4-mile 69 kV line from Evenside to Northwest Henderson with 1233.6 ACSR/TW. Replace breaker at Evenside.
50336 | 50336 | BasePlan | #N/A | TP2011022 | #REF! | Yes |  | TP2011022 | 20122 | 30298 | AEP | Device - Logansport 138 kV | LOGANSPORT 138KV | Regional Reliability | 2016-09-10 | 2016-09-10 | 2016-06-01 | 2011-02-14 | 1166400 | 2014 | 1319675 | 1731419 |  |  | COMPLETE | Install 28.8 MVAR capacitor bank at Logansport 138 kV substation.
10648 | 10648 | BasePlan | #N/A | TP2011023 | #REF! | Yes |  | TP2011023 | 200167 | 503 | AEP | Line - Diana - Perdue 138 kV | Diana - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2013-06-01 | 2012-04-09 | 1004187 | 2012 | 1193662 | 1004187 |  |  | COMPLETE | Replace two breakers, jumpers, and wave traps at Perdue substation. Replace wave traps at Diana substation.
50531 | 50531 | BasePlan | #N/A | TP2011023 | #REF! | Yes |  | TP2011023 | 200216 | 30436 | AEP | Line - New Gladewater - Perdue 138 kV | New Gladewater - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2016-06-01 | 2013-02-20 | 1000000 | 2013 | 1159693 | 1000000 |  |  | COMPLETE | Replace 138 kV breaker at Perdue.
#N/A | 51448 | BasePlan | TP2011110 | #N/A | #REF! | Yes |  | TP2011110 | 200386 | 31005 | AEP | Sub - Elk City 138 kV Move Load (BPID P11110001) | Elk City 138 kV Move Load | Regional Reliability | 2018-05-25 | 2018-05-25 | 2017-06-01 | 2016-05-17 | 2904911 | 2016 | 3128271 | 2904911 |  |  | COMPLETE | Move load from 69 kV bus to 138 kV bus at Elk City.
10583 | 10583 | BasePlan | #N/A | TP2011147 | #REF! | Yes |  | TP2011147 | 200216 | 451 | AEP | Multi - Chamber Springs - Farmington 161 kV | Chamber Springs - Farmington REC 161 kV Ckt 1 | Regional Reliability | 2017-03-28 | 2017-03-28 | 2013-06-01 | 2013-02-20 | 12705537 | 2013 | 14734528 | 12705537 |  |  | COMPLETE | Rebuild and reconductor 11.1-mile 161 kV line from Chamber Springs to Farmington REC with 2-959.6 ACSR/TW. Upgrade wavetraps, CT ratios, and relay settings at Chamber Springs.
50413 | 50413 | BasePlan | #N/A | #N/A | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm - Gracemont 345kV Ckt 1 (AEP) | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 65082311 | 2017 | 68377103 | 65082311 |  |  | COMPLETE | Build new single circuit 345 kV line from new Chisholm substation to point of interconnection with Oklahoma Gas & Electric Co. (OGE) towards Gracemont. The approximate line length for the Chisholm - Gracemont 345 kV line is 100 miles, of which AEP will construct approximately 70 miles from Chisholm to the OGE interconnection point.
50414 | 50414 | BasePlan | #N/A | #N/A | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 345/230 kV Substation | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 17471695 | 2017 | 18356200 | 17471695 |  |  | COMPLETE | Construct new 345/230 kV Chisholm substation between existing 230 kV substations, Sweetwater and Elk City. Cut-in existing Sweetwater - Elk City 230 kV Ckt 1 line into new Chisholm substation and install any necessary 230 kV terminal equipment. Install new 345/230 675 MVA transformer at new Chisholm substation.
50768 | 50768 | BasePlan | #N/A | #N/A | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 230 kV | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 1270623 | 2017 | 1334948 | 1270623 |  |  | COMPLETE | Install approximately 2 miles of 230 kV transmission line for a cut-in to existing 230 kV line from Sweetwater to Elk City, creating termination points at new Chisholm substation.
51047 | 51047 | TBD | #N/A | #N/A | #REF! | Yes |  | TP2012055 | 200272 | 30770 | AEP | Sub - Ellis 138 kV | Ellis 138 kV Substation | High Priority | 2013-06-01 | 2013-06-01 | 2015-06-01 | 2014-05-19 | 4100000 | 2014 | 4638774 | 4100000 | 4086696 | Formula Rate Update | COMPLETE | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation.
10615 | 10615 | BasePlan | #N/A | TP2012145 | #REF! | Yes |  | TP2012145 | 200216 | 478 | AEP | Line - Forbing Tap - South Shreveport 69 kV | Forbing Tap - South Shreveport 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2013-06-01 | 2013-02-20 | 1221505 | 2013 | 1416572 | 1221505 |  |  | COMPLETE | Rebuild 2.3-mile 69 kV line from Forbing to South Shreveport with 1233.6 ACSR/TW.
10657 | 10657 | BasePlan | #N/A | TP2012145 | #REF! | Yes |  | TP2012145 | 200246 | 512 | AEP | Line - Ellerbe Road - Forbing Tap 69 kV Ckt 1 | Ellerbe Road - Forbing T 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2014-06-01 | 2014-02-19 | 8174689 | 2014 | 9248911 | 8174689 |  |  | COMPLETE | Rebuild 2.0-mile 69 kV line from Ellerbe Road to Forbing T with 1233.6 ACSR/TW conductor.
50569 | 50569 | BasePlan | #N/A | TP2012164 | #REF! | Yes |  | TP2012164 | 200216 | 30473 | AEP | Line - Midland REC - North Huntington 69 kV | Midland REC - North Huntington 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 1829026 | 2013 | 2121109 | 1829026 | 11990487 | Formula Rate Update | COMPLETE | Rebuild 4.0-mile 69 kV line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington.
50570 | 50570 | BasePlan | #N/A | TP2012164 | #REF! | Yes |  | TP2012164 | 200216 | 30474 | AEP | Line - Midland - Midland REC 69 kV | Midland - Midland REC 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 5653353 | 2013 | 6556157 | 5653353 | Included in UID 50569 | Formula Rate Update | COMPLETE | Rebuild 1.3-mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland.
50571 | 50571 | BasePlan | #N/A | TP2012164 | #REF! | Yes |  | TP2012164 | 200216 | 30475 | AEP | Line - Howe Interchange - Midland 69 kV | Howe Interchange - Midland 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 9145130 | 2013 | 10605547 | 9145130 | Included in UID 50569 | Formula Rate Update | COMPLETE | Rebuild 7.0-mile portion of the 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of line to be rebuilt is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland.
51014 | 51014 | BasePlan | TP2013002 | #N/A | #REF! | Yes |  | TP2013002 | 200272 | 30747 | AEP | Line - Grady - Round Creek 138 kV Ckt 1 | Grady - Round Creek 138 kV Ckt 1 | High Priority | 2015-11-05 | 2015-11-05 | 2015-06-01 | 2014-05-19 | 12132497 | 2014 | 13726807 | 12132497 |  |  | COMPLETE | Construct new Round Creek box bay tap structure adjacent to the Rush Springs 138 kV substation. Construct new 6-mile 138 kV line from Grady to Round Creek. Install 3-breaker ring bus where hard tap to Round Creek intersects the Cornville to Duncan 138 kV transmission line.
51015 | 51015 | BasePlan | TP2013002 | #N/A | #REF! | Yes |  | TP2013002 | 200272 | 30748 | AEP | Line - Grady - Phillips Gas 138 kV Ckt 1 and 2 | Grady - Phillips 138 kV Ckt 1 and 2 | High Priority | 2014-12-31 | 2014-12-31 | 2015-06-01 | 2014-05-19 | 8318584 | 2014 | 9411714 | 8318584 |  |  | COMPLETE | Construct new 4-mile double circuit 138 kV line from the new 4-breaker ring bus station at Grady. Circuit 1 will terminate at Phillips Gas and Circuit 2 will terminate at Lindsey Water Flood.
50990 | 50990 | BasePlan | #N/A | TP2013081 | #REF! | Yes |  | TP2013081 | 200306 | 30731 | AEP | Line - Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | Mt Pleasant - West Mt Pleasant 69 kV Ckt 1 Rebuild | Regional Reliability | 2015-04-20 | 2015-04-20 | 2015-06-01 | 2014-11-24 | 4715419 | 2015 | 5204940 | 7381799 |  |  | COMPLETE | Rebuild 2.75-mile 69 kV line from Mt. Pleasant to West Mt. Pleasant to achieve a new emergency rating of 84 MVA.
50334 | 50334 | BasePlan | #N/A | TP2013122 | #REF! | Yes |  | TP2013122 | 20122 | 30296 | AEP | Device - Winnsboro 138 kV | WINNSBORO 138KV | Regional Reliability | 2016-04-21 | 2016-04-21 | 2016-06-01 | 2011-02-14 | 1166400 | 2014 | 1319675 | 1166400 |  |  | COMPLETE | Install a new 28.8 MVAR capacitor bank at Winnsboro 138 kV substation.
50718 | 50718 | BasePlan | #N/A | TP2013165 | #REF! | Yes |  | TP2013165 | 200246 | 30573 | AEP | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-21 | 2017-06-21 | 2019-06-01 | 2014-02-19 | 6695986 | 2014 | 7575893 | 6695986 |  |  | COMPLETE | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor.
50719 | 50719 | BasePlan | #N/A | TP2013166 | #REF! | Yes |  | TP2013166 | 200246 | 30574 | AEP | Line - Daingerfield - Jenkins Rec 69 kV Ckt 1 Rebuild | Daingerfield - Jenkins REC T 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-11-09 | 2017-11-09 | 2019-06-01 | 2014-02-19 | 2819806 | 2014 | 3190352 | 2819806 |  |  | COMPLETE | Rebuild 1.3-mile 69 kV line from Daingerfield to Jenkins REC T with 959.6 ACSR/TW conductor.
50720 | 50720 | BasePlan | #N/A | TP2013167 | #REF! | Yes |  | TP2013167 | 200246 | 30575 | AEP | Line - Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-03-02 | 2018-03-02 | 2014-06-01 | 2014-02-19 | 8851677 | 2014 | 10014860 | 11571330 |  |  | COMPLETE | Rebuild 6.6-mile 69 kV line from Longview Heights to Hallsville with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Longview Heights.
50721 | 50721 | BasePlan | #N/A | TP2013167 | #REF! | Yes |  | TP2013167 | 200246 | 30576 | AEP | Line - Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-02 | 2017-06-02 | 2014-06-01 | 2014-02-19 | 15248925 | 2014 | 17252760 | 19751448 |  |  | COMPLETE | Rebuild 11.2-mile 69 kV line from Hallsville to Marshall with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Marshall.
#N/A | 51215 | BasePlan | #N/A | TP2014138 | #REF! | Yes |  | TP2014138 | 200314 | 30895 | AEP | Line - Brooks Street - Edwards Street 69kV Ckt 1 Rebuild | Brooks Street - Edwards Street 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-12-20 | 2017-12-20 | 2016-06-01 | 2015-02-18 | 4294228 | 2015 | 4740025 | 4294228 |  |  | COMPLETE | Rebuild 0.8-mile 69 kV line from Brooks Street to Edwards Street. Upgrade jumpers at both substations.
51033 | 51033 | BasePlan | #N/A | TP2014139 | #REF! | Yes |  | TP2014139 | 200298 | 30761 | AEP | Line - Cedar Grove - South Shreveport 138 kV | Cedar Grove - South Shreveport 138 kV | Transmission Service | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2014-09-30 | 6566218 | 2014 | 7429073 | 6566218 |  |  | ON SCHEDULE < 4 | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove.
#N/A | 51207 | BasePlan | #N/A | TP2014139 | #REF! | Yes |  | TP2014139 | 200406 | 30889 | AEP | Line - Linwood - South Shreveport 138kV Ckt 1 Rebuild | Linwood - South Shreveport 138 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-10 | 2018-05-10 | 2017-06-01 | 2016-08-17 | 5285437 | 2016 | 5691838 | 5919107 |  |  | COMPLETE | Rebuild the 2.4-mile 138kV line from Linwood to Cedar Grove to South Shreveport. Upgrade the jumpers at Linwood.
51034 | 51034 | BasePlan | #N/A | TP2014154 | #REF! | Yes |  | TP2014154 | 200339 | 30762 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | 6629465 | 2015 | 7317689 | 9905114 |  |  | COMPLETE | Rebuild existing 3.2-mile 69 kV line from Ellerbe Road to Lucas.
51035 | 51035 | BasePlan | #N/A | TP2014154 | #REF! | Yes |  | TP2014154 | 200339 | 30762 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Terminal Upgrades | Regional Reliability | 2019-02-27 | 2019-03-01 | 2019-03-01 | 2015-03-17 | 652658 | 2015 | 720412 | 1144751 |  |  | COMPLETE | Replace jumpers at 69 kV substations Ellerbe Road and Lucas. Replace relay panel at Ellerbe Road. Change relay setting at Lucas.
#N/A | 51187 | BasePlan | #N/A | #N/A | #REF! | Yes |  | TP2014207 | 200314 | 30873 | AEP | Line - Southwestern Station - Carnegie 138kV Ckt 1 Rebuild | Southwestern Station - Carnegie 138 kV Ckt 1 Rebuild | Regional Reliability | 2017-07-06 | 2017-07-06 | 2016-06-01 | 2015-02-18 | 15821763 | 2015 | 17464266 | 9397311 |  |  | COMPLETE | Rebuild 16.5-mile 138 kV from Southwestern Station to Carnegie.
50802 | 50802 | BasePlan | TP2015027 | #N/A | #REF! | Yes |  | TP2015027 | 200310 | 30619 | AEP | Line - Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | High Priority | 2017-06-29 | 2017-06-29 | 2015-06-01 | 2014-12-02 | 11652107 | 2014 | 13183289 | 11652107 |  |  | COMPLETE | Construct AEP's portion of new 25-mile 138 kV line from Darlington to Roman Nose (OGE).
50759 | 50759 | BasePlan | #N/A | TP2015106 | #REF! | Yes |  | TP2015106 | 200361 | 30598 | AEP | Device - Letourneau 69 kV Cap Bank | Letourneau 69 kV Cap Bank | Regional Reliability | 2017-06-26 | 2017-06-26 | 2017-06-01 | 2015-12-11 | 1409347 | 2016 | 1517713 | 1409347 |  |  | COMPLETE | Install 16.2-MVAR 69 kV capacitor bank at Letourneau.
#N/A | 51096 |  | #N/A | #N/A | #REF! | No | Need to Add | TP2015118 | 200382 | 30809 | AEP | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2016-04-12 | 4319501 | 2016 | 4651630 | 6445009 |  |  | ON SCHEDULE < 4 | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation.
#N/A | 51454 |  | TP2015191 | #N/A | #REF! | Yes |  | TP2015191 | 200406 | 31009 | AEP | Line - Duncan - Tosco 69 kV Ckt 1 Rebuild (Paula Keefe BPID P15190001) | Duncan - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-04 | 2018-05-04 | 2018-06-01 | 2016-08-17 | 5974766 | 2016 | 6434170 | 5974766 |  |  | COMPLETE | Rebuild 69 kV line from Duncan to Tosco. Replace wave trap at Duncan.
#N/A | 51524 |  | TP2015191 | #N/A | #REF! | Yes |  | TP2015191 | 200406 | 31039 | AEP | Line - Comanche Tap - Tosco 69 kV Ckt 1 Rebuild (Brent Garrett BPID's A11012077&A11012447) | Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2016-12-19 | 2016-12-19 | 2020-06-01 | 2016-08-17 | 4365864 | 2016 | 4701558 | 4365864 |  |  | COMPLETE | Rebuild 69 kV line from Comanche Tap to Tosco.
#N/A | 51433 | BasePlan | TP2015202 | #N/A | #REF! | Yes |  | TP2015202 | 200386 | 30997 | AEP | Device - Sayre 138 kV Cap Bank | Sayre 138 kV Cap Bank | Regional Reliability | 2018-12-19 | 2018-12-31 | 2017-06-01 | 2016-05-17 | 758441 | 2016 | 816758 | 1997360 |  |  | COMPLETE | Install new 14.4-MVAR capacitor bank at Sayre 138 kV.
#N/A | 51561 | BasePlan | TP2015204 | #N/A | #REF! | Yes |  | TP2015204 | 200386 | 31058 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Fort Towson - Kiamichi Pump Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-12-21 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 11778983 | 2016 | 12684677 | 11778983 |  |  | DELAY - MITIGATION | Rebuild 9.0-mile 69 kV line from Fort Towson to Kiamichi Pump Tap.
#N/A | 51562 | BasePlan | TP2015204 | #N/A | #REF! | Yes |  | TP2015204 | 200386 | 31058 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-12-21 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 7699929 | 2016 | 8291982 | 7699929 |  |  | DELAY - MITIGATION | Rebuild 4.8-mile portion of 69 kV line from Kiamichi Pump Tap to Valliant.
#N/A | 51738 | BasePlan | #N/A | TP2017010 | #REF! | Yes |  | TP2017010 | 200431 | 31131 | AEP | Line - Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild | Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild (AEP) | Economic | 2019-05-31 | 2020-01-01 | 2017-01-01 | 2017-02-21 | 4780000 | 2017 | 5021988 | 4780000 |  |  | DELAY - MITIGATION | Rebuild 2.1-mile 161 kV line from Siloam Springs (AEP) - Siloam Springs City (GRDA) and upgrade terminal equipment at Siloam Springs.
#N/A | 61858 | BasePlan | TP2017011 | #N/A | #REF! | Yes |  | TP2017011 | 200446 | 41202 | AEP | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | 2019-12-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 6014381 | 2017 | 6318859 | 6510937 |  |  | DELAY - MITIGATION | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line.
#N/A | 51831 | BasePlan | #N/A | TP2017012 | #REF! | Yes |  | TP2017012 | 200446 | 31186 | AEP | Device - IPC 138 kV Cap Bank | IPC 138 kV Cap Bank | Regional Reliability | 2018-12-13 | 2018-12-01 | 2018-12-01 | 2017-05-12 | 1298048 | 2017 | 1363762 | 1917591 |  |  | COMPLETE | Install 28.8-MVAR capacitor bank at IPC 138 kV
#N/A | 71945 | BasePlan | TP2017016 | #N/A | #REF! | Yes |  | TP2017016 | 200446 | 41233 | AEP | Line - Broken Arrow North - Lynn Lane East 138 kV Ckt 1 | Broken Arrow North - Lynn Lane East 138 kV Ckt 1 Reconductor | Regional Reliability | 2019-03-19 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 5714095 | 2017 | 6003371 | 5714095 |  |  | COMPLETE | Reconductor Broken Arrow - Lynn Lane East 7.2-mile 138 kV line
#N/A | 82137 |  | #N/A | #N/A | #REF! | No | Not Base Plan | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | 2019-08-09 | 2019-02-15 | [5 empty] | 700000 |  |  | ON SCHEDULE < 4 | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation.
#N/A | 82138 |  | #N/A | #N/A | #REF! | No | Not Base Plan | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | 2019-08-09 | 2019-03-31 | [5 empty] | 8700000 |  |  | ON SCHEDULE < 4 | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer.
Formulas:
Q4 2018 Project Owner Indicated ISD = IFNA(VLOOKUP([UID],'Q4 2018 Initial PTP'!$B2:Q61,16,0),"Not Found")

## Q2 2019 Initial PTP (hidden)
Cost Allocation | Superproject | NTC ID | RFP ID | PID | UID | Project Owner | Project Name | Upgrade Name | Project Type | Q4 2018 Project Owner Indicated ISD | Project Owner Indicated In-Service Date | RTO Determined Need Date | Latest NTC Issue Date | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Final Cost Source | Project Status | Project Description/Comments
Zonal | TA2011012 | 200386 |  | 31057 | 51558 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 13512897 | 2016 | 14551912 | 13512897 |  |  | DELAY - MITIGATION | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester.
Zonal | TA2011012 | 200386 |  | 31057 | 51559 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 15146464 | 2016 | 16311085 | 13767520 |  |  | DELAY - MITIGATION | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg.
Zonal | TA2011012 | 200386 |  | 31057 | 51560 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 21668582 | 2016 | 23334693 | 23047526 |  |  | DELAY - MITIGATION | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg.
BasePlan | TA2016806 | 210491 |  | 51300 | 72066 | AEP | Multi - Fig Five - VBI 69kV | Fig Five - VBI North 69kV Ckt 1 | Regional Reliability | Not In Previous Update | 2019-06-01 | 2019-06-01 | 2018-08-17 | 3357600 | 2018 | 3441540 | 3357600 |  |  | ON SCHEDULE < 4 | Rebuild 4.2 miles of 69 kV line from Fig Five to VBI.
BasePlan | TFS/Failure | 200386 |  | 31003 | 51446 | AEP | Sub - Northeastern Station 138 kV Terminal Upgrades | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | 2016-10-05 | 2016-10-05 | 2017-06-01 | 2016-05-17 | 518011 | 2016 | 518011 | 518011 |  |  | COMPLETE | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah.
TBD | TP2006067 | 200272 |  | 30750 | 51017 | AEP | Line - Stonewall - Wapanucka 138 kV Ckt 1 | Stonewall - Wapanucka 138 kV Ckt 1 | High Priority | 2013-12-31 | 2013-12-31 | 2015-06-01 | 2014-05-19 | 8934149 | 2014 | 8716242.9268 | 8934149 | 7200874 | Formula Rate Update | COMPLETE | Construct new 6.4-mile 138 kV line from Stonewall to Wapanucka.
| TP2009089 | 20096 |  | 936 | 11236 | AEP | Line - Valliant - NW Texarkana 345 kV | NORTHWEST TEXARKANA - VALLIANT 345KV CKT 1 | High Priority | 2016-12-16 | 2016-12-16 | 2014-10-01 | 2010-06-30 | 185751250 | 2016 | 185751250 | 185751250 |  |  | COMPLETE | Build a new 76 mile 345 kV line from Valliant to NW Texarkana with at least 3000 A capacity. Upgrade the Valliant and NW Texarkana substations with the necessary breakers and terminal equipment.
BasePlan | TP2009104 | 200216 |  | 504 | 10649 | AEP | Line - Brownlee - North Market 69 kV | Brownlee - North Market 69 kV Ckt 1 | Regional Reliability | 2017-03-22 | 2017-03-22 | 2013-06-01 | 2013-02-20 | 12424849 | 2013 | 13714708.4903 | 17162457 |  |  | COMPLETE | Rebuild 4.7-mile 69 kV line from Brownlee to North Market with 1233.6 ACSR/TW.
| TP2010067 | 200231 |  | 30449 | 50545 | AEP | Line - Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Regional Reliability | 2016-09-19 | 2016-09-19 | 2014-06-01 | 2013-09-23 | 25060655 | 2013 | 26987584.4259 | 25060655 |  |  | COMPLETE | Rebuild 27.6-mile 138 kV line from Rock Hill to Springridge Pan-Harr REC with 1926.9 ACSR/TW conductor.
| TP2010092 | 20104 |  | 947 | 11261 | AEP | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | 2016-05-25 | 2016-05-25 | 2015-06-01 | 2010-08-25 | 6072000 | 2014 | 6379395 | 6072000 |  |  | COMPLETE | Rebuild 4.33 of 795 ACSR with 1590 ACSR.
BasePlan | TP2010094 | 200216 |  | 879 | 11158 | AEP | Line - Bluebell - Prattville 138 kV | Bluebell - Prattville 138 kV Ckt 1 | Regional Reliability | 2015-06-02 | 2015-06-02 | 2014-06-01 | 2013-02-20 | 10241314 | 2013 | 10759780.5212 | 10241314 |  |  | COMPLETE | Rebuild 9.0-mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW.
BasePlan | TP2010100 | 200216 |  | 501 | 10646 | AEP | Line - Evenside - Northwest Henderson 69 kV | Evenside - Northwest Henderson 69 kV Ckt 1 | Regional Reliability | 2018-05-11 | 2018-05-11 | 2018-06-01 | 2013-02-20 | 11980465 | 2013 | 13554796.4952 | 11980465 |  |  | COMPLETE | Rebuild 6.4-mile 69 kV line from Evenside to Northwest Henderson with 1233.6 ACSR/TW. Replace breaker at Evenside.
BasePlan | TP2011022 | 20122 |  | 30298 | 50336 | AEP | Device - Logansport 138 kV | LOGANSPORT 138KV | Regional Reliability | 2016-09-10 | 2016-09-10 | 2016-06-01 | 2011-02-14 | 1166400 | 2014 | 1225449 | 1731419 |  |  | COMPLETE | Install 28.8 MVAR capacitor bank at Logansport 138 kV substation.
BasePlan | TP2011023 | 200167 |  | 503 | 10648 | AEP | Line - Diana - Perdue 138 kV | Diana - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2013-06-01 | 2012-04-09 | 1004187 | 2012 | 1055023.9669 | 1004187 |  |  | COMPLETE | Replace two breakers, jumpers, and wave traps at Perdue substation. Replace wave traps at Diana substation.
BasePlan | TP2011023 | 200216 |  | 30436 | 50531 | AEP | Line - New Gladewater - Perdue 138 kV | New Gladewater - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2016-06-01 | 2013-02-20 | 1000000 | 2013 | 1025000 | 1000000 |  |  | COMPLETE | Replace 138 kV breaker at Perdue.
| TP2011033 | 200231 |  | 30495 | 50607 | AEP | Sub - Messick 500/230 kV | Layfield 500/230 kV Transformer Ckt 1 | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 30369537 | 2013 | 32704669.6809 | 22851755 |  |  | COMPLETE | Build Messick 500/230 kV substation. Connect to Carrol, Clarence, and Western Kraft 230 kV lines. Install 500/230 kV 675 MVA transformer. This upgrade is contingent upon approval from Cleco Power LLC.
| TP2011033 | 200231 |  | 30495 | 50615 | AEP | Sub - Messick 500/230 kV | Layfield 500 kV Terminal Upgrades | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 21508234 | 2013 | 23162015.5549 | 32212715 |  |  | COMPLETE | Install terminal equipment on 500 kV side of new Messick substation. Connect to Mt. Olive - Hartburg 500 kV line. This upgrade is contingent upon approval from Cleco Power LLC for Upgrade ID 50607.
BasePlan | TP2011110 | 200386 |  | 31005 | 51448 | AEP | Sub - Elk City 138 kV Move Load | Elk City 138 kV Move Load | Regional Reliability | 2018-05-25 | 2018-05-25 | 2017-06-01 | 2016-05-17 | 2904911 | 2016 | 3051972.1194 | 2904911 |  |  | COMPLETE | Move load from 69 kV bus to 138 kV bus at Elk City.
BasePlan | TP2011147 | 200216 |  | 451 | 10583 | AEP | Multi - Chamber Springs - Farmington 161 kV | Chamber Springs - Farmington REC 161 kV Ckt 1 | Regional Reliability | 2017-03-28 | 2017-03-28 | 2013-06-01 | 2013-02-20 | 12705537 | 2013 | 14024535.5229 | 12705537 |  |  | COMPLETE | Rebuild and reconductor 11.1-mile 161 kV line from Chamber Springs to Farmington REC with 2-959.6 ACSR/TW. Upgrade wavetraps, CT ratios, and relay settings at Chamber Springs.
BasePlan | TP2011150 | 200255 |  | 30361 | 50413 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm - Gracemont 345kV Ckt 1 (AEP) | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 65082311 | 2017 | 65082311 | 65082311 |  |  | COMPLETE | Build new single circuit 345 kV line from new Chisholm substation to point of interconnection with Oklahoma Gas & Electric Co. (OGE) towards Gracemont. The approximate line length for the Chisholm - Gracemont 345 kV line is 100 miles, of which AEP will construct approximately 70 miles from Chisholm to the OGE interconnection point.
BasePlan | TP2011150 | 200255 |  | 30361 | 50414 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 345/230 kV Substation | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 17471695 | 2017 | 17471695 | 17471695 |  |  | COMPLETE | Construct new 345/230 kV Chisholm substation between existing 230 kV substations, Sweetwater and Elk City. Cut-in existing Sweetwater - Elk City 230 kV Ckt 1 line into new Chisholm substation and install any necessary 230 kV terminal equipment. Install new 345/230 675 MVA transformer at new Chisholm substation.
BasePlan | TP2011150 | 200255 |  | 30361 | 50768 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 230 kV | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 1270623 | 2017 | 1270623 | 1270623 |  |  | COMPLETE | Install approximately 2 miles of 230 kV transmission line for a cut-in to existing 230 kV line from Sweetwater to Elk City, creating termination points at new Chisholm substation.
TBD | TP2012055 | 200272 |  | 30770 | 51047 | AEP | Sub - Ellis 138 kV | Ellis 138 kV Substation | High Priority | 2013-06-01 | 2013-06-01 | 2015-06-01 | 2014-05-19 | 4100000 | 2014 | 4000000 | 4100000 | 4086696 | Formula Rate Update | COMPLETE | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation.
BasePlan | TP2012144 | 200216 |  | 30471 | 50567 | AEP | Line - Dekalb - New Boston 69 kV | Dekalb - New Boston 69 kV Ckt 1 | Regional Reliability | 2015-06-05 | 2015-06-05 | 2013-06-01 | 2013-02-20 | 16548317 | 2013 | 17386075.5481 | 16548317 | 15777911 | Formula Rate Update | COMPLETE | Rebuild 13.2-mile 69 kV line from Dekalb to New Boston with 1233.6 ACSR/TW. Upgrade CT ratios and relay settings at New Boston.
BasePlan | TP2012145 | 200216 |  | 478 | 10615 | AEP | Line - Forbing Tap - South Shreveport 69 kV | Forbing Tap - South Shreveport 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2013-06-01 | 2013-02-20 | 1221505 | 2013 | 1315427.2829 | 1221505 |  |  | COMPLETE | Rebuild 2.3-mile 69 kV line from Forbing to South Shreveport with 1233.6 ACSR/TW.
BasePlan | TP2012145 | 200246 |  | 512 | 10657 | AEP | Line - Ellerbe Road - Forbing Tap 69 kV Ckt 1 | Ellerbe Road - Forbing T 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2014-06-01 | 2014-02-19 | 8174689 | 2014 | 8588532.6306 | 8174689 |  |  | COMPLETE | Rebuild 2.0-mile 69 kV line from Ellerbe Road to Forbing T with 1233.6 ACSR/TW conductor.
BasePlan | TP2012146 | 200216 |  | 30472 | 50568 | AEP | Line - Hardy Street - Waterworks 69 kV | Hardy Street - Waterworks 69 kV Ckt 1 | Regional Reliability | 2015-06-25 | 2015-06-25 | 2013-06-01 | 2013-02-20 | 7519658 | 2013 | 7900340.6862 | 7519658 | 5366606 | Formula Rate Update | COMPLETE | Rebuild 1.6-mile 69 kV line from Hardy Street to Waterworks with 1233.6 ACSR/TW.
BasePlan | TP2012164 | 200216 |  | 30473 | 50569 | AEP | Line - Midland REC - North Huntington 69 kV | Midland REC - North Huntington 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 1829026 | 2013 | 1921620.4412 | 1829026 | 11990487 | Formula Rate Update | COMPLETE | Rebuild 4.0-mile 69 kV line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington.
BasePlan | TP2012164 | 200216 |  | 30474 | 50570 | AEP | Line - Midland - Midland REC 69 kV | Midland - Midland REC 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 5653353 | 2013 | 5939553.9956 | 5653353 | Included in UID 50569 | Formula Rate Update | COMPLETE | Rebuild 1.3-mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland.
BasePlan | TP2012164 | 200216 |  | 30475 | 50571 | AEP | Line - Howe Interchange - Midland 69 kV | Howe Interchange - Midland 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 9145130 | 2013 | 9608102.2062 | 9145130 | Included in UID 50569 | Formula Rate Update | COMPLETE | Rebuild 7.0-mile portion of the 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of line to be rebuilt is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland.
BasePlan | TP2013002 | 200272 |  | 30747 | 51014 | AEP | Line - Grady - Round Creek 138 kV Ckt 1 | Grady - Round Creek 138 kV Ckt 1 | High Priority | 2015-11-05 | 2015-11-05 | 2015-06-01 | 2014-05-19 | 12132497 | 2014 | 12435809.425 | 12132497 |  |  | COMPLETE | Construct new Round Creek box bay tap structure adjacent to the Rush Springs 138 kV substation. Construct new 6-mile 138 kV line from Grady to Round Creek. Install 3-breaker ring bus where hard tap to Round Creek intersects the Cornville to Duncan 138 kV transmission line.
BasePlan | TP2013002 | 200272 |  | 30748 | 51015 | AEP | Line - Grady - Phillips Gas 138 kV Ckt 1 and 2 | Grady - Phillips 138 kV Ckt 1 and 2 | High Priority | 2014-12-31 | 2014-12-31 | 2015-06-01 | 2014-05-19 | 8318584 | 2014 | 8318584 | 8318584 |  |  | COMPLETE | Construct new 4-mile double circuit 138 kV line from the new 4-breaker ring bus station at Grady. Circuit 1 will terminate at Phillips Gas and Circuit 2 will terminate at Lindsey Water Flood.
BasePlan | TP2013081 | 200306 |  | 30731 | 50990 | AEP | Line - Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | Mt Pleasant - West Mt Pleasant 69 kV Ckt 1 Rebuild | Regional Reliability | 2015-04-20 | 2015-04-20 | 2015-06-01 | 2014-11-24 | 4715419 | 2015 | 4715419 | 7381799 |  |  | COMPLETE | Rebuild 2.75-mile 69 kV line from Mt. Pleasant to West Mt. Pleasant to achieve a new emergency rating of 84 MVA.
BasePlan | TP2013122 | 20122 |  | 30296 | 50334 | AEP | Device - Winnsboro 138 kV | WINNSBORO 138KV | Regional Reliability | 2016-04-21 | 2016-04-21 | 2016-06-01 | 2011-02-14 | 1166400 | 2014 | 1225449 | 1166400 |  |  | COMPLETE | Install a new 28.8 MVAR capacitor bank at Winnsboro 138 kV substation.
BasePlan | TP2013165 | 200246 |  | 30573 | 50718 | AEP | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-21 | 2017-06-21 | 2019-06-01 | 2014-02-19 | 6695986 | 2014 | 7210844.5485 | 6695986 |  |  | COMPLETE | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor.
BasePlan | TP2013166 | 200246 |  | 30574 | 50719 | AEP | Line - Daingerfield - Jenkins Rec 69 kV Ckt 1 Rebuild | Daingerfield - Jenkins REC T 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-11-09 | 2017-11-09 | 2019-06-01 | 2014-02-19 | 2819806 | 2014 | 3036622.6457 | 2819806 |  |  | COMPLETE | Rebuild 1.3-mile 69 kV line from Daingerfield to Jenkins REC T with 959.6 ACSR/TW conductor.
BasePlan | TP2013167 | 200246 |  | 30575 | 50720 | AEP | Line - Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-03-02 | 2018-03-02 | 2014-06-01 | 2014-02-19 | 8851677 | 2014 | 9770595.1762 | 11571330 |  |  | COMPLETE | Rebuild 6.6-mile 69 kV line from Longview Heights to Hallsville with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Longview Heights.
BasePlan | TP2013167 | 200246 |  | 30576 | 50721 | AEP | Line - Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-02 | 2017-06-02 | 2014-06-01 | 2014-02-19 | 15248925 | 2014 | 16421424.3738 | 19751448 |  |  | COMPLETE | Rebuild 11.2-mile 69 kV line from Hallsville to Marshall with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Marshall.
BasePlan | TP2014138 | 200314 |  | 30895 | 51215 | AEP | Line - Brooks Street - Edwards Street 69kV Ckt 1 Rebuild | Brooks Street - Edwards Street 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-12-20 | 2017-12-20 | 2016-06-01 | 2015-02-18 | 4294228 | 2015 | 4511623.2925 | 4294228 |  |  | COMPLETE | Rebuild 0.8-mile 69 kV line from Brooks Street to Edwards Street. Upgrade jumpers at both substations.
BasePlan | TP2014139 | 200298 |  | 30761 | 51033 | AEP | Line - Cedar Grove - South Shreveport 138 kV | Cedar Grove - South Shreveport 138 kV | Transmission Service | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2014-09-30 | 6566218 | 2014 | 7429073 | 6566218 |  |  | ON SCHEDULE < 4 | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove.
BasePlan | TP2014139 | 200406 |  | 30889 | 51207 | AEP | Line - Linwood - South Shreveport 138kV Ckt 1 Rebuild | Linwood - South Shreveport 138 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-10 | 2018-05-10 | 2017-06-01 | 2016-08-17 | 5285437 | 2016 | 5553012.2481 | 5919107 |  |  | COMPLETE | Rebuild the 2.4-mile 138kV line from Linwood to Cedar Grove to South Shreveport. Upgrade the jumpers at Linwood.
BasePlan | TP2014154 | 200339 |  | 30762 | 51034 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | 6629465 | 2015 | 7317689 | 9905114 |  |  | ON SCHEDULE < 4 | Rebuild existing 3.2-mile 69 kV line from Ellerbe Road to Lucas.
BasePlan | TP2014154 | 200339 |  | 30762 | 51035 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Terminal Upgrades | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | 652658 | 2015 | 720412 | 1144751 |  |  | ON SCHEDULE < 4 | Replace jumpers at 69 kV substations Ellerbe Road and Lucas. Replace relay panel at Ellerbe Road. Change relay setting at Lucas.
BasePlan | TP2014207 | 200314 |  | 30873 | 51187 | AEP | Line - Southwestern Station - Carnegie 138kV Ckt 1 Rebuild | Southwestern Station - Carnegie 138 kV Ckt 1 Rebuild | Regional Reliability | 2017-07-06 | 2017-07-06 | 2016-06-01 | 2015-02-18 | 15821763 | 2015 | 16622739.7519 | 9397311 |  |  | COMPLETE | Rebuild 16.5-mile 138 kV from Southwestern Station to Carnegie.
BasePlan | TP2015027 | 200310 |  | 30619 | 50802 | AEP | Line - Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | High Priority | 2017-06-29 | 2017-06-29 | 2015-06-01 | 2014-12-02 | 11652107 | 2014 | 12548044.7898 | 11652107 |  |  | COMPLETE | Construct AEP's portion of new 25-mile 138 kV line from Darlington to Roman Nose (OGE).
BasePlan | TP2015106 | 200361 |  | 30598 | 50759 | AEP | Device - Letourneau 69 kV Cap Bank | Letourneau 69 kV Cap Bank | Regional Reliability | 2017-06-26 | 2017-06-26 | 2017-06-01 | 2015-12-11 | 1409347 | 2016 | 1444580.675 | 1409347 |  |  | COMPLETE | Install 16.2-MVAR 69 kV capacitor bank at Letourneau.
| TP2015118 | 200382 |  | 30809 | 51096 | AEP | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2016-04-12 | 4319501 | 2016 | 4651630 | 4319501 |  |  | ON SCHEDULE < 4 | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation.
| TP2015191 | 200406 |  | 31009 | 51454 | AEP | Line - Duncan - Tosco 69 kV Ckt 1 Rebuild | Duncan - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-04 | 2018-05-04 | 2018-06-01 | 2016-08-17 | 5974766 | 2016 | 6277238.5287 | 5974766 |  |  | COMPLETE | Rebuild 69 kV line from Duncan to Tosco. Replace wave trap at Duncan.
| TP2015191 | 200406 |  | 31039 | 51524 | AEP | Line - Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2016-12-19 | 2016-12-19 | 2020-06-01 | 2016-08-17 | 4365864 | 2016 | 4365864 | 4365864 |  |  | COMPLETE | Rebuild 69 kV line from Comanche Tap to Tosco.
BasePlan | TP2015202 | 200386 |  | 30997 | 51433 | AEP | Device - Sayre 138 kV Cap Bank | Sayre 138 kV Cap Bank | Regional Reliability | 2018-12-31 | 2018-12-19 | 2017-06-01 | 2016-05-17 | 758441 | 2016 | 816758 | 1997360 |  |  | DELAY - MITIGATION | Install new 14.4-MVAR capacitor bank at Sayre 138 kV.
BasePlan | TP2015204 | 200386 |  | 31058 | 51561 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Fort Towson - Kiamichi Pump Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 11778983 | 2016 | 12684677 | 11778983 |  |  | DELAY - MITIGATION | Rebuild 9.0-mile 69 kV line from Fort Towson to Kiamichi Pump Tap.
BasePlan | TP2015204 | 200386 |  | 31058 | 51562 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 7699929 | 2016 | 8291982 | 7699929 |  |  | DELAY - MITIGATION | Rebuild 4.8-mile portion of 69 kV line from Kiamichi Pump Tap to Valliant.
BasePlan | TP2017010 | 200431 |  | 31131 | 51738 | AEP | Line - Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild | Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild (AEP) | Economic | 2020-01-01 | 2020-01-01 | 2017-01-01 | 2017-02-21 | 4780000 | 2017 | 5021988 | 4780000 |  |  | DELAY - MITIGATION | Rebuild 2.1-mile 161 kV line from Siloam Springs (AEP) - Siloam Springs City (GRDA) and upgrade terminal equipment at Siloam Springs.
BasePlan | TP2017011 | 200446 |  | 41202 | 61858 | AEP | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 6014381 | 2017 | 6318859 | 6014381 |  |  | DELAY - MITIGATION | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line.
BasePlan | TP2017012 | 200446 |  | 31186 | 51831 | AEP | Device - IPC 138 kV Cap Bank | IPC 138 kV Cap Bank | Regional Reliability | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2017-05-12 | 1298048 | 2017 | 1363762 | 1917591 |  |  | ON SCHEDULE < 4 | Install 28.8-MVAR capacitor bank at IPC 138 kV
BasePlan | TP2017016 | 200446 |  | 41233 | 71945 | AEP | Line - Broken Arrow North - Lynn Lane East 138 kV Ckt 1 | Broken Arrow North - Lynn Lane East 138 kV Ckt 1 Reconductor | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 5714095 | 2017 | 6003371 | 5714095 |  |  | DELAY - MITIGATION | Reconductor Broken Arrow - Lynn Lane East 7.2-mile 138 kV line
| TP2017247 |  |  | 51337 | 82137 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | 2019-02-15 | 2019-02-15 | [5 empty] | 700000 |  |  | ON SCHEDULE < 4 | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation.
| TP2017247 |  |  | 51337 | 82138 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | 2019-03-31 | 2019-03-31 | [5 empty] | 8700000 |  |  | ON SCHEDULE < 4 | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer.
Formulas:
Q4 2018 Project Owner Indicated ISD = IFNA(VLOOKUP([UID],'Q4 2018 Initial PTP'!$B1:AJ61,16,0),"Not In Previous Update")

## Q4 2018 Initial PTP (hidden)
UID Lookup | UID | Cost Allocation | PSO Super Lookup | SWEPCO Super Lookup | OKTCO Super Lookup | Found? | Verified? | Superproject | NTC ID | PID | Project Owner | Project Name | Upgrade Name | Project Type | Q2 2019 Project Owner Indicated ISD | Project Owner Indicated In-Service Date | RTO Determined Need Date | Latest NTC Issue Date | NTC Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Final Cost Source | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion
#N/A | 51558 | Zonal | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (A11012198&A11012075) | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 13512897 | 2016 | 14196987 | 13512897 |  |  | DELAY - MITIGATION | 510912 | ARMY AMMUNITION DEPOT | 510899 | McALESTER 69KV | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester. | 69
#N/A | 51559 | Zonal | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (A11012444) | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15146464 | 2016 | 15913253 | 13767520 |  |  | DELAY - MITIGATION | 510912 | ARMY AMMUNITION DEPOT | 510885 | PITTSBURG 69KV | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg. | 69
#N/A | 51560 | Zonal | #N/A | #N/A | #REF! | No | Zonal | TA2011012 | 200386 | 31057 | AEP | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild (A11012445&46) | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2019-12-31 | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668582 | 2016 | 22765554 | 23047526 |  |  | DELAY - MITIGATION | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69
#N/A | 51446 | Base Plan | TP2015169 | #N/A | #REF! | Yes |  | TP2015169 | 200386 | 31003 | AEP | Sub - Northeastern Station 138 kV Terminal Upgrades (WO T0176861) | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | 2016-10-05 | 2016-10-05 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 518011 | 2016 | 544235 | 518011 |  |  | COMPLETE | 510396 | NORTHEAST STATION 138KV |  |  | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah. | 138
51017 | 51017 | TBD | #N/A | #N/A | #REF! | Yes |  | TP2012141 | 200272 | 30750 | AEP | Line - Stonewall - Wapanucka 138 kV Ckt 1 | Stonewall - Wapanucka 138 kV Ckt 1 | High Priority | 2013-12-31 | 2013-12-31 | 2015-06-01 | 2014-05-19 | HPILS | 8934149 | 2014 | 9861629 | 8934149 | 7200874 | Formula Rate Update | COMPLETE | 521075 |  | 510949 |  | Construct new 6.4-mile 138 kV line from Stonewall to Wapanucka. | 138 | 6.4
11236 | 11236 |  | TP2009089 | TP2009089 | #REF! | Yes |  | TP2009089 | 20096 | 936 | AEP | Line - Valliant - NW Texarkana 345 kV | NORTHWEST TEXARKANA - VALLIANT 345KV CKT 1 | High Priority | 2016-12-16 | 2016-12-16 | 2014-10-01 | 2010-06-30 | Priority Projects | 185751250 | 2016 | 195154907 | 185751250 |  |  | COMPLETE | 510911 | VALLIANT 345KV | 508072 | NORTHWEST TEXARKANA 345KV | Build a new 76 mile 345 kV line from Valliant to NW Texarkana with at least 3000 A capacity. Upgrade the Valliant and NW Texarkana substations with the necessary breakers and terminal equipment. | 345 | 76.25
10649 | 10649 | Base Plan | #N/A | TP2009104 | #REF! | Yes |  | TP2009104 | 200216 | 504 | AEP | Line - Brownlee - North Market 69 kV | Brownlee - North Market 69 kV Ckt 1 | Regional Reliability | 2017-03-22 | 2017-03-22 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 12424849 | 2013 | 14057576 | 17162457 |  |  | COMPLETE | 507718 | BROWNLEE | 507745 | NORTH MARKET | Rebuild 4.7-mile 69 kV line from Brownlee to North Market with 1233.6 ACSR/TW. | 69 | 4.7
50545 | 50545 |  | #N/A | TP2010067 | #REF! | Yes |  | TP2010067 | 200231 | 30449 | AEP | Line - Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Regional Reliability | 2016-09-19 | 2016-09-19 | 2014-06-01 | 2013-09-23 | 2013 ITPNT | 25060655 | 2013 | 28353831 | 25060655 |  |  | COMPLETE | 509083 | ROCK HILL 138 | 507757 | SPRINGRIDGE PAN-HARR REC | Rebuild 27.6-mile 138 kV line from Rock Hill to Springridge Pan-Harr REC with 1926.9 ACSR/TW conductor. | 138 | 27.6
11261 | 11261 |  | #N/A | #N/A | #REF! | No | Direct Assigned | TP2010092 | 20104 | 947 | AEP | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | 2016-05-25 | 2016-05-25 | 2015-06-01 | 2010-08-25 | SPP-2008-AGP1-AFS-9 | 6072000 | 2014 | 6702352 | 6072000 |  |  | COMPLETE | 509806 | ONETA 138KV | 509786 | BROKEN ARROW NORTH - SOUTH TAP | Rebuild 4.33 of 795 ACSR with 1590 ACSR. | 138 |  | 4.33
11158 | 11158 | Base Plan | #N/A | #N/A | #REF! | Yes |  | TP2010094 | 200216 | 879 | AEP | Line - Bluebell - Prattville 138 kV | Bluebell - Prattville 138 kV Ckt 1 | Regional Reliability | 2015-06-02 | 2015-06-02 | 2014-06-01 | 2013-02-20 | 2013 ITPNT | 10241314 | 2013 | 11587107 | 10241314 |  |  | COMPLETE | 515242 | BLUEBELL 138 | 509758 | PRATTVILLE | Rebuild 9.0-mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW. | 138 |  | 9
10646 | 10646 | Base Plan | #N/A | TP2010100 | #REF! | Yes |  | TP2010100 | 200216 | 501 | AEP | Line - Evenside - Northwest Henderson 69 kV | Evenside - Northwest Henderson 69 kV Ckt 1 | Regional Reliability | 2018-05-11 | 2018-05-11 | 2018-06-01 | 2013-02-20 | 2013 ITPNT | 11980465 | 2013 | 13554796 | 11980465 |  |  | ON SCHEDULE < 4 | 509061 | EVENSIDE | 509075 | NORTHWEST HENDERSON 69KV | Rebuild 6.4-mile 69 kV line from Evenside to Northwest Henderson with 1233.6 ACSR/TW. Replace breaker at Evenside. | 69 |  | 6.4
50336 | 50336 | Base Plan | #N/A | TP2011022 | #REF! | Yes |  | TP2011022 | 20122 | 30298 | AEP | Device - Logansport 138 kV | LOGANSPORT 138KV | Regional Reliability | 2016-09-10 | 2016-09-10 | 2016-06-01 | 2011-02-14 | 2010 STEP | 1166400 | 2014 | 1287487 | 1731419 |  |  | COMPLETE | 509071 | LOGANSPORT 138KV |  |  | Install 28.8 MVAR capacitor bank at Logansport 138 kV substation. | 138
10648 | 10648 | Base Plan | #N/A | TP2011023 | #REF! | Yes |  | TP2011023 | 200167 | 503 | AEP | Line - Diana - Perdue 138 kV | Diana - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2013-06-01 | 2012-04-09 | 2012 ITPNT | 1004187 | 2012 | 1164549 | 1004187 |  |  | COMPLETE | 508351 | PERDUE 138KV | 508831 | DIANA 138KV | Replace two breakers, jumpers, and wave traps at Perdue substation. Replace wave traps at Diana substation. | 138
50531 | 50531 | Base Plan | #N/A | TP2011023 | #REF! | Yes |  | TP2011023 | 200216 | 30436 | AEP | Line - New Gladewater - Perdue 138 kV | New Gladewater - Perdue 138 kV Ckt 1 | Regional Reliability | 2014-12-31 | 2014-12-31 | 2016-06-01 | 2013-02-20 | 2013 ITPNT | 1000000 | 2013 | 1131408 | 1000000 |  |  | COMPLETE | 508560 | NEW GLADEWATER | 508351 | PERDUE 138KV | Replace 138 kV breaker at Perdue. | 138
50607 | 50607 |  | #N/A | TP2011033 | #REF! | Yes |  | TP2011033 | 200231 | 30495 | AEP | Sub - Messick 500/230 kV | Layfield 500/230 kV Transformer Ckt 1 | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 2013 ITPNT | 30369537 | 2013 | 34360344 | 22851755 |  |  | COMPLETE | 999113 | Messick 500 kV | 999114 |  | Build Messick 500/230 kV substation. Connect to Carrol, Clarence, and Western Kraft 230 kV lines. Install 500/230 kV 675 MVA transformer. This upgrade is contingent upon approval from Cleco Power LLC. | 500/230
50615 | 50615 |  | #N/A | TP2011033 | #REF! | Yes |  | TP2011033 | 200231 | 30495 | AEP | Sub - Messick 500/230 kV | Layfield 500 kV Terminal Upgrades | Regional Reliability | 2016-04-29 | 2016-04-29 | 2013-06-01 | 2013-09-23 | 2013 ITPNT | 21508234 | 2013 | 24334593 | 32212715 |  |  | COMPLETE | 999113 | Messick 500 kV |  |  | Install terminal equipment on 500 kV side of new Messick substation. Connect to Mt. Olive - Hartburg 500 kV line. This upgrade is contingent upon approval from Cleco Power LLC for Upgrade ID 50607. | 500
#N/A | 51448 | Base Plan | TP2011110 | #N/A | #REF! | Yes |  | TP2011110 | 200386 | 31005 | AEP | Sub - Elk City 138 kV Move Load (BPID P11110001) | Elk City 138 kV Move Load | Regional Reliability | 2018-05-25 | 2018-05-25 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2904911 | 2016 | 3051972 | 2904911 |  |  | DELAY - MITIGATION | 511458 | ELK CITY 138 | 511459 | ELK CITY 69 | Move load from 69 kV bus to 138 kV bus at Elk City. | 138
10583 | 10583 | Base Plan | #N/A | TP2011147 | #REF! | Yes |  | TP2011147 | 200216 | 451 | AEP | Multi - Chamber Springs - Farmington 161 kV | Chamber Springs - Farmington REC 161 kV Ckt 1 | Regional Reliability | 2017-03-28 | 2017-03-28 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 12705537 | 2013 | 14375149 | 12705537 |  |  | COMPLETE | 506944 | CHAMBER SPRINGS 161KV | 504020 | FARMINGTON AECC | Rebuild and reconductor 11.1-mile 161 kV line from Chamber Springs to Farmington REC with 2-959.6 ACSR/TW. Upgrade wavetraps, CT ratios, and relay settings at Chamber Springs. | 161 |  | 11.1
50413 | 50413 | Base Plan | #N/A | #N/A | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm - Gracemont 345kV Ckt 1 (AEP) | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 65082311 | 2017 | 66709369 | 65082311 |  |  | COMPLETE | 700345 | Chisholm 345 kV | 515800 | Gracemont 345kv | Build new single circuit 345 kV line from new Chisholm substation to point of interconnection with Oklahoma Gas & Electric Co. (OGE) towards Gracemont. The approximate line length for the Chisholm - Gracemont 345 kV line is 100 miles, of which AEP will construct approximately 70 miles from Chisholm to the OGE interconnection point. | 345 | 72
50414 | 50414 | Base Plan | #N/A | #N/A | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 345/230 kV Substation | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 17471695 | 2017 | 17908487 | 17471695 |  |  | COMPLETE | 700345 | Chisholm 345 kV | 700231 | Chisholm 230 kV | Construct new 345/230 kV Chisholm substation between existing 230 kV substations, Sweetwater and Elk City. Cut-in existing Sweetwater - Elk City 230 kV Ckt 1 line into new Chisholm substation and install any necessary 230 kV terminal equipment. Install new 345/230 675 MVA transformer at new Chisholm substation. | 345/230
50768 | 50768 | Base Plan | #N/A | #N/A | #REF! | Yes |  | TP2011150 | 200255 | 30361 | AEP | Multi - Chisholm - Gracemont 345 kV | Chisholm 230 kV | Regional Reliability | 2017-12-07 | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 1270623 | 2017 | 1302389 | 1270623 |  |  | COMPLETE | 700345 | Chisholm 345 kV |  |  | Install approximately 2 miles of 230 kV transmission line for a cut-in to existing 230 kV line from Sweetwater to Elk City, creating termination points at new Chisholm substation. | 230 | 2
51047 | 51047 | TBD | #N/A | #N/A | #REF! | Yes |  | TP2012055 | 200272 | 30770 | AEP | Sub - Ellis 138 kV | Ellis 138 kV Substation | High Priority | 2013-06-01 | 2013-06-01 | 2015-06-01 | 2014-05-19 | HPILS | 4100000 | 2014 | 4525633 | 4100000 | 4086696 | Formula Rate Update | COMPLETE | 511561 |  | 521001 | MOREWOOD SW | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation. | 138
50567 | 50567 | Base Plan | #N/A | TP2012144 | #REF! | Yes |  | TP2012144 | 200216 | 30471 | AEP | Line - Dekalb - New Boston 69 kV | Dekalb - New Boston 69 kV Ckt 1 | Regional Reliability | 2015-06-05 | 2015-06-05 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 16548317 | 2013 | 18722901 | 16548317 | 15777911 | Formula Rate Update | COMPLETE | 508067 | NEW BOSTON | 508289 | DEKALB | Rebuild 13.2-mile 69 kV line from Dekalb to New Boston with 1233.6 ACSR/TW. Upgrade CT ratios and relay settings at New Boston. | 69 | 13.2
10615 | 10615 | Base Plan | #N/A | TP2012145 | #REF! | Yes |  | TP2012145 | 200216 | 478 | AEP | Line - Forbing Tap - South Shreveport 69 kV | Forbing Tap - South Shreveport 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 1221505 | 2013 | 1382021 | 1221505 |  |  | COMPLETE | 507728 | FORBING TAP | 507754 | SOUTH SHREVEPORT 69KV | Rebuild 2.3-mile 69 kV line from Forbing to South Shreveport with 1233.6 ACSR/TW. | 69 |  | 2.3
10657 | 10657 | Base Plan | #N/A | TP2012145 | #REF! | Yes |  | TP2012145 | 200246 | 512 | AEP | Line - Ellerbe Road - Forbing Tap 69 kV Ckt 1 | Ellerbe Road - Forbing T 69 kV Ckt 1 | Regional Reliability | 2016-04-13 | 2016-04-13 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 8174689 | 2014 | 9023327 | 8174689 |  |  | COMPLETE | 507723 | ELLERBE ROAD 69 kV | 507728 | FORBING TAP | Rebuild 2.0-mile 69 kV line from Ellerbe Road to Forbing T with 1233.6 ACSR/TW conductor. | 69 | 2
50568 | 50568 | Base Plan | #N/A | TP2012146 | #REF! | Yes |  | TP2012146 | 200216 | 30472 | AEP | Line - Hardy Street - Waterworks 69 kV | Hardy Street - Waterworks 69 kV Ckt 1 | Regional Reliability | 2015-06-25 | 2015-06-25 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 7519658 | 2013 | 8507803 | 7519658 | 5366606 | Formula Rate Update | COMPLETE | 507734 | HARDY STREET | 507766 | WATERWORKS | Rebuild 1.6-mile 69 kV line from Hardy Street to Waterworks with 1233.6 ACSR/TW. | 69 | 1.65
50569 | 50569 | Base Plan | #N/A | TP2012164 | #REF! | Yes |  | TP2012164 | 200216 | 30473 | AEP | Line - Midland REC - North Huntington 69 kV | Midland REC - North Huntington 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 1829026 | 2013 | 2069375 | 1829026 | 11990487 | Formula Rate Update | COMPLETE | 507196 | MIDLAND REC | 507188 | NORTH HUNTINGTON 69KV | Rebuild 4.0-mile 69 kV line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington. | 69 | 1.3
50570 | 50570 | Base Plan | #N/A | TP2012164 | #REF! | Yes |  | TP2012164 | 200216 | 30474 | AEP | Line - Midland - Midland REC 69 kV | Midland - Midland REC 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 5653353 | 2013 | 6396250 | 5653353 | Included in UID 50569 | Formula Rate Update | COMPLETE | 507187 | MIDLAND | 507196 | MIDLAND REC | Rebuild 1.3-mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | 69 | 4.3
50571 | 50571 | Base Plan | #N/A | TP2012164 | #REF! | Yes |  | TP2012164 | 200216 | 30475 | AEP | Line - Howe Interchange - Midland 69 kV | Howe Interchange - Midland 69 kV Ckt 1 | Regional Reliability | 2015-05-15 | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 9145130 | 2013 | 10346875 | 9145130 | Included in UID 50569 | Formula Rate Update | COMPLETE | 515259 | HOWE INT 69 | 507187 | MIDLAND | Rebuild 7.0-mile portion of the 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of line to be rebuilt is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | 69 | 7
51014 | 51014 | Base Plan | TP2013002 | #N/A | #REF! | Yes |  | TP2013002 | 200272 | 30747 | AEP | Line - Grady - Round Creek 138 kV Ckt 1 | Grady - Round Creek 138 kV Ckt 1 | High Priority | 2015-11-05 | 2015-11-05 | 2015-06-01 | 2014-05-19 | HPILS | 12132497 | 2014 | 13392006 | 12132497 |  |  | COMPLETE | 511560 |  | 511427 | RUSH SPRINGS NATURAL GAS | Construct new Round Creek box bay tap structure adjacent to the Rush Springs 138 kV substation. Construct new 6-mile 138 kV line from Grady to Round Creek. Install 3-breaker ring bus where hard tap to Round Creek intersects the Cornville to Duncan 138 kV transmission line. | 138
51015 | 51015 | Base Plan | TP2013002 | #N/A | #REF! | Yes |  | TP2013002 | 200272 | 30748 | AEP | Line - Grady - Phillips Gas 138 kV Ckt 1 and 2 | Grady - Phillips 138 kV Ckt 1 and 2 | High Priority | 2014-12-31 | 2014-12-31 | 2015-06-01 | 2014-05-19 | HPILS | 8318584 | 2014 | 9182160 | 8318584 |  |  | COMPLETE | 511514 | PHILLIPS | 511560 |  | Construct new 4-mile double circuit 138 kV line from the new 4-breaker ring bus station at Grady. Circuit 1 will terminate at Phillips Gas and Circuit 2 will terminate at Lindsey Water Flood. | 138 | 4
50990 | 50990 | Base Plan | #N/A | TP2013081 | #REF! | Yes |  | TP2013081 | 200306 | 30731 | AEP | Line - Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | Mt Pleasant - West Mt Pleasant 69 kV Ckt 1 Rebuild | Regional Reliability | 2015-04-20 | 2015-04-20 | 2015-06-01 | 2014-11-24 | DPA-2013-SEP-351 | 4715419 | 2015 | 5077991 | 7381799 |  |  | COMPLETE |  |  |  |  | Rebuild 2.75-mile 69 kV line from Mt. Pleasant to West Mt. Pleasant to achieve a new emergency rating of 84 MVA. | 69 |  | 2.72
50334 | 50334 | Base Plan | #N/A | TP2013122 | #REF! | Yes |  | TP2013122 | 20122 | 30296 | AEP | Device - Winnsboro 138 kV | WINNSBORO 138KV | Regional Reliability | 2016-04-21 | 2016-04-21 | 2016-06-01 | 2011-02-14 | 2010 STEP | 1166400 | 2014 | 1287487 | 1166400 |  |  | COMPLETE | 508317 | Winnsboro 138 kV |  |  | Install a new 28.8 MVAR capacitor bank at Winnsboro 138 kV substation. | 138
50718 | 50718 | Base Plan | #N/A | TP2013165 | #REF! | Yes |  | TP2013165 | 200246 | 30573 | AEP | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-21 | 2017-06-21 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 6695986 | 2014 | 7391116 | 6695986 |  |  | COMPLETE | 507716 | BROADMOOR | 507730 | FORT HUMBUG 69KV | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor. | 69 |  | 1.7
50719 | 50719 | Base Plan | #N/A | TP2013166 | #REF! | Yes |  | TP2013166 | 200246 | 30574 | AEP | Line - Daingerfield - Jenkins Rec 69 kV Ckt 1 Rebuild | Daingerfield - Jenkins REC T 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-11-09 | 2017-11-09 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 2819806 | 2014 | 3112538 | 2819806 |  |  | COMPLETE | 508288 | DAINGERFIELD | 508293 | JENKINS REC T | Rebuild 1.3-mile 69 kV line from Daingerfield to Jenkins REC T with 959.6 ACSR/TW conductor. | 69 |  | 1.3
50720 | 50720 | Base Plan | #N/A | TP2013167 | #REF! | Yes |  | TP2013167 | 200246 | 30575 | AEP | Line - Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-03-02 | 2018-03-02 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 8851677 | 2014 | 9770595 | 11571330 |  |  | COMPLETE | 508543 | HALLSVILLE | 508553 | LONGVIEW HEIGHTS 69KV | Rebuild 6.6-mile 69 kV line from Longview Heights to Hallsville with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Longview Heights. | 69 |  | 6.6
50721 | 50721 | Base Plan | #N/A | TP2013167 | #REF! | Yes |  | TP2013167 | 200246 | 30576 | AEP | Line - Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-06-02 | 2017-06-02 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 15248925 | 2014 | 16831960 | 19751448 |  |  | COMPLETE | 508556 | MARSHALL 69KV | 508543 | HALLSVILLE | Rebuild 11.2-mile 69 kV line from Hallsville to Marshall with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Marshall. | 69 |  | 11.2
11423 | 11423 | Base Plan | #N/A | #N/A | #REF! | No | Suspended | TP2013169 | 200305 | 1083 | AEP | Line - Welsh Reserve - Wilkes 138 kV Ckt 1 | Welsh Reserve - Wilkes 138 kV Ckt 1 Rebuild | Regional Reliability | Not Found in Future | 2019-06-01 | 2019-06-01 | 2014-09-30 | 2014 ITPNT | 24880495 | 2014 | 27463411 | 24880495 |  |  | RE-EVALUATION | 508355 | Welsh Reserve 138 kV | 508840 | WILKES 138KV | Rebuild 23.7-mile 138 kV line from Welsh Reserve to Wilkes with 1926.9 ACSR/TW conductor. Upgrade switches at Welsh Reserve and Wilkes and wave traps, jumpers, CT ratios, and relay settings at Wilkes. | 138 |  | 23.74
50697 | 50697 | Base Plan | #N/A | #N/A | #REF! | No | Suspended | TP2013169 | 200246 | 30559 | AEP | Line - Chapel Hill REC - Welsh Reserve 138 kV Ckt 1 | Chapel Hill REC - Welsh Reserve 138 kV Ckt 1 Rebuild | Regional Reliability | Not Found in Future | 2019-06-01 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 6651694 | 2014 | 7342226 | 6651694 |  |  | RE-EVALUATION | 508337 | CHAPEL HILL REC | 508355 | Welsh Reserve 138 kV | Rebuild 4.4-mile 138 kV line from Chapel Hill REC to Welsh Reserve. | 138 |  | 4.39
#N/A | 51215 | Base Plan | #N/A | TP2014138 | #REF! | Yes |  | TP2014138 | 200314 | 30895 | AEP | Line - Brooks Street - Edwards Street 69kV Ckt 1 Rebuild | Brooks Street - Edwards Street 69 kV Ckt 1 Rebuild | Regional Reliability | 2017-12-20 | 2017-12-20 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 4294228 | 2015 | 4624414 | 4294228 |  |  | COMPLETE | 507717 | BROOKS STREET | 507722 | EDWARDS STREET | Rebuild 0.8-mile 69 kV line from Brooks Street to Edwards Street. Upgrade jumpers at both substations. | 69 |  | 0.85
51033 | 51033 | Base Plan | #N/A | TP2014139 | #REF! | Yes |  | TP2014139 | 200298 | 30761 | AEP | Line - Cedar Grove - South Shreveport 138 kV | Cedar Grove - South Shreveport 138 kV | Transmission Service | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2014-09-30 | SPP-2010-AGP1-AFS-8 | 6566218 | 2014 | 7247876 | 6566218 |  |  | ON SCHEDULE < 4 | 507771 | CEDARGROVE | 507755 | SOUTH SHREVEPORT 138KV | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove. | 138
#N/A | 51207 | Base Plan | #N/A | TP2014139 | #REF! | Yes |  | TP2014139 | 200406 | 30889 | AEP | Line - Linwood - South Shreveport 138kV Ckt 1 Rebuild | Linwood - South Shreveport 138 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-10 | 2018-05-10 | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 5285437 | 2016 | 5553013 | 5919107 |  |  | DELAY - MITIGATION | 507738 | LINWOOD | 507771 | CEDARGROVE | Rebuild the 2.4-mile 138kV line from Linwood to Cedar Grove to South Shreveport. Upgrade the jumpers at Linwood. | 138 |  | 2.42
51034 | 51034 | Base Plan | #N/A | #N/A | #REF! | No | Need to Add | TP2014154 | 200339 | 30762 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | DPA-2013-MAR-296 | 6629465 | 2015 | 7139209 | 6629465 |  |  | ON SCHEDULE < 4 | 507723 | ELLERBE ROAD 69 kV | 507739 | LUCAS | Rebuild existing 3.2-mile 69 kV line from Ellerbe Road to Lucas. | 69 | 3.2
51035 | 51035 | Base Plan | #N/A | #N/A | #REF! | No | Need to Add | TP2014154 | 200339 | 30762 | AEP | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Terminal Upgrades | Regional Reliability | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2015-03-17 | DPA-2013-MAR-296 | 652658 | 2015 | 702841 | 652658 |  |  | ON SCHEDULE < 4 | 507723 | ELLERBE ROAD 69 kV |  |  | Replace jumpers at 69 kV substations Ellerbe Road and Lucas. Replace relay panel at Ellerbe Road. Change relay setting at Lucas. | 69
#N/A | 51187 | Base Plan | #N/A | #N/A | #REF! | Yes |  | TP2014207 | 200314 | 30873 | AEP | Line - Southwestern Station - Carnegie 138kV Ckt 1 Rebuild | Southwestern Station - Carnegie 138 kV Ckt 1 Rebuild | Regional Reliability | 2017-07-06 | 2017-07-06 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 15821763 | 2015 | 17038308 | 9397311 |  |  | COMPLETE | 511477 | SOUTHWESTERN STATION 138KV | 511445 | CARNEGIE | Rebuild 16.5-mile 138 kV from Southwestern Station to Carnegie. | 138 |  | 16.52 | 138
50802 | 50802 | Base Plan | TP2015027 | #N/A | #REF! | Yes |  | TP2015027 | 200310 | 30619 | AEP | Line - Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | High Priority | 2017-06-29 | 2017-06-29 | 2015-06-01 | 2014-12-02 | HPILS | 11652107 | 2014 | 12861746 | 11652107 |  |  | COMPLETE | 511559 |  | 514823 | ROMAN NOSE 138 | Construct AEP's portion of new 25-mile 138 kV line from Darlington to Roman Nose (OGE). | 138 | 14.25
50759 | 50759 | Base Plan | #N/A | TP2015106 | #REF! | Yes |  | TP2015106 | 200361 | 30598 | AEP | Device - Letourneau 69 kV Cap Bank | Letourneau 69 kV Cap Bank | Regional Reliability | 2017-06-26 | 2017-06-26 | 2017-06-01 | 2015-12-11 | 2016 ITPNT | 1409347 | 2016 | 1480696 | 1409347 |  |  | COMPLETE | 508536 | LETOURNEAU STEEL | 508594 | Letouteau W tap 69 kV | Install 16.2-MVAR 69 kV capacitor bank at Letourneau. | 69
#N/A | 51096 |  | #N/A | #N/A | #REF! | No | No 2018-2019 Forecast | TP2015118 | 200382 | 30809 | AEP | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2016-04-12 | SPP-2014-AG1-AFS-6 | 4319501 | 2016 | 4538176 | 4319501 |  |  | ON SCHEDULE < 4 | 505610 | Keystone Dam | 509757 | WEKIWA 138KV | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation. | 138 | 2 | 2 | 2
#N/A | 51454 |  | TP2015191 | #N/A | #REF! | Yes |  | TP2015191 | 200406 | 31009 | AEP | Line - Duncan - Tosco 69 kV Ckt 1 Rebuild (Paula Keefe BPID P151910001) | Duncan - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-05-04 | 2018-05-04 | 2018-06-01 | 2016-08-17 | 2016 ITPNT | 5974766 | 2016 | 6277239 | 5974766 |  |  | DELAY - MITIGATION | 511452 | DUNCAN 69KV | 511457 | TOSCO 69KV | Rebuild 69 kV line from Duncan to Tosco. Replace wave trap at Duncan. | 69 | 3.86 | 3.86 | 69
#N/A | 51524 |  | TP2015191 | #N/A | #REF! | Yes |  | TP2015191 | 200406 | 31039 | AEP | Line - Comanche Tap - Tosco 69 kV Ckt 1 Rebuild (Brent Garret BPID's A11012077&A11012447) | Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | 2016-12-19 | 2016-12-19 | 2020-06-01 | 2016-08-17 | 2016 ITPNT | 4365864 | 2016 | 4586886 | 4365864 |  |  | COMPLETE | 511498 | COMANCHE TAP 69KV | 511457 | TOSCO 69KV | Rebuild 69 kV line from Comanche Tap to Tosco. | 69 | 3.2 | 3.2 | 69
#N/A | 51433 | Base Plan | TP2015202 | #N/A | #REF! | Yes |  | TP2015202 | 200386 | 30997 | AEP | Device - Sayre 138 kV Cap Bank | Sayre 138 kV Cap Bank | Regional Reliability | 2018-12-19 | 2018-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 758441 | 2016 | 796837 | 1483426 |  |  | DELAY - MITIGATION | 511504 | SAYRE |  |  | Install new 14.4-MVAR capacitor bank at Sayre 138 kV. | 138
#N/A | 51561 | Base Plan | TP2015204 | #N/A | #REF! | Yes |  | TP2015204 | 200386 | 31058 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Fort Towson - Kiamichi Pump Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 2016 ITPNT | 11778983 | 2016 | 12375294 | 11778983 |  |  | DELAY - MITIGATION | 510876 | KIAMICHI PUMP TAP | 510917 | FORT TOWSON | Rebuild 9.0-mile 69 kV line from Fort Towson to Kiamichi Pump Tap. | 69
#N/A | 51562 | Base Plan | TP2015204 | #N/A | #REF! | Yes |  | TP2015204 | 200386 | 31058 | AEP | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2016-05-17 | 2016 ITPNT | 7699929 | 2016 | 8089738 | 7699929 |  |  | DELAY - MITIGATION | 510876 | KIAMICHI PUMP TAP | 510910 | VALLIANT 69KV | Rebuild 4.8-mile portion of 69 kV line from Kiamichi Pump Tap to Valliant. | 69
#N/A | 51738 | Base Plan | #N/A | #N/A | #REF! | No | Need to Add | TP2017010 | 200431 | 31131 | AEP | Line - Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild | Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild (AEP) | Economic | 2020-01-01 | 2020-01-01 | 2017-01-01 | 2017-02-21 | 2017 ITP10 | 4780000 | 2017 | 4899500 | 4780000 |  |  | DELAY - MITIGATION | 506948 | SILOAM SPRINGS | 512643 | SILOAM CITY 161 | Rebuild 2.1-mile 161 kV line from Siloam Springs (AEP) - Siloam Springs City (GRDA) and upgrade terminal equipment at Siloam Springs. | 161
#N/A | 61858 | Base Plan | TP2017011 | #N/A | #REF! | No | Need to Add | TP2017011 | 200446 | 41202 | AEP | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 6014381 | 2017 | 6164741 | 6014381 |  |  | DELAY - MITIGATION | 509811 | TULSA SOUTHEAST 138KV | 509831 | EAST 61st STREET | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line. | 138 | 1.8
#N/A | 51831 | Base Plan | #N/A | TP2017012 | #REF! | Yes |  | TP2017012 | 200446 | 31186 | AEP | Device - IPC 138 kV Cap Bank | IPC 138 kV Cap Bank | Regional Reliability | 2018-12-13 | 2018-12-01 | 2018-12-01 | 2017-05-12 | 2017 ITPNT | 1298048 | 2017 | 1330499 | 1917591 |  |  | ON SCHEDULE < 4 |  |  |  |  | Install 28.8-MVAR capacitor bank at IPC 138 kV | 138
#N/A | 71945 | Base Plan | TP2017016 | #N/A | #REF! | No | Need to Add | TP2017016 | 200446 | 41233 | AEP | Line - Broken Arrow North - Lynn Lane East 138 kV Ckt 1 | Broken Arrow North - Lynn Lane East 138 kV Ckt 1 Reconductor | Regional Reliability | 2019-06-01 | 2019-06-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 5714095 | 2017 | 5856947 | 5714095 |  |  | DELAY - MITIGATION | 509786 | BROKEN ARROW NORTH - SOUTH TAP | 509804 | LYNN LANE TAP | Reconductor Broken Arrow - Lynn Lane East 7.2-mile 138 kV line | 138 |  | 7.13
#N/A | 82137 |  | #N/A | #N/A | #REF! | No | Not Base Plan | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | 2019-02-15 | 2019-02-15 | [6 empty] | 700000 |  |  | ON SCHEDULE < 4 |  |  |  |  | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation.
#N/A | 82138 |  | #N/A | #N/A | #REF! | No | Not Base Plan | TP2017247 |  | 51337 | AEP | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | 2019-03-31 | 2019-03-31 | [6 empty] | 8700000 |  |  | ON SCHEDULE < 4 |  |  |  |  | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer.
10001 | 10001 |  | #N/A | #N/A | #REF! | No | OLD |  | 19999 | 1 | AEP | Line - Bann - Kings Highway 69 kV | BANN - KINGS HIGHWAY 69 kV CKT 1 | Regional Reliability | Not Found in Future | 2007-06-01 | 2008-06-01 | 2007-02-02 | 2006 STEP |  |  |  | 5174095 | 0 | Formula Rate Update | COMPLETE | 508053 | BANN 69KV | 508061 | KINGS HIGHWAY | Replace Switch in King Hwy substation | 69
Formulas:
Q2 2019 Project Owner Indicated ISD = IFNA(VLOOKUP([UID],'Q2 2019 Initial PTP'!$F1:L59,7,0),"Not Found in Future")